## GAVI
FY 2014 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ankeny Regional | Construct 6-unit tee hangar | 326250 | 150000 | Airport funds |  | 150000 | Under construction | 2014-04-01
Davenport Municipal | Rehabilitate hangar 8970 | 56660 | 48161 | City funds |  | 48161 | Under contract | 2014-05-15
Emmetsburg Municipal | Construct 80x100 hangar | 529170 | 100000 | Local funding uncertain |  | 100000 | Project on hold | 2014-12-31
Marshalltown Municipal | Renovate hangar | 88200 | 74970 | City funds |  | 74970 | In design | 2014-12-31
Northeast Iowa Regional | Construct 70x120 hangar | 300000 | 150000 | Utility complany loan | 5684 | 144316 | Rebidding in February 2014 | 2014-09-01
Ottumwa Regional | Renovate hangar | 74470 | 59470 | Local airport funds |  | 59470 | Under contract | 2014-01-31
Perry Municipal | Construct 45x100 hangar | 422375 | 150000 | City bonding | 0 | 150000 | In design | 2014-06-01
Red Oak Municipal | Renovate hangar door | 20700 | 16560 | City funds | 16560 | 0 | Completed | 2013-12-18
Webster City Municipal | Renovate maintenance hangar | 40500 | 20250 | Airport funds |  | 20250 | Contract signed | 2014-06-01
| Total | 1817825 | 769411 |  | 22244 | 747167
FY 2013 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Boone Municipal Airport | Construct hangar | 187500 | 150000 | Airport funds | 122457 | 27543 | Final punch list items. | 2014-01-31
Clinton Municipal Airport | Construct transient hangar | 600000 | 150000 | Airport funds | 83261 | 66739 | Under construction | 2014-04-30
Iowa Falls Municipal Airport | Construct hangar | 326760 | 150000 | Airport funds | 15985 | 134015 | Under construction | 2014-04-30
Red Oak Municipal Airport | Construct hangar | 210000 | 150000 | Airport funds | 150000 | 0 | Completed | 2013-07-23
Vinton Veterans Airpark | Construct hangar | 271000 | 150000 | Airport funds | 9864 | 140136 | Substantially complete, punchlist items | 2013-12-31
| Total | 1595260 | 750000 |  | 381567 | 368433
FY 2012 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Atlantic | Rehabilitate hangar | 35000 | 7649 | City funds, other infrastructure funds | 7649 | 0 | Completed | 2012-01-17
Clinton Municipal Airport | Design airport terminal and transient hangar | 63600 | 54060 | Airport funds | 54060 | 0 | Completed | 2013-06-03
Fairfield Municipal Airport | Design terminal building | 75000 | 63750 | Airport funds | 57820 | 5930 | Near completion. | 2014-01-31
Iowa City Municipal Airport | Rehabilitate terminal building | 118000 | 100300 | Airport funds | 100300 | 0 | Completed | 2012-08-29
Maquoketa Airport | Replace B-Cap roof | 42962 | 25266 | Airport funds | 25266 | 0 | Completed | 2013-01-28
Monticello Municipal Airport | Rehabilitate FBO city owned building | 103124 | 65999 | Airport funds | 65999 | 0 | Completed | 2012-06-05
Osceola Municipal Airport | Improve terminal / office building | 64630 | 43962 | Airport funds | 43962 | 0 | Completed | 2012-10-15
Ottumwa Regional Airport | Construct 6 unit t-hangar | 169000 | 135200 | Airport funds | 135200 | 0 | Completed | 2013-06-18
Shenandoah Airport | Construct 4 unit t-hangar | 200000 | 150000 | Airport funds | 150000 | 0 | Completed | 2012-12-31
Iowa City Municipal Airport | Rehabilitate terminal and building D roofs (FY 2013 project) | 118000 | 75000 | Airport funds | 15985 | 59015 | Under construction | 2014-04-30
Ottumwa Regional Airport | Rehabilitate terminal roof (FY 2013 project) | 65000 | 30297 | Airport funds, other infrastructure funds from other years | 30297 | 0 | Completed | 2013-10-11
| Total | 871316 | 751483 |  | 686538 | 64945
FY 2011 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ankeny Regional Airport | Rehabilitate terminal building roof | 226000 | 93275 | Airport Authority funds | 93275 | 0 | Completed | 2011-12-10
Council Bluffs Airport | Construct two conventional hangars | 416474 | 196000 | Authority funds | 196000 | 0 | Completed | 2012-10-30
Davenport Municipal Airport | Construct 6-unit box hangar | 500000 | 150000 | Local bonding | 150000 | 0 | Completed | 2011-03-21
Iowa City Municipal Airport | Construct box hangar | 900000 | 200000 | Revenue from land sales, general revenue bonds | 200000 | 0 | Completed | 2013-03-15
Spencer Municipal Airport | Rehabilitate hangar roofs | 140000 | 91000 | City funds, other infrastructure funds | 91000 | 0 | Completed | 2011-12-10
Ottumwa Regional Airport | Rehabilitate terminal roof (FY 2013 project) | 65000 | 19725 | Airport funds, other infrastructure funds from other years | 19725 | 0 | Completed | 2013-10-11
| Total | 2247474 | 750000 |  | 750000 | 0

## CSVI
FY 2014 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington - Southeast Iowa | Construct hangar | 480000 | 96594 | Authority Funds, Other Infrastructure Funds |  | 96594 | Plans in progress | Sept. 2014
Cedar Rapids - Eastern Iowa | Replace roofs on four buildings | 330000 | 311190 | City funds, other infrastructure funds |  | 311190 | Contract Awarded on 10/28/13 | 6-30-14
Des Moines | Construct aircraft maintenance building | 4500000 | 579215 | Airport funds, other infrastructure funds |  | 579215 | Design on hold until 2016 | 2016-12-31
Dubuque | Construct terminal building | 1277920 | 108456 | Federal AIP funds, PFC's, CFC's, local airport funds, other infrastructure funds |  | 108456 | In progress | Summer 2014
Fort Dodge | Re-design flight service station, replace overhead doors in ARFF/Maintenance building, demolish two hangars | 150000 | 98159 | Airport funds |  | 98159 | In progress | 2014-12-31
Mason City | Rehabilitate terminal: replace terminal cooling system, install security cameras, improve entrance soffit and ceiling | 99144 | 98450 | Airport funds | 15605 | 82845 | In progress | Fall 2014
Sioux City | Rehabilitate and construct new hangars | 120000 | 105151 | City funds, other infrastructure funds |  | 105151 | In progress | 12/31/2014
Waterloo | Rehabilitate hangars | 106000 | 102785 | Local funds |  | 102785 | Under design | Sept. 2014
| Total | 7063064 | 1500000 |  | 15605 | 1484395
FY 2013 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington - Southeast Iowa | Replace hangar | 450000 | 94903 | Authority funds, other infrastructure funds |  | 94903 | Plans in progress | 2014-09-01
Cedar Rapids - Eastern Iowa | Renovate terminal building lobby | 3430000 | 325782 | City funds, other infrastructure funds |  | 325782 | Contract Awarded 12/9/13 | 5/31/14
Des Moines | Install parking garage bridge, construct fixed base operator building | 5200000 | 568101 | City funds, other infrastructure funds | 568101 | 0 | Completed | 2012-11-15
Dubuque | Construct terminal building | 9368855 | 107598 | Federal Airport Improvement funds, other infrastructure funds, airport funds | 31505 | 76093 | In progress | Summer 2014
Fort Dodge | Renovate terminal operation area and former flight service station building | 100000 | 97119 | Airport funds | 0 | 97119 | In progress | 2014-03-31
Mason City | Construct office addition | 722170 | 99415 | City funds, other infrastructure funds | 99415 | 0 | Completed | 2012-12-06
Sioux City | Rehabilitate hangars | 200000 | 103848 | City funds, other infrastructure funds | 2837 | 101011 | In progress | 09/30/2014
Waterloo | Rehabilitate hangars and snow removal equipment building | 103560 | 103234 | Infrastructure funds | 6658 | 96576 | Phase I complete, Phase II in design | Sept. 2014
| Total | 19574585 | 1500000 |  | 708516 | 791484
FY 2012 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington - Southeast Iowa | Construct hangars | 898500 | 94579 | Authority funds, other infrastructure funds | 0 | 94579 | Plans In progress | 2014-09-01
Cedar Rapids - Eastern Iowa | Renovate terminal - relocate baggage screening area | 3904000 | 328020 | City funds, other infrastructure funds | 328020 | 0 | Completed | 2013-01-07
Des Moines | Renovate Aircraft Rescue Fire Fighting facility (ARFF); construct parking garage bridge | 800000 | 562349 | Other infrastructure funds, airport funds | 562349 | 0 | Completed | 2012-09-24
Dubuque | Construct terminal building | 9368855 | 110137 | Federal Airport Improvement funds, other infrastructure funds, airport funds | 110137 | 0 | Completed | 2013-08-08
Fort Dodge | Renovate terminal to prevent drainage issues; design renovation to flight service station; hangar A and B demolition | 225000 | 95992 | Airport funds | 70471 | 25521 | In progress | 2014-03-31
Mason City | Construct office addition | 500000 | 98366 | City funds, other infrastructure funds including carryover from 2009 | 99205 | 0 | Completed | 2012-12-03
Sioux City | Rehabilitate hangars | 200000 | 107536 | City funds, other infrastructure funds | 107536 | 0 | Completed | 2013-08-02
Waterloo | Rehabilitate hangars | 104929 | 103021 | Infrastructure funds | 12032 | 90989 | Phase I complete, Phase II in design | Sept. 2014
| Total | 16001284 | 1500000 |  | 1289750 | 211089
FY 2011 Revenue Bonding- Commercial Service Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington - Southeast Iowa | Rehabilitate hangars | 111491 | 94769 | Airport authority funds | 94769 | 0 | Completed | 2013-06-28
Cedar Rapids - Eastern Iowa | Rehabilitate terminal heating system | 1100000 | 320984 | Airport funds | 320984 | 0 | Completed | 2011-06-24
Des Moines | Construct sand and chemical storage and Aircraft Rescue Firefighting building renovation | 3922155 | 562574 | Other infrastructure funds | 562574 | 0 | Completed | 2012-05-07
Dubuque | Construct terminal building | 9368855 | 110245 | Federal Airport Improvement funds, other infrastructure funds, airport funds | 110245 | 0 | Completed | 2013-08-08
Fort Dodge | Install airport security system, renovate hangar, renovate terminal windows and HVACC | 205000 | 96145 | Airport funds, additional vertical infrastructure funds | 96145 | 0 | Completed | 2013-01-30
Mason City | Construct FBO office addition | 500000 | 98248 | Infrastructure funds | 98248 | 0 | Completed | 2012-10-19
Sioux City | Rehabilitate hangars | 112953 | 112953 | Infrastructure funds | 112953 | 0 | Completed | 2011-12-23
Waterloo | Rehabilitate hangars | 111530 | 104082 | Infrastructure funds | 104082 | 0 | Completed | 2013-10-01
| TOTAL | 15431984 | 1500000 |  | 1500000 | 0
FY 2010 General Fund - Commercial Service Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington - Southeast Iowa | Construct aircraft hangar | 418000 | 85011 | Other vertical infrastructure funds | 85011 | 0 | Completed | 2013-06-23
Cedar Rapids - Eastern Iowa | Renovate terminal building - airline ticket office area | 550000 | 287705 | Airport funds, Passenger facility charge (PFC) revenue | 287705 | 0 | Completed | 2010-03-23
Des Moines | Construct sand chemical storage building, renovate aircraft rescue fire fighting (ARFF) building | 674286 | 510057 | Additional vertical infrastructure funds, Federal Airport Improvement Funds, Passenger Facility Fees | 510057 | 0 | Completed | 2012-09-24
Dubuque | Construct terminal building | 9368855 | 99582 | Federal Airport Improvement funds, other infrastructure funds, airport funds | 99582 | 0 | Completed | 2013-08-08
Fort Dodge | Rehabilitate t-hangars, install security system, rehabilitate terminal | 115000 | 86705 | Airport funds , additional vertical infrastructure funds | 86705 | 0 | Completed | 2011-05-08
Mason City | Construct FBO office addition | 500000 | 88219 | Infrastructure funds | 88219 | 0 | Completed | 2012-07-30
Sioux City | Renovate terminal building (non federal eligible portions) | 375000 | 98783 | Airport funds, Federal Airport Improvement Program, ARRA funds | 98783 | 0 | Completed | 2010-04-14
Waterloo | Rehabilitate hangars A and B - replace doors | 117000 | 93938 | Infrastructure funds | 92055 | 1883 | In process, punch list items remain | 2014-04-30
| TOTAL | 12118141 | 1350000 |  | 1348117 | 1883
FY 2009 Revenue Bonding- Commercial Service Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington - Southeast Iowa | Construct hangar | 253379 | 96738 | Other vertical infrastructure funds | 96738 | 0 | Completed | 2010-08-30
Cedar Rapids - Eastern Iowa | Renovate terminal building | 2871920 | 317526 | Airport funds, Passenger facility charge (PFC) revenue | 317526 | 0 | Completed | 2009-08-24
Des Moines | Construct sand and chemical storage building | 1500000 | 567255 | Additional vertical infrastructure funds, Federal Airport Improvement Funds, Passenger Facility Fees | 567255 | 0 | Completed | 2011-10-04
Dubuque | Construct terminal | 9368855 | 111471 | Federal Airport Improvement funds, other infrastructure funds, airport funds | 111471 | 0 | Completed | 2013-04-09
Fort Dodge | Renovate terminal | 297000 | 96339 | Airport funds , additional vertical infrastructure funds | 96339 | 0 | Completed | 2010-08-16
Mason City | Replace and improve hangar doors; replace heating system in maintenance shop | 98295 | 98295 | Infrastructure funds | 97456 | 0 | Completed | 2010-07-23
Sioux City | Renovate terminal building | 4317060 | 106195 | Airport funds, Federal Airport Improvement Program, ARRA funds | 106195 | 0 | Completed | 2010-04-14
Waterloo | Renovate maintenance hangar; rehabilitate maintenance building and hangars | 106181 | 106181 | Infrastructure funds | 106181 | 0 | Completed | 2012-08-09
| TOTAL | 18812690 | 1500000 |  | 1499161 | 0

## SRT
State Recreational Trails
|  | Fund | Fiscal Year | Description of Project | Progress of Work | Total Estimated Project Cost | Revenue Sources | Funds Obligated ** |  | Funds Expended | Date of Completion / Estimated Completion
|  | Recreational Trails - RIIF - 0017 | 2014 | Ankeny Connector to High Trestle Trail (Polk County Conservation Board and City of Ankeny) | Agreement signed 10/25/2013 - work not started | 3065000 | State Recreational Trail (SRT) Fund, city funds and county funds | 782500 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Bellevue Rivervue Trail-Phase II (City of Bellevue and Jackson County Conservation Board) | Agreement not signed - work not started | 722275 | State Recreational Trail (SRT) Fund, city funds, REAP, Regional Transportation Alternative funds and private donations | 260774 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Bridging the Gap: Phase I Dry Run Trail-Connecting Decorah's Trout Run Trail to the Prairie Farmer Recreational Trail (Winneshiek County Conservation Board and City of Decorah) | Agreement not signed - work not started | 1604512 | State Recreational Trail (SRT) Fund, Statewide Transportation Enhancement grant, REAP and local public/private funds | 380265 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Farragut to Shenandoah Trail Connection (City of Farragut) | Agreement signed 10/31/2013 - work not started | 650000 | State Recreational Trail (SRT) Fund and land value | 487500 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Iowa River Scenic Trail (Hardin County Board of Supervisors and City of Marshalltown) | Agreement signed 11/12/2013 - work not started | 1375694 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and land value | 775000 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Multiuse Mississippi River Trail, Riverdale Section, Phase 2 (City of Riverdale) | Agreement not signed - development in process | 1017000 | State Recreational Trail (SRT) Fund, city funds, County Regional Authority Grant and National Scenic Byways Grant | 318644 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Pioneer Beach Road Trail (City of Orleans and Dickinson County Trails Board) | Agreement not signed - work not started | 521479 | State Recreational Trail (SRT) Fund, city funds and County Trails Board funds | 371479 |  | 0 | 2015-06-30
|  | Recreational Trails - RIIF - 0017 | 2014 | Raccoon River Valley Trail to High Trestle Trail Connector (Dallas County Conservation Board) | Agreement signed 7/30/2013 - development in process | 290000 | State Recreational Trail (SRT) Fund, other grants, donations and foundations | 92897 |  | 0 | 2015-06-30
|  |  | 2014 | [5 empty] | #REF! |  | #REF!
2013-RT-001 | RT-000S(605)--9H-00 | Recreational Trails - RIIF - 0017 | 2013 | Brushy Creek All-Weather Multi-Use Lake Trail Bridge (Iowa DNR) | Agreement signed 12/05/2012 - work not started | 110000 | State Recreational Trail (SRT) Fund and DNR REAP Grant Award | 78000 |  | 0 | 2014-06-30
2013-RT-002 | RT-1415(623)--9H-23 | Recreational Trails - RIIF - 0017 | 2013 | City of Clinton Mississippi River Trail Final Connection (City of Clinton) | Agreement signed 11/28/2012 - work not started | 550000 | State Recreational Trail (SRT) Fund and city G.O. Bonds | 400000 |  | 0 | 2014-06-30
2013-RT-003 | RT-000S(609)--9H-00 | Recreational Trails - RIIF - 0017 | 2013 | Fayette-Volga River Multi-Use Trail (Upper Iowa University and Fayette County) | Agreement signed 11/13/2012 - development in process | 1190931 | State Recreational Trail (SRT) Fund, Upper Iowa University, city funds, County Community Foundation, Black Hills Energy, private donors, additional fundraising and DNR REAP Grant Award | 700000 |  | 341201 | 2014-06-30
| RT-3715(655)--9H-52 | Recreational Trails - RIIF - 0017 | 2013 | Iowa River Trail – Phase 8 of 8 (City of Iowa City) | Agreement not signed - work not started | 2100000 | State Recreational Trail (SRT) Fund, city G.O. Bonds, Regional STP Funds, Earmark funds and Regional TE Funds | 441000 |  | 0 | 2014-06-30
2013-RT-005 | RT-2100(676)--9H-31 | Recreational Trails - RIIF - 0017 | 2013 | Mines of Spain Trail and Trailhead (City of Dubuque and Iowa DNR) | Agreement signed 11/28/2012 - work not started | 227500 | State Recreational Trail (SRT) Fund, city funds and fundraising/naming opportunities | 170500 |  | 0 | 2014-06-30
| RT-5330(624)--9H-70 | Recreational Trails - RIIF - 0017 | 2013 | Musser Park to Wiggens Road Trail (City of Muscatine) | Agreement not signed - work not started | 984400 | State Recreational Trail (SRT) Fund, Federal Earmark funds and local contribution | 300000 |  | 0 | 2014-06-30
2013-RT-007 | RT-8155(731)--9H-07 | Recreational Trails - RIIF - 0017 | 2013 | Shaulis Road Trail Extension – Phase I (City of Waterloo) | Agreement signed 7/11/2013 - work not started | 1007592 | State Recreational Trail (SRT) Fund and city funds | 755694 |  | 0 | 2014-06-30
2012-RT-008 | RT-6520(604)--9H-57 | Recreational Trails - RIIF - 0017 | 2013 | South Troy Park Trail (City of Robins) | Agreement signed 12/12/2012 - development in process | 354000 | State Recreational Trail (SRT) Fund and city funds | 204000 |  | 0 | 2014-06-30
[6 empty] | #REF! |  | #REF!
2012-RT-001 | RT-000S(521)--9H-00 | Recreational Trails - RIIF - 0017 | 2012 | Bee Branch Creek Trail-MRT Route (City of Dubuque) | Agreement not signed - work not started | 506100 | State Recreational Trail (SRT) Fund and city funds | 100000 |  | 0 | 2014-06-30
2012-RT-002 | RT-000S(522)--9H-00 | Recreational Trails - RIIF - 0018 | 2012 | Bluff Creek OHV Park Development Plan (Iowa DNR) | Agreement signed 12/20/2011 - work not started | 80000 | State Recreational Trail (SRT) Fund and ATV registration funds | 60000 |  | 0 | 2014-06-30
2013-EDP-005 | RT-0952(602)--9H-82 | Recreational Trails - RIIF - 0018 | 2012 | Buffalo to Wild Cat Den Road MRT (City of Buffalo) | Agreement signed 5/05/2012 - development in process | 562500 | State Recreational Trail (SRT) Fund and city funds | 108500 |  | 0 | 2014-06-30
2012-RT-004 | RT-C007(127)--9H-07 | Recreational Trails - RIIF - 0019 | 2012 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board) | Agreement signed 12/20/2011 - project completed with other funding | 3612516 | State Recreational Trail (SRT) Fund and CDBG Jumpstart Infrastructure | 396516 | ***** | 0 | 2014-06-30
2012-RT-005 | RT-C077(192)--9H-77 | Recreational Trails - RIIF - 0020 | 2012 | Central IA Trail Loop-Chichaqua Valley Trail to Gay Lea Wilson Trail (Polk County Conservation Board) | Agreement signed 12/15/2011 - development in process | 1005000 | State Recreational Trail (SRT) Fund, Polk County Conservation and Partners | 753750 |  | 706202.11 | 2014-06-30
2012-RT-006 | RT-0232(609)--9H-30 | Recreational Trails - RIIF - 0021 | 2012 | Dickinson County Spine Trail-Henderson Woods to US71 in Arnolds Park (Arnolds Park and Dickinson County Trails Board) | Agreement signed 12/22/2011 - project completed | 165500 | State Recreational Trail (SRT) Fund, city funds and County Trails Board | 115850 |  | 115850 | 2013-10-08
2012-RT-007 | RT-1945(791)--9H-77 | Recreational Trails - RIIF - 0022 | 2012 | Gray's Lake Neighborhood Connecting Trail & SW 14th Quiet Street (City of Des Moines) | Agreement signed 5/15/2012 - development in process | 586570 | State Recreational Trail (SRT) Fund, city CIP, Gray's Lake Neighborhood Association and land donations | 439920 |  | 254671.7 | 2014-06-30
2012-RT-008 | RT-C094(94)--9H-94 | Recreational Trails - RIIF - 0023 | 2012 | Gypsum City OHV Park (WCIC and Iowa DNR) | Agreement signed 2/6/2012 - development in process | 768860 | State Recreational Trail (SRT) Fund, Federal Recreational Trails, Webster County Conservation and ATV registration funds | 211500 |  | 0 | 2014-06-30
2012-RT-009 | RT-000S(523)--9H-00 | Recreational Trails - RIIF - 0024 | 2012 | Iowa DNR Trails Program (Iowa DNR) | Agreement signed 12/20/2011 - development in process | 350000 | State Recreational Trail (SRT) Fund, REAP and Lake Restoration Fund | 262500 |  | 160175.68 | 2014-06-30
2012-RT-010 | RT-3827(614)--9H-77 | Recreational Trails - RIIF - 0025 | 2012 | NW Beaver Drive Trail (City of Johnston) | Agreement signed 1/10/2012 - work not started | 2400000 | State Recreational Trail (SRT) Fund, city G.O. bond and city park and trail improvement fund | 181464 |  | 0 | 2014-06-30
2012-RT-011 | RT-C022(69)--9H-22 | Recreational Trails - RIIF - 0026 | 2012 | Turkey River Recreational Corridor Trail-Elkader to Motor Mill (Clayton County Conservation Board) | Agreement signed 1/18/2012 - work not started | 880576 | State Recreational Trail (SRT) Fund, statewide TE grant and local contributions | 250000 |  | 0 | 2014-06-30
2012-RT-012 | RT-000S(523)--9H-00 | Recreational Trails - RIIF - 0027 | 2012 | Water Trails Planning, Design and Construction Activities (Iowa DNR) | Agreement signed 2/23/2012 - development in process | 240000 | State Recreational Trail (SRT) Fund, marine fuel tax, U.S. Coast Guard, boat registration fees and RIIF | 120000 |  | 60021.12 | 2014-06-30
[6 empty] | #REF! |  | 3000000
2010-SRT-002 | SRT-C003(044)--9H-03 | Recreational Trails - RIIF - 0017 | 2010 | Allamakee County Mississippi River Bike Trail (Allamakee County and Allamakee County Economic Development) | Agreement signed 1/5/2010 - work not started | 7245382 | State Recreational Trail (SRT) Fund, Private and Local, Federal Earmark and Other State and Federal Grants | 750000 |  | 0 | 2014-06-30
2010-SRT-003 | SRT-C007(119)--9H-07 | Recreational Trails - RIIF - 0017 | 2010 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board) | Agreement signed 11/20/2009 - project completed | 2658938 | State Recreational Trail (SRT) Fund, CDBG - Jumpstart Infrastructure and FEMA-PA | 250000 |  | 250000 | 2012-09-30
2010-SRT-004 | SRT-1945(761)--9H-77 | Recreational Trails - RIIF - 0017 | 2010 | Des Moines River Regional Trail Phase 1 (City of Des Moines) *** | Agreement signed 1/29/2010 - development in process | 1500000 | State Recreational Trail (SRT) Fund, DNR REAP Grant Award and City of Des Moines Capital Funds | 73474 | *** | 69800 | 2014-06-30
2010-SRT-005 | SRT-000S(416)--9H-00 | Recreational Trails - RIIF - 0017 | 2010 | Iowa Department of Natural Resources (DNR) Trail Crew (Iowa DNR) | Agreement signed 11/20/2009 - project completed | 350000 | State Recreational Trail (SRT) Fund, REAP and Lake Restoration Fund | 262500 |  | 262500 | 2012-12-03
2010-SRT-006 | SRT-3715(646)--9H-52 | Recreational Trails - RIIF - 0017 | 2010 | Iowa River Corridor Trail Connection - Sand Lake (City of Iowa City) *** | Agreement signed 1/29/2010 - project completed | 375000 | State Recreational Trail (SRT) fund and Capital Improvement Funds | 281000 | *** | 180059.72 | 2012-08-06
2010-SRT-007 | SRT-7057(667)--9H-97 | Recreational Trails - RIIF - 0017 | 2010 | Lewis and Clark Historic Riverfront Trail (City of Sioux City and Iowa DOT) *** | Agreement signed 2/1/2010 - project completed | 1600000 | State Recreational Trail (SRT) Fund and City Funds | 128000 | *** | 128000 | 2013-08-07
2009-SRT-001 | SRT-C057(106)--9H-57 | Recreational Trails - RIIF - 0017 | 2010 | Pinicon Ridge Trail (Linn County Conservation Board) * | Please see Agreement 2009-SRT-001. Agreement signed 7/20/2009 - project completed | 666667 | State Recreational Trail (SRT) Fund and Local Contributions | 500000 | * | 500000 | 2012-08-27
2010-SRT-009 | SRT-1945(762)--9H-77 | Recreational Trails - RIIF - 0017 | 2010 | Principal Riverwalk Recreational Trail (city of Des Moines) * | Agreement signed 12/2/2009 - project completed | 1000000 | State Recreational Trail (SRT) fund and Local Contributions | 750000 | * | 750000 | 2013-04-15
2010-SRT-010 | SRT-C025(080)--9H-25 | Recreational Trails - RIIF - 0017 | 2010 | Raccoon River Valley Trail Addition--Forest Park to Minburn Trail (Dallas County Conservation Board) *** | Agreement signed 11/6/2009 - project completed | 6655696 | State Recreational Trail (SRT) Fund, Community Attraction and Tourism Program, State Enhancement Project, Central Iowa Regional Transportation Planning Alliance, Dallas County, City of Perry, City of Waukee, Guthrie County Cash and Stimulus, City of Dallas Center, City of Jamaica, City of Redfield, City of Linden, Raccoon Valley Bank, Bock Family Foundation, Dallas County Conservation Foundation, Raccoon River Valley Trail Association, Celebrations Committee Dallas Center, Committee for Super Cooper, Dallas Center Beta Sigma Phi, Rotary Club of Dallas Center, Community of Herndon, Waukee YMCA, City of Dawson, Casey's Stores, Alliant Energy, Bikes Belong, Letter campaign, Prairie Meadows Community Betterment, Prairie Woodland Conservation Foundation and Bock Family Foundation October 08 | 484995 | *** | 460745.25 | 2012-08-23
2010-SRT-011 | SRT-C030(040)--9H-30 | Recreational Trails - RIIF - 0017 | 2010 | Railbanking Purchase of IANW Railroad (Dickinson County Trails Board and Osceola County Conservation Board) | Agreement signed 1/4/2010 - project completed | 1203795 | State Recreational Trail (SRT) Fund, IANWRR Donated Land and Transportation Enhancement Grant | 525000 |  | 525000 | 2010-07-19
2010-SRT-012 | SRT-C091(084)--9H-91 | Recreational Trails - RIIF - 0017 | 2010 | Summerset Trail Flood Repairs (Warren County Conservation Board) | Agreement signed 1/5/2010 - project completed | 143028 | State Recreational Trail (SRT) Fund and County Budget | 107271 | **** | 107271 | 2012-05-29
2010-SRT-013 | SRT-1867(608)--9H-96 | Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Box Culverts and Bridge Project (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 11/25/2009 - project completed | 782722 | State Recreational Trail (SRT) Fund, County Foundation, Winneshiek County and Winneshiek County Bridge Grant | 300000 |  | 300000 | 2012-03-05
2010-SRT-014 | SRT-000S(417)--9H-00 | Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Decorah Fish Hatchery's Interpretive Restroom Facility (Northeast Iowa Resources Conservation and Development, Inc and Iowa DNR's Fisheries) | Agreement signed 12/6/2009 - project completed | 105000 | State Recreational Trail (SRT) Fund and Friends of the Decorah Hatchery | 75000 |  | 75000 | 2012-07-02
[6 empty] | 24286228 |  | 4487240
2009-RT-005 | RT-AMGT(005)--9H-90 | Recreational Trails - RIIF - 0017 | 2009 | American Gothic Regional Trail Project (Area 15 Regional Planning Commission)* | Agreement signed 12/3/2008 - development in process | 133333 | State Recreational Trail (SRT) Fund, RPA, county, city, and private funds | 100000 | * | 84202.07 | 2014-06-30
2009-RT-011 | RT-CRAW(011)--9H-24 | Recreational Trails - RIIF - 0017 | 2009 | Crawford County Trail (Crawford County)* | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund and county funds | 30000 | * | 30000 | 2010-09-20
2009-RT-007 | RT-GARL(007)--9H-30 | Recreational Trails - RIIF - 0017 | 2009 | Garlock Slough Recreational Trail (City of West Okoboji and Dickinson County Tails Board) | Agreement signed 11/3/2008 - project completed | 653550 | State Recreational Trail (SRT) Fund, Dickinson County Conservation, MPO, and City of West Okoboji | 490162 |  | 408425.41 | 2012-10-09
2009-RT-001 | RT-LNCR(001)--9H-64 | Recreational Trails - RIIF - 0017 | 2009 | Linn Creek Trail Connection with Iowa Highway 330 Trail (Marshall County) | Agreement signed 7/20/2009 - project completed | 1476000 | State Recreational Trail (SRT) Fund and county funds | 800000 |  | 800000 | 2012-09-05
2009-RT-004 | RT-MARV(004)--9H-53 | Recreational Trails - RIIF - 0017 | 2009 | Maquoketa River Water Trail (Jones County)* | Agreement signed 7/8/2008 - project completed | 133334 | State Recreational Trail (SRT) Fund and county funds | 100000 | * | 100000 | 2011-08-08
2009-RT-006 | RT-LBRT(006)--9H-23 | Recreational Trails - RIIF - 0017 | 2009 | Mississippi River Trail - Liberty Avenue Connection (Clinton) | Agreement signed 12/3/2008 - project completed | 469000 | State Recreational Trail (SRT) Fund and City of Clinton | 351750 |  | 351750 | 2010-04-26
2009-RT-003 | RT-RWLK(003)--9H-77 | Recreational Trails - RIIF - 0017 | 2009 | Principal Riverwalk (Des Moines)* | Agreement signed 11/4/2008 - project completed | 1000000 | State Recreational Trail (SRT) Fund and City of Des Moines | 750000 | * | 750000 | 2013-04-15
2009-RT-009 | RT-RREA(009)--9H-07 | Recreational Trails - RIIF - 0017 | 2009 | Riverview Recreation Area Expansion (Trailblazers Off Road Club) | Agreement signed 6/8/2009 - funding rescinded | 71000 | State Recreational Trail (SRT) Fund | 40000 |  | 0 | N/A
2009-RT-002 | RT-STST(002)--9H-97 | Recreational Trails - RIIF - 0017 | 2009 | Stone State Park Trail (Woodbury County/DNR)* | Agreement signed 10/8/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund and county funds | 100000 | * | 0 | 2014-06-30
2009-RT-010 | RT-SUMM(010)--9H-77 | Recreational Trails - RIIF - 0017 | 2009 | Summerset Trail (Cities of Indianola, Carlisle and Des Moines)* | Agreement signed 3/9/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund and city funds | 100000 | * | 0 | 2014-06-30
2009-RT-008 | RT-TRTL(008)--9H-96 | Recreational Trails - RIIF - 0017 | 2009 | Trout Run Trail - Bridging the Past and the Present (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 3/16/2009 - project completed | 443750 | State Recreational Trail (SRT) Fund, Winneshiek County Conservation, and City of Decorah | 138088 |  | 138088 | 2010-10-18
[6 empty] | 4686633 |  | 3000000
2008-RT-004 | RT-ANWD(004)--9H-08 | Recreational Trails - RIIF - 0017 | 2008 | Ankeny to Woodward Trail Corridor (Boone County Conservation Board) | Agreement signed 3/25/2008 - project completed | 3415960 | State Recreational Trail (SRT) Fund, Land Value and Regional Enhancement | 565960 |  | 565960 | 2012-07-31
2008-RT-003 | RT-CO24(003)--9H-24 | Recreational Trails - RIIF - 0017 | 2008 | Crawford County Trails (Crawford County)* | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund, county, city, and private funds | 30000 | * | 30000 | 2010-09-20
2008-RT-002 | RT-2465(002)--9H-51 | Recreational Trails - RIIF - 0017 | 2008 | Fairfield Loop Trail (Fairfield)* | Agreement signed 3/10/2009 - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | * | 200000 | 2012-05-29
2008-RT-005 | RT-HART(005)--9H-85 | Recreational Trails - RIIF - 0017 | 2008 | Heart of Iowa Nature Trail Phases VII & VIII (Story County Conservation Board) | Agreement signed 12/14/2007 - development in process | 1937254 | State Recreational Trail (SRT) Fund and county funds | 100000 |  | 95000 | 2014-06-30
2008-RT-001 | RT-CO40(001)--9H-40 | Recreational Trails - RIIF - 0017 | 2008 | Jewell to Ellsworth Trail (Hamilton County Conservation Board)* | Agreement signed 9/5/2007 - development in process | 246667 | State Recreational Trail (SRT) Fund and county funds | 185000 | * | 143164.66 | 2014-06-30
2008-RT-006 | RT-IDOT(006)--9H-00 | Recreational Trails - RIIF - 0017 | 2008 | Lewis & Clark Trail Planning Study (Iowa DOT) | Agreement IDOT - project completed | 66667 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2011-07-11
2008-RT-007 | RT-MAQU(007)--9H-53 | Recreational Trails - RIIF - 0017 | 2008 | Maquoketa River Water Trail (Jones County Conservation Board) | Agreement signed 12/13/2007 - project completed | 549605 | State Recreational Trail (SRT) Fund and county funds | 69300 |  | 69300 | 2011-08-08
2008-RT-008 | RT-MISSI(008)--9H-82 | Recreational Trails - RIIF - 0017 | 2008 | Mississippi River Trail Upper Scott County (Le Claire) *** | Project was rescinded. Funding to be reprogrammed for flood damage projects. | 1227779 | State Recreational Trail (SRT) Fund and county funds | 799740 | *** | Rescinded | N/A
[6 empty] | 7750599 |  | 2000000 |  | 0
2007-RT-001 | RT-PCCB(001)--9H-77 | Recreational Trails - RC2 - 0942 | 2007 | 4-Mile Creek Greenway Trail (Polk County Conservation Board/City of Ankeny Parks and Recreation Department) | Agreement signed 3/06/2007 - project completed | 1334331 | State Recreational Trail (SRT) Fund, Polk County Conservation, MPO, and City of Ankeny | 690000 |  | 690000 | 2012-05-30
2007-RT-002 | RT-RVVW(002)--9H-07 | Recreational Trails - RC2 - 0942 | 2007 | 18th Street to Riverview Trail Development (Waterloo) | Agreement signed 3/29/2007 - project completed | 336250 | State Recreational Trail (SRT) Fund and City of Waterloo | 252187 |  | 252187 | 2011-04-04
2007-RT-003 | RT-ALCE(003)--9H-25 | Recreational Trails - RC2 - 0942 | 2007 | Alice's Road Greenbelt Trail Improvements (Clive) | Agreement signed 2/07/2007 - development in process | 536540 | State Recreational Trail (SRT) Fund and City of Clive | 402405 |  | 381907.38 | 2014-06-30
2007-RT-004 | RT-CEMR(004)--9H-57 | Recreational Trails - RC2 - 0942 | 2007 | Cemar Trail - Phase 2 (Cedar Rapids) | Agreement signed 1/12/2010 - development in process | 200000 | State Recreational Trail (SRT) Fund and Cedar Rapids CIP Funds | 150000 |  | 0 | 2014-06-30
2007-RT-005 | RT-TWLP(005)--9H-14 | Recreational Trails - RC2 - 0942 | 2007 | Coon Rapids Town Loop Trail (Coon Rapids) | Agreement signed 4/16/2007 - project completed | 142500 | State Recreational Trail (SRT) Fund and City of Coon Rapids/Whiterock Conservancy | 106875 |  | 106875 | 2010-03-15
2007-RT-006 | RT-DSMT(006)--9H-29 | Recreational Trails - RC2 - 0942 | 2007 | Des Moines County Recreational Trail - Phase 1 Burlington to Starr's Cave (Des Moines County) | Agreement signed 2/19/2007 - development in process | 480000 | State Recreational Trail (SRT) Fund and county funds | 360000 |  | 203243 | 2014-06-30
2007-RT-007 | RT-LKVW(07)--9H-52 | Recreational Trails - RC2 - 0942 | 2007 | Lakeview OHV Park Upgrades (Dirt Surfers Inc) | Agreement signed 6/27/2007 - development in process | 52420 | State Recreational Trail (SRT) Fund | 39315 |  | 17717 | 2014-06-30
2007-RT-008 | RT-C090(008)--9H-90 | Recreational Trails - RC2 - 0942 | 2007 | Trail Projects in Wapello County (Wapello County) * | Agreement signed 4/16/2007 - $30,000 was awarded to city of Eldon - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | * | 196072.35 | 2010-03-22
[6 empty] | 4674520 |  | 1124651
2006-RT-006 | RT-GOHV(006)--9H-94 | Recreational Trails - RIIF - 0017 | 2006 | Phase I of the Gypsum City OHV Park. (Webster County) | Agreement signed 8/21/2006 - project completed | 1660250 | State Recreational Trail (SRT) Fund and All-Terrain Vehicle Registration Funds | 250000 |  | 250000 | 2010-07-06
2006-RT-007 | RT-LSVT(007)--9H-97 | Recreational Trails - RIIF - 0017 | 2006 | Trail construction connecting the Little Sioux County Park to the city of Correctionville. (Woodbury County Conservation Board) | Agreement signed 7/10/2006 - project completed | 1027760 | State Recreational Trail (SRT) Fund, Federal Transportation Enhancement Funds, REAP grant, county, city, and private funds | 150000 |  | 150000 | 2007-10-01
2006-RT-003 | RT-CCTR(003)--9H-52 | Recreational Trails - RIIF - 0017 | 2006 | Phase 4 of the Clear Creek Trail from Mormon Handcart Park to the Clear Creek bridge on U.S. Highway 6. (Coralville) | Agreement signed 8/9/2006 - Final Voucher entered 6/11/08; Remaining funds to be used on next phase of project - project completed | 437216 | State Recreational Trail (SRT) Fund and city hotel/motel tax | 327912 |  | 327912 | 2008-05-01
2006-RT-009 | RT-TRES(009)--9H-77 | Recreational Trails - RIIF - 0017 | 2006 | Construction of trail connecting existing trails in Johnston to the Neal Smith Trail in Des Moines. (Polk County Conservation Board) | Agreement signed 7/31/2006 - project completed | 1406960 | State Recreational Trail (SRT) Fund, county funds, Federal Transportation Enhancement Funds and MPO Transportation Enhancement Funds | 346739 |  | 346739 | 2010-06-21
2006-RT-010 | RT-VCLT(010)--9H-17 | Recreational Trails - RIIF - 0017 | 2006 | Development of a trail to fill a gap in the trail network around Clear Lake and extending to Mason City. (Cerro Gordo County) | Agreement signed 7/10/2006 - project completed | 71167 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2008-05-09
[6 empty] | 4603353 |  | 1074651
NOTE: To avoid loss of funding, it is the Iowa Department of Transportation's policy to expend the oldest funding first when reimbursing any project costs. Thus, the FY 2006 $1,000,000 appropriation was spent, even though some of the FY 2006 projects listed don't show all their funding was utilized by the expiration date.
* Direct Appropriation From Iowa Legislature
** Funds obligated per Department of Transportation Commission Order.
*** FY 2006 and FY 2008 Funding Rescinded by Local Sponsors - Funding Reallocated to SRT Projects in FY 2010
**** The initial $87,500 is from I-Jobs and the remaining $19,771 from rescinded funds from FY 2008.
*****Funding Rescinded by Local Sponsor - Funding Reallocated to SRT Projects in FY 2014
The FY 2006 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,000,000 as result of awarding additional funding from previous project underruns.
The FY 2007 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is over $2,000,000 as result of awarding additional funding from previous project underruns.
The FY 2008 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is $2,000,000.
The FY 2009 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2010 SRT appropriation was for $3,500,000. The total amount of SRT funding for projects listed in this report is over $3,500,000 as a result of awarding additional funding from previous project underruns.
There was no SRT appropriation for FY 2011.
The FY 2012 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2013 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2014 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.

## Bridge Safety Fund
Bridge Safety Fund
($40 milion from Revenue Bonds Capitals (FY 2010) and $10 million from Revenue Bonds Capitals II (FY 2011))
[8 empty] | Project Info | [5 empty] | Fund Source
Program Year | Status | Contract Number | County | Route | Project Number | Location | Features Intersected | Work Type | Letting Date | Old Letting Date | Estimated Cost | Contract Amount | Paid To Date | Bridge Safety Funds (Obligated) | Bridge Safety Fund paid | Primary Road Fund | Anticipated Completion Date | Actual Completion (Form 435 Date) | Work Progress
2010 | Completed | 07-0572-022 | Black Hawk | IA 57 | FSSN-057-2(22)--3T-07 | OVER SMALL NATURAL STREAM 0.4 MI. EAST OF GRUNDY CO. LINE |  | Bridge Replacement-CCS | 2009-10-20 | 2012-01-18 | 732000 | 674550 | 656490.04 | 674550 | 656490.04 |  | 2010-11-12 | 2010-11-22 | Completed
2010 | Completed | 12-0147-025 | Butler | IA 14 | FSSN-014-7(25)--3T-12 | IOWA HIGHWAY 14 OVER COLDWATER CREEK 1.1 MILES S. OF GREENE |  | Bridge Replacement-PPCB | 2009-11-17 | 2008-11-18 | 1176000 | 947505.91 | 960730.3 | 947505.91 | 947505.91 | 13224.39 | 2010-11-12 | 2010-12-20 | Completed
2010 | Completed | 01-0802-218 | Adair | I-80 | ISSN-080-2(218)76--1T-01 | COUNTY RD. N54 OVER INTERSTATE 80 |  | Bridge Deck Overlay | 2009-12-15 | 2010-01-20 | 189000 | 173502.9 | 165051.05 | 173502.9 | 165051.05 |  | 2010-09-30 | 2010-09-10 | Completed
2010 | Completed | 24-0595-050 | Crawford | US 59 | FSSN-059-5(50)--3T-24 | OVER W. BOYER RIVER IN CITY OF DENISON(NBL) |  | Bridge Deck Overlay | 2009-12-15 | 2010-01-20 | 504000 | 490900.4 | 568043.23 | 490900.4 | 490900.4 | 77142.83 | 2010-11-19 | 2012-01-27 | Completed
2010 | Completed | 37-0303-031 | Greene | US 30 | FSSN-030-3(31)--3T-37 | OVER N. RACCOON RIVER 0.8 MILE W. OF CO. RD. P-14 |  | Bridge and Approaches-PPCB | 2009-12-15 | 2010-01-20 | 2680000 | 2368203.02 | 2364798.9 | 2368203.02 | 2364798.9 |  | 2010-11-19 | 2011-12-15 | Completed
2010 | Completed | 64-3302-086 | Marshall | IA 330 | FSSN-330-2(86)--3T-64 | OVER ASHER CREEK 2 MILES W. OF IA. 14 |  | Bridge Deck Overlay | 2009-12-15 | 2010-01-20 | 350000 | 271796.5 | 293115.05 | 271796.5 | 271796.5 | 21318.55 | 2010-11-19 | 2011-01-04 | Completed
2010 | Completed | 67-1412-054 | Monona | IA 141 | FSSN-141-2(54)--3T-67 | OVER MAPLE RIVER IN MAPLETON 0.2 MILE EAST OF THE WEST JCT. WITH IA.175 |  | Bridge Deck Overlay | 2009-12-15 | 2010-01-20 | 452000 | 355649.5 | 434372.03 | 355649.5 | 355649.5 | 78722.53 | 2010-11-19 | 2011-06-21 | Completed
2010 | Completed | 79-0805-283 | Poweshiek | I-80 | ISSN-080-5(283)188--1T-79 | COUNTY RD. T-58 OVER INTERSTATE 80 4 MILES W. OF US 63 |  | Bridge Deck Overlay | 2009-12-15 | 2010-01-20 | 235000 | 258431.26 | 276320.81 | 258431.26 | 258431.26 | 17889.55 | 2010-11-19 | 2011-01-04 | Completed
2010 | Completed | 25-0802-217 | Dallas | I-80 | ISSN-080-2(217)100--1T-25 | COUNTY ROAD F-60/P-53 OVER I-80 |  | Bridge Deck Replacement | 2010-01-20 |  | 795000 | 680934.4 | 701094.96 | 680934.4 | 680934.4 | 20160.56 | 2010-10-29 | 2011-09-19 | Completed
2010 | Completed | 47-1753-033 | Ida | IA 175 | FSSN-175-3(33)--3T-47 | OVER SMALL NATURAL STREAM 1.2 MILES SOUTHWEST OF BATTLE CREEK |  | RCB Culvert Replacement - Single Box | 2010-01-20 | 2011-12-20 | 400000 | 155950.1 | 158799.19 | 155950.1 | 155950.1 | 2849.09 | 2010-11-19 | 2011-08-15 | Completed
2010 | Completed | 48-1511-020 | Iowa | US 151 | FSSN-151-1(20)--3T-48 | OVER PRICE CREEK 0.3 MILE N. OF IA. 220 |  | Bridge Replacement-CCS | 2010-01-20 | 2012-02-21 | 1406000 | 1136401.5 | 1082602.59 | 1136401.5 | 1082602.59 |  | 2010-11-19 | 2011-12-12 | Completed
2010 | Completed | 59-0346-074 | Lucas | US 34 | FSSN-034-6(74)--3T-59 | OVER BIKE PATH (ABANDONED R.R. LINE) 1.1 MILESW. OF IA. 14 |  | Bridge Deck Replacement | 2010-01-20 | 2010-02-16 | 404000 | 523208.2 | 586512.74 | 523208.2 | 523208.2 | 63304.54 | 2010-09-30 | 2010-09-20 | Completed
2010 | Completed | 76-0151-007 | Pocahontas | IA 15 | FSSN-015-1(7)--3T-76 | OVER BEAVER CREEK 2 MILES N. OF ROLFE |  | Bridge Deck Replacement | 2010-01-20 |  | 500000 | 288285.75 | 293179.2 | 288285.75 | 288285.75 | 4893.45 | 2010-11-12 | 2011-04-25 | Completed
2010 | Completed | 79-0212-017 | Poweshiek | IA 21 | FSSN-021-2(17)--3T-79 | OVER BEAR CREEK 1 MILE S. OF W. JCT. US 6 |  | Bridge Deck Replacement | 2010-01-20 |  | 672000 | 420685.12 | 435497.2 | 420685.12 | 420685.12 | 14812.08 | 2010-11-19 | 2011-09-14 | Completed
2010 | Completed | 43-0295-215 | Harrison | I-29 | ISSN-029-5(215)82--1T-43 | F50 OVER I-29 |  | Bridge Deck Replacement | 2010-02-16 |  | 814000 | 655706.69 | 701216.65 | 655706.69 | 655706.69 | 45509.96 | 2010-11-19 | 2012-01-17 | Completed
2010 | Completed | 77-0171-018 | Polk | IA 17 | FSSN-017-1(18)--3T-77 | OVER DES MOINES RIVER 3.6 MILES N. OF IA 141 |  | Bridge Deck Replacement | 2010-02-16 | 2010-01-20 | 1912000 | 1740854.95 | 1793302.92 | 1740854.95 | 1740854.95 | 52447.97 | 2010-12-09 | 2011-02-04 | Completed
2010 | Completed | 99-0174-033 | Wright | IA 17 | FSSN-017-4(33)--3T-99 | OVER BOONE RIVER 3.0 MILES SOUTH OF EAGLE GROVE |  | Bridge Deck Replacement | 2010-02-16 | 2010-01-20 | 665000 | 616732.3 | 631737.01 | 616732.3 | 616732.3 | 15004.71 | 2010-11-12 | 2010-11-29 | Completed
2010 | Completed | 13-0074-018 | Calhoun | IA 7 | FSSN-007-4(18)--3T-13 | OVER CCP R.R. 0.9 MILE E. OF CO. RD. P-19 |  | Bridge Deck Overlay | 2010-03-16 | 2010-01-20 | 620000 | 475596.8 | 469549.1 | 475596.8 | 469549.1 |  | 2010-11-19 | 2011-04-04 | Completed
2010 | Completed | 47-0596-035 | Ida | US 59 | FSSN-059-6(35)--3T-47 | OVER ODEBOLT CREEK 0.1 MILE S. OF IA. 175 |  | Bridge Deck Overlay | 2010-03-16 | 2010-01-20 | 393000 | 257139.57 | 508058.95 | 257139.57 | 257139.57 | 250919.38 | 2010-11-19 | 2011-05-10 | Completed
2010 | Completed | 67-1832-041 | Monona | IA 183 | FSSN-183-2(41)--3T-67 | OVER JORDAN CREEK 0.2 MILES SOUTH OF MOORHEAD |  | Bridge Deck Overlay | 2010-03-16 | 2010-01-20 | 299000 | 350972.4 | 359480.96 | 350972.4 | 350972.4 | 8508.56 | 2010-09-30 | 2011-01-06 | Completed
2010 | Completed | 78-6802-151-A | Pottawattamie | I-680 | ISSN-680-2(151)17--1T-78 | OVER 185TH ST./CO. RD. G-14(WBL) |  | Bridge Deck Replacement | 2010-03-16 | 2010-01-20 | 677000 | 624993.7 | 724669 | 624993.7 | 624993.7 | 99675.3 | 2010-11-24 | 2011-04-04 | Completed
2010 | Completed | 24-0391-024 | Crawford | IA 39 | FSSN-039-1(24)--3T-24 | OVER SPANGLER CREEK 0.4 MILE E. OF CO. RD. M-35 |  | Deck Joint Repair | 2010-04-20 | 2010-01-20 | 400000 | 249213.25 | 267707.89 | 249213.25 | 249213.25 | 18494.64 | 2010-11-19 | 2012-02-15 | Completed
2010 | Completed | 52-0015-087 | Johnson | IA 1 | FSSN-001-5(87)--3T-52 | SOUTHBOUND IA 1 OVER IOWA RIVER IN IOWA CITY |  | Bridge Deck Overlay | 2010-04-20 | 2010-03-16 | 439000 | 509775.89 | 557170.06 | 509775.89 | 509775.89 | 47394.17 | 2010-09-30 | 2011-01-13 | Completed
2010 | Completed | 67-0371-047 | Monona | IA 37 | FSSN-037-1(47)--3T-67 | OVER SOLDIER RIVER 0.4 MILE E. OF IA 183 |  | Deck Joint Repair | 2010-04-20 |  | 274000 | 207800.9 | 210588.5 | 207800.9 | 207800.9 | 2787.6 | 2010-09-30 | 2010-10-13 | Completed
2010 | Completed | 97-0296-213 | Woodbury | I-29 | ISSN-029-6(213)142--1T-97 | SB OVER 8TH ST. 2.0 MILES S. OF JUNCTION U.S. 20 |  | PPCB Repair | 2010-04-20 | 2009-12-15 | 126000 | 25501 | 25289.39 | 25501 | 25289.39 |  | 2010-11-19 | 2010-11-09 | Completed
2010 | Completed | 78-0061-121 | Pottawattamie | US 6 | FSSN-006-1(121)--3T-78 | WESTBOUND US 6 OVER MOSQUITO CREEK 1 MILE W. OF I-80 |  | Deck Joint Repair | 2010-05-18 | 2010-04-20 | 269000 | 233458.13 | 230365.94 | 233458.13 | 230365.94 |  | 2010-10-28 | 2011-04-04 | Completed
2010 | Completed | 78-0292-069 | Pottawattamie | I-29 | ISSN-029-2(69)47--1T-78 | NORTHBOUND I-29 OVER BNSF/CBEC R.R. 1.3 MILES S. OF IA. 92 |  | Bridge Deck Overlay | 2010-05-18 | 2010-04-20 | 544000 | 554481.7 | 606088.07 | 554481.7 | 554481.7 | 51606.37 | 2011-01-21 | 2011-04-04 | Completed
2010 | Completed | 78-0292-069 | Pottawattamie | I-29 | ISSN-029-2(70)47--1T-78 | SOUTHBOUND I-29 OVER BNSF/CBEC R.R. 1.3 MILES S. OF IA. 92 |  | Bridge Deck Overlay | 2010-05-18 | 2010-04-20 | 572000 | 553800.3 | 645738.99 | 553800.3 | 553800.3 | 91938.69 | 2011-01-21 | 2011-04-04 | Completed
2010 | Completed | 15-0802-216-A | Cass | I-80 | ISSN-080-2(216)65--1T-15 | OVER N28 4 MILES E. OF U.S. 71. |  | Bridge Deck Replacement | 2010-06-15 | 2010-03-16 | 1324000 | 1362347.2 | 2494247.76 | 1362347.2 | 1362347.2 | 1131900.56 | 2011-11-11 | 2013-10-09 | Completed
2010 | Completed | 59-0346-075 | Lucas | US 34 | FSSN-034-6(75)--3T-59 | OVER BNSF AND UP RAILROADS 0.4 MILES EAST OF IA 14 |  | Deck Joint Repair | 2010-06-15 | 2011-01-19 | 519000 | 284812.26 | 310711.6 | 284812.26 | 284812.26 | 25899.34 | 2010-11-12 | 2011-06-06 | Completed
2010 | Completed | 97-1411-031 | Woodbury | IA 141 | FSSN-141-1(31)--3T-97 | OVER DRAINAGE DITCH 2 MILES W. OF CO. RD. K-64 |  | Bridge Deck Replacement | 2010-06-15 | 2010-01-20 | 499000 | 452244.13 | 455185.28 | 452244.13 | 452244.13 | 2941.15 | 2010-11-19 | 2011-04-28 | Completed
2011 | Completed | 42-0656-042 | Hardin | US 65 | FSSN-065-6(42)--3T-42 | OVER IOWA RIVER IN IOWA FALLS |  | Bridge and Approaches - Other | 2010-07-20 |  | 13167000 | 12338471.8 | 12366749.21 | 12338471.8 | 12338471.8 | 28277.41 | 2011-11-18 | 2012-08-06 | Completed
2011 | Completed | 91-0352-309 | Warren | I-35 | ISSN-035-2(309)45--1T-91 | OVER SOUTH RIVER 1.5 MILES SOUTH OF G-64(NBL) |  | Bridge Replacement-Steel Girder | 2010-10-19 | 2010-09-21 | 2119000 | 1772432.14 | 2010235.4 | 1772432.14 | 1772432.14 | 237803.26 | 2011-12-16 | 2012-11-16 | Completed
2011 | Completed | 91-0352-309 | Warren | I-35 | ISSN-035-2(394)45--1T-91 | OVER SOUTH RIVER, 1.5 MILES SOUTH OF G-64(SBL) |  | Bridge Replacement-Steel Girder | 2010-10-19 | 2010-09-21 | 1766000 | 1475254.68 | 1740712.89 | 1475254.68 | 1475254.68 | 265458.21 | 2011-12-16 | 2012-11-16 | Completed
2011 | Completed | 78-0801-350-A | Pottawattamie | I-80 | ISSN-080-1(350)40--1T-78 | OVER WEST NISHNABOTNA RIVER 0.8 MILE W. Of US 59(EBL) |  | Bridge Replacement-Steel Girder | 2010-11-16 | 2010-10-19 | 2731000 | 2714877.33 | 2750231.11 | 2714877.33 | 2714877.33 | 35353.78 | 2011-11-18 | 2012-02-06 | Completed
2011 | Completed | 01-0802-198 | Adair | I-80 | ISSN-080-2(198)85--1T-01 | I-80 OVER MIDDLE RIVER 1.4 MILES WEST OF IA 25 (WBL) |  | Bridge Replacement-Steel Girder | 2011-01-19 | 2011-02-15 | 2095000 | 1640110.28 | 1782711.71 | 1640110.28 | 1640110.28 | 142601.43 | 2011-11-11 | 2012-03-05 | Completed
2011 | Completed | 15-0802-219 | Cass | I-80 | ISSN-080-2(194)69--1T-15 | I-80 EASTBOUND OVER CROOKED CREEK 1.6 MILES WEST OF JCT. IA 148 |  | Bridge Replacement-PPCB | 2011-01-19 | 2013-02-19 | 1794000 | 1063616.3 | 1127674.69 | 1063616.3 | 1063616.3 | 64058.39 | 2011-11-11 | 2012-10-26 | Completed
2011 | Completed | 15-0802-219 | Cass | I-80 | ISSN-080-2(219)69--1T-15 | I-80 WESTBOUND OVER CROOKED CREEK 1.6 MILES WEST OF JCT. IA 148 |  | Bridge Replacement-PPCB | 2011-01-19 | 2014-02-18 | 1218000 | 1090721.27 | 1155862.02 | 1090721.27 | 1090721.27 | 65140.75 | 2011-11-11 | 2012-10-26 | Completed
2011 | Completed | 26-0028-029 | Davis | IA 2 | FSSN-002-8(29)--3T-26 | OVER SOUTH FOX CREEK ,1.7 MILES EAST OF APPANOOSE CO. LINE. |  | RCB Culvert New - Triple Box | 2011-01-19 | 2012-01-18 | 1173000 | 1063106.75 | 1123205.34 | 1063106.75 | 1063106.75 | 60098.59 | 2011-11-18 | 2012-05-29 | Completed
2011 | Completed | 77-0352-301 | Polk | I-35 | ISSN-035-2(301)69--1T-77 | I-35 SB & NB OVER IAIS R.R. IN CITY OF WEST DES MOINES (STAGE 1 - MEDIAN) |  | Bridge Replacement-PPCB | 2011-01-19 | 2010-01-20 | 1736000 | 1199337 | 1886671.18 | 1199337 | 1199337 | 687334.18 | 2011-11-11 | 2013-06-06 | Completed
2011 | Completed | 92-0929-129 | Washington | IA 92 | FSSN-092-9(129)--3T-92 | OVER W. BRANCH CROOKED CREEK 2.6 MILES W. OF W. JCT. IA. 1 |  | Bridge Replacement-PPCB | 2011-01-19 | 2014-10-21 | 1441000 | 1056191.13 | 1092619.73 | 1056191.13 | 1056191.13 | 36428.6 | 2011-11-18 | 2012-04-24 | Completed
2011 | Completed | 48-1511-027 | Iowa | US 151 | FSSN-151-1(23)--3T-48 | OVER IOWA RIVER OVERFLOW 0.9 MILES SOUTH OF IA. 220 |  | RCB Culvert Replacement - Twin Box | 2011-02-15 | 2012-11-20 | 617000 | 460552.55 | 771401.57 | 460552.55 | 599303.07 | 172098.5 | 2011-11-18 | 2012-09-20 | Completed
2011 | Completed | 48-1511-027 | Iowa | US 151 | FSSN-151-1(27)--3T-48 | US 151 OVER MILL RACE CREEK 0.4 MILES SOUTH OF IA 220 |  | Bridge Replacement-CCS | 2011-02-15 | 2012-10-16 | 886000 | 754827.9 | 769524.17 | 754827.9 | 754827.9 | 14696.27 | 2011-11-18 | 2012-09-20 | Completed
2011 | Completed | 75-0752-055 | Plymouth | US 75 | FSSN-075-2(55)--3T-75 | OVER DRY CREEK, 2.0 MILES SOUTH OF S.R. C-44 |  | Reconstruction - RCB Culvert Ext - Twin | 2011-02-15 | 2011-10-18 | 230000 | 265792 | 283554.41 | 265792 | 265792 | 17762.41 | 2011-11-18 | 2011-08-30 | Completed
2011 | Completed | 84-0753-047 | Sioux | US 75 | FSSN-075-3(47)--3T-84 | OVER BURR OAK CREEK 3.1 MILES N. OF THE N. JCT. US 18 |  | Bridge Replacement-CCS | 2011-02-15 | 2013-02-19 | 953000 | 777765 | 767127.47 | 777765 | 767127.47 |  | 2011-11-18 | 2011-12-09 | Completed
2011 | Completed | 12-0147-029 | Butler | IA 14 | FSSN-014-7(29)--3T-12 | Ia. 14 Over Small Stream 0.6 Mile S. Of Ia. 57 |  | RCB Culvert Replacement - Twin Box | 2011-03-15 |  | 948000 | 421990.8 | 422336.72 | 421990.8 | 421990.8 | 345.92 | 2011-11-18 | 2012-05-02 | Completed
2011 | Completed | 27-0691-036 | Decatur | US 69 | FSSN-069-1(36)--3T-27 | US 69 Over Grand River 0.6 Miles North of County Road J-66 |  | Bridge Replacement-PPCB | 2011-03-15 | 2012-12-18 | 2021000 | 2584251.62 | 2549204.97 | 2584251.62 | 2549204.97 |  | 2011-11-18 | 2012-04-10 | Completed
2014 | Completed | 33-1871-027 | Fayette | IA 187 | FSSN-187-1(27)--3T-33 | IA 187 Over Maquoketa River 2.1 Miles North Of IA 3 |  | Bridge Replacement - CCS | 2011-03-15 |  | 1283000 | 592658.12 | 634522.85 | 592658.12 | 592658.12 | 41864.73 | 2011-11-18 | 2012-04-10 | Completed
2011 | Completed | 81-0716-045 | Sac | US 71 | FSSN-071-6(45)--3T-81 | US 71 Over Small Natural Stream 1.7 Miles South Of Lake View |  | Structures - Miscellaneous | 2011-03-15 | 2012-02-21 | 731000 | 826607.6 | 860445.95 | 826607.6 | 826607.6 | 33838.35 | 2011-11-18 | 2012-02-08 | Completed
| BRIDGE SAFETY FUNDS TOTALS | [9 empty] | 57750000 | 50000000 | 54062506.75 | 50000000 | 50000000 | 4062506.75

## City County RIIF
City/County FY 2010/11 Appropriation Project Status
(includes $39.45 million from RIIF and $5.55 million from Recovery Act Government Stabilization Funds (HF 820))
AgencyName | Description of Project | Location of Project | I-JOBS Funds Appropriated in FY 2010 | I-JOBS Funds Appropriated in FY2011 | Project Estimated Costs | I-JOBS Funds Expended to Date | Status of Project | List of All Revenue Sources | Estimated Completion Date
Ackley | 1/2" roadstone for street repair | city of Ackley | 7901.17 | 9613.67 | 82.05 | 82.05 | Fully Completed | streets | 2010-10-28
| 12.55 tons cold mix for street repair |  |  |  | 1066.75 | 1066.75 | Fully Completed | streets | 2010-12-10
| 124.95 tons of salt/sand mixture |  |  |  | 5622.75 | 5622.75 | 50% or More Complete | Streets | 2009-09-09
| 96 tons of salt/sand mixture |  |  |  | 4800 | 4800 | 50% or More Complete | streets | 2010-10-24
Ackworth | PROVIDE HANDICAP ACCESS TO CITY HALL | WITHIN CITY | 371.25 | 451.72 | 2300 | 451.72 | Fully Completed | ROAD USE TAX FUNDS | 2011-06-30
Adair County | Bridge Replacement with CMP | Jackson Twshp 75-33-01-52 | 94406.54 | 114102.01 | 1787.4 | 1787.4 | Fully Completed | I-jobs | 2011-09-26
| Lumber for Bridge Deck replacements | Various |  |  | 22972.46 | 22972.46 | Fully Completed | Ijobs | 2011-10-14
| Materials for Bridge replacement | North 29 Union Township 29-74-30 |  |  | 65000 | 42174.55 | Fully Completed | IJobs & Local | 2010-11-30
| Redeck Steel stringer bridge with wood deck | T-75 R-31 S-22 west side |  |  | 15000 | 6262.06 | Fully Completed | I-jobs Materials local funds for labor | 2011-05-17
| Steel beams, piling, & flats for bridge reconstruction | Various County locations |  |  | 95408.44 | 89146.38 | Fully Completed | Ijobs | 2011-12-21
| Steel Beams, Piling, and Sheet piling | Various |  |  | 105689.94 | 4862.28 | Fully Completed | I-jobs | 2011-12-20
| Structural Steel Shapes for bridge reconstruction | Various County Locations |  |  | 19556.9 | 19556.9 | Fully Completed | Ijobs | 2010-02-10
| Structural steel shapes for bridge reconstruction | Various locations in County |  |  | 21746.52 | 21746.52 | Fully Completed | Ijobs | 2011-03-09
Adams County | Class-A bridge deck repair | At various locations thoughout the county | 68378.79 | 84115.68 | 80000 | 51292.51 | Fully Completed | Secondary road fund | 2010-10-29
| Full depth PC concrete pavment patching | At various locations thoughout the county |  |  | 150000 | 101201.96 | Fully Completed | Secondary road fund | 2010-10-22
Adel | Street Project completed August 2011. Ripped out old brick streets, and replace with new along with new street scape. | Dowtown area, historic district around courthouse. | 15003.06 | 18254.81 | 2800000 | 33257.87 | Fully Completed | GO bonds and I-jobs money | 2011-08-30
Afton | Asphalt repairs to various corners on several streets in Afton | Various Street Corners (Browning at Hwy 169, Clayton at Scott, Polk, and Filmore, Webster at Polk and Filmore, McEldery at Grand & Scott) | 4005.18 | 4873.26 | 930 | 930 | Fully Completed | IJOBS | 2010-09-15
| Fix water drainage problem on Street | South Clayton near Scott Street |  |  | 50.4 | 27.6 | Fully Completed | Road Use Tax | 2009-11-25
| Repair Street by tearing out ruts and leveling back with rock. | East Iowa Street |  |  | 89.03 | 89.03 | Fully Completed | None | 2010-06-30
| Replace culvert under South Clayton Street. | Clayton Street-in front of 308 S. Clayton St., Afton, IA 50830 |  |  | 3736.97 | 3736.97 | Fully Completed | IJOBS | 2010-09-30
| Replace Culvert under Street | South Dodge Street near Highway 169 Intersection |  |  | 3888.55 | 3888.55 | Fully Completed | None | 2010-06-30
| Rock | Used on various streets in Afton |  |  | 206.29 | 206.29 | Fully Completed | Road Use Tax | 2010-11-30
Agency | Maintenance patch repair to existing asphalt street. | N Vine Street and N Oak Street | 2716.71 | 3305.53 | 3305.53 | 3305.53 | Fully Completed | I job funds | 2010-11-22
| Replace existing wood poles with steele and replace street and city signs. | Throughout City. |  |  | 3000 | 2716.71 | Fully Completed | I-Job funds, along with general fund misc. | 2009-12-15
Ainsworth | 1 Type A Seal Coat Work 2 Type B Seal Coat Work 4 Patch Mix delivered and placed 5 3/4" road stone | City Street of Ainsworth | 2288.68 | 2784.72 | 25353.55 | 2784.72 | Fully Completed | I Jobs & RUT funds | 2010-09-07
| Re-shape & prepare road bed. Apply double layer 3/8" chip and seal coat. | Hwy. 92 to West end of Tam St. then south to end of Tam stub street. |  |  | 8366.07 | 2288.68 | Fully Completed | Road Use Tax Funds. | 2009-09-16
Akron | Street Maintainence and Reconstruction | Throughout Town | 6503.51 | 7913.08 | 100000 | 7913.08 | Fully Completed | IJOBS Funding | 2010-09-01
| Street paving for Portlandville Heights | Portlandville Heights |  |  | 300000 | 6503.51 | Fully Completed | IJOBS | 2010-09-24
Albert City | The project has not yet been determined | Albert City | 3096.7 | 3767.88 | 59000 | 6864.58 | Fully Completed | Road Use Tax Fund | 2011-06-30
Albia | none | various in City of Albia | 16186.71 | 19695 | 0 | 0 | Not Started | I Jobs funding recieved | 2010-03-31
Albion | purchase a Western V plow snow plow from Central Iowa Machine in Marshalltown Iowa for the purpose of maintaining the cities streets for snow removal | purshased from Central Iowa Machine in Marshalltown Iowa | 2585.68 | 3146.1 | 5269.94 | 5269.94 | Fully Completed | I-jobs money | 2010-08-01
| purchase of Road stone for street maintenance | Meyer Avenue |  |  | 1335.25 | 461.84 | Fully Completed | I-Jobs and Road Use Tax Funds | 2011-09-30
Alburnett | STREET REPAIR - OVER THE WINTER A SEVERE POT HOLE DEVELOPED | MAIN STREET & 2ND STREET | 2441.55 | 2970.72 | 6650 | 5412.27 | Fully Completed | I-Jobs | 2011-05-20
Alden | Repaired Storm Sewer Tile | Intersection of Water Street and Center Street | 3948.4 | 4804.18 | 4900.74 | 4804.18 | Fully Completed | Road Use Tax Money | 2010-09-17
| We purchased a Poly-Tornado Sander, Boss-T Frame RT3 V Plow and 2 new 8'2" Formed Cutting Edge Blades for snow removal | City of Alden Street Department 1018 Water Street Alden, Iowa 50006 |  |  | 4236.59 | 3948.4 | Fully Completed | Road Use Tax Funding | 2009-12-28
Alexander | asphalt patching and single coat | Harriman Street Alexander, Iowa 50420 | 486.19 | 591.57 | 7700 | 1077.76 | Fully Completed | IJobs | 2010-06-16
Algona | 3 1/2 inch mill and overlay | Phillips Street to Diagonal to Commercial to Main Street. | 25074.98 | 30509.72 | 350000 | 33797.2 | Fully Completed | I-Jobs;T-21;Road Use Tax funds | 2010-10-28
| milling and 5 inches of asphalt | E. North Street from Hall Street to Thorington Street |  |  | 21787.5 | 21787.5 | Fully Completed | Road Use Tax monies | 2009-11-30
Allamakee County | New Motorgrader and New Snow Plow Tandem Truck | Waukon, Iowa | 101583.01 | 124867.44 | 212531 | 124867.44 | Fully Completed | IJOBS & Allamakee County Secondary Road Department | 2011-06-30
| New snow plow tandem truck | Waukon |  |  | 150000 | 101583.01 | Fully Completed | IJOBS Allamakee County | 2010-02-11
Alleman | CONCRETE REPAIR ON DENNLER DRIVE/ALLEMAN/DIAMOND REPAIR IN SEVERAL LOCATIONS ON THAT STREET | DENNLER DRIVE ALLEMAN IOWA | 1004.36 | 1222.05 | 11151.01 | 1004 | Fully Completed | road use taxes and loans | 2009-07-14
Allerton | MONEY WILL GO TOWARDS THE PURCHASE OF COLD PATCH AND ROCK FOR THE ROADS FOLLOWING THE WINTER SEASON. | TO BE DETERMINED | 2441.55 | 2970.72 | 3000 | 326.63 | Less than 50% Complete | I JOB AND CITY | 2011-06-30
| ROAD ROCK OR COLD PATCH FOR ROAD REPAIR | Roads in Allerton |  |  | 3000 | 2441.55 | Fully Completed | ROAD FUND - $369.67 I JOBS - 2441.55 | 2010-05-31
| The City has purchased some rock for road repair. We will also be purchasing cold patch and possibly more rock for road repairs. | to be determined |  |  | 3000 | 2595.63 | Fully Completed | I-JOBS CITY | 2011-06-30
Allison | no projets to report to date | NO WORK IS DONE - NO LOCATION | 4393.91 | 5346.24 | 55000 | 4393.91 | Fully Completed | no I-JOBS FUNDS USED | 2010-03-17
Alta | New Pickup for use by the Alta Street Dept. | 223 Main | 8145.77 | 9911.27 | 23000 | 8145.77 | Fully Completed | IJOBS and RUT Funds will be used to purchase a pickup for the street dept. | 2010-04-01
| Project to be determined during budget preparation. Main Street concrete replacement is a possibility. | 1000 Main Street. |  |  | 10000 | 9911.27 | Fully Completed | IJOBS | 2011-03-31
Alta Vista | Repair work on curb and street. Work was completed as stated. | North White Avenue, Alta Vista Iowa | 652.43 | 793.84 | 4326.8 | 652.43 | Fully Completed | Total cost of project was $4326.80. $652.43 from IJOBS and the remaining portion paid by the City of Alta Vista | 2009-10-20
Alton | Router out and fill cracks with tar. | 3rd Avenue from Highway 10 to South City Limits | 4782.63 | 5819.22 | 10601.85 | 1061.85 | Fully Completed | IJOBS & RUT | 2010-11-30
Altoona | 2010 International - 7400 SFA 6X4 | Altoona | 58094.82 | 70686.25 | 146831 | 58094.82 | Fully Completed | ROAD USE FUNDS | 2009-11-13
| ASPHALT RESURFACING IN ALTOONA | NE 64TH ST. TO CASEBEER TO HIGHWAY 163 |  |  | 37373.56 | 37373.56 | Fully Completed | ROAD USE TAX FUND | 2010-08-19
Amana Colonies* | Repair and single lift of Seal Coat Road | On 7th Avenue from the intersection of F15 Blvd to the intersection of F Street in West Amana | 5621.23 | 6839.58 | 6000 | 3214.81 | Fully Completed | ijobs, local | 2011-07-15
| Study of the Amana Drainage Issues to Determine a Plan and Policy for Future Drainage Projects. | Amana, IA |  |  | 10900 | 9246 | Fully Completed | Ijobs | 2010-10-29
Ames | Reconstruction of full depth Asphalt by Asphalt Resurfacing restores surface texture, corrects structural deficiencies, and prevents deterioration of various streets. This process results in better riding surfaces, increased safety with improved surface | Multiple routes to be determined. | 221577.94 | 269602.59 | 1285338.53 | 491180.53 | Fully Completed | I-Jobs, Road-Use Tax, Local Option Sales Tax | 2010-10-29
Anamosa | Cored out existing material, installed 18" of base stone and installed a 4" asphalt matt. | Chamber Drive | 23996.16 | 29197.07 | 54526.95 | 23996.16 | Fully Completed | IJOBS stimulus funds and Local Opiton Sales Tax | 2009-09-29
| Mill old surface and lay 2" asphalt and repair broken curb | Nasinus Road, Pratt St, E. Cedar St, N. Pratt St, Mill St, N. Division St. |  |  | 168783.77 | 29197.07 | Fully Completed | Total project cost was $168,783.77. The City used $29,197.07 in I-JOBs stimulus funds and the remaining balance was paid with RUT funds and LOT funds. | 2010-09-14
Andover | Filling and repairing potholes | Main Street | 203.43 | 247.52 | 40 | 40 | Fully Completed | Street Fund | 2009-10-30
| Ground down and resurfaced main street through town | Washington Street |  |  | 42000 | 163.43 | Fully Completed | RUT | 2010-06-03
| Put up new speed limit signs, slow children at play signs, and red flags. |  |  |  | 259.78 | 247.52 | Fully Completed | I-jobs | 2010-12-08
Andrew | Design & Planning and construction of continuation of West VanBuren Stree w/curb & gutter from Johnson Street intersection. | West VanBuren Street | 1816.04 | 2209.65 | 36806.36 | 4025.69 | Fully Completed | I Jobs Funds and Road Use Tax Funds | 2010-12-13
Anita | Placed cold patch in various holes on city streets | Streets in Anita Iowa | 4581.72 | 5574.76 | 320.12 | 320.12 | Fully Completed | IJOBS FUNDING FROM FY09/10 | 2011-05-12
| Put asphalt over streets in town that were heavily damaged from all the rain and flooding during the storms in the summer of 2008. | Anita |  |  | 4211.72 | 4211.72 | Fully Completed | I-Jobs Stimulus funds, FY09/10 funds. | 2010-02-28
| Repair to Main Street and or Cherry Street in Anita iowa | Anita Ia. |  |  | 13000 | 5574.76 | Fully Completed | General Fund and IJOBS $, FY10/11 Funds | 2011-07-05
Ankeny | Removal of existing pavement and PCC paving on the two lanes of NW 9th Street from NW Greenwood Street to NW Beechwood Street. | NW 9th Street from NW Greenwood Street to NW Beechwood Street. | 157940.51 | 192172.43 | 594859.22 | 350112.94 | Fully Completed | $350,113 I-Jobs Remainder from GO Bonds-Capital Project Funds | 2010-11-15
Anthon | Street resurfacing and patching | City limits of Anthon | 2834.64 | 3449.02 | 7000 | 6283.66 | Fully Completed | none | 2010-06-30
Aplington | resurface portion of 10th street | corner of 10th Street and Parriott (Hwy57) North to City Limits | 4603.56 | 5601.33 | 19953.36 | 4603.56 | Fully Completed | City street funds | 2009-09-30
Appanoose County | Place 2inc AC overlay over existing asphalt pavement on road accessing airport. | 545th Street | 83466.67 | 102019.31 | 153000 | 83467 | Fully Completed | All of 2010 IJOBS money plus Local funds | 2010-06-15
| Reconstruct Approx 2000' of road with entrance culverts and one small bridge | 493rd Street 1.7 miles east of State Highway #2 Northwest quarter Section 21, T69N, R17W |  |  | 240000 | 102018.98 | Fully Completed | All of 2011 Ijobs plus local money | 2011-06-03
Arcadia | Narrow, May, & Towne reconstruction design services | Denison, Iowa | 1707.26 | 2077.29 | 30250 | 3784.55 | 50% or More Complete | Road Use Tax Fund | 2011-10-31
Aredale | washed out roads and pot holes from the flood repaired with road rock. | To be determined by City Council at October 12, 2009 Council Meeting. | 222.77 | 271.05 | 0 | 0 | Not Started |  | 2009-11-09
Arion | to be determined at a latter date | to be determined | 508.26 | 618.41 | 0 | 0 | Not Started | to be determined | 2010-01-29
Arlington | Patched areas where needed and seal coated areas of South, Liberty, High, Upper and Fairfield streets. Applied Pea gravel over seal coated areas | City of Arlington. | 1631.88 | 1985.57 | 17505.7 | 1631.88 | Fully Completed |  | 2009-08-11
| Seal coated South Street from Park to Columbus, patched and sealcoated various other streets in the City. | South Street, Arlington, Iowa |  |  | 14815.07 | 1985.57 | Fully Completed | Ijobs and RUT | 2010-08-31
Armstrong | City started a storm sewer improvement project in September 2008. There was street replacement involved in this project. With the I-JOBS road funding monies, the City replaced additional street resurfacing which the original project did not call for. | A Avenue Armstrong, Iowa | 4275.98 | 5202.75 | 14284.38 | 4275.98 | Fully Completed |  | 2009-07-31
| Replaced gravel street with new concrete. Installed 60 feet long and from 20 feet wide to 50 feet wide to match existing pavement. Installed 44 feet of 18" culvert under the Hwy. 9 approach. | 8th Street and C Avenue. Approach off Hwy. 9. |  |  | 31546.53 | 0 | Fully Completed | Road Use Tax Funds and IJOBS funding | 2011-10-03
Arnolds Park | Purchase a new 3/4-ton street pick-up | City of Arnolds Park | 5075.27 | 6175.28 | 32500 | 11250.55 | Fully Completed | General Fund (Street Equipment) | 2010-06-30
Arthur | Mill & resurface street | 3rd St | 971.09 | 1181.57 | 971.09 | 971.09 | Fully Completed | Borrowed money against a CD | 2009-08-04
Asbury | Design and planning for road reconstruction of Seippel Road between Middle Road and Asbury Road | Asbury Iowa | 10700.87 | 13020.17 | 1500000 | 13020.04 | 50% or More Complete | City funds and Ijobs | 2012-12-31
| Resurface Asbury Road from the East City Limits to Radford Road. | East City Limits to Radford Road |  |  | 102000 | 10700.87 | 50% or More Complete | City Road Use Tax Funds | 2009-08-20
Ashton | To be determined at a later date. | To be determined | 1694.41 | 2061.66 | 108916.4 | 3756.07 | Fully Completed | To Be Determined | 2009-09-23
[5 empty] | 0 | 0 | Not Started | To Be Determined. | 2009-12-31
Aspinwall | repair along roadways to fix run off from heavy rains | City of Aspinwall | 227.89 | 277.27 | 500 | 500 | Fully Completed | RUT Fund/I-Jobs fund | 2009-08-18
Atalissa | street repairs and providing better drainage to the alley between Hwy 6 and 1st street. | various city streets | 1216.02 | 1479.57 | 24809.22 | 1479.57 | Fully Completed | I JOBS AND ROAD USE MONEY | 2011-01-31
| TYPE B SEAL COAT WORK CONSISTING OF POWER BROOM STREETS, FURNISH AND APPLY SINGE SEAL COAT OF MC-3000 ASPHALT FURNISH AND SPREAD AND ROLL 3/8" CHIPS | VARIOUS CITY STREETS -LINN / 3RD / 4TH / 5TH / CITY HALL PARKING |  |  | 22892.64 | 1216.02 | Fully Completed | I JOBS AND ROAD USE MONEY | 2009-07-24
Atlantic | Crack Sealing of several streets | Several streets througout the City | 31696.42 | 38566.28 | 38566 | 38566 | Fully Completed | I-JOBS Funds | 2011-04-07
| Crack sealing of various streets | Various locations in the City of Atlantic |  |  | 22830.5 | 22830.5 | Fully Completed | I JOBS | 2010-10-13
Auburn | portion of expense to repave parking area along Hwy 71 | Pine Street | 1292.84 | 1573.05 | 5000 | 1292.84 | Fully Completed | IA Dot | 2010-04-29
| repair/maintenance/street cleaning/snow removal wages | unknown |  |  | 13113.13 | 1573.05 | Fully Completed | IJOBS | 2011-06-30
Audubon | Asphalt overlay and/or seal coating of several streets | Various blocks within the City limits | 10403.87 | 12658.8 | 23079.81 | 12658.8 | Fully Completed | I-JOBS funds and Local Option Tax funds | 2010-08-20
| asphalt overlay of street | Seventh Avenue |  |  | 37287.73 | 10403.87 | Fully Completed | stimulus funds and local option tax funds | 2009-09-30
Audubon County | Purchase of Granular Material | McAlister Bayard Pit | 74617.8 | 91538.35 | 230000 | 91538.35 | Fully Completed | Secondary Road Funding | 2010-07-06
| Purchase of Granular Material and hauling | 2147 Highway 71, Audubon, IA 50025 & 408 W. Washington St., Exira, IA 50076 |  |  | 126856.31 | 74617.8 | Fully Completed | ijb461-6000-461, Secondary Funding | 2009-10-22
Aurelia | Asphalt rubber crack repair, Infrared patching, and skin patching | Locust Street, W. 3rd Street, Hill Street, 4th Street, 5th Street, 7th Street, Maple Street, Pearl Street, Main Street, Myrtle Street, Beech Street, Miller Drive, Pitcher Drive, Alleyways | 4638.5 | 5643.85 | 50317.7 | 5643.85 | Fully Completed | I-Jobs and Road Use Tax money | 2010-11-03
| Milling of existing asphalt along gutter 7' wide and 1 1/4 inch depth followed by furnishing and installing a 1 1/4 asphalt overlay. | 7th Street between Myrtle & Walnut 7th Street between Walnut & Willow Pearl Street between 6th & 5th Pearl Street between 4th & 3rd Pearl Street between 3rd & 2nd |  |  | 40217 | 4638.5 | Fully Completed |  | 2009-09-22
Aurora | Street light repairs, road rock to fill pot holes in alleys and city park road ways | Main street , city alleys, park road way | 478.61 | 582.35 | 191 | 191 | Fully Completed | RIIF funds & road use funds | 2010-08-13
| TGS2 Tailgate Sander | Fairbank |  |  | 2035 | 478.61 | Fully Completed | Road Use Tax Funds | 2009-12-09
Ayrshire | Street Lighting | In City of Ayrshire | 591.19 | 719.32 | 591.19 | 0 | Not Started |  | 2009-11-30
Badger | repair and add new storm drainage tile to intersection. This project will be done with the county. No bid letting has been done at this time and project start and finish date is unknown. | intersection if P-59 and Center Avenue | 2664.3 | 3241.76 | 30000 | 5906.06 | Fully Completed | other funding source will be from RUT money and General Fund | 2010-09-30
Bagley | Asphalt resurface | 2nd Avenue | 1415.21 | 1721.94 | 28780.8 | 1721.94 | Fully Completed | I-JOBS & Road Use Tax | 2010-09-21
| asphalt resurfacing | Main street from highway 141 south to 2nd St |  |  | 26828.4 | 1415.21 | Fully Completed |  | 2009-09-23
Balltown | snow removal Horseshoe RD maintenance | Horseshoe Road Balltown | 114.64 | 139.49 | 414.31 | 114.64 | Fully Completed | I-Jobs street finance | 2010-03-30
| Snow removal Horseshoe RD Maintenance | Horseshoe RD Balltown |  |  | 460.63 | 139.49 | Fully Completed | I-Jobs street finance | 2011-03-30
Barnes City | Patch and single seal coating | Elm Street between Pine and Spruce Streets | 558.84 | 679.96 | 27000.96 | 558.84 | Fully Completed |  | 2009-06-23
| Street repairs in Barnes City | North Cherry Street (V13) |  |  | 1000 | 679.96 | Fully Completed | IJOBS and Town of Barnes City | 2010-12-07
Barnum | alley patch, mill out and patch back in with hot mix asphalt | behind Post Office, alley between West Street and Center Street | 851.7 | 1036.3 | 500 | 500 | Fully Completed |  | 2009-08-03
| mill out and patch back in with hot mix asphalt | Intersection of Center Street and Pierce Street |  |  | 300 | 300 | Fully Completed |  | 2009-08-03
| Mill out and patch back in with hot mix asphalt, water main patch | Pierce Street across from the school |  |  | 1750 | 51.7 | Fully Completed |  | 2009-08-03
| Repair area on Center Street around railroad crossing. As reported previously, City is in contact with railroad and will work with railroad to complete street repairs when old tracks are removed. | Center Street railroad crossing |  |  | 1888 | 0 | Fully Completed | I-JOBS and City Street Financial | 2011-05-27
| Repair area on Center Street. Areas discussed were around telephone pole on south side of street, railroad crossing, and patching areas on East end of Front Street. After contacting railroad, council decided to wait until spring after railroad completes w | Center Street and Front Street, Barnum, IA |  |  | 0 | 0 | Not Started | I-JOBS and City Street Financial | 2011-06-30
| Repair area on Center Street. Areas discussed were around telephone pole on south side of street, railroad crossing, and patching areas on East end of Front Street. After contacting railroad, council decided to wait until spring after railroad completes w | Center Street and Front Street, Barnum, IA |  |  | 5375 | 0 | Not Started | I-JOBS and City Street Financial | 2011-06-30
Bassett | Snow removal in Bassett, Iowa | BASSETT CITY HALL | 150.06 | 182.58 | 536.87 | 332.64 | Fully Completed | I-JOBS | 2011-09-30
Batavia | Repair to city tractor used for road and ditch maintenance. | Throughout city. | 2183.85 | 2657.18 | 2367.89 | 2183.85 | Fully Completed |  | 2009-09-24
Battle Creek | To repair and/or maintenance streets | To be determined | 3245.2 | 3948.57 | 80000 | 7193.77 | Fully Completed | IJOBS | 2010-02-25
Baxter | Engineering Design for partial street reconstruction to include curb and gutter. | S. West Avenue | 4594.82 | 5590.7 | 8388 | 0 | Fully Completed | Road Use/I-Job Funding | 2011-06-23
| Patch damaged areas of streets. | Community-wide |  |  | 1797.75 | 0 | Fully Completed | Road Use/I-Jobs Funding | 2012-05-31
| Resurface intersection. Patch various areas around town. | State Street & Harrison Ave. Various streets as needed. |  |  | 1797.75 | 1797.75 | Fully Completed | Road Use | 2010-07-08
Bayard | City wide sealcoating design services | Bayard, Iowa | 2341.09 | 2848.5 | 3900 | 2341.09 | Fully Completed |  | 2009-07-21
Beaman | The project will not be started until spring. | City of Beaman | 810.7 | 986.42 | 15000 | 1797.12 | 50% or More Complete | I-Jobs and City of Beaman | 2011-08-30
Bedford | These funds will be used to do full depth patching on existing concrete streets and gravel for spot repairs in public alleys. | Various locations around town. | 7075.68 | 8609.26 | 17500 | 15684.94 | Fully Completed | general fund | 2011-06-10
Belle Plaine | Repair of Streets | Belle Plaine | 12570.25 | 15294.72 | 570.25 | 570.25 | Fully Completed | I jobs funding | 2010-01-21
| Sealcoating & Patch Work of Streets | 4th Avenue 1st Avenue & 16th Street to 77th Street |  |  | 12000 | 12000 | Fully Completed |  | 2009-08-06
| Street Repairs in Belle Plaine | Belle Plaine Streets |  |  | 15865 | 15294.72 | Fully Completed | I-Jobs Revenue | 2012-09-30
Bellevue | Jefferson and 7th Street Paving Project | Jefferson and 7th Street | 10264.1 | 12488.74 | 212297.11 | 12488.74 | Fully Completed | IJobs Revenue Borrowed funds | 2011-09-30
| Jefferson Avenue reconstruction | Jefferson Avenue starting at Sunrise Court running south to North Motte Street |  |  | 15000 | 10264.1 | Fully Completed | IJobs Revenue | 2010-06-30
| Replace water main and reconstruct Jefferson Street | Jefferson Street starting at 4th Street and continuing to 7th Street. |  |  | 0 | 0 | Not Started | I Jobs Revenue Local Option Sales Tax Utility Funds | 2011-06-30
Belmond | We are going to repair portions of street that have deteriorated in at least four locations | Throughout the city | 11181.32 | 13604.75 | 26058.8 | 8077.3 | Fully Completed | About $8000 will be from I-Jobs and roughly $14,000 from Streets funding | 2010-08-13
| We are going to replace manholes in the area of the city that receives flooding - the flooding comes back up through the storm sewers then infiltrates the sanitary sewer system. The river waters become contaminated but most importantly the flooded waters | Manholes east of the Iowa River, west of 3rd Avenue NE and north of 5th Street SE to the city boundary. |  |  | 22000 | 15050 | Fully Completed | I-Jobs funding | 2010-09-30
| We have replaced manholes in the area of the city that receives flooding - the flooding comes back up through the storm sewers then infiltrates the sanitary sewer system. The river waters become contaminated but most importantly the flooded waters, out o | Along U.S. Highway 69 and on 3rd Street NE near 8th Avenue NE |  |  | 1700 | 3317.54 | Fully Completed | I-Jobs | 2010-09-07
Bennett | Emergency Repair sink hole created by broken sewer line | South of hiway 130 between Main Street and 6th street | 1497.68 | 1822.29 | 1400 | 1208.27 | Fully Completed | I-Jobs funds | 2012-07-30
| Replace and restore sidewalk | Sidewalk on south side of 3rd St. from Main to alley. Sidewalk on East side of Main St from 3rd St intersection to end of City Equipment bldg. |  |  | 7799.22 | 2111.7 | Fully Completed | I-Jobs, Leland Smith Foundation Grant and Community Club donation, & LOST funds | 2012-06-30
Benton | Provide and install 2 24" HDPE pipe for culvert repair Moblization Ditch Cleaning | Town of Benton | 174.71 | 212.57 | 3403.15 | 174.71 | Fully Completed | I-jobs money and FEMA money received | 2009-08-03
| Replace Gravel on several streets in the town of Benton |  |  |  | 910.58 | 212.57 | Fully Completed | I jobs money and FEMA money received | 2010-09-21
Benton County | PCC Full Depth Patching | On Benton County road E66 from the south city limits of Norway south and east to US Hwy 151 (3.7 mi.) | 138827.32 | 168846.07 | 96395.68 | 96395.68 | Fully Completed | Secondary Road fund | 2009-10-07
| PCC Full Depth Patching on Benton County road E44 | On Benton County road E44 between Newhall and Atkins |  |  | 65958.5 | 42431.64 | Fully Completed | Secondary Road fund | 2009-10-14
| Purchase of Gravel for Roads | Benton County Secondary Roads |  |  | 168846.07 | 168846.07 | Fully Completed | I-JOBS | 2012-06-30
Berkley | City Street Lighting Bills | Various Streets in Berkley, Iowa | 59.67 | 72.6 | 132.83 | 132.27 | Fully Completed | I-JOBS and RUT | 2011-05-31
Bettendorf | 31st Street Reconstruction PCC grade adjustment at IC&E RR crossing | 31st Street South of State Street | 136525.66 | 166116.14 | 82836.61 | 81487.16 | Fully Completed | I-JOBS Funds | 2010-06-30
| Replacement of vehicle number 0027, 2001 International 4900, with a similar single axle dump truck to be used primarily for street maintenance and repair. The truck will also be equipped with a snow plow and related equipment. | Municipal Maintenance Center 4403 Devils Glen Rd Bettendorf, IA 52722 |  |  | 99298.32 | 96018 | Fully Completed | $55,038.50 of remaining FY 2010 I-JOBS allocation plus $44,259.82 of the FY 2011 I-JOBS allocation. Any additional costs will be funded by City's Vehicle Replacement Fund. | 2011-06-30
| Replacement of vehicle number 0121, 2002 International 4900, with a similar tandem axle dump truck to be used primarily for street maintenance and repair. The truck will also be equipped with a snow plow and salt spreader equipment. |  |  |  | 126291.89 | 125136.64 | Fully Completed | $121,856.32 of FY 2011 I-JOBS funding. Any additional costs will be funded by City's Vehicle Replacement Fund. | 2011-06-30
Bevington | Hut for mail boxes | Bevington | 200.71 | 244.21 | 1700 | 200.71 | Fully Completed | City of Bevington | 2010-02-03
Birmingham | Repair damaged culvert. | Mohawk Street, Birmingham, IA | 1353.97 | 1647.43 | 1482.28 | 1353.97 | Fully Completed | Road Use Tax Fund | 2009-10-29
| Repair plugged Storm Sewer | 211 S. Cross Street |  | 1647.43 | 1800 | 256.62 | Fully Completed | IJobs Grant and Road Use Tax | 2011-04-05
| Repaired broken culvert in storm sewer. | 240 N. Liberty Birmingham, IA |  | 1647.43 | 325.85 | 651.7 | Fully Completed | I-Jobs Grant | 2010-12-08
Black Hawk County | 217.3 ton road deicing salt | Secondary Roads | 121195.5431 | 145676.72 | 16650.92 | 33301.84 | Fully Completed | Secondary Roads | 2012-01-27
| 333.63 ton deicing road salt | Secondary Roads |  |  | 23137.25 | 38274.5 | Fully Completed | Secondary Rd Fund | 2012-01-25
| Brandon Rd Bridge Replacements Final Design Phase 1 - Supplemental Agreement 5 and Phase 2 - Supplemental Agreement 5 | Brandon Road Section 19 & 20, T87N, R11W |  |  | 515000 | 121195.54 | Fully Completed | Ijobs | 2011-06-30
| culverts, tierods, fabric | Wagner Rd |  |  | 5000 | 8108.8 | Fully Completed | Secondary Roads | 2012-05-15
| Final design | Fox Road Bridge over Spring Creek |  |  | 19500 | 6913.56 | Less than 50% Complete | Secondary Roads | 2012-05-31
| installation of ceiling fans | Gilbertville Secondary Roads facility |  |  | 872 | 1744 | Fully Completed | Secondary Roads | 2012-02-03
| Power sweep for debris removal | Raymar addition |  |  | 562.5 | 1125 | Fully Completed | Secondary Roads | 2012-03-15
| repair flashing traffic signal light | Dunkerton Rd and Raymond Rd Intersection |  |  | 1188.42 | 2376.84 | Fully Completed | Secondary Roads | 2012-03-15
| Replacement dump box truck #32 | Secondary Roads |  |  | 13365 | 26730 | Fully Completed | Secondary Roads | 2012-02-07
| replacement pipe culverts and anchors | Dunkerton Rd |  |  | 20000 | 39482.9 | Fully Completed | Secondary Roads | 2012-02-28
| roadstone | secondary roads |  |  | 4600 | 9009.8 | Fully Completed | Secondary Roads | 2012-04-03
| roadstone | secondary roads |  |  | 7000 | 12795.58 | Fully Completed | Secondary Roads | 2012-04-17
| roadstone | secondary roads |  |  | 8000 | 15259.26 | Fully Completed | Secondary Roads | 2012-05-01
| roadstone | Secondary Roads |  |  | 9000 | 17058.82 | Fully Completed | Secondary Roads | 2012-05-08
| roadstone | Secondary Roads |  |  | 25000 | 48547.22 | Fully Completed | Secondary Roads | 2012-05-22
| roadstone for various county roads | Secondary Roads |  |  | 2400 | 4668.42 | Fully Completed | Secondary Roads | 2012-04-17
| roadstone for various county roads | secondary roads |  |  | 9000 | 17956.9 | Fully Completed | Secondary Roads | 2012-04-24
Blairsburg | Asphalt resurfacing | Second Street and Main Street repairs to streets | 943.63 | 1148.15 | 1822.6 | 943.63 | Fully Completed |  | 2009-07-28
| Filling holes and doing patching repairs. | Second Street and Main Street |  |  | 1500 | 1148.15 | Fully Completed | Road Use Tax Fund | 2011-08-08
| Filling of holes and patching repairs. The City is on the Pavement Doctor's Schedule to be done as soon as possible within the next couple of months. At this time, we do not know the exact cost of the same, but is approximately $1,500.00. | Especially Lake Street and will be doing patching repairs on any other City streets in need of the same. |  |  | 1500 | 0 | Not Started | Road Use Fund | 2010-08-30
Blairstown | Repair all pot holes in city streets before winter | throughout city | 2978.77 | 3624.39 | 2500 | 1000 | Less than 50% Complete |  | 2009-11-20
| Repair and replace street signs throughout the city |  |  |  | 3000 | 1100 | Less than 50% Complete |  | 2009-10-30
Blakesburg | Raising manhole covers for road work | Franklin St. and Mill St. | 1178.79 | 1434.28 | 1500 | 451.79 | Fully Completed | IJOBS and RUT was used for this project. | 2010-06-30
| Road Manhole risers and improvements | alleyway on Polk corner of Monroe and State St. Corner of Cass and High |  |  | 1800 | 1454 | Fully Completed | Ijobs and RUT were used on this report | 2009-11-05
| rock for alleyways, roads and lagoon access road | Blakesburg |  |  | 2000 | 0 | Fully Completed | I-Jobs | 2010-11-01
Blanchard | GRAVEL APPLICATION ON CITY STREET | NORTH ST | 173.81 | 211.49 | 663.45 | 385.3 | Fully Completed | ROAD USE TAX | 2010-07-30
Blockton | gravel and blading of roads | around town as necessary | 675.17 | 821.5 | 3163.86 | 821.5 | Fully Completed | I JOBS and RUT | 2010-07-07
| gravel and blading on city streets | as needed around town |  |  | 675.17 | 675.17 | Fully Completed | I Jobs and Community Disaster Grants | 2009-11-24
Bloomfield | Plan to purchase a roller for the Street Department to help with street construction. | To be determined | 11360.4 | 13822.64 | 11360.4 | 0 | Not Started | The entire amount of I-Jobs money we received, $11,360.40, plus around $3,000 to $3,500 of City monies will be needed to purchase the roller | 2010-02-28
| Purchased a BOMAG BW900-2 TANDEM ROLLER in the total amount of $14,000 | Purchased from Carroll Distributing, Ottumwa, IA 52501 |  |  | 14000 | 11360.4 | Fully Completed | I-Job funds of $11,360.40 and City funds of $2,739.60 | 2010-02-01
Blue Grass | 1st Quarter Reporting - project fully completed | Blue Grass, Iowa | 5105.84 | 6212.48 | 0 | 0 | Fully Completed | I-JOBS/road Use Funds | 2010-06-30
| I-JOBS monies were allocated to the City's 2010 Sealcoat Project of several streets. Construction to begin June 2010. |  |  |  | 50003.63 | 5105.84 | Fully Completed | I-JOBS/Road Use Funds | 2010-06-30
| I-JOBS monies were allocated to the City's 2011 Sealcoat Project consisting of several streets. Construction began in June 2011. |  |  |  | 42141.84 | 6212.48 | Fully Completed | I-JOBS monies and Road Use Funds | 2011-07-31
Bode | To be determined | Within City Limits | 1018.89 | 1239.72 | 5000 | 0 | Not Started | I jobs funding | 2010-03-30
| To be determined, project will be completed once trhe weather cooperates. |  |  |  | 5000 | 0 | Not Started | i jobs funding | 2010-06-30
Bonaparte | Purchase pumper for the fire department. | Bonaparte Fire Department | 1489.75 | 1812.64 | 1812.64 | 1812.64 | Fully Completed | State Central Bank Farmington, Iowa | 2011-05-13
| Seal coat Lions Street that had been gravel. Pull in shoulders on misc. streets. | 200 block of Lions Street and misc streets in Bonaparte |  |  | 1489.75 | 1489.75 | Fully Completed | IJOBS $1489.75 Road Use Funds 411.35 | 2009-06-23
Bondurant | 2011 Ford F350 4WD 1 TN Reg Cab SL SRW truck | 200 Second St NE Bondurant, IA | 12998.28 | 15815.52 | 19927 | 15815.52 | Fully Completed | I-JOBS | 2010-08-20
| Class A Rock 55.25 Ton | Des Moines, IA |  |  | 665.76 | 665.76 | Fully Completed | I-JOBS | 2009-09-14
| Crack Sealing NE 80 St/NE 94th Ave to N side of I-80 Bridge | NE 80 St/NE 94th Ave to N side of I-80 Bridge |  |  | 7875.73 | 7875.73 | Fully Completed | I-JOBS | 2009-11-30
| Haul Rock and Blade Road | Garfield St SW, Bondurant, IA from 15th St SW to Hwy 330/65 |  |  | 1280.79 | 1280.79 | Fully Completed | I-JOBS | 2009-09-11
| Haul Skid Sand 7 loads 110 ton | Ankeny, IA |  |  | 495 | 495 | Fully Completed | I-JOBS | 2009-10-27
| Mixed Skied Sand - 110 ton for winter roads | Des Moines, IA |  |  | 2123 | 2123 | Fully Completed | I-JOBS | 2009-11-19
| Snow Fence Posts w/ Anchors 50@6.5' | Ames, IA |  |  | 247.5 | 247.5 | Fully Completed | I-JOBS | 2009-09-28
| Snow Fence Qty-6 of 4'x100' |  |  |  | 310.5 | 310.5 | Fully Completed | I-JOBS | 2009-09-30
Boone | Router, blowout and seal cracks along city streets HAD TO CHANGE START AND END DATE DUE TO WET WEATHER | Boone,Ia | 55919.7 | 68039.7 | 113135 | 49553 | Fully Completed | I-Jobs Grant | 2010-07-31
Boone County | Annual Graveling operations throughout Boone County. The contract covers crushing appropriate amounts of gravel and hauling it to designated areas around Boone County | Throughout Boone County on appoximately 742 miles | 108070.95 | 131702.91 | 394063.22 | 239773.86 | Fully Completed | Secondary Road Fund | 2010-10-01
Boxholm | DID SOME PATCHWORK AT 4TH AND BEECH NEAR THE COOP | 4TH AND BEECH NEAR THE COOP | 809.36 | 984.77 | 400 | 400 | Fully Completed | IJOBS | 2010-10-12
| PUT DOWN ROAD GRAVEL AT 4TH AND WALNUT NEAR SCHOOL PARKING LOT | 4TH AND WALNUT NEAR SCHOOL |  |  | 820 | 584.77 | Fully Completed | IJOBS AND ROAD USE FUND | 2010-10-27
| ROAD REPAIRS AT BEECH AND 3RD AND 4TH STREETS AND INTERSECTION OF 2ND STREET | 3RD & 4TH AND BEECH AND INTERSECTION OF 2ND |  |  | 1450 | 809.36 | Fully Completed | ROAD USE FUNDS AND IJOBS FUNDS | 2009-11-12
Boyden | Concrete patching to repair and stabilze portions of existing City Streets. | South Sheridan Street from the intersection of Railroad Street to the intersection of Southern Street | 2935.1 | 3571.25 | 8603 | 0 | Fully Completed | I JOBS & RUT Funds | 2011-09-01
| Concrete patching to repair and stablize portions of existing city streets. | W Webb street cudesac; W Prairie Street intersection; S Grant Street; S Lincoln Street; S Sherman Street; S Main Street; E Walnut Street. |  |  | 8422.5 | 3571.25 | Fully Completed | Road Use Tax Fund | 2010-10-21
| Hot-mix asphalt patching to repair and stabilize portions of existing city streets. | S. Lincoln Street between Webb St. & Railroad St. intersections; E Webb St. at Aurora St intersetion; and Pleasant St. and Blaine St. intersection |  |  | 9750 | 2935.1 | Fully Completed |  | 2009-08-03
Brayton | gravel depot & clinton streets | depot & clinton streets | 387.37 | 471.33 | 387.37 | 387.37 | Fully Completed | I-Jobs & City of Brayton | 2009-10-16
| purchase of Cold Patch to Repair Winter Road/Street Damage | City of Brayton |  |  | 1913.36 | 471.33 | Fully Completed | I-Jobs & City of Brayton | 2010-10-01
Breda | Repairing alley approaches | Alley between Main Street and Bruning Street on the west side of the block, in the 100 Block. | 1729.42 | 2104.25 | 4500 | 1729.42 | Fully Completed | I Jobs Funding and Road Use Funds | 2009-10-16
[5 empty] | 2500 | 1729.42 | Fully Completed | IJOBS and road use tax funds | 2009-10-26
| Repairing Alley approaches/curb and gutter | Alley between Main Street and Maple Street in the 200 block on the west side of the block |  |  | 4000 | 374.83 | Fully Completed | I Jobs Funding and Road Use Funding | 2010-07-10
Bremer County | Contract Maintenance, Furnish and applied Center line paving marking and edgeline marking to approx. 80 mi. of county paved system. | Various locaton within Bremer County | 88549.02 | 109792.8 | 30000 | 0 | Fully Completed | Secondary Road Fund | 2009-09-18
| Full Depth Reclamation with HMA Resurfacing. Let June 7, 2010 | 0.758 Miles of Roadway within Huber Subdivision, Sec 26, T-91N, R-14W. |  |  | 150620.25 | 120553.39 | Fully Completed | Local LOST FUNDS | 2010-09-02
| Piling for Day Labor Bridge Constrution and Bridge Maintenance | County Yard |  |  | 22325 | 22325 | Fully Completed | Secondary Road Fund | 2010-05-10
| Stock material for day labor bridges construction and bridge maintenance. | County yards |  |  | 55463.43 | 55463.43 | Fully Completed | Secondary Road Funds | 2010-05-10
Bridgewater | Ditch and culvert repair within city limits | East 4th Street | 553.39 | 673.34 | 0 | 0 | Fully Completed | I-Jobs and Bridgewater Road Account | 2009-10-14
| Maintain culvert and rain water runoff conversion | Main street east to NE Oak Street |  |  | 860 | 673.34 | Fully Completed | IJOBS and City of Bridgewaer Road Account | 2011-02-28
| Repair washouts in ditches | Main, Maples and north |  |  | 775 | 553.39 | Fully Completed | IJOBS and Bridgewater Road account | 2010-07-31
| The City of Bridgewater has not selected a project at this time | bridgewater |  |  | 0 | 0 | Fully Completed | IJOBS | 2009-09-30
Brighton | 32.21 tons of patch mix delivered and placed | streets within the city limits of Brighton | 3000.61 | 3650.96 | 2011.81 | 0 | Fully Completed | Road Use Tax Fund | 2010-06-14
| Patch crew plus material to patch potholes. | Brighton City Streets |  |  | 3650.96 | 3560.96 | Fully Completed | Road Use Tax Funds & IJOBS | 2011-09-07
| Removed old broken street tube and replaced it with a new one | 100 Block of East Railroad Street |  |  | 988.8 | 988.8 | Fully Completed | Road Use Tax Fund | 2009-10-08
Bristow | we are continuing to rock streets and alley used by the publc | Railroad st and 3 blocks of alleys behind Main st | 526.46 | 640.57 | 750 | 640.57 | Fully Completed | road use tax | 2010-07-31
| WE WILL BE USING THE EXTRA FUNDS TO ROCK ALLEYS IN TOWN THAT ARE FOR PUBLIC USE. WE HAVE NOT COMPLETED THE PROJECT AT THIS TIME BUT SHOULD BE DONE IN ABOUT A WEEK Locations to be determined | BRISTOW IOWA |  |  | 557.01 | 526.46 | Fully Completed | road use tax fund | 2009-10-12
Britt | Concrete Joint Repair cracks sawed 1/2" wide by 3/4" deep, cleaned of debris and filled flush with MN DOT 3723 ruberized sealant | 1st Ave SW to 8th Ave SW and 5th Street SW, 7th Street SW and 9th Street SW | 8962.53 | 10905.06 | 19250.15 | 10905.06 | Fully Completed | I jobs and local option sales tax | 2011-09-08
| PCC hot pour joint sealing and crack repair | nine blocks of 1st Ave from 2nd Street NW to 7th Street SW |  |  | 10000 | 8962.53 | Fully Completed | Local Option Sales Tax | 2009-08-18
Bronson | TARING AND REPAIRING OF THE STREETS | VARIOUS STREETS/TO BE DETERMINED YET. | 917.09 | 1115.86 | 2230.2 | 917.09 | Fully Completed | I JOBS | 2009-11-02
Brooklyn | Brooklyn has not decided on a project at this time | Brooklyn, Iowa | 5970.65 | 7264.72 | 0 | 0 | Not Started | none | 2011-03-31
| Brooklyn has not yet decided on a project to use the $5970.65. | Brooklyn, Iowa |  |  | 0 | 0 | Not Started | none at this time | 2010-03-08
Brunsville | Clean or sweep Streets in City of Brunsville. | Brunsville, IA | 637.68 | 775.9 | 1475 | 775.9 | Fully Completed | I Jobs Funds | 2011-05-26
| Gravel Elm St., Brunsville, Iowa | Elm St. Brunsville, IA |  |  | 447.97 | 317.8 | Fully Completed | I Jobs Funding | 2010-04-15
| Pave entrance into Recycle Bin | Ash Street, Brunsville, Iowa |  |  | 0 | 0 | Not Started | I Jobs Funds | 2011-06-30
[5 empty] | 775.9 | 0 | Not Started | I Jobs Funds | 2011-06-30
| Repair entrance driveway to Recyle Bin | Ash St., Brunsville, IA |  |  | 319.88 | 319.88 | Fully Completed | I Jobs Funds | 2010-03-18
Buchanan County | Contracted Road Resurfacing | Northern half of Buchanan County including the townships of Fairbank, Hazleton, Buffalo, Madison, Fremont, Byron, Washington, and Perry | 117153.45 | 143009.48 | 143009.48 | 143009.48 | Fully Completed | I JObs Funds & Local funds | 2011-08-05
| Road resurfacing contracted |  |  |  | 117153.45 | 0 | Fully Completed | I-Jobs money and Local funds | 2010-06-30
Buck Grove | kane between 4th & 5th 5th st | to be dertermined | 154.25 | 187.68 | 3384.64 | 154.25 | Fully Completed | i jobs | 2010-06-30
Buckeye | We haven't determined when to do our roads yet | City Of buckeye | 337.3 | 410.41 | 0 | 0 | Not Started | ijobs | 2010-06-22
Buena Vista County | Construct a structure to store ice control materials | County Maintenance yard 1910 Richland, Storm Lake, IA | 102509.06 | 121821.86 | 150000 | 131952.36 | Fully Completed | I-JOBS | 2012-03-16
| Recycle of stockpiled concrete and asphalt materials for use as edgerut materials | Storm Lake Maintenance Facility on Radio Road |  |  | 32500 | 32142.5 | Fully Completed | I-JOBS | 2011-04-22
| Replace existing bridge with Precast RC Box Culvert | West side Section 8 Grant Twp |  |  | 85000 | 60236.06 | Fully Completed | I-JOBS and local | 2011-05-27
Buffalo | Repair approach to HWY 22 on Oak Street | Spruce Street and HWY 22 | 5769.74 | 7020.26 | 2000 | 1950.2 | Fully Completed | I-Job | 2010-07-26
| Repair curb and street from water main break | Main Street and HWY 22 |  |  | 1780.93 | 1780.93 | Fully Completed | I-job | 2010-07-09
| Repair ditch and culverts | Spruce Street |  |  | 5000 | 5000 | Fully Completed | I-Jobs | 2010-09-24
| Repair street cave in and replace culvert below street | 200 Block of Fourth Street |  |  | 6164.8 | 4020.06 | Fully Completed | I-Jobs | 2010-06-01
Buffalo Center | street lighting for our city | all streets in our city | 4206.1 | 5117.73 | 4206.1 | 4206.1 | Fully Completed | IJobs | 2009-09-25
Burlington | 1 Ton Dump Truck for roadway maintenance - $35,000 | City-wide | 117224.78 | 142632 | 25000 | 21581 | Fully Completed | I-JOBS | 2010-06-30
| 2-1/2 TON DUMP TRUCK - $90,000 | CITY-WIDE |  |  | 94514 | 94514 | Fully Completed | I-JOBS | 2011-06-30
| 2-1/2 Ton Dump Truck for roadway maintenance - $75,000 | City-wide |  |  | 85000 | 82145 | Fully Completed | I-JOBS | 2010-06-30
| HFE 90 OIL FOR TOTAL PATCHER TO REPAIR CITY STREETS - $40,000 | CITY-WIDE |  |  | 40000 | 40000 | Fully Completed | I-JOBS | 2011-06-30
| PAINT FOR CITY STREETS - $12,632 | CITY-WIDE |  |  | 13510 | 8118 | Fully Completed | I-JOBS | 2011-06-30
| Purchase LED bulbs and indicators to provide more energy efficient signals - $26,200 | Traffic signals city-wide |  |  | 26200 | 5548.78 | Fully Completed | I-JOBS | 2010-05-17
| Snow plow for roadway maintenance - $9,000 | City-wide |  |  | 8000 | 7950 | Fully Completed | I-JOBS | 2010-06-30
Burt | 7th Street asphalt leveling | 7th Street from Beech Street to Bush Street | 2428.44 | 2954.78 | 2900 | 2428.44 | Fully Completed |  | 2009-09-03
| level & seal coat on Bush Street | Bush Street between 4th Street & 5th Street |  |  | 4231.64 | 2954.78 | Fully Completed | Road Use Fund | 2010-07-28
Bussey | Patch potholes and seal coat a city street. | Edwards street from 8th street to 6th street. | 1612.89 | 1962.46 | 3600 | 3575.35 | Fully Completed | $3575.35 from IJOBS funding and $24.65 from Road Use Tax. | 2010-10-07
Butler County | Purchase concrete pipe and aprons to replace and extend various culverts under C13 ahead of next years resurfacing | C13 | 109622.21 | 132967.55 | 25590.09 | 22565.15 | Fully Completed | IJOBS & Local | 2010-12-21
| Purchase of a backhoe for use in roadside management program | Allison Shop |  |  | 110925 | 109100.43 | Fully Completed | IJOBS | 2010-03-30
| Purchase of backhoe for use in roadside management program. Project is entered to shw that we expended 100% of FY2010 IJOBS funds. | Allison |  |  | 110925 | 521.78 | Fully Completed | IJOBS | 2010-03-22
| Purchase of corrugated metal pipe culverts | Various |  |  | 10402.4 | 10402.4 | Fully Completed | IJOBS | 2010-10-28
| Purchase tractor and boom mower for use in roadside management program | Allison shop |  |  | 100000 | 100000 | Fully Completed | IJOBS | 2010-10-19
Calamus | street repair and seal coating | calamus city streets | 1316.84 | 1602.26 | 1316.84 | 1316.84 | Fully Completed | i jobs | 2009-06-30
Calhoun County | 2009 Cat 140M motorgrader | Lake City | 94784.21 | 116134.22 | 162000 | 94784.21 | Fully Completed | Secondary Road Fund | 2009-08-11
| cutting edge and new rim for CAT loaders | Rockwell City |  |  | 3566.61 | 6000.44 | Fully Completed | Secondary Roads fund | 2012-06-29
| purchase a 2011 Cat 140M motorgrader with wing |  |  |  | 193000 | 113134 | Fully Completed | Secondary Road Fund | 2011-04-26
Callender | PURCHASED ROCK TO REPAIR STREETS | Callender, IA | 1350.67 | 1643.41 | 1382.1 | 1350.67 | Fully Completed | IJOBS | 2010-06-01
| To Be Determined Project Not Started Yet 12/2009 |  |  |  | 0 | 0 | Not Started | Project not started yet 12/2009. | 2009-09-30
Calmar | Asphalt 6 feet of the parking area along West Main street from Washington to Charles on both sides of the street | West Main street from Washington to Charles | 4621.03 | 5622.59 | 4621.03 | 4621.03 | Fully Completed |  | 2009-09-17
| Chip and seal cracks and bad areas of the street with the the chip seal machine. | Various City streets |  |  | 5622.59 | 5622.59 | Fully Completed | I job funds | 2010-09-14
Calumet | Repair the potholes on the streets of Calumet. Apply crushed red rock to places where the blacktop is showing through. | Calumet, Iowa | 672.97 | 818.83 | 19799.12 | 1491.8 | Fully Completed | Road Use Fund & Taxation | 2010-07-31
Camanche | Plan to place asphalt overlay on portion of Washington Blvd | Washington Blvd | 18409.87 | 22400.01 | 110000 | 40809.88 | Fully Completed | I-JOBS money and exisiting cash reserves | 2010-06-10
Cambridge | Repair or maintenance of additional residential streets beyond usual budgeted amounts. | 7th Street and Main Street north of 4th Street | 3577.15 | 4352.46 | 7707.2 | 3577.15 | Fully Completed | Road Use Tax Fund and General Fund | 2009-10-13
Carbon | Gravel for Streets | Streets of Carbon Carbon IA | 68.4 | 83.22 | 100 | 68.4 | Fully Completed |  | 2009-03-01
Carpenter | The project is to Chip Seal City Streets | Carpenter City Streets | 353.58 | 430.22 | 27500 | 783.8 | Fully Completed | IJOBS and RUT Money | 2010-05-07
Carroll | hot mix asphalt resurfacing, water main, and storm sewer improvements | Burgess Avenue from W. 6th Street to US Hwy 30 Heires Avenue from US Hwy 30 to US Hwy 71 7th Street from Simon Avenue to Crawford Street 7th Street from West Street to East Street | 44105.06 | 53664.37 | 656440.05 | 97769.43 | Fully Completed | I-JOBS funds, Road Use Tax Funds, and storm water and water utility user fees | 2010-11-30
Carroll County | 40,000 ton stockpile of road gravel at packer pit | Section 26-86-34 Calhoun County Iowa | 105732.32 | 130461.8 | 161200 | 130461.8 | Fully Completed | I Jobs and Local Funds | 2010-08-20
| PURCHASE 1 NEW CATERPILLAR 140M MOTORGRADER | CARROLL COUNTY, IOWA |  |  | 253000 | 105732.32 | Fully Completed | Secondary Road and I-Jobs | 2009-11-15
Carson | Repair streets. Cut out cracked concrete and replace. | 321 South Oak St, intersection of Vine Street/South Oak, Intersection of Vine Street/South Central. | 2917.63 | 3549.99 | 3000 | 2483.45 | 50% or More Complete |  | 2009-09-30
Carter Lake | Locust Street masterscaping - street replacement and street scaping | Locust St. Eastern city limits to 5th Street | 14186.3 | 17261.03 | 4787000 | 31447.33 | 50% or More Complete | STIP, State Recreational Trails, TIF Revenue bonds, IJOBS | 2011-06-30
Cascade | Resurface two alleys with hot mix asphalt. | Downtown alley that lies between 1st & 2nd Avenue SW and Lincoln & Johnson Street. Residential alley between 1st & 2nd Avenue NW and Cleveland and Arthur Strees. | 8551.96 | 10405.51 | 23857.83 | 18957.47 | Fully Completed | I-Jobs | 2010-11-05
Cass County | Full Depth PCC Patching Cass County Route M-56 | 560th Street from Marne city limits to Shelby Co. line and 570th Street from White Pole Road to Highland Road. | 90066.79 | 111310.93 | 95324 | 90006.79 | Fully Completed | $65,442.62 - RIIF, $24,624.17 - ARRA Block Grant, $5,257.21 - Local 467 PCC Paving. Total contract amount = $95,324.00 | 2010-03-09
Castalia | To replace sidewalk and truck entrance | Fire Station and City Hall | 472.61 | 575.04 | 4476 | 1047.65 | Fully Completed | I-Jobs and Road Use Funds | 2010-09-30
Cedar County | Bridge Repair/Strengthening to achieve a legal rating | Y14 south of Lowden in Section 2, T81N R1W of Springfield Township | 109540.63 | 130811.28 | 50000 | 45371 | Fully Completed | Secondary Road Fund | 2009-12-16
| Bridge replacement project at 510 Rose Avenue | Rose Avenue in Section 36, T82N R2W of Dayton Township |  |  | 70000 | 63580 | Fully Completed | Secondary Road Fund | 2009-11-03
| Bridge replacement project at 860 Kelly Avenue | Section 14, T81N R3W in Red Oak Township on Kelly Avenue |  |  | 73000 | 72963.84 | Fully Completed | Secondary Road Fund | 2009-09-02
| Bridge replacement project on Washington Avenue | Section 11, T-82N R-1W in Massillon Township |  |  | 85000 | 58437 | Fully Completed | I-Jobs/Secondary Road Fund | 2010-09-01
Cedar Falls | City wide hot and cold patching | city wide | 157870.62 | 192087.4 | 35000 | 25759 | Fully Completed | Road Use Tax/IJOBS | 2011-06-30
| City Wide Salt and Sanding | City Wide |  |  | 105000 | 104779.16 | Fully Completed | IJOBS/Road Use Tax | 2010-06-30
| City Wide Salt and Sanding | Cedar Falls - city wide |  |  | 150000 | 149619.45 | Fully Completed | Road Use Taxes/IJOBS | 2011-06-30
| Crack Sealing city wide project | City wide |  |  | 70000 | 53091.46 | Fully Completed | IJOBS | 2010-06-30
| Crack Sealing city wide project | Cedar Falls - city wide |  |  | 20000 | 16708.95 | Fully Completed | Road Use Taxes/IJOBS | 2011-06-30
Cedar Rapids | 3rd Street SE Reconstruction and Streetscape Improvements from 8th Avenue SE to 14th Avenue SE | 3rd Street SE from 8th Avenue SE to 14th Avenue SE | 529487.89 | 644248.75 | 4594621.6 | 126000 | Fully Completed | City GO Bonds and Road Use Tax Funds | 2011-12-31
| Milling of existing asphalt pavement, partial depth and full depth repairs to original PCC pavement, construction of HMA widening pavement, HMA overlay of orginal pavement and widenings, shouldering and pavement markings. | 6th St SW (IA 965), Swisher Turn-off to Johnson County Line |  |  | 1200000 | 529487.89 | Fully Completed | Road Use Tax Fund and General Obligation Bonds | 2011-04-30
| Reconstruct Northland Avenue from the south side of the Rockwell Daycare (approx. 600' north of Collins Road) to the north City limit as 43' back to back roadway. Improve storm sewer system and prepare the corridor to accept planned improvements at Colli | Northland Avenue from 600' north of Collins Road to North City Limit |  |  | 1078300 | 518248.75 | Fully Completed | GO Bonds and Road Use Tax Funds. | 2011-12-31
Centerville | Double sealcoat numerous streets | East Prairie, Hwy 5 to Wilson; East Walden, 21st to East end; East Merion, Hwy 5 to Drake Avenue; South 23rd, Cottage to Oneal; North 3rd, VanBuren to West State | 25874.27 | 31482.24 | 28792 | 25874.27 | Fully Completed |  | 2009-08-10
Central City | Seal Coat City Streets | Second Street from State St.- Grove St. Seventh Street from Commercial - Main St. South Ave. from River St.-Marion Rd. Alley between North Ave. & Broadway, 1st & 2nd St. | 5053.43 | 6148.71 | 16216.99 | 5053.43 | Fully Completed | I-JOBS funds and Road Use Funds | 2009-10-06
Cerro Gordo County | 2011 County Stockpile for Road Stone | Portland Quarry near Mason City | 114224.66 | 132596.51 | 306000 | 92421.17 | Fully Completed | IJOBS/Local | 2011-04-30
| Precast Box Culvert Replacements | On County Road B60 1/2 mile east of Thrush Ave. On 195th Street west of Spruce. |  |  | 154400 | 154400 | Fully Completed | IJOBS/Local Dollars | 2010-09-30
Chariton | Extended alley approach to street with concrete | 7th Street 1/2 block north of Court Avenue | 19973.51 | 24302.55 | 135.3 | 0 | Fully Completed | I-Jobs | 2011-11-15
| Filled void under road with concrete, patched approx. a 24'x30' area with hot mix asphalt. | Ilion Avenue |  |  | 576 | 0 | Fully Completed | I-Jobs | 2011-11-17
| Install intake box, curb, gutter and shoulder on Albia Road to prevent road damage. | Started on 1st Street and went 54 feet west along Albia Road |  |  | 1592.37 | 1592.37 | Fully Completed | I-JOBS | 2010-09-08
| Rebuilt box on South side and replaced the culvert | 1400 Block of Lucas Avenue |  |  | 723.64 | 0 | Fully Completed | I-Jobs | 2012-04-02
| Reconstructed the intake box on the southeast corner of Grand and Osage. | Grand Street and Osage Avenue |  |  | 192.48 | 0 | Fully Completed | I-Jobs | 2012-03-23
| Repair storm intake in the 1700 block of Court Avenue | 1700 block of Court Avenue |  |  | 5500 | 0 | Fully Completed | I-Jobs | 2012-05-08
| Repaired a 12' x 35' section of broken up concrete approximately 100' west of 7th Street on the north side of Ilion Avenue and a 12' x 60' section of broken up concrete approximately 140' from 7th Street in the middle of Ilion Avenue | 700 Block of Ilion |  |  | 1425.95 | 1425.95 | Fully Completed | I-JOBS | 2010-10-11
| Repaired approx. a 10'x20' area on the west side and a 15'x15' on the east side of 8th Street. | Ashland Avenue and 8th Street |  |  | 207 | 0 | Fully Completed | I-Jobs | 2011-11-17
| Replaced approx. an 8'x60' section of concrete | 900 Block of Ashland Avenue |  |  | 1978.44 | 0 | Fully Completed | I-Jobs | 2011-11-30
| Replaced approximately a 14'x30' section of concrete. | 11th Street and Ashland Avenue |  |  | 1036.95 | 1036.95 | Fully Completed | I-Jobs | 2011-08-09
| Replaced plastic pipe, rebuilt box and replaced a section of concrete on the road | 1901 Osceola Avenue |  |  | 1014.19 | 0 | Fully Completed | I-Jobs | 2012-04-12
| Resurfacing and widening Albia Road | Albia Road from 5th Street to City Limits |  |  | 34248.67 | 34248.67 | Fully Completed | I-JOBS | 2010-04-27
Charter Oak | Edge mill then clean tack and overlay approximately 4,930 square feet with 2" hot mix ashpalt | 1st Street South between Aspen and Birch Street | 2314.88 | 2816.61 | 5100 | 2314.88 | Fully Completed | I-Jobs $2,314.88 Road Use $2,785.12 | 2009-09-18
Cherokee | Furnishing and installation of asphalt wedge on bridge approaches on Union St. followed by the furnishing and installation of the oil and chip single seal on Euclid, Willow, Union, Cedar and 5th Streets as agreed. Crack sealing on streets and downtown pa | Various streets as follows: Union, Euclid, Willow, Cedar, 5th, Pilot, River Road, N. 11th, Walnut, Centennial, Greta. Maple St. parking lot. | 23450.2 | 28532.78 | 54276.8 | 51982.98 | Fully Completed | I-Jobs funds - $51,982.98 Road Use tax - $2,293.82 | 2010-09-30
Cherokee County | Joint and crack repair and filling on asphalt surfaced road using Nuvogap material | C Ave. from HWY # 3 to 470'th Street in Cherokee County | 101096.83 | 122504.48 | 38610 | 38610 | Fully Completed | I-Jobs funding | 2009-10-07
| Materials for the repair of bridges Tilden 187, (FHWA # 108500), and Liberty 95, (FHWA # 109900). | Tilden 187 is located between B & C Aves. on 550'th street, and Liberty 95 is located between L & M Aves. on 470'th street. |  |  | 94120 | 38675 | Fully Completed | I-jobs and local funds | 2010-06-30
| Purchase of JD 772GP grader from Murphy Tractor in Sioux City, IA | Machine works in the southeastern part of Cherokee County |  |  | 190780 | 27673.11 | Fully Completed | I-jobs funding and local tax revenues | 2026-01-31
| Repair of the abutment and bridge pier piling due to fact bridge was closed from reccommnedations from Calhoun-Burns inspection conducted in August 2009. All wooden piling were replaced with steel H- piling supplied by Cherokee County | 3/4 mile west of the intersection of 600'th street and L- 40 in Chrerokee County. Site is along the north line of Sec. 6, T-90-N, R-42-W in Willow Township, Cherokee County |  |  | 30749.2 | 30749.2 | Fully Completed | I-Jobs funding | 2009-11-13
| Sealcoat C Ave. to provide for better sealing of roadway, to protect the joint repair work done in 2009, and to provide additional life to the roadway. | From Hwy # 3 to 470'th on C Ave. in Cherokee County |  |  | 43947 | 87894 | Fully Completed | I-jobs and local funds | 2010-07-20
Chickasaw County | Bridge Replacement with Double Cell 12'X8'X30' Box Culvert with End Sections | Pembroke Avenue S34, T94N, R12W, South of 300th Street. | 94611.72 | 117081.68 | 70000 | 47305.86 | Fully Completed |  | 2009-09-17
| Bridge Replacement with Double Cell 12'X8'X30' Box Culvert with End Sections. | Ridgeway Avenue S24, T94N, R12W, North of 290th Street. |  |  | 70000 | 47305.86 | Fully Completed |  | 2009-09-17
| Bridge Replacement with two 12'X6'X60' Structural Concrete Box Culverts. Bridge #0260 | Stevens Avenue North of 310th Street East Section Line of Section 32, T94N, R11W. |  |  | 70000 | 46578.14 | Fully Completed | Local Dollars along with I-Jobs Funds. | 2010-10-26
| Replace Bridge with two 12'X6"X54' Structural Concrete Box Culvert. Bridge #2590 | 165th Street West of Kenwood Avenue. Near East Quarter Corner of Section 23, T96N, R13W. |  |  | 70000 | 39884.18 | Fully Completed | Local Dollars with I-Jobs Funds. | 2010-10-12
| Replace Bridge with two 12'X6'X54' Structural Concrete Box Culvert. Bridge #2450 | 140th Street West of LaSalle Avenue. North Section Line of Section 12, T96N, R13W. |  |  | 70000 | 30619.36 | Fully Completed | Local Dollars with I-Jobs Funds. | 2010-09-29
Chillicothe | Replace storm drain line under Main St., uncover broken line and repour street with concrete patch. | Intersection of Market St. and Main St. | 143.29 | 174.35 | 4000 | 143.29 | Fully Completed |  | 2009-08-12
Churdan | Repair and resurface roads | Sand Street | 1381.1 | 1680.44 | 12000 | 1680.44 | Fully Completed | Road Use Tax | 2011-07-15
| Street repair-use of asphalt | Hill Street |  |  | 2100 | 1381.1 | Fully Completed | Road Use Tax Fund | 2009-08-31
Cincinnati | Order & have installed no parking & emergency snow route signs along Hwy 5 within Cincinnati city limits. | CINCINNATI, PLEASANT STREET, |  | 1647.08 | 700.92 | 1401.84 | Fully Completed | IJOBS, ROAD USE TAX | 2010-11-30
| Purchase 4 new tires for 1997 Case Backhoe | Seymour Tire Shop in Seymour, IA |  |  | 1205.31 | 1201.83 | Fully Completed | none | 2009-10-01
| Purchase new street signs | Cincinnati city wide |  |  | 500 | 594.84 | Fully Completed | IJOBS | 2011-06-01
| Purchase new tires for City Maintenance Truck Project Complete | Cincinnati, Iowa |  |  | 600 | 397.1 | Fully Completed | IJOBS | 2010-11-10
Clare | Repair of potholes and adding rock | All streets in Clare | 356.58 | 433.87 | 500 | 356.58 | Fully Completed | IJOBS State of Iowa-DOT | 2010-03-05
| repair potholes & rock on all streets in Clare. All work done by City maintance personal | Clare, all streets |  |  | 433.87 | 433.87 | Fully Completed | IJOBS | 2011-12-19
Clarence | Regular repairs and maintenance to streets included a large amount of repairs due to extreme winter weather causing heaving of streets. | City-wide | 4402.64 | 5356.87 | 29214.25 | 5356.87 | Fully Completed | Road Use Tax and IJOBS funding | 2010-08-13
| The city plans to make regular repairs and maintain the existing streets. | Various locations. |  |  | 37093.7 | 4402.64 | Fully Completed | Road Use Tax Fund | 2010-07-30
Clarinda | Asphalt Resurfacing, which includes milling and resurfacing with asphalt | Boundary Street from 16th Street to 22nd Street | 24852.23 | 30238.69 | 63636 | 55090.92 | Fully Completed | General Obligation Bonds and IJOBS Money | 2010-09-30
Clarion | LEVELING AND SEAL COATING | 4TH ST NE BETWEEN 2ND AVE NE & 3RD AVE NE $6492.50 3RD AVE NE BETWEEN 2ND AVE NE & 3RD AVE NE $5725.00 MAPLE LANE FROOM WILLOW TO CUL-DE-SAC $5890.00 | 12963.34 | 15773.01 | 58689 | 12963.34 | Fully Completed | Road use Sewer Utility | 2009-06-10
Clarke County | Purchase of Roadstone to place on various gravel surfaced roads. | Various Locations | 62558.32 | 76889.53 | 63000 | 26137.9 | Less than 50% Complete | IJOBS | 2009-08-31
Clarksville | Curb & Gutter, Sidewalk & Approach, Resurface Street | 100 Block East Weare Street, Clarksville, IA | 6293.86 | 7657.99 | 13951.85 | 13951.85 | Fully Completed | Road Use Tax | 2010-10-01
Clay County | Replace 2 bridges with 2 twin box culverts. | One located on 410th Street, Section 17, Clay Township and one located on 120th Avenue, Section 16, Clay Township | 102784.29 | 124671.84 | 302000 | 124671.84 | Fully Completed | Secondary Road Fund | 2011-12-30
| Shoulder wideneing and fore slope improvements. | On B24 from M27 west 8 miles to M44. |  |  | 1485090.98 | 102784.29 | Fully Completed | Secondary Road Fund | 2009-11-01
Clayton County | Ironwood Road (X41)Seal Coat Project. Beginning at intersection with Hemlock Rd on County Rd X41 going North 6.9 miles to the intersection of State Highway 128. | 6.9 miles located in Sections 14, 11, and 2 of Volga Township, Sections 26 and 35 in Garnavillo Township, and Sections 10, 15, 22, and 27 in Read Township. | 129635.97 | 154322.87 | 1471756 | 283958.84 | Fully Completed | I-Jobs Funding | 2010-08-16
Clear Lake | Reconstruction of 2 blocks of N 4th St including sidewalk replacement, storm sewer construction, water main and sanitary sewer replacement and repairs | N 4th St from 1st Ave N to 3rd Ave N | 35644.82 | 43370.46 | 356984 | 35644.82 | Fully Completed | Ijobs, General, RUT, TIF, Water, Sewer, Special Assessments | 2010-05-31
| Street, storm sewer, on-street parking and park improvements for the Buddy Holly Drive Record Park, Phase 1. | 474 North Shore Drive area |  |  | 253855 | 43370.46 | Fully Completed | General, TIF, Donations, Ijobs | 2010-09-01
Clearfield | Council is undecided at this point as to where exactly they are going to use this money. It will be used to repair roads damaged by the heavy rains. They used $1372 on FY2010 for road maintenance. That is where we entered it on the City Street Financial | City of Clearfield | 1371.84 | 1669.18 | 0 | 0 | Not Started | Road Use Tax Fund | 2010-06-30
Cleghorn | removal and replacing of existing asphalt for streets | cleghorn | 1056.56 | 1285.56 | 18670 | 1056.56 | Fully Completed |  | 2009-08-21
| removal of asphalt and replacement | South Lewis Ave. in Cleghorn |  |  | 13350 | 1285.56 | Fully Completed | I-Jobs money and Road Use money | 2010-09-09
Clemons | Ditch Dredging on Bromely St for 3 blocks to enable runoff water flow out of town. | City of Clemons 3 blocks on Bromley Ave | 472.92 | 575.42 | 1350 | 575.42 | Fully Completed | Ijobs money $575.42 and street fund money $774.58. | 2010-12-08
| Repairs of street signs and road signs. | Within Clemons City Limits |  |  | 473 | 422.73 | Fully Completed | ijobs money | 2010-06-30
| Replace the broken chains on the snow plow. | City of Clemons |  |  | 60.42 | 50.19 | Fully Completed | ijobs money | 2009-12-17
Clermont | Asphalt McGregor Street from State Street to Spring Street and include doing the necessary water drainage on the street. | McGregor Street | 3127.27 | 3805.08 | 9200 | 6932.35 | Fully Completed | I-JOBS AND RUT Funds | 2009-12-14
Clinton | 3 inch pavenment milling, 3 inch hot-mix asphalt overlay, PCC pavement patching, and related appurtenances for the roadway rehabilitation of approximately 9,180 feet of North 2nd Street between 7th Avenue North and Main Avenue, continuing on Main Avenue f | Clinton, Iowa; North 2nd Street (Highway 67) from 7th Avenue North to Main Avenue and Main Avenue (North 2nd Street to North 3rd Street | 121299.85 | 147590.29 | 1538733.5 | 268890.14 | Fully Completed | Iowa DOT 3R Funding GO Bonds | 2010-08-31
Clinton County | Bridge replacement by County Bridge Crew | 210th Street west of Y-44 | 129380.59 | 155839.61 | 70000 | 33012 | Fully Completed | Local Secondary Road funds | 2010-11-30
| Bridge replacement on County Road | On 185th Street in Section 18 of Center Township |  |  | 50000 | 26283 | Fully Completed | Secondary Road Fund | 2009-10-08
| Bridge replacement on County Road | On 260th Avenue in Section 3 of Orange Township |  |  | 130000 | 103097 | Fully Completed | Secondary Road Fund | 2009-10-29
| Bridge replacement project by County Bridge crew | On 118th Street west of Y-32 |  |  | 78000 | 36794 | Fully Completed | Local Secondary Road funds | 2010-11-30
| Replace existing bridge with new bridge | 148th Street |  |  | 70000 | 12994 | Fully Completed | local funds | 2011-06-30
| Replace existing bridge with new bridge | 185th Street |  |  | 75000 | 33397 | Fully Completed | local funds | 2011-06-30
| Replace existing bridge with RCBC | Y44/170th Avenue |  |  | 105000 | 39643.2 | Fully Completed | local funds | 2012-06-30
Clive | Meredith Drive overlay in Clive, Iowa | Meredith Drive in Clive from Urbandale Corp limits to Waukee Copr limits | 61693.8 | 75065.28 | 160331.81 | 75065.88 | Fully Completed | I-jobs and road use funds. | 2011-04-30
| overlay on Buffalo Road at 73rd Street | Buffalo Road |  |  | 21794.99 | 21794.99 | Fully Completed | I-jobs | 2010-01-31
| Overlayment of Buffalo Road at 73rd Street | Buffalo Road and 73rd in Clive |  |  | 32000 | 0 | Fully Completed |  | 2009-09-30
| patch paving | varous locations throughout the community |  |  | 30000 | 16633.21 | Fully Completed | i-Jobs | 2010-06-03
| slab stabilization | various locations in teh city |  |  | 23265 | 23265 | Fully Completed | I-jobs | 2009-09-30
Clutier | Repair and maintenance of various streets around town. | Curtis Street, 5th St between Main and Carter, 2nd St, north half of Carter between 2nd to 3rd St, Carter from 3rd to 4th St, Elm from 3rd to 4th St, surface patch that would be necessary to repair th | 654.08 | 795.85 | 9272.6 | 1449.93 | Fully Completed | IJOBS. | 2010-09-22
Coggon | Aspahlt repair of streets | Approx. 545 2nd Street | 3253.94 | 3959.2 | 3253.94 | 3253.94 | Fully Completed |  | 2009-09-03
| Asphalt repair of streets 500 and 900 block 2nd street | 500 and 900 block 2nd street |  |  | 3959.2 | 3959.2 | Fully Completed | Road Use Tax | 2010-07-30
Coin | gravel street to city cemetery | south end of town | 800.79 | 974.36 | 0 | 0 | Not Started | I-Jobs dollars | 2010-05-01
| gravel street to city cemetery | south end of town |  |  | 1000 | 0 | Not Started | I-Jobs dollars | 2010-05-01
Colesburg | Reconstruct one block of 2nd Street with new asphalt and curb & gutter. | 2nd St. between Main St. and Jackson St. | 1426.19 | 1735.3 | 39789.04 | 1426.19 | Fully Completed | IJobs, RUT fund | 2009-09-22
Colfax | City Council will act on project decision October 12th, 2009. | Decision on location determined by City Council October 12th | 9709.4 | 11813.81 | 0 | 0 | Not Started | I-Jobs | 2009-11-30
| City Council will act on project decision October 12th, 2009. | Decision on location determined by City Council October 12th |  |  | 10000 | 0 | Not Started | I-Jobs | 2009-11-30
| Filling holes with CRS-2 | Downtown Colfax |  |  | 367.5 | 0 | Fully Completed | I-Jobs | 2010-03-01
| Funds have not been expended but City Council wants Public Works Director to do street maintenance projects with the funds. | City of Colfax streets |  |  | 0 | 0 | Not Started | I-jobs 9709.40 | 2010-04-15
| Hired Dickerson Mechanical to help with snow removal | Downtown Colfax |  |  | 6115 | 0 | Fully Completed | I-Jobs | 2010-03-02
| purchase of gravel and rock for patching streets | entire town |  |  | 3227.2 | 3227.2 | Fully Completed | IJobs | 2010-04-07
| Replace curb and gutter at Walnut and E Front St. Clean out ditch,flume and street maintenance materials | Front St |  |  | 15342.15 | 15342.15 | Fully Completed | I-Jobs | 2010-11-22
Collins | To Be Determined | To Be Determined | 2034.55 | 2475.52 | 0 | 0 | Not Started | I Jobs | 2010-08-31
Colo | Repair and resurface main street. | Main Street entire length. | 3791.17 | 4612.86 | 105245 | 3791.17 | Fully Completed | Local/Ijobs | 2009-08-31
| Slurry Coat West Street - Entire length | West Street, Colo, IA |  |  | 32000 | 4612.86 | Fully Completed | Local Funds/IJobs Funds | 2010-08-27
Columbus Junction | Curb & Gutter replacement | 2nd Street, from Cherry to Gamble | 8298.64 | 10097.28 | 65127.2 | 8298.64 | Fully Completed |  | 2009-07-31
Colwell | Laying asphalt on top of gravel road. | From Railroad Ave.and 4th Street around 5th Street down Liberty Ave. to 3rd Street. | 145.23 | 176.7 | 16500 | 145.23 | Fully Completed | Road Use Tax Fund and Transfer of Jurisdiction Funds | 2009-08-28
| Rock Alleys in Town | Alleys |  |  | 193.84 | 176.7 | Fully Completed | Road Use Tax and Transfer of Jurisdition | 2010-12-14
Conrad | Concrete City alleyway for safe transportation to the Conrad Family Aquatic Center and Shelterhouse | Alley off of Boyd Street between the properties located at 108 E Boyd and 601 N Main | 4607.93 | 5606.65 | 13197.5 | 4607.93 | Fully Completed | IJobs Funds | 2009-09-21
| Repair south and north approach on South Main Street bridge over Wolf Creek. This was a shared funding project with Grundy County | South Main Street |  |  | 20169 | 5606.65 | Fully Completed | Ijobs funds, City RUT funds, and Grundy County cost share | 2011-08-16
Conway | maintain roads using blade to move gravel | conway,iowa city | 176.31 | 214.52 | 214.52 | 214.52 | Fully Completed | i-jobs road use tax | 2011-06-01
| Purchase of rock for city streets | Conway, IA |  |  | 612.33 | 176.31 | Fully Completed | I-Jobs and RUTF | 2009-10-05
Coon Rapids | Project to be determined.. | to be determined | 5699.85 | 6935.24 | 31136 | 12635.09 | 50% or More Complete | Project to be determined | 2009-12-31
Coppock | cold mix for street patching | Locust, Mill Street in Coppock | 165.37 | 201.21 | 421 | 165.37 | Fully Completed |  | 2009-08-28
| purchase street patching materials | locust ave |  |  | 201.21 | 201.21 | Fully Completed | IJOBS funds (second half) | 2010-07-12
Coralville | Patching including traffic control & subgrade repair | 2nd Ave. 7 Glen Oaks Knoll | 75425.86 | 91773.61 | 13513.4 | 13513.4 | Fully Completed | I-Jobs | 2011-05-31
| Remove & replace concret & seed, fertizie & mulch ground | 12 Ave @ I-80 & Oakdale @ Coral Ct. |  |  | 34404.96 | 32485.96 | Fully Completed | I-Jobs | 2011-06-28
| Remove & replace, full depth saw cutting & subgrade repair. Patching | Avalon Lane & Westminster |  |  | 8898.11 | 8898.11 | Fully Completed | I-Jobs | 2011-06-28
| Street Repairs of existing streets. | James Street, Holiday Rd & 12th Ave., Heartland Dr., |  |  | 87811 | 75425.86 | Fully Completed | I-Jobs funds | 2009-09-30
| Street Repais - remove & replace paving | Ozark Ridge & Woolridge Patching |  |  | 36374.1 | 36876.1 | Fully Completed | I-Jobs | 2011-06-28
Corning | 1995 Chevy Kodiak Truck from The City of Wesley, Iowa for $7,000 | to be determined | 7787.61 | 9475.5 | 7787.61 | 7000 | 50% or More Complete | $7,000 | 2009-12-31
| UNIT #205485, SERIAL #5418DGE511CB124MA, MODEL MAGNUM 91000 AMZ MACHINE. PURCHASED FROM LOCAN CONTRACTORS SUPPLY, INC FOR $10,750.00. | CITY STREETS OF CORNING |  |  | 10263.11 | 7000 | Fully Completed | I JOBS MONEY $10,263.11, BALANCE TO BE PAID FROM ROAD USE TAX MONEY $486.89. | 2010-07-29
Correctionville | Reconstructed intersection of Aspen Street and Sioux Avenue with Highway 20. | Aspen Street and west end of Sioux Avenue and Highway 20. | 3716.91 | 4522.52 | 30000 | 3716.91 | Fully Completed | RUT Fund | 2009-07-02
| Street Repair on several streets in the city limits. | 308 Birch; 109 Birch; 206 Fir; South End Gumwood; 3rd & Hackberry; 6th Street; 611 Railroad Ave; Welsch Ave; Welsch Ave & Fir; 506 4th St; 10 & Driftwood. |  |  | 28362.15 | 4522.52 | Fully Completed | RUT - I-JOBS | 2010-07-21
Corwith | Streets within the city limits will be repaired. | Various locations within the city limits | 897.01 | 1091.42 | 2000 | 1988.43 | Fully Completed | Road Use Tax Fund | 2010-09-02
Corydon | Asphalt resurfacing/sealcoating. Rock replacement | 100 to 300 Block of West South St and 200-400 Block of East South Street. E. Monroe St-north of hospital, E South St-south of hospital, N Lincoln and N East north of Hwy 2. | 6949.02 | 8455.14 | 8455.14 | 8455.14 | Fully Completed | I-Jobs Funding | 2011-08-31
| Patch & Asphalt Resurfacing | 200-400 blks of S LaFayette, 200-400 blks of S Franklin, 300-500 blks of E Monroe, 500 blk of E South, 100 & 300 blks W Monroe, 500 & 600 blks of S East, 2178 Lake Park Rd |  |  | 6949.02 | 6949.02 | Fully Completed | I Jobs Funding | 2009-10-08
Cotter | Build Walk bridge and pour new sidewalk | Cotter Street | 139.77 | 170.06 | 3000 | 139.77 | Fully Completed |  | 2009-09-16
Coulter | Repairubg cracks in asphalt on all city streets. | 1st street to 5th street, and Grant street to Taft Street. | 814.33 | 990.82 | 11753 | 814 | Fully Completed | Street Repair Fund and RUT Fund | 2009-07-23
Council Bluffs | Purchase of equipment for street maintenance and snow removal | tbd | 267845.01 | 325897.57 | 593742.58 | 593742.58 | Fully Completed | I-JOBS | 2011-06-30
| Purchased a 2012 F150 pickup. | Various street maintenance |  |  | 23620 | 18764.58 | Fully Completed | IJOBS | 2012-06-29
Craig | repaint striping on streets and handicap parking places | the whole city of Craig | 322.92 | 392.9 | 1080.8 | 322.92 | Fully Completed |  | 2009-08-24
| To Be Determined | To Be Determined |  |  | 0 | 0 | Not Started | To Be Determined | 2011-06-01
Crawford County | 2010 Pavement Markings on hard surfaced roads. | Major Collector Routes. | 115779.06 | 141422.44 | 26341 | 26341 | Fully Completed | Secondary Roads | 2010-12-03
| Hot Mix Asphalt to patch pavements. | County Routes E16, L51 and Lincoln Way. |  |  | 137252 | 115081.44 | Fully Completed | Secondary Road Funds. | 2010-11-05
| Milling and asphalt cement placement. | County Rd. E16 from Schlewig to County Rd. L51, and County Rd. L51 from County Rd. E16 to State Hwy. #141. |  |  | 260304.79 | 115779.06 | Fully Completed |  | 2009-09-21
Crawfordsville | repairs and resurfacing of city streets | Crawfordsville, IA | 958.44 | 1166.17 | 22182.9 | 958.44 | Fully Completed | Road Use Tax Funds | 2009-08-07
Crescent | Approx. 6' long patch along east side of OLH slightly across from Henry's Diner. Asphalt/shoulder giving way. City is waiting on bids from asphalt companies as of 6-7-11 | OLH/Jackson St. | 2345.46 | 2853.81 | 5000 | 2857 | Fully Completed | Remaining IJOB $$$ in RUT funds. | 2011-08-31
| TBD possible row reconstruction | east side of Old Lincoln Hwy |  |  | 2736 | 2341.35 | Fully Completed | RUT monies | 2011-09-30
Cresco | Chip Sealing City Streets - Purchased 6,041 gallons of oil, 178.2 tons of chips, 181.7 gallons of LP | Chip Sealed about 30 blocks around the City of Cresco. Purchased the oil from Tama, Iowa and the chips and LP from Cresco Iowa. | 17055.88 | 20752.56 | 17860.24 | 17860.24 | Fully Completed | I Jobs only | 2010-05-24
| Chip Sealing City Streets in Cresco | Various Locations |  | 20752.56 | 31369 | 19948.2 | Fully Completed | I-JOBS and Local Option Tax | 2011-06-20
Creston | Reasphalting and patching streets | Various | 33181.44 | 40373.16 | 6302.72 | 5544.27 | Fully Completed | I-JOBS Funds, City Funds | 2011-06-02
| Resurface North Lincoln Street from Townline Street to City Limit | North Lincoln Street |  |  | 73614 | 68010.33 | Fully Completed | I-JOBS Funds, STP Funds, City Funds | 2010-12-31
Cromwell | purchase and haul gravel and blade streets. $359.23 was used. | City of Cromwell | 359.23 | 437.09 | 2601.83 | 359.23 | Fully Completed | I-Jobs and local state road use money | 2009-08-03
Crystal Lake | Replace sidewalks along both side's of State Ave. | from 2nd Street to 1st Street | 865.78 | 1053.43 | 21500 | 1053 | Fully Completed | i-jobs plus various grants and general fund | 2011-06-15
| Sealcoat 5th Street W from Summit Ave to end of street | 5ht Street W |  |  | 8576 | 865.78 | Fully Completed | Road funds | 2009-09-10
Cumberland | Project to be determined at a later date. | To be determined. | 974.29 | 1185.46 | 0 | 0 | Not Started | To be determined. | 2009-09-23
Curlew | no project has been identified | not identified | 97.21 | 118.28 | 0 | 0 | Not Started | not determined | 2010-06-30
Cushing | Culvert Project | Third Street | 756.91 | 920.97 | 7400 | 756.91 | Fully Completed |  | 2009-09-01
| Grade alleys & drainage ditches | Within city limits |  |  | 2000 | 920.97 | Fully Completed | Road Use Fund | 2011-06-30
Cylinder | TO BE DETERMINED AT A LATER DATE | TO BE DETERMINED | 480.45 | 584.58 | 0 | 0 | Not Started | TO BE DETERMINED | 2010-08-31
| TO BE DETERMINED AT A LATER DATE | TO BE DETERMINED AT A LATER DATE |  |  | 0 | 0 | Not Started | TO BE DETERMINED | 2010-12-31
Dakota City | Blacktop work in and around City Hall and shop. | To be determined | 3978.98 | 4841.38 | 3978.98 | 0 | Not Started | IJOBS | 2010-04-09
Dallas Center | Repair of miscellaneous streets | Dallas Center | 6966.49 | 8476.4 | 8488.64 | 8476.4 | Fully Completed | I-jobs | 2011-08-01
| Repairs of various streets | to be determined |  |  | 6966.49 | 6966.49 | Fully Completed | I-Jobs | 2009-10-20
| Roadstone for rock roads 2010 2011 | County Roads | 114512.76 | 139889.31 | 254402.07 | 254402.07 | Fully Completed | I-JOBS | 2010-11-12
Dana | SNOW REMOVAL OR LAWN MOWING | ALL AREAS OF CITY OF DANA | 248.25 | 302.06 | 550.31 | 550.31 | Fully Completed | I JOBS | 2011-06-30
Danbury | Resurfacing of Thomas Street from D-54 to State 175. | Thomas Street, Danbury Iowa | 1211.1 | 1473.59 | 67649.97 | 1473.59 | Fully Completed | City Savings, RUT & IJOBS | 2010-09-09
| Street Repair | Areas in and surrounding the entire lengths of Main, East, Liston and Peach Streets. |  |  | 3006.64 | 1211.1 | Fully Completed |  | 2009-08-18
Danville | Applied the funds towards the following project: Dug out, formed, graded and poured 142 feet of curb and gutter. Installed two ADA detectable warning devices in sidewalk. Poured six feet by four feet and five feet by eight feet handicap ramps. Poured | Sidewalk on the east side of North Main Street, in front of the following businesses: 112, 114, 202, and 204 North Main Street | 3992.08 | 4857.32 | 7400 | 3992.08 | Fully Completed |  | 2009-09-15
| to be determined at a later date | to be dtermined at a later date |  |  | 0 | 0 | Not Started | I job monies and RUT revenue | 2011-06-30
Davenport | Correct Forest Grove Road at Somerset sight distance problem. | Forest Grove Road at Somerset | 429602.89 | 522714.74 | 0 | 0 | Not Started | I JOBS FUNDS | 2010-09-30
| Paving on Utica Ridge Road from Forest Grove to Davenport City Limits | Forest Grove Road to Davenport City Limits |  |  | 383169.42 | 383169.42 | Fully Completed | I JOBS FUNDS | 2010-09-30
| The improvements consist of removing the existing concrete pavement and constructing new nine inch (9”) P.C.C. pavement on a drainable subbase with subdrains on Eastern Ave. between Duck Creek and Kimberly Rd. Also included with this project is the remov | Eastern Ave. between Duck Creek and Kimberly Rd. |  |  | 569148.21 | 569148.21 | Fully Completed | I-JOBS | 2011-09-30
Davis County | Placing granular in various local roads in Davis County | Various local roads in Davis County | 83962.53 | 101491.61 | 85000 | 0 | Not Started |  | 2010-10-14
Dayton | New tires and other repairs to 1992 GMC dump truck and 2000 JCB 214 tractor/loader/backhoe. | City maintenance shop | 3861.05 | 4697.89 | 3882.06 | 6984.52 | Fully Completed | Road Use Tax | 2011-04-01
| Street Maintenance Materials purchased. | Dayton |  |  | 3861.05 | 368.79 | Less than 50% Complete | Road Use Tax Fund | 2011-06-30
De Soto | HMA patching on Madison and Marshall streets; Sawcut, remove, and install HMA pavement. HMA resurfacing on Walnut Street; Mill to transition, clean, tack with CSS-1 emulsion, and resurface with 3 inch depth HMA pavement. | Madison, Marshall and Walnut Streets, De Soto, IA | 4407.01 | 5362.18 | 0 | 0 | Not Started | Road Use Monies and I-Jobs money | 2010-06-30
De Witt | crack & joint sealing of streets | Scenic Hill Lane from N Ridge Rd to Cul-de-sac, Scenic Ridge from Scenic Hill Lane to end, Mackin Dr/Silver Valley Dr intersection, Silver Valley Dr from #1516 to 14th Ave and by house #1511, 15th Ave | 22052.53 | 26832.18 | 26560.17 | 26560.17 | Fully Completed | I-Jobs | 2010-11-19
| Crack sealing various streets throughout DeWitt | Westwood Dr south of 11th St, 11th Ave north of 15th St, 14th St between 11th Ave and 14th Ave, 2nd Ave south of 8th Street thru east 7th St, 6th St between 7th Ave and 3rd Ave, 2nd St between 6th Ave |  |  | 23154.04 | 22052.53 | Fully Completed | $22,052.53 I-Jobs and $1,101.51 local option sales tax | 2009-11-25
| curb & gutter | 102 12th Avenue |  |  | 571.73 | 272.01 | Fully Completed | $272.01 I jobs $299.72 local option tax | 2010-10-29
Decatur County | Asphalt overlay of damaged areas on Little River Lake Road and NW 18th Street in Leon, Iowa. Damage resulte from use as a detour during DOT bridge deck overlay BRFN-69-1(34)--39-27. | Little River Lake Road and NW 18th Street in sections 19,20,29,and 30 of Center Township T-69-N; R-25-W in Decatur County, IA. | 83387.21 | 101555.18 | 115977.75 | 39660.25 | Fully Completed | Decatur County IJOBS $ 39,660.25 City of Leon IJOBS 7,000.00 IOWA DOT 69,317.50 | 2009-08-27
| Grind and relay surface of existing seal coat road (three inches deep by 24 feet wide). | 280th Street from Davis City, IA to Lamoni, IA. |  |  | 14700 | 14700 | Fully Completed | Decatur County IJOBS $ 14,700.00 | 2009-08-31
| Purchase crushed limestone for surface application to rural secondary roads | Secondary rock surfaced roads in 9 of 16 Townships |  |  | 6870.65 | 6868.96 | Fully Completed | Decatur County IJOBS $6,868.96 Decatur County Secondary Road Funds $ 1.70 | 2009-12-03
| Purchase oil and limestone chips to reseal 280th Street (24 ft wide x 5.491 miles long) Application rates of 0.397 gal oil/sq yd @$2.632/gal and 53.130 lbs/sq yd @ $13.05/Ton | From the NW cor NE 1/4 NW 1/4 Sec 2, T-67-N, R-26-W to NW cor Sec 1, T-67-N, R-27-W. |  |  | 107496.55 | 101555.18 | Fully Completed | I-JOBS $101,555,18 Decatur County Sec Rds $ 5,941.37 Total $107,496.55 | 2010-08-18
| Rebuild Radii at the intersection of County Route J-66 (Dale Miller Road) and US Hwy 69 at Davis City, IA | Intersection of County Route J-66 (Dale Miller Road) and US Highway 69 at Davis City, IA |  |  | 19118 | 19118 | Fully Completed | Decatur County IJOBS $ 19,118.00 | 2009-08-25
| Repair shop facility by replacing 12'x12'overhead door in east end of shop. | 1401 South Main Leon, IA 50144 |  |  | 3040 | 3040 | Fully Completed | IJOBS $3,040.00 | 2009-08-14
Decorah | Extension of Montgomery St. Storm Sewer | East of Montgomery St. near Charlie Miller Drive, Decorah IA 52101 | 35692.87 | 43428.92 | 88252.97 | 35692.87 | Fully Completed |  | 2010-07-01
Dedham | PATCH STREETS: POTHOLES & BLACKTOP. HIRED TO PATCH STREETS. MATERIAL PROVIDED BY STA-BILT CONSTRUCTION CO.. | ALL CITY STREETS EXCLUDING 4TH AVE & 4TH ST | 914.16 | 1112.29 | 2400 | 1828.32 | Fully Completed | ROAD USE TAX FUND | 2010-12-01
| REPAIR STREETS | ALL CITY STREETS |  |  | 2980.1 | 1112.29 | Fully Completed | ROAD USE TAX | 2011-09-12
Deep River | Repair of existing street surface. | Streets within the City of Deep River | 1146.15 | 1394.56 | 8532 | 1146.15 | Fully Completed | Road use funds and I-jobs funds | 2009-10-09
Defiance | Repair or crack filling in the fall of 2010 | city streets | 1367.02 | 1663.3 | 15000 | 0 | Not Started | IJOBS/RUTS | 2010-10-08
| Repair or crack filling in the fall of 2010 | city streets |  |  | 50000 | 0 | Not Started | IJOBS/RUTS | 2010-10-08
Delaware County | PCC maintenance patching | PCC patching on W63 south of D22, and at the intersection of W69 and D22. | 117801.26 | 140524.57 | 291760.14 | 140524.57 | Fully Completed | FY 2011 I-Jobs and Local Funds | 2010-08-10
| Replace bridge with two cast-in-place box culverts. | Between Sections 6 & 7 of Bremen Township. 170th Street approximately 500 feet west of 290th Avenue. |  |  | 173479.4 | 117801.26 | Fully Completed | Local money and I-Jobs money | 2009-10-30
Delhi | Road Repair and Seal | Franklin Street from 6th to West end | 1481.01 | 1802 | 2295 | 1481.01 | Fully Completed |  | 2009-09-18
Deloit | Deep dips by manholes that need filled in on the streets | Different street locations | 902.05 | 1097.55 | 2200 | 0 | Fully Completed | Road Use Tax Fund | 2010-06-24
| Fixing valves and restoring our lagoons | Deloit |  |  | 15000 | 0 | Not Started | Sewer utility | 2012-08-31
| Need repair on many of our Deloit streets. | Deloit |  |  | 0 | 0 | Fully Completed | Road Use Tax Funds | 2011-05-31
| Repair and Maintance of Sewer | City of Deloit |  |  | 18000 | 0 | Not Started | Sewer Utility Fund | 2011-06-30
| Televising and sewer cleaning | City of Deloit |  |  | 18000 | 0 | Not Started | Sewer Utility Fund | 2011-07-01
Delphos | Clean ditches for better drainage / runoff. | Washington Sreet | 70.6 | 85.91 | 125 | 70.6 | Fully Completed | General Fund | 2010-03-30
Delta | New gravel/rock will be purchased for streets in City of Delta | To be determined | 1311.87 | 1596.2 | 1311.87 | 1311.87 | Fully Completed | I-JOBS road fund | 2010-05-31
Denison | 1st Ave North & 1st Ave South street repairs | 1st Ave North & 1st Ave South | 32054.57 | 39002.06 | 6472.97 | 6472.97 | Fully Completed | I-Jobs | 2011-09-07
| repairing potholes all over the city streets | various locations throughout the city |  |  | 3123.8 | 3123.8 | 50% or More Complete | I-Jobs | 2010-07-23
| repairing potholes around city streets | entire city |  |  | 9506.36 | 19012.72 | 50% or More Complete | Road Use Taxes | 2010-03-05
| Repairing potholes in city streets | entire city |  |  | 11374.39 | 11374.39 | 50% or More Complete | Road Use Taxes | 2010-05-29
| REPLACEMENT OF EXISTING STORM SEWER PIPE | 9th Ave. North & 24th Street |  |  | 8200 | 8195 | Fully Completed | Road use tax - | 2009-09-08
| Street repairs | various streets |  |  | 7235 | 7235 | Fully Completed | I-Jobs | 2010-12-10
| Ten Point Construction | remove & replace intersecton at Fort & Settlers lane |  |  | 15642.75 | 15642.75 | Fully Completed | I-Jobs | 2011-01-03
Derby | Ditching & Culvert replacement | Prairie Ave @ John Street | 507.74 | 617.79 | 650 | 507.74 | Fully Completed | I-Jobs and Iowa road use tax receipts | 2010-04-30
| Replace culvert and deepen ditch. | Prairie Avenue just west of Center Street |  |  | 860 | 617.53 | Fully Completed | I-Jobs and road use tax monies | 2011-10-31
Des Moines | Mill and overlay of various streets with in the City of Des Moines. | Various streets with in the City of Des Moines. | 867783.87 | 1055866.74 | 2522375.44 | 1055866.61 | Fully Completed | IJOBS | 2011-08-01
| Project started 9/1/10. Resurfacing completed 10/16/10. Permanent epoxy paint completed 11/15/10. Remaining work (durable tape pavement markings) will be complete second quarter 2011 (May). | Various streets with in the City of Des Moines |  |  | 1950000 | 867784 | Fully Completed | IJOBS | 2010-12-15
Des Moines County | Generator installation at Des Moines County Secondary Road Department Maintenance Facility | Main Shop Building - Washington Road | 82345.81 | 100116.62 | 60000 | 22993.21 | Fully Completed | Secondary Road Fund | 2010-02-01
| Highway 99 slide/culvert damage repair | Hwy 99 |  |  | 38481.1 | 27388.59 | Fully Completed | Secondary Road Fund | 2010-05-11
| Jimtown Road Wash-out/Culvert Repair | Jimtown Road |  |  | 24684.29 | 24684.29 | Fully Completed | Secondary Road Fund | 2009-11-09
| Salt storage building | Des Moines County Secondary Road Department Facility, Washington Road, West Burlington, IA |  |  | 126805 | 0 | Fully Completed | local funds | 2010-08-25
| Washington Road Intake Repair | Washington Road/Bohlen |  |  | 7279.72 | 7279.72 | Fully Completed | Secondary Road Fund | 2009-12-01
Dexter | TBD | TBD | 3013.71 | 3666.91 | 0 | 0 | <not selected> |  | 2010-04-30
Diagonal | 40 ft 24" DW Tube = $628.40 7.1400 Tons rock = $ 78.90 equipment to dig $375.00 | intersection of east 7th street and north union street | 1090.18 | 1326.46 | 1100 | 1082.3 | Fully Completed | Road Use Tax | 2009-10-26
| Class D rock was used for the maintenance and prep on city streets in order to chip and oil. This will help with the flow of water when we get heavy rains, and will prevent losing gravel on some roads that seem to wash away into ditches and culverts, plu | Various locations throughout the city. E 3rd Street and Madison Streets mainly |  |  | 28500 | 1326.46 | Fully Completed | RUT funds, Local Option Sales Tax, and FTM funds | 2011-08-25
Dickinson County | P.C.C. Full-Depth Patching on County Road M-34 to repair damage caused by Lost Lakes Windfarm new windmill construction. Includes Planning, Design and Contract Administration. | County Road M-34 in Excelsior and Okoboji Townships | 70103.16 | 88577.71 | 300000 | 158680.87 | Fully Completed | Local Maintenance Funds | 2011-12-31
Dike | Project to seal cracks and joints in the streets listed below. | E. Elder, Mayme, 7th, Fox Ridge | 4123.11 | 5016.75 | 0 | 0 | Not Started | RUT taxes and IJOBs | 2009-10-09
Dolliver | Project for city being discussed at this time, possibly for year 2010. | City of Dolliver | 224.21 | 272.8 | 0 | 0 | Not Started | I-Jobs Monies | 2011-10-31
| Repair of Dolliver Streets after snow | City of Dolliver |  |  | 0 | 0 | Not Started | I-JOBS Monies | 2011-04-08
| Snow Removal of Main Street ( 2 1/2 blocks) | Don Griese Construction 5087 Main Street Dolliver, IA 50531 |  |  | 497 | 0 | Fully Completed | I Jobs Monies | 2012-02-15
Donnellson | Remove sealcoat street. Form and pour concrete pavement. | East Street and Madison Avenue, north 90 feet. | 4206.1 | 5117.73 | 11630 | 9323.83 | Fully Completed | Road Use Tax Funds TE Funds | 2011-05-19
Doon | The City of Doon, IA contracted The Road Guy Construction Co. to resurface some streets in Doon. Total amount spent on this project was $26,045.28. These funds were taken from our Road Use Tax Account in which our I-Jobs Grant was deposited on July 26, | Doon, IA | 2327.99 | 2832.55 | 20000 | 0 | Fully Completed | I-Jobs and RUT Account of the City of Doon | 2010-06-24
| The City of Doon, IA contracted The Road Guy Construction Co. to resurface some streets in Doon. Total funds spent on this project were $21,628.87. These funds were taken from our Road Use Tax Account in which the I-Jobs Grant was deposited on July 30, | City of Doon, IA |  |  | 20000 | 2327.99 | Fully Completed | I-Jobs and RUT Fund Account of the City of Doon. | 2009-07-22
Dougherty | SNOW REMOVAL ON CITY STREETS | MAIN ST. DOUGHERTY | 150.48 | 183.09 | 200 | 300.96 | Fully Completed | IJOBS & RUT | 2010-03-31
| still working on plans FOR CITY STREETS | streets in dougherty |  |  | 150.48 | 0 | Not Started | RUT | 2011-06-30
Dow City | Construct storm sewer along S. Prince Street (Hillside) | South Prince Street (Hillside Project) | 2196.95 | 2673.12 | 4187.93 | 2673.12 | Fully Completed | I-JOBS and Road Use Tax | 2010-11-01
| Reconstruction of west side of School Street and Park Street | West side of School and Park Streets intersection |  |  | 15702.75 | 2196.95 | Fully Completed | $2,196.95 from I-JOBS Funds; $13,505.80 from Road Use Tax Funds | 2009-09-08
Dows | repairing a section of Rowan Road (county line road) by Coop and doing the railroad track crossing on E. Ellsworth Street | Rowan Road | 2948.2 | 3587.19 | 23000 | 0 | Fully Completed | I jobs money and road use funds | 2010-08-30
Drakesville | Replace tube, grade ditch and put in a drain | S. Polk Street & 180th ST | 665.26 | 809.44 | 0 | 0 | Not Started | I-Jobs money | 2011-10-01
| The road bed was scarified and material brought upf rom the ditches. It was then regraded and ditches cleaned. A new surface of gravel/oil was put on it. | S Polk St. from Main St. to City Limits of Drakesville, Ia |  |  | 6043.59 | 665.26 | Fully Completed | I-Jobs funds plus funds the City had in their Road Use Tax Fund | 2009-06-23
Dubuque | Consultant design consultant to complete the final engineering (FE) design, develop construction documents, and perform the required archaeological and cultural resource phase III mitigation work for the development of the Southwest Arterial project. | Southwest Arterial, Highway 20 to Highway 151/61 in Dubuque, Iowa | 252151.86 | 306803.09 | 10804400 | 558954.95 | Fully Completed | Federal SAFETEA-LU Funding State I-Jobs Distribution City - Sales Tax (30%)/RUT | 2014-08-31
Dubuque County | Cost of materials for North Cascade overlay project Invoice #4300003847 dated 10/21/09 - 2,409.49 ton hot mix = $95,319.46. Invoice #4300003891 dated 10/30/09 - 2,140.67 ton hot mix = $84,684.88. Invoice #4300003924 dated 10/31/09 - 69.74 ton hot mix = $2 | North Cascade Rd from New Melleray Road to Sundown Road | 137446.75 | 171482.94 | 234332 | 154464.85 | Fully Completed | Secondary Road funds | 2009-10-31
| Overlay of Flannagan Road, Sec 13-14-15-16-17, Concord Twp Invoice 4300005456 dated 10/27/10 - 2,899.02 ton hot mix = $114,772.21. Invoice 4300005480 dated 10/31/10 - 1,105.16 ton hot mix = $43,753.30 | Flannagan Road |  |  | 220324 | 154464.84 | Fully Completed | Secondary Road Funds | 2010-10-31
Dumont | build a base to prepare for resurfacing city street | State Street from 202 Locust Street to the corner of Franklin Street | 2952.57 | 3592.51 | 7465 | 3592.51 | Fully Completed | Road Use Tax Fund | 2010-10-15
| build a base to prepare for resurfacing city street | finish Pittsford Street and all of Franklin Street |  |  | 8833.16 | 2952.57 | Fully Completed | Road Use Tax Fund | 2009-11-01
Duncombe | Rocked the gravel road and grading. | 4500 feet east on Oak Street from the intersection of Collins Street. | 1496.27 | 1820.56 | 2370 | 2370 | 50% or More Complete | IJOBS FUNDING | 2010-08-11
| Rocking and Grading Road. | Gravel part of Oak Street at the intersection of Oak Street and Collins east 4500 feet. |  |  | 2285.32 | 946.83 | Fully Completed | I-JOBS FUNDING: 946.83 RUT:1338.49 | 2011-04-22
| To be determined at a later date. | To be determined. |  |  | 0 | 0 | Not Started | IJOBS FUNDS | 2010-03-04
| To be determined at a later date. | To be determined. |  |  | 0 | 0 | Not Started | I-JOBS FUNDS | 2009-09-25
| To be determined at a later date. | To be determined. |  |  | 0 | 0 | Not Started | IJOBS Funds. | 2009-12-30
Dunkerton | Clean, patch and seal coat various streets in Dunkerton. | 1. Alley behind Baptist Church 2. Parking by Veteran's Park 3. 210 E Sycamore 4. Tower St from Canfield to Jefferson to Marilyn 5. E Williams from Canfield to Jefferson to Marilyn 6. Jefferson fr | 3275.78 | 3985.77 | 22168.44 | 3985.77 | Fully Completed | I-JOBS $3,985.77 (All of FY2011) & RUT $18,182.67 | 2011-05-31
| Curb & Gutter and Storm Sewer Inlet Replacements at 2 locations. | 1. Stickney and Main St., Dunkerton 2. Lincoln St., Dunkerton |  |  | 2550 | 2550 | Fully Completed | I-Jobs $2550 | 2009-11-30
| Street Cold Mix Patch - 4.56 Tons at 1 location | Dunkerton Road |  |  | 334.48 | 334.48 | Fully Completed | I-Jobs $334.48 | 2010-03-24
| Street Maintenance Seal Coat and Patching at 7 locations. | 1. West Williams from new asphalt west of Canfield to west end. 2. Marble from Dunkerton Road to Williams. 3. Washington from Dunkerton Road to Williams. 4. Washington from Williams to south end. |  |  | 20936.8 | 391.3 | Fully Completed | I-Jobs $391.30 (Remaining FY10) Road Use Tax $18,628.90 General Fund Streets Budget (Property Tax Levied) $6700.00 | 2010-06-03
Dunlap | milling 700 block Iowa Avenue north side grindings alley entrance 300 block South 6th Str east side asphalt alley entrance 3" thick -Park to Eagle Street Asphalt 2" deep South 8th Street - | 700 block Iowa Avenue 300 block South 6th Street alley-Park Street to Eagle Street South 8th Street | 4974.81 | 6053.05 | 11468.5 | 4974.81 | Fully Completed |  | 2009-10-30
Durango | we have no projects at this time | Durango, Iowa | 65.52 | 79.71 | 0 | 0 | Not Started | none | 2010-03-09
Durant | Repair park parking lot at Feldhahn Ballpark from heavy equipment use. The equipment tore up the asphalt and left ruts. It will be done as soon as the asphaly contractors are up and running this spring or summer | East Park and County Hwy F58 (Feldhahn Park Ball diamond) Scott County | 7324.64 | 8912.17 | 20000 | 0 | Not Started | The I-Jobs money will help pay for it with Road Use tax Funds. | 2011-07-29
| Tear out 3 blocks of 7th Street and put new concrete in. Reconstruct 6th Street from 5th Ave to 10th Ave with new water, sewer, storm, curb & gutter. Including 7th & 10th Avenues between 5th and 6th Streets | 6th and 7th Streets |  |  | 1822173.36 | 7324.64 | Fully Completed | Funding source is assessments at completion, bond proceeds, and I-JOB funding | 2009-11-13
Dyersville | Paving & Storm Sewer Project | 8th Street NW | 17623.68 | 21443.43 | 187558.5 | 39067.11 | Fully Completed | Capital Projects | 2010-08-01
Dysart | Patch, curb repair and chip seal two blocks of city street | South Main Street from Sherman to Park Streets | 5691.12 | 6924.61 | 49000 | 12615.73 | Fully Completed | I-Jobs, road use funds | 2010-09-01
Eagle Grove | Kirkwood and S.E. 5th Intersection reconstruction | South Kirkwood and S.E. 5th Street intersection | 16212.91 | 19726.89 | 32467 | 16212.91 | Fully Completed |  | 2009-08-21
| Resurface streets: NE. 9th, South Cadwell, South Park, North Jackson and North Washington | Eagle Grove city limits |  |  | 183000 | 19726.89 | 50% or More Complete | I-Jobs, Local Option Sales tax | 2011-08-30
| Resurface streets: NE. 9th, South Cadwell, South Park, North Jackson and North Washington | Eagle Grove city limits |  |  | 188943.6 | 19726.89 | 50% or More Complete | I-Jobs, Local Option Sales tax | 2011-08-30
Earlham | 2 inch asphalt overlay in Earlham, Iowa | W 1st Street between Chestnut and Walnut | 5669.28 | 6898.03 | 72700 | 6898.03 | Fully Completed | i-jobs, RUT, LOST | 2010-10-27
| Repair of street on corner of Chestnut & 3rd, other misc patches. | Chestnut & 3rd Street |  |  | 6600 | 5669.28 | Fully Completed |  | 2009-09-11
Earling | The City of Earling is in the process of possibly purchasing a new maintenance vehicle. | Earling, Iowa | 1744.84 | 2123.01 | 24650 | 0 | Not Started | RUT monies, possible Local Option Sales Tax monies also | 2010-07-12
| The City purchased a used tractor to replace an exsisting broken down tractor | Earling, Iowa |  |  | 25150 | 1744.84 | Fully Completed | I-JOBS and Local Option Sales Tax | 2010-05-19
Earlville | Removal of sealcoat, coreout, raise manholes as necessary, prep and rave, base work, patching. | 2nd and Thomas, 4th Street, patching on Elizabeth & William, Patching on Stow, S. Wine streets | 3930.93 | 4782.92 | 34006.82 | 4782.92 | Fully Completed | Local Option Fund | 2010-07-15
| Seal Coat Maintenance, Fourth St. to Thomas St. | Fourth St. to Thomas Street |  |  | 9407.87 | 3930.93 | Fully Completed |  | 2009-09-24
Early | 11.84 ton of spray injection pating | City Streets | 2642.46 | 3215.19 | 3078.4 | 3078.4 | Fully Completed | IJobs | 2011-08-26
| 118 foot of 4 foot gutter | 1st and main |  |  | 2832 | 2642.46 | Fully Completed | I-Jobs and LOST | 2009-10-29
East Peru | Bridge repair/work due to wash out | 214 McClelland Way, East Peru, IA | 223.33 | 271.74 | 12546 | 0 | Not Started | Road Use Tax Fund and FEMA grant. | 2011-11-30
Eddyville | PLACE A BATHROOM IN THE SHOP MAINT. BUILDING, ALSO INSULATE SHOP WITH REMAINDER OF MONEY | 105 N. FRONT ST. | 4647.24 | 5654.47 | 7655 | 5654.71 | Fully Completed | I JOBS MONEY AND LOCAL OPTION SALES TAX FUNDS | 2011-05-31
| REPLACE SIDEWALK AND PARKING FOR DRAINAGE PURPOSES. 66 1/2'X25'= 35 YARDS OF CONCRETE REBAR 1 1/2 TON | 101 AND 103 N. FRONT ST. |  |  | 4805 | 4647 | Fully Completed | I-JOBS AND LOCAL | 2009-10-31
Edgewood | Street and driveway repair - tear out and replace - tile, rock, backhoe and labor | 104 W Newton Street | 4031.39 | 4905.15 | 5770 | 4031.39 | Fully Completed | I-Jobs and RUT | 2010-10-06
| The city cracked sealed existing streets (cleaned cracks and joints with D-3405 hot applied rubberized sealant) | Existing streets in the southern portion of Edgewood |  |  | 7500 | 4031.39 | Fully Completed | IJobs Revenue and City of Edgewood | 2010-04-28
Elberon | FINISH WORK AND SEED GRASS IN DITCHES RECENTLY DUG RAILROAD STREET AND STREET ALONG THE PARK 3RD STREET | CITY LIMITS OF ELBERON | 861.73 | 1048.5 | 500 | 0 | <not selected> |  | 2010-06-01
Eldon | Base Repair & Double Seal Coat was done | Caster Street from Elm Street to Finney Street | 4358.97 | 5303.73 | 31802.92 | 4358.97 | Fully Completed |  | 2009-08-14
| Bse Repair, Rock and Double Seal | Railroad Street from American Gothic to Lute Street |  |  | 5303.73 | 5303.73 | Fully Completed | IJOBS | 2011-08-16
Eldora | Asphalt overlay | 14th St. & Edgington Ave. | 13255.98 | 16129.07 | 31240.78 | 0 | Fully Completed | I-jobs and city money | 2010-09-14
| Full Depth Patching | 12th Ave.; 9th Ave.; 17th Ave.; and Intersection of 6th Street and 9th Avenue |  |  | 68224 | 13255.98 | Fully Completed | Street Resurfacing and IJOBs | 2009-09-01
Eldridge | Replacement of existing storm sewer and concrete pavement | Intersection of S. 8th Street and W. Prairie Vista Drive Eldridge, Iowa | 20995.55 | 25546.11 | 60904 | 46541.66 | 50% or More Complete | Road Use Taxes and I-Jobs funds | 2010-10-01
Elgin | Asphalt of road in Hidden Valley | Hidden Valley section in Elgin | 2952.57 | 3592.51 | 199999 | 6545 | Fully Completed | IJOBS ASSESSMENT | 2010-09-30
Elk Horn | Constructed a new alley bewteen Union and Main | between Union and Main | 2834.64 | 3449.02 | 2368.69 | 2368.69 | Fully Completed | I-JOBS funds only were used. | 2009-09-30
Elk Run Heights | To be determined | To be determined | 4594.82 | 5590.7 | 0 | 0 | Not Started |  | 2009-09-23
Elkader | Asphalt overlay | Bridge Street from High to 5th; Bridge Street from Main to First; Cedar Street from Main to First | 6398.68 | 7785.53 | 75000 | 6398.68 | Fully Completed |  | 2009-09-23
| Complete Miller Street (part of a larger project) | Industrial Park (NE quandrant of town) | 6398.68 | 7785.53 | 810000 | 7785.53 | 50% or More Complete | RISE grant funds and Bond | 2011-12-30
Elkhart | Repair broken sidewalks in Elkhart | Repair sidewalks in various locations in Elkhart | 812.41 | 988.5 | 3723 | 1800.91 | Fully Completed | I Jobs and General Fund | 2010-09-23
Elliott | 1990 Eldgin Pelican Street Sweeper | City of Elliott | 1571.88 | 1912.56 | 9956 | 1912.56 | Fully Completed | Bank Loan and I-jobs | 2010-08-25
| Class D Rock/stone for Streets 13.63 Tons | City Streets |  |  | 280.34 | 280.34 | Fully Completed | I-JobS | 2009-09-24
| Class D Rock/stone for Streets 29.94 Tons 16.2 Tons | City Streets |  |  | 465.26 | 392.97 | Fully Completed | I-Jobs | 2009-09-24
| Cleaning Supplies 24in Premium Broom Braced with Screws | City Streets |  |  | 39.99 | 39.99 | Fully Completed | I-Jobs | 2009-09-09
| Sixty-six hrs of labor @ $10.00/hr with the use of his skidloader | City Streets |  |  | 665 | 665 | Fully Completed | I-Jobs | 2009-09-28
| Thirty-three and a half hrs of labor @ $10.00/hr | City Streets |  |  | 335 | 193.58 | Fully Completed | I-Jobs | 2009-09-28
Ellsworth | 25.46 TON HWY SALT | ST. PAUL, MN. | 2319.25 | 2821.92 | 2057.17 | 798.25 | Fully Completed | I-JOBS FUNDS ROAD USE TAX FUNDS | 2009-11-12
| 5.85 ton Spray injection asphalt patching | City wide |  |  | 1521 | 1521 | Fully Completed | I-JOBS FUNDS | 2009-07-15
| 8.96 Ton Spray injection asphalt patching | all city streets |  |  | 2329.6 | 2329.6 | Fully Completed | I-Job funds | 2010-07-12
| Prepayment on remainder of 2010/2011 contract for bulk highway course salt | Atlanta, GA |  |  | 4133 | 492.32 | Fully Completed | Road Use Tax Fund | 2011-12-30
Ely | Mill the top four-inches of existing asphalt surface and replace with a new surface of four-inch hot mix asphaltic cement on two segments of Dows Street. | Dows Street in Ely, Iowa in two segments: from Knoll Court to Hillcrest Street and Main Street to State Street. | 5018.49 | 6106.19 | 230032.88 | 0 | 50% or More Complete |  | 2009-09-15
Emerson | Repair edges of streets and repair old patches of asphalt. | Throughout town. Majority on King Street. | 1859.4 | 2262.4 | 0 | 0 | Not Started | I-Jobs Money. | 2011-03-15
| work to be started next month | streets throughout town |  |  | 0 | 0 | Not Started | IJOBS/City Funds | 2009-10-30
Emmet County | 2011 John Deere 772GP Motor Grader | Murphy Tractor & Equipment 1303 3rd Ave NW Fort Dodge, IA 50501 | 64331.19 | 78815.32 | 288000 | 24243.13 | Fully Completed | Road Use Tax Fund | 2011-03-04
| Gravel crushing @$2.34 per ton. We have crushed 23,321.45 tons to date for FY11. | Peterson Pit, Estherville, IA |  |  | 54572.19 | 54572.19 | Fully Completed | Road Use Tax Fund | 2010-08-09
| Gravel crushing @$2.34 per ton. We have crushed 32,038 tons to date for FY10. The Secondary Roads I-Job money was expended by 12/08/2009. | Peterson Pit, Estherville, IA |  |  | 74968.92 | 64331.19 | Fully Completed | Road Use Tax Fund | 2009-12-02
Emmetsburg | Crush Concrete Materials for Road Construction | City of Emmetsburg - 17th Street Dump Site | 17051.51 | 20747.25 | 40879 | 20747.25 | Fully Completed | I-Jobs Funding and City Capital Improvement Reserve Funds | 2010-11-30
| Purchase 2010 Ford 4x4 Pickup | Emmetsburg, IA 50536 |  |  | 25000 | 17051.51 | Fully Completed | I-Jobs Funding and Capital Equipment Reserves | 2009-11-30
Epworth | PPC paving project approx 450' | S. Center Avenue | 6997.06 | 8513.6 | 180000 | 15510.66 | Fully Completed | Local Option Tax | 2010-10-30
Estherville | Mill and overlay on various city streets | west north 9th street | 29071.43 | 35372.35 | 413744.5 | 1809.92 | 50% or More Complete | Road use tax, Ijobs | 2011-12-31
| PCC Alley reconstruction and storm sewer improvements | South half of the N/S Alley in the 700 Block between Central Ave & 1st Ave N |  |  | 65000 | 62633.86 | 50% or More Complete | Road Use Tax, IJOBS | 2011-07-29
Evansdale | This project involves placement of an ashpalt concrete overlay on approximately one-half mile of city streets. | Colleen Avenue, Elliott Avenue, and Phillips Avenue | 19768.22 | 24052.77 | 95700 | 19768.22 | Fully Completed | IJOBS and Road Use funds | 2009-11-30
Everly | Project to be determined at a later date. | City of Everly | 2825.9 | 3438.39 | 3438.39 | 0 | 50% or More Complete | Road Use Tax. | 2011-04-30
| Purchase and installation of 2 radar speed signs. | On Ocheyedan St. One on the south end of town accross from the City Park and the other on the North end of town accross from Green Plains Grain's main offices |  |  | 4290 | 2825.9 | Fully Completed | City of Everly. Road Use money was used to help supplement the excess cost of this project. | 2009-12-30
| Repair and seal coating of City streets/alleys | various Alleys Area 1 of 3 on the rotation of seal coating map. |  |  | 27276.75 | 2986.78 | Fully Completed | Road Tax | 2011-08-29
Exira | 21.71 Tons of Salt/to be used on snow and ice covered roads | Audubon, IA | 3537.84 | 4304.63 | 1671.02 | 754.72 | Fully Completed | Road use funds 9.71 T I-Jobs 12 T. | 2009-10-15
| 46.59 Tons of rock/Class D | Greenfield, IA |  |  | 528.8 | 528.8 | Less than 50% Complete | I-Jobs | 2009-08-24
| 95.95 Tons of washfill sand (to be used on icy streets) | Exira Brayton Pit |  |  | 1074.64 | 1074.64 | 50% or More Complete | I-Jobs | 2009-10-16
| Asphalt resurfacing and sealcoating of existing streets | Factory Street, from W. Harrison to Dump entrance Washington Street, from Carthage to Factory W.South Street, from David's Creek Bridge to Westside Drive South Edgerton, from City limits to E. Sout |  |  | 33719.9 | 4304.63 | Fully Completed | Road Use Tax Fund | 2010-08-17
| Purchase of 7.83 T. Cold Patch | Place on Streets within City Limits |  |  | 939.6 | 939.6 | Fully Completed | I-Jobs | 2009-09-30
| Purchase of 70.33 Tons of Road Rock | Place on City Streets within City Limits |  |  | 240.08 | 240.08 | Fully Completed | I-Jobs | 2009-09-30
Exline | repair road on E 4th & Willow. | gravel on the roads between E 4th and Willow street in Exline, Ia | 475.54 | 578.61 | 918 | 578.61 | Fully Completed | RUT | 2010-11-23
| Repaired and sealed asphalt on city street. | East 2nd St. North where it joins Highway T 30 |  |  | 700 | 475.54 | Fully Completed |  | 2009-09-01
Fairbank | Crack and joint filling of city streets. | Washington St., Benton St., Catherine St., Rainbow Dr., Front St., Amy Ave., Christians Trail, Collins Rd., Forest St., and 4th St N. | 4546.78 | 5532.24 | 8005.83 | 4546.78 | Fully Completed |  | 2009-09-03
Fairfax | Clean, parch and seal coat various streets | RR Street by elevator, Park Street from Main Street North 100' and South 75', 510 Main Street, Rynolds Street from Church Street to Main STreet, Church Street from Vanderbilt to Fairfax Road, Park STr | 7259.12 | 8832.46 | 48271.67 | 8832.46 | Fully Completed | Road Use Funds $39,439.21 | 2010-09-10
Fairfield | The city has not initiated an I jobs project as of yet. The city may want to combine the 2009 & 2010 I Jobs Funds into a projec this summer. | Fairfield Streets | 41938.68 | 51028.45 | 436500 | 92967.13 | Fully Completed | Local | 2010-09-30
Farley | The City will use the funds to repair and maintain existing streets or use funds to help in reconstructing First Street. | City of Farley | 5826.52 | 7089.35 | 2300000 | 12915.87 | 50% or More Complete | General Obligation Note SRF Note | 2011-06-30
Farmersburg | coring out, grading, rolling, and rocking surface of previously plotted but unimproved street | east 158.5 feet x 22 feet of West McAlvin Street in City of Farmersburg in Clayton County, Iowa | 859.67 | 1046 | 2833.03 | 1046 | Fully Completed | I-Jobs $1,046.00 Road Use Tax $1,787.03 Total $2,833.03 | 2010-09-10
| Sealcoat | part of the south 145 feet of Block 400 of South Main Street |  | 1046 | 1249.1 | 859.67 | Fully Completed |  | 2009-08-11
Farnhamville | Furnishing and Installing 1" asphalt overlay on street of Farnhamville--the city is doing a well and water line and treatment plant and the start date is 3/27/2012 -- the streets will be done when the project is completed | Farnhamville | 1578.87 | 1921.07 | 0 | 0 | Not Started | RUT funds | 2013-06-18
| Furnishing and installing approximately a l" asphalt overlay on some of our city streets | Farnhamville |  |  | 0 | 0 | Not Started | RUT funds | 2010-05-14
| Furnishing and installing approximately a l" asphalt overlay on some of our city streets. | Farnhamville |  |  | 0 | 0 | Not Started | RUT funds | 2010-04-15
| Furnishing and Installing l" Asphalt overlay on streets of Farnhamville | City of Farnhamville |  |  | 0 | 0 | Not Started | RUT Funds | 2010-05-11
Farragut | laying asphalt | Essex Ave. (North end) | 2223.16 | 2705.01 | 6700 | 2223.16 | Fully Completed |  | 2009-08-24
Fayette | Furnish & Install 2" asphalt patch 8 s.y. and Furnish & Install 3" asphalt patch 130 s.y. | Streets: Main, Mechanic,Clark & Volga, Jones, College, Union, State | 5900.77 | 7179.69 | 7179.69 | 7179.69 | Fully Completed | I-Jobs Street funds | 2010-11-05
| Replacing asphalt paving after a sewer & water main project | Mechanics Street from W. Water to Clark and State Street from Mechanics to Volga Street |  |  | 56884.29 | 2600.77 | Fully Completed | State Road Use Tax Funds | 2009-11-30
| Streets patching - saw cut, remove and haul away the spoils from seven separate areas on Fayette Streets and replaced with 3" compacted hot mix asphalt. | Water St. near Post Office, Jones St., Washington St., Main St. Lovers Lane, King St., and an alley. |  |  | 3300 | 3300 | Fully Completed | State Road Use Tax Funds | 2009-07-16
Fayette County | Culvert extension along Apple Rd | Sec 36 Clermont Twp Sta 102 | 127670.59 | 158356.68 | 70915 | 70915 | Fully Completed |  | 2009-06-25
| Culvert Extensions along W Ave between US 18 and IA24 | Sta 138, Sta 192, Sta 274 |  |  | 60000 | 56755.59 | Fully Completed |  | 2009-07-09
| Seal Coat work 2010 - various routes Single Seal coat over selected asphalt pavements in County | B44, W51 |  |  | 230000 | 158356.68 | Fully Completed | I Jobs, Local secondary road funds | 2010-09-09
Fenton | Clean & Single Seal Coat and Patching- Hot mix patch:2 Ton approx. Hot liquid Crack Filler-1000 L.F. | Maple St.:B-19 to 2nd St. Pine St.:B-19 to Washington St. Railroad St.:B-15 to Maple St. | 1329.18 | 1617.26 | 23661.5 | 1617.26 | Fully Completed | RUT Monies & I-JOBS Funds | 2011-08-11
| Single Seal Coat and Patching-Ash St.-B-19 to Railroad St., Single Seal Coat and Crack Filling-Railroad St.-B-15 to Maple St., Single Seal Coat-1 Block on Washington plus parking in front of Methodist Church on Maple St. and Misc. Patching. | Ash St., Railroad St., 1 Block on Washington between Ash and Maple St. |  |  | 17001.36 | 1329.18 | Fully Completed | I-Jobs & RUT | 2009-08-29
Ferguson | Purchase and install culverts to improve drainage on Railway Street ditch. | Railway Street on north edge of Ferguson. | 390.02 | 474.55 | 11700 | 390 | Fully Completed | Federal I-Jobs funds, Road Use Tax funds, Iowa Community Disaster grant, State share FEMA disaster grant | 2009-11-30
| Purchase new street signs | Within Ferguson city limits |  |  | 0 | 0 | Not Started | I-Jobs, Road Use Tax | 2012-06-30
Fertile | Blacktopping 8 City streets with 2.5" asphalt mat | 7 blocks of Washington Street and 1 block of 3rd Street | 832.91 | 1013.44 | 83068.38 | 832.91 | Fully Completed |  | 2009-07-09
Floris | Floris Streets graded and new gravel | Floris Streets | 420.36 | 511.47 | 550.95 | 420.36 | Fully Completed | I-JOBS | 2010-06-30
Floyd | Repairing storm sewer, replacing cover, channeling water | Corner of Second Avenue and Highway 218 | 1273.52 | 1549.54 | 2823.06 | 2823.06 | Fully Completed | Rebuild Iowa and ARRA Funds; Road Use Funds | 2010-04-29
Floyd County | Replace old wooden Bridge with 65' Double Tee Concrete Bridge with Stub abutments. | River Road Section 25, T97N, R17W, Bridge #156020 | 94584.86 | 115924.82 | 89742.1 | 69000 | Fully Completed | I-Jobs money with Local Dollars. | 2010-09-14
| Replace Small Bridge Structure with Double Cell 10'X4'X36' Box Culvert with end sections. | Timber Avenue S29, T94N, R15W South of 230th Street. |  |  | 75000 | 47292.43 | Fully Completed | Local I-Jobs | 2010-06-18
| Replace Small Bridge with Double Cell 12'X7'X30' Box Culvert with end sections | 220th Street S24, T95N, R18W West of Glass Avenue |  |  | 100000 | 47292.43 | Fully Completed | Local I-Jobs Funding | 2010-05-14
| Replace two Corrugated Metal Pipe with 7' X 4' X 90' Precast Concrete Box. | B57, 220th Street, Section 22, T95N, R15W, |  |  | 50000 | 29721 | Fully Completed | I-Jobs Funds with Local Dollars | 2011-04-29
| Replace two Corrugated Metal Pipes(24" & 36") with Reinforced Concrete Pipe, 24" X 56' with Aprons, and 36" X 56' with Aprons. | B65, 300th Street, Section 32, T94N, R18W, |  |  | 30000 | 17203.82 | Fully Completed | IJob Funds with Local Funds. | 2011-05-13
Fonda | To be determined but will be used in conjunction with other RUT funds to seal coat city streets. | To be determined | 2830.27 | 3443.7 | 61500 | 6273.97 | Fully Completed | I-Jobs funds used in conjuction with other RUT funds received. | 2010-12-31
Fontanelle | Adding 2" asphalt overlay for approximately 330' by 20' | North on 5th Street from the intersection of 5th Street and Summerset Street, 2" overlay of asphalt for approximately 330 feet | 3022.45 | 3677.53 | 7735 | 3677.53 | Fully Completed | IJOBS, road use taxes | 2011-06-30
| Replacing Culvert | Corner of 12th Street and Jefferson Street |  |  | 10516.81 | 3022.45 | Fully Completed |  | 2009-07-17
Forest City | 2009 Street Reconstruction Project - storm sewer work | East L, North Central, and East K Streets in Forest City, Iowa | 19200.42 | 23361.91 | 81885.18 | 19200.42 | 50% or More Complete | IJOBS Road Funding | 2009-11-15
| Asphalt Resurfacing on Clark Street, from L Street to I Street (3 blocks) | Clark Street |  |  | 23361.91 | 23361.91 | Fully Completed | I JOBS Road Funding | 2010-07-26
Fort Atkinson | Asphalt Resurfacing | 3rd Street NW | 1493.91 | 1817.7 | 13192 | 1493.91 | Fully Completed |  | 2009-08-20
| Asphalt resurfacing was done to a street that had been tarred and chipped. | 3rd Street NW |  |  | 13192 | 1817.7 | Fully Completed | I-JOBS,Road Use Tax, Local Option Tax | 2010-07-30
Fort Dodge | G St Road Construction Project | G St - Fort Dodge | 114909.9 | 139815.39 | 2000000 | 139815.39 | Fully Completed | I-Jobs and other Road Use Tax Fund | 2011-08-26
| Materials for snow and ice control on various roadways within the city limits | Various |  |  | 540566.03 | 6930.91 | Fully Completed | Road Use Tax | 2010-04-30
| Purchase of Bobcat 250 Skid Loader | Chicago, IL |  |  | 20929 | 20929 | Fully Completed | Road Use Tax | 2009-12-31
| repair and/or maintenance of exisiting roadways within the city limits | various |  |  | 616156.86 | 87049.99 | Fully Completed | Road Use tax | 2009-11-30
Fort Madison | Reconstruction of the intersection of Highway 61 and 48th Street, create a center turning lane. | Highway 61 and 48th Street | 50123.76 | 60987.55 | 633946.61 | 100247.52 | Fully Completed | Federal Grant I-Jobs Local Option Sales Tax | 2011-06-30
| removal of old surface and replacing street | Avenue M 23rd Street to 25th Street |  |  | 262163 | 37792.16 | Less than 50% Complete | Local Option Sales Tax & I-Jobs Funding | 2011-11-30
Franklin County | Construction of New Twin Pre-Cast Concrete Box Culvert | 60th Street between County Route S56 and Timber Avenue | 98221.89 | 122729.43 | 127407.21 | 98221.89 | Fully Completed | Secondary Road Fund | 2010-07-31
| Pavement Patching on County Route C13 (250th Street) | County Route C13 (250th Street)from Balsam Avenue to Grouse Avenue |  |  | 141323.12 | 122729.43 | Fully Completed | Secondary Road Fund | 2011-05-31
Fredericksburg | Grade, Crown & Appy Mc-70 asphalt | From the intersection of South Jefferson & West Railroad to the intersection of South Washington & West Railroad in Fredericksburg, Iowa | 4297.82 | 5229.33 | 10301.86 | 4297.82 | Fully Completed | I-Job dollars of $4,297.82 and the balance came out of the Street Fund & regular Road Use Tax Dollars | 2009-11-16
| To Be Determined at a later date | To be determined |  |  | 0 | 0 | Not Started | I-Jobs | 2009-09-30
Frederika | Build up 5th Street install 3 culverts and rock | 5th Street | 624.64 | 760.03 | 8993.59 | 624.64 | Fully Completed | Road Use Funds | 2009-09-12
Fredonia | Installing new culverts in a ditch on 3rd Ave Fredonia so the road may be opened back up | 3rd Ave Fredonia | 944.71 | 1149.47 | 3260 | 1100 | Less than 50% Complete | City Of Fredonia | 2011-07-29
Fremont | 6'x10'x7" concrete street patch 901.00 | North Walnut | 3074.86 | 3741.31 | 3741.31 | 3741.31 | Fully Completed | Road use tax fund | 2012-06-26
| cut the road to get to the drain, to repair, so water does not flood the road. Labor 27.75 hours= 601.11 Labor 12 hours= 120.00 Labor 18.75 hours= 187.50 Blade for cutter 390.00 60'-8" pvc pipe and 8" fernco coupling 462.63 | North Walnut |  |  | 0 | 0 | Not Started | Road use tax fund | 2012-05-24
| Dump Truck to be used for general street maintenance and snow removal. Equipment expected to be purchased within the next month. | Ames, Iowa |  |  | 13500 | 3074.86 | Fully Completed | Road Use Tax Fund | 2009-10-30
| Pickup and install culverts. 60ft dualwall 744.00 Labor 8.75 hours = 185.15 Labor 6 hours = 60.00 | South Harrison |  |  | 0 | 0 | Not Started | Road use tax fund | 2012-04-10
| putting down 1 ton gravel 20.00 Labor 1/2 hour=10.15 | North Walnut |  |  | 0 | 0 | Not Started | Road use tax fund | 2012-06-05
| Replaced man hole cover that was letting water get in. Cleaned ring. 1 hour at 20.29 Manhole cover 202.80 | North Chestnut |  |  | 0 | 0 | Not Started | Road use tax fund | 2012-05-18
| Street temp patch labor 1 hour at 20.29 per hour | South Harrison |  |  | 0 | 0 | Not Started | Road use tax fund | 2012-04-09
| To be determined at a later date. | Unknown |  |  | 0 | 0 | Not Started | Unknown | 2011-06-30
Fremont County | PCC patching of bridge deck. | On J18 west of Randolph, IA. | 82655 | 101197.66 | 98558.3 | 82655 | Fully Completed | I-Jobs, Local Funding | 2009-11-06
| Purchased Used Motor Grader to replace old one. It is a John Deere model 770G. | Fremont County - Randolph Iowa patrol |  |  | 149417 | 101197.66 | Fully Completed | I-Jobs money and Local money | 2010-09-09
Fruitland | Seal coating applied to streets in need of repair. | Fruitland | 3070.49 | 3735.99 | 91007.76 | 3735.99 | Fully Completed | I-JOBS and Road Use Tax | 2010-09-10
| Seal coating applied to streets in need of repair. | Fruitland |  |  | 91011.75 | 6140.98 | Fully Completed | I-JOBS and Road Use Tax | 2010-08-01
| To be determined at a later date. | Fruitland, IA |  |  | 0 | 0 | Not Started | I-JOBS and Road Use Tax | 2011-12-31
Galt | Street Lighting | Town of Galt | 97.88 | 119.09 | 216.97 | 216.97 | Fully Completed | IJOBS monies | 2011-06-30
Galva | Seal coating | Buena Vista Street and 3rd Street | 1164.96 | 1417.45 | 15513 | 1164.96 | Fully Completed |  | 2009-07-28
| Seal Coating | 1st St |  |  | 21958.94 | 1417.45 | Fully Completed | Local Option Sales Tax along with the Ijobs dollars | 2010-08-01
Garnavillo | Apply base rock and sealcoat West Centre Street - section of street was previously gravel only | West Centre Street | 3293.25 | 4007.02 | 11996.5 | 4007.02 | Fully Completed | Road Use Tax Funds/IJOBS Funds | 2010-08-27
| Street Sealcoat Project on various street throughout the city. | Various Street Citywide |  |  | 30838.2 | 3293.25 | Fully Completed | IJobs Funds and Road Use Tax Funds | 2009-08-18
Garner | 2011 International Dump Truck | Garner Iowa | 12762.43 | 15528.55 | 63280 | 28290.98 | Fully Completed | I-Jobs, RUT and LOST | 2010-11-04
Garrison | Repair & maintenance on the streets - Seal coating streets | Oak Street and Pine Street | 1582.11 | 1925.02 | 4000 | 3507.13 | Fully Completed | RUT | 2010-08-31
Garwin | to be determined | to be determined | 2467.75 | 3002.61 | 0 | 0 | Not Started |  | 2010-06-30
Geneva | Materials only on repairing hole in street | 308 Monroe Street | 463.85 | 564.38 | 50 | 50 | Fully Completed | I-Jobs | 2009-10-14
| Resurface 5 blocks of Mary Street and 3 blocks of South street. | City of Geneva, IA. |  | 564.38 | 11000 | 978.23 | Fully Completed | I-JOBS and road use tax monies | 2010-09-14
George | Asphalt resurfacing on South Baldwin Street | 200-300 South Baldwin Street | 4590.46 | 5585.39 | 5000 | 4590.46 | Fully Completed | I-Jobs Funding | 2009-08-31
| Repair street surface on 600 block of E Minnesota | 600 Block E Minnesota |  |  | 15000 | 5585.39 | Fully Completed | IJobs | 2010-09-16
Gibson | This project will be determined at a later date. | To be determined. | 214.31 | 260.76 | 0 | 0 | Not Started | State of Iowa | 2014-09-24
Gilbert | 328 S.Y. PAVEMENT REMOVAL 266 S.Y. 7-INCH P.C.C. PAVEMENT 18 S.Y. 6-INCH P.C.C. DRIVEWAY 34 S.F. TRUNCATED DOME PAVER 12 S.Y. 6-INCH P.C.C. PEDESTRIAN RAMP 23 S.Y. 4-INCH P.C.C. SIDEWALK 1 TRAFFIC CONTROL 303 S.Y. SUBGRADE PREPARATION | INTERSECTION OF MATHEWS DRIVE AND ROTHMOOR DRIVE GILBERT IOWA 50105 | 4310.92 | 5245.27 | 15958 | 4310.92 | Fully Completed |  | 2009-08-14
| To Be Determined at a later date. | To Be Determined. |  |  | 6908.75 | 5245.27 | Fully Completed | I-Jobs and City cash on hand. | 2011-05-31
Gilbertville | Asphalt Resurfacing - Approximately 1,036 square yards 3" Asphalt Paving | Parkview Drive | 3350.03 | 4076.11 | 18900 | 3350.03 | Fully Completed | Road Use Tax | 2009-09-11
| Crack Sealing city streets | 13th Ave from 5th St. to 4th St. 14th Ave. from bridge East of 5th to bridge over river 18th Ave. from ashpalt to west end 17th Ave. from 5th to 6th St. 7th St. from 10th to 14th Ave 6th St. from |  |  | 7211 | 0 | Fully Completed | I-Jobs and Road Use Funds | 2010-08-20
Gilmore City | Core out and preparation of the base followed by installing asphalt patch on water main break | Intersection of SW 'D' Ave and SW 3rd Street | 2428.44 | 2954.78 | 2000 | 1900 | Fully Completed | I-Jobs funding | 2009-09-11
| Purchase Road Salt for winter of 2010/2011 | Gilmore City, Iowa |  |  | 2184.36 | 450 | Fully Completed | I-Jobs Funding | 2010-11-15
| Street Repairs - Oil & Single Chip Seal Coat | Gilmore City |  |  | 25335.96 | 528.44 | Fully Completed | I-Jobs & City Street Funds | 2010-05-20
Gladbrook | Seal Coat of select residential streets. | Edgeland St., 4th St. from Lincoln to Garfield, Gould from 2nd to 5th. | 4433.22 | 5394.07 | 29231.4 | 9827.29 | Fully Completed | Road Use Tax Fund | 2010-07-16
Glenwood | Mill & asphalt overlay on Walnut Street from Fourth St. North to Sixth Street | Walnut Street | 23402.15 | 28474.32 | 28474.32 | 28474.32 | Fully Completed | IJOBS portion - $28,474.32 | 2010-09-09
| Mill and asphalt overlay on Fourth Street from Myrtle St West to Elm Street and Mill and asphalt overlay on Grove Street from Third St North to Fifth Street | Fourth Street and Grove Street |  |  | 42263.48 | 23402.15 | Fully Completed |  | 2009-09-17
Glidden | Asphalt overlays and maintenance | various sections of city roads | 5472.73 | 6658.89 | 84600 | 6658.89 | Fully Completed | Road Use Tax Fund | 2010-10-31
| Crack sealing and asphalt maintenance | Various sections of city roads |  |  | 5472.73 | 5472.73 | Fully Completed |  | 2009-06-30
| Slurry surfacing and asphalt maintenance | Several block sections |  |  | 100000 | 0 | Not Started | Road Use Tax Fund Local Option Sales Tax Fund | 2011-09-01
Goldfield | Patch City streets/cold patch | City Streets | 2970.04 | 3613.76 | 936.6 | 936.6 | Fully Completed | I-Jobs | 2011-12-05
| Project identified. Need to patch city streets. Waiting on Council approval which will be April 11, 2011. The Pavement Doctor has already been contacted so the PW Superintendent knows what the cost per ton is. The Council approved. PW Superintendent | Street repair/miscellaneous streets within city |  |  | 2823.6 | 2823.6 | Fully Completed | IJOBS Funds | 2011-05-30
| Spray injection patching of city streets | Miscellaneous streets in Goldfield |  |  | 2823.6 | 5647.2 | Fully Completed | IJOBS Funds | 2010-04-21
Goodell | All city allies were maintained with gravel in 2011 | Goodell Ia | 554.09 | 674.18 | 650 | 554.09 | Fully Completed | IJOB money | 2011-08-11
| Repair of Alleys in Goodell using road stone. | Goodell IA |  |  | 625 | 554.09 | Fully Completed | Road use tax fund money 554.09 | 2010-06-01
| The I Jobs money will be used for maintenance of the city alleys in April or May of 2010. | City of Goodell |  |  | 0 | 0 | Not Started | I-Jobs Money $554.09 | 2010-05-29
| We have not determined a project at this time. | Goodell IA |  |  | 0 | 0 | Not Started | I-Job Money $554.09 | 2009-12-31
| We have not determined what we will do with this IJobs money as yet. | Goodell IA |  |  | 0 | 0 | Not Started | Whatever we decide the IJobs money will be used before July 1, 2011. | 2011-06-30
| We have not yet determined a project for the I Job money of $554.09 for this year. | Goodell IA |  |  | 0 | 0 | Not Started | I Job money of $554.09 | 2009-12-31
Goose Lake | Repair Main Street after water main break under road. | 213 Main Street Goose Lake, IA | 687.6 | 836.63 | 1200 | 687.6 | Fully Completed | I-Jobs funds of $687.60 Plus Road Use Tax Funds | 2009-10-27
Gowrie | Asphalt resurfacing | North part of 4th Street | 4533.68 | 5516.3 | 4533.68 | 4533.68 | Not Started |  | 2009-12-31
Graettinger | 4" asphalt matt on South Wilson Avenue, Graettinger, Iowa | South Wilson Avenue, Graettinger, Iowa | 3930.93 | 4782.92 | 58100 | 4782.92 | Fully Completed | Total project 58,100 32502.50- Palo Alto County 4782.92- Ijobs 20814.58- General fund City of Graettinger | 2010-07-08
| Purchasing a new snow plow, Henke 36R10IS Reversialbe Truck Plow, cost $8,300, with hydraulic of $4,350. Total cost $12,650. | 201 S. Washington Avenue | 3930.93 |  | 12650 | 3930.93 | Fully Completed | Road Use Fund | 2009-10-12
Graf | Clean out storm water detention pond with excavator. | West end of Graf Ct. | 152.68 | 185.78 | 1000 | 152.68 | Fully Completed |  | 2009-07-30
| Repair potholes in Lola Lane and Graf Court. Perform maintenance at detention pond. | Graf, IA |  |  | 260 | 185.78 | Fully Completed | I-jobs and State Road Use Tax | 2010-08-02
Grafton | Blacktop patching to repair potholes | 6th Avenue | 763.88 | 929.44 | 815.32 | 815.32 | Fully Completed | I jobs | 2011-07-18
| to be determined. repair a pothole in the street | 6th Avenue |  |  | 878 | 878 | Fully Completed | to be determined | 2011-06-01
Grand Mound | Base repair including scarifying, pulverizing, grading, compacting and second seal coat. | DeWitt Street, Joyce Court | 2952.57 | 3592.51 | 2952.57 | 2952.57 | Fully Completed | Road Use Fund | 2009-09-24
Grand River | Repairing streets and cleaning ditches | City of Grand River | 803.85 | 978.07 | 400 | 400 | Fully Completed | I-jobs and road use tax money | 2011-05-30
| Snow removal for City streets | Grand River |  |  | 803.85 | 803.85 | Fully Completed | I-jobs and road use money | 2010-02-27
| street sealcoating and repairing | Grand River |  |  | 577.57 | 577.57 | Fully Completed | IJobs | 2011-07-31
Grandview | sealcoating of streets and patch work | 3 blocks on S. Market, 2 blocks on S. Jefferson, Cemetery Lane, 2 blocks on E. Washington, 2 blocks on W. Union, 3 blocks on N. Madison, 1 block on W. Vernon | 2620.62 | 3188.61 | 27215.45 | 2620.62 | Fully Completed |  | 2009-08-20
Granger | wages for asphalt repairs | several streets in town | 2546.37 | 3098.27 | 3000 | 2546.37 | Fully Completed | IJOBs funding | 2010-02-26
Grant | Patching Streets in the City of Grant | Grant, Iowa | 414.43 | 504.24 | 700 | 504.64 | Fully Completed | I-Jobs Revenue | 2011-12-31
| Replacement of rock on city streets | Miscellaneous streets and alleys |  |  | 528.04 | 414.03 | Fully Completed | I-Jobs Funds and Road Use Tax | 2009-12-30
Granville | project to be determined as council sees the need | location to be determined as council sees the need | 1408.38 | 1713.64 | 0 | 0 | Not Started | road use tax fund | 2009-09-30
Gravity | DITCHING AND RESHAPING STREETS/ PURCHASED GRAVEL FOR STREETS THAT ARE UNDER RESHAPING | SEVERAL STREETS WITHIN CITY LIMITS | 766.13 | 932.18 | 1055.61 | 932.18 | Fully Completed | I-JOB/ROAD USE | 2011-03-08
| Gravel for floor of newly construction maintaince addition | City of Gravity Third Street Gravity, Ia |  |  | 912.96 | 1532.26 | Fully Completed | Road Use Funds/i-jobs | 2010-04-30
Greene | SEALCOAT NORTH FIRST STREET BETWEEN BUTLER TO IOWA | NORTH FIRST STREET | 4800.11 | 5840.48 | 0 | 0 | Not Started | General Fund & I-Jobs money | 2010-11-01
| SEALCOAT NORTH FIRST STREET BETWEEN BUTLER TO IOWA | NORTH FIRST STREET |  |  | 10000 | 0 | Not Started | General Fund & I-Jobs money | 2010-11-01
Greene County | Caterpillar 2005 Wheel Loader 950G | Jefferson | 93852.63 | 115010.16 | 105000 | 93852.63 | Fully Completed | Secondary Road Fund | 2009-12-14
| Purchase of Armory Building for equipment storage | Jefferson |  |  | 150000 | 115010.16 | Fully Completed | Secondary Road Fund | 2010-11-15
Greenfield | Asphalt repair of SW 2nd Street from Highway 92 south to Linn St. | SW 2nd Street | 9298.84 | 11314.26 | 13469.75 | 11314.26 | Fully Completed | I-JOBS & Road Use | 2011-09-15
| Repair of streets, intersections, and alley approaches | HW Iowa & Hayes, SE Linn & 1st, SE Linn & 2nd, SE Linn, NW Grant between 3rd & 4th |  |  | 6601.4 | 6601.4 | Fully Completed |  | 2009-09-30
| Repair of streets, intersections, and alley approaches. | SE 4th St south of Hwy 92; SE 2nd St & Lynn; and Hwy 25 north to Darby Dr |  |  | 3127.07 | 2697.44 | Fully Completed | $2,697.44 from I-Jobs and the remaining $429.63 from Road Use Fund. | 2009-09-18
Greenfield | To Be Determined at a later date. | City of Greenfield |  |  | 0 | 0 | Not Started | I-Jobs | 2011-06-30
Grimes | Asphalt overlay of approximately 4 blocks of city street with extensive deterioration. Overlay was completed to preserve and extend the life of the road | Valleyview Drive from NW 3rd St to NW 7th Street | 25603.47 | 31152.76 | 40700 | 31152.73 | Fully Completed | I-jobs money and Road Use Tax funds | 2010-11-24
| Asphalt seal-coat overlay on appropximately 20 blocks of road in the "older" section of town. This extends the life of the road to delay the need for the complete reconstruction of the road. | Grimes, Iowa |  |  | 79196.65 | 25603.47 | Fully Completed | I-Jobs Funds and Road Use Tax Funds | 2009-10-30
Grinnell | 1st Avenue and 8th Avenue Resurfacing Project | 1st Avenue and 8th Avenue in the city of Grinnell - HMA RESURFACING AND MILLING | 39767.94 | 48387.21 | 259280 | 39707 | 50% or More Complete | IJOBS Grant, IJOBS RUT Stimulus Funds and Capital Loan Notes | 2009-10-30
Griswold | Repair and maintenance of the alleys | within the city of Griswold | 4538.04 | 5521.62 | 10059.66 | 10059.66 | Fully Completed | I-JOBS | 2011-05-31
Grundy Center | Reconstruction of a three block street. | East 1st Street from G Avenue to J Avenue. | 11338.56 | 13796.07 | 117861.87 | 13796.07 | 50% or More Complete | I-Jobs for FY2011 and GO Bond | 2011-09-30
| replacing curb & gutter around Liberty Park | 13th Street north to E Avenue, then east to 12th street then north on 12th street |  | 13796.07 | 11844 | 11338.56 | Fully Completed |  | 2009-08-12
Grundy County | 2010 pavement marking painting with edge and center lines | Various roads - 94 miles | 97102.36 | 115112.85 | 56000 | 55179 | Fully Completed | Local | 2010-08-04
| 2011 Pavement Marking Painting on edge and center lines | Various roads - 87 miles |  |  | 70000 | 23000 | Fully Completed | Local | 2011-07-29
| Purchase of winter road rock salt for snow/ice control | Entire hard surfaced roads in Grundy County |  |  | 200000 | 50000 | Fully Completed | Local | 2010-03-31
| RCB Replacement 12'x'6'x44' on 170th St. east of X Ave | Section 11, T88N, R15W |  |  | 51419.42 | 51100 | Fully Completed | Local | 2009-08-20
| Repair bridge D14 (FHWA 16630) with new abutments to bring bridge to legal loads | Located on 130th St, Section 20, T89N, R18W |  |  | 38000 | 34937 | Fully Completed | Local | 2010-09-10
Guthrie Center | Dust control, paint traffice lines, street opening | various | 7285.33 | 8864.35 | 1532.52 | 1532.52 | Fully Completed |  | 2009-09-09
| fill sand, road rock, ice sand and salt, snow removal | throughout town |  |  | 7376.14 | 7376.14 | Fully Completed | i jobs | 2011-02-09
| snow removal, replacing rock, salt, sand | Guthrie Center, IA |  |  | 2255.98 | 2255.98 | Fully Completed | IJOBS | 2010-03-16
| traffic paint, dust control, concrete, downtown snow removal | various |  |  | 3496.83 | 3496.83 | Fully Completed | IJOBS | 2009-12-14
Guthrie County | 2010 Caterpillar 320DLH2R Excavator | Guthrie Center IA | 101023.22 | 123794.42 | 170000 | 123794.42 | Fully Completed | Secondary Road Fund | 2010-08-01
| Bridge overlay with HPC-0 mix | On County route F51 approximately 3.75 miles east of State Hwy 25 |  |  | 69066 | 69066 | Fully Completed | Secondary Road Fund | 2009-09-16
| Crack repair/sealing on County Road F65 | F65 from County Line Avenue to Frontier Road and from Frontier Road to Grant Street |  |  | 14275 | 14275 | Fully Completed | Secondary Road Fund | 2009-10-20
| Replace existing bridge with 46' precast concrete bridge | 220th St, NL Section 1, Bear Grove Twp |  |  | 47500 | 17682.22 | Fully Completed | Secondary Road Fund | 2010-02-18
Guttenberg | 2009 Seal Coat Project | First St. and Dekalb St | 8678.63 | 10559.63 | 24383.8 | 8678.63 | Fully Completed |  | 2009-08-31
| Resurface street(s) in Guttenberg, Iowa | South 4th St |  |  | 17661 | 10559 | Fully Completed | I-Jobs | 2011-06-01
Halbur | Street patching and repairs. Fill cracks in streets with Hot Pour Joint Sealing and Random Crack Repair.Diamond sawing the PCC joints to remove old sealant and debris, sandblast and clean. Air blown clean and sealed concrete curb & gutters. | All streets in Halbur | 641.85 | 780.96 | 14500 | 641.85 | Fully Completed |  | 2009-08-27
| Street patching and repairs. Fill cracks in streets with Hot Pour Joint Sealing and Random Crack Repair.Diamond sawing the PCC joints to remove old sealant and debris, sandblast and clean. Air blown clean and sealed concrete curb & gutters. | All streets in Halbur needing repair. |  |  | 10000 | 780 | Fully Completed | Road Use funds, IJobs and general funds. | 2011-11-01
Hamilton County | Drain tile video inspection camera | Various throughout Hamilton County | 95331.94 | 116699.45 | 0 | 0 | Not Started | Rut | 2010-03-01
| Pavement crack sealing on R-77 | R-77 from D41 to Hwy 175 |  |  | 80000 | 40379 | Fully Completed | I-Jobs as part of road use tax | 2010-07-08
| Pavement Markings | Various hard surface secondary roads in Hamilton County |  |  | 80000 | 76319.54 | Fully Completed | I- Jobs as part of secondary roads road use tax | 2010-07-28
| Purchase a 15,000 ton stockpile of Class A road stone. | Grandgeorge Quarry - for various roads in Hamilton County |  |  | 103000 | 95332 | Fully Completed | I-Jobs as part of RUT | 2009-10-15
Hampton | Mill and overlay of asphalt to residential street | 1st Street NE, from 5th Avenue to 7th Avenue NE | 18422.97 | 22415.95 | 18564.8 | 18422.97 | Fully Completed |  | 2009-07-31
| Milling & resurfacing City streets with asphalt. | 2nd Ave Drive SE from 8th St SE to 3rd Ave SE 3rd St NW - Central Avenue W to 1st Ave NW |  |  | 22000 | 22000 | Fully Completed | Iowa Department of Transportation (I-Jobs) | 2010-07-23
Hancock | Will use this money for rock in the alleys in Hancock | City of Hancock | 746.32 | 908.08 | 746 | 1123.68 | 50% or More Complete | Road Use Tax | 2010-05-31
| Will use this money for rock in the alleys in Hancock | City of Hancock |  |  | 1654.4 | 1123.68 | 50% or More Complete | Road Use Tax | 2010-05-31
Hancock County | Bridge replacement in Magor Township Contract Let 12-21-10 | Hancock County | 101926.33 | 123417.94 | 244000 | 144066.96 | Fully Completed | I-Jobs | 2012-12-31
| Maintainence Rock | Hancock County |  |  | 81277.31 | 81277.31 | Fully Completed | IJOBS/LOCAL FUNDS | 2011-06-20
Hanlontown | Crackfilling Paving | Crackfilling various locations in city Pave Sundown Drive from Main ST to IA 9 | 820.24 | 998.02 | 50343.1 | 820.24 | Fully Completed | IJobs Road Use Tax | 2009-06-30
Hansell | PURCHASING STREET SIGNS FOR TIMBER AVE. IN HANSELL BY THE FIRE DEPT. NO PARKING SIGNS.... | TIMBER AVE. IN FRONT AND ACROSS THE STREET FROM THE FIRE DEPT. | 193.7 | 235.68 | 235.68 | 235.68 | Fully Completed | I-JOBS MONEY RECEIVED IN THE AMOUNT OF $235.68 | 2010-11-01
| Repairing of the Grating over the Drainage System. | In town of Hansell |  |  | 193.7 | 193.7 | Fully Completed | I-Jobs monies and some road funds monies. | 2010-01-11
Harcourt | City of Harcourt will use monies for road repairs. | Fourth Street- Harcourt, Iowa | 1341.4 | 1632.13 | 0 | 0 | Not Started | I_Jobs monies | 2010-06-30
Hardin County | Bridge 10170 repair work - new abutment piling | R Ave 1/4 mile south of State Hwy 175 | 106117.32 | 132896.98 | 60000 | 750 | Fully Completed | Local | 2010-10-27
| Pavement Markings on variuos county roads center and edge lines | Various roasds - 60 miles |  |  | 35300 | 0 | Fully Completed | Local | 2010-10-30
| Purchase of rock salt for snow/ice control used on hard surfaced roads in Hardin County | Entire county |  |  | 415000 | 158264 | Fully Completed | Local | 2010-04-01
| Yantis Quad-Tee Bridge Replacement | Sec 36, T86N, R19W |  |  | 80000 | 80000 | Fully Completed | Local | 2009-11-01
Hardy | various repairs to roads | within City of Hardy | 125.01 | 152.1 | 500 | 0 | Not Started | City of Hardy | 2010-09-30
Harlan | 2011 STREET OVERLAY AND MILLING PROJECT. SOLD BONDS $300,000 TOWARD THIS PROJECT, PLUS I-JOBS FUNDS Transferred all I-Jobs funds in June 2011 to appropriate toward the contracted street work for 2011. | VARIOUS STREETS IN HARLAN | 23070.21 | 28070.43 | 0 | 0 | Not Started | ROAD USE TAX FUNDS, LOST FUNDS, I-JOBS AND BOND FUNDS | 2011-06-22
| DURING THE BUDGET PROCESS IN JANUARY, WE WILL FURTHER DISCUSS AND DETERMINE A SPECIFIC PROJECT TO USE THE I-JOBS FUNDS. AS OF 9/27/10 WE HAVE NOT DETERMINED A SPECIFIC PROJECT BUT WILL YET THIS FALL. | various streets in Harlan |  |  | 23070.21 | 0 | Not Started | I-JOBS FUNDS AND MAY INCORPORATE ROAD USE TAX FUNDS OR LOST FUNDS TOWARD A PROJECT. | 2010-12-31
| DURING THE BUDGET PROCESS IN JANUARY, WE WILL FURTHER DISCUSS AND DETERMINE A SPECIFIC PROJECT TO USE THE I-JOBS FUNDS. AS OF 9/27/10 WE HAVE NOT DETERMINED A SPECIFIC PROJECT BUT WILL YET THIS FALL. | various streets in Harlan |  |  | 51140.64 | 0 | Not Started | I-JOBS FUNDS AND MAY INCORPORATE ROAD USE TAX FUNDS OR LOST FUNDS TOWARD A PROJECT. | 2010-12-31
Harper | Removal of stumps from trees damaged by recent ice storms | 202 Hutchinson Street 301 Lafayette Street 313 Lafayette Street | 415.93 | 506.08 | 400 | 387.71 | Fully Completed | Community Disaster Grant I-Jobs Funds | 2009-11-30
Harpers Ferry | Alley and Street Maintenance | City of Harpers Ferry | 1245.86 | 1515.9 | 0 | 0 | Not Started | IJOBS & Road Use Tax | 2010-07-31
| Maintenance of City Streets | Harpers Ferry |  |  | 0 | 0 | Not Started | IJobs and Road Use Tax | 2010-06-30
Harris | Sealcoating non farm to market city streets | Non farm to market streets in city | 579.17 | 704.7 | 24040.38 | 1283.87 | Fully Completed | Road Use Tax | 2011-06-30
Harrison County | PCC PAVEMENT OVERLAY (BONDED) ON COUNTY ROAD F32 FROM U.S. HWY. 30 EAST TO TOLEDO AVENUE | HARRISON COUNTY; EAST OF WOODBINE ON F32 (194TH STREET) | 110183.41 | 135010.26 | 1375000 | 245193.67 | Fully Completed | ESFM | 2010-06-24
Hartley | Asphalt level, single seal and patching | 2nd St NW, 1st St. NE, 1st St. SE, 4th Avenue, 6th Avenue E,6th Avenue W | 7569.23 | 9209.78 | 90847 | 0 | Fully Completed | Road Use Fund | 2010-06-10
| Asphalt Leveler and Single Seal Coat | 2nd St. between 1st Ave W and 3rd Ave W |  |  | 13571.25 | 7569.23 | Fully Completed | Road Use Tax Fund | 2009-08-26
Hartwick | Maintaining our roadway mowing | I-Jobs money for the City of Hartwick | 259.86 | 316.18 | 316 | 316 | Fully Completed | I-Jobs funds | 2011-06-30
| Used to help pay our annual street repairs of oil and tar and gravel chips. We select certain streets each year to relay as needed. | City streets of Hartwick |  |  | 7362.5 | 259.86 | Fully Completed |  | 2009-08-11
Harvey | TO COMPLETE UNEXPECTED WORK | VARIOUS LOCATIONS | 1121.32 | 1364.37 | 97500 | 1121.32 | Fully Completed |  | 2009-08-04
Hastings | Rock hauled in by Crushed Aggregate Products LLC | S. Railway & Buffalo St | 805.92 | 980.59 | 2100 | 805.92 | Fully Completed | state | 2009-11-18
| Street repair, resurfacing Purchased Dump Truck | Indian Ave |  |  | 2745 | 980.59 | Fully Completed | State | 2011-06-09
Havelock | ASPHALT/SEALCOAT | City Street | 639.35 | 777.92 | 7500 | 639.35 | Fully Completed |  | 2009-07-07
| Patch and oil and chip single seal coat | Town streets |  |  | 8935.2 | 0 | Fully Completed | Secondary Road fund | 2010-07-01
| Street repair from broken water main | Clay Street |  |  | 3000 | 777.92 | 50% or More Complete | Road fund | 2011-09-01
Haverhill | Our Blacktopped Streets are in need of Maintenance. Mobilization, 2" HMA Surface Patch, 2"HMA Resurfacing, 4: HMA Paving | 1 St and 2nd Street | 610.98 | 743.4 | 20852 | 743.4 | Fully Completed | I Jobs & RUT monies | 2011-10-01
| The council will be improving 1st streets width for parking. | City of Haverhill |  |  | 6304 | 610.98 | Fully Completed | I job and RUT monies | 2009-11-16
Hawarden | Street Sweeper for Street Deparatment | City Street Dept, Hawarden, IA | 10823.17 | 13168.97 | 135000 | 23992.14 | Fully Completed | Capital Equipment Fund & I-Jobs Revenue | 2011-06-30
Hawkeye | add gravel to alleys and side streets. Then add oil to control dust | Bevins Street, Peoria Street, Peters Street | 1575.54 | 1917.01 | 1668.1 | 1575.54 | Fully Completed |  | 2009-09-15
| HIRED KLUESNER CONSTRUCTION TO MILL FROST HEAVES AND PATCH CRACKS ON MAIN STREET | MAIN STREET IN HAWKEYE, IA |  |  | 6641 | 1917 | Fully Completed | INVOICE TOTAL $6641.20 I-JOBS MONEY -1917.01 | 2010-08-10
Hayesville | Maintain city alleys in Hayesville | All city alleys | 185.07 | 225.18 | 1077.86 | 410.25 | Fully Completed | I-Jobs funds | 2010-12-01
Hazleton | Repair of a roadway in Hazleton. | Undecided at this time. | 4149.32 | 5048.64 | 21000 | 8298.64 | Fully Completed | I-Jobs & Road Use | 2009-11-16
| Seal Coat streets | Through out Town |  |  | 28000 | 0 | Not Started | I-Jobs & Road Use | 2010-05-26
Hedrick | Henderson FSP-8' Salt/Sand Spreader | Hedrick, Iowa | 3655.77 | 4448.12 | 4375 | 4375 | Fully Completed | Road Use Stimulus money | 2011-04-30
| Maintenance supplies for our streets | Hedrick, Iowa |  |  | 2155.77 | 4311.54 | Fully Completed | Stimulus money | 2009-12-08
| Street supplies for road maintenance | Hedrick, Iowa |  |  | 765.94 | 146.24 | Fully Completed | Stimulus money and Road Use Tax | 2010-10-31
| Street Sweeper for use on our city streets | Hedrick, IA 52563 |  |  | 1500 | 1500 | Fully Completed | Stimulus money | 2009-08-26
Henderson | snow removal | town of henderson--north west to south east street | 583.01 | 709.36 | 2000 | 709.36 | Fully Completed | ijobs and road use funds | 2011-03-31
| Two loads [18.82 Ton] of 1" rock for street repair | Highway Street & North Street |  |  | 583.01 | 583.01 | Fully Completed | none | 2009-10-19
Henry County | 2" HMA overlay | Courtland Street - west of Mt. Pleasant Goodyear Road east to City limits | 87896.76 | 105524.6 | 50000 | 48485.92 | Fully Completed |  | 2009-08-24
| Bituminous Seal Coat project | Swedesburg, Trenton, Green Valley |  |  | 90947.95 | 90947.95 | Fully Completed | Secondary Road Fund | 2010-09-14
| Portland Cement Concrete paving | New London |  |  | 22577.06 | 14576.65 | Fully Completed | Secondary Road Funds | 2010-09-09
| Reroof of maintenance shop and grader shed | 1510 East Washington Street |  |  | 30000 | 29192.04 | Fully Completed |  | 2009-08-27
| Slide repair of Nebraska Avenue | Baltimore Township, Section 29 |  |  | 15000 | 10218.8 | Fully Completed | Local funds | 2009-11-24
Hepburn | Gravel for maintenance of 2nd Street in front of city property. | 2nd Street from Railroad Street approximately 1/2 block to the east to maintain street in front of city property. | 144.61 | 175.95 | 189.14 | 144.61 | Fully Completed | I-Jobs money will be supplemented with Road Use Tax Fund money. | 2010-06-30
| Gravel for maintenance of public alley between 1st and 2nd Streets | Alley beginning at 1st Street extending to the South toward 2nd Street |  |  | 216 | 175.95 | Fully Completed | I-Jobs money will be supplemented with Road Use Tax Fund money | 2011-06-30
| Gravel for maintenance of Railroad Street in front of city property. | Railroad Street from 2nd Street approximately 1/2 block to the north to maintain street by city property. |  |  | 0 | 0 | Not Started | I-Jobs money will be supplemented with Road Use Tax Fund money. | 2011-06-30
Hiawatha | 3rd Avenue from Marion Street to West Clark Street Pavement Reconstruction | 3rd Avenue | 28376.97 | 34527.37 | 281068.8 | 21592.71 | Fully Completed | I-Jobs funding and General Obligation Notes | 2011-06-30
| Boyson Rd and Robins Rd Intersection Project | Boyson Road and Robins Road Intersection |  |  | 1088500 | 41311.63 | Less than 50% Complete | I-Jobs,Federal Funding and Capital Project Fund | 2012-06-30
Hills | Reconstruction of storm sewer bypass line on First Street | First Street, Hills, Ioa | 2965.67 | 3608.45 | 6574.12 | 6574.12 | Fully Completed | Road Use Funds, LOST, Time funds | 2011-06-20
Hillsboro | Repair maintenace building | 100 North Cedar | 657.09 | 799.51 | 700 | 657.09 | Fully Completed |  | 2009-09-30
Hinton | 2nd Ave. design and inspection services | 2nd Ave. from Grand to 1st. Ave. | 3529.1 | 4294 | 20000 | 7823.1 | Fully Completed | Road Use Fund | 2011-06-30
Holland | SEALCOAT AND CHIP THE ENTIRE TOWN, 31,000 SQ. YARDS OF STREET. | HOLLAND, IA | 814.12 | 990.57 | 72884.58 | 814.12 | Fully Completed | $20,000 RUT FUND, $43,000 GENERAL, $13,000 WATER FUND | 2009-09-03
| SEALCOAT/CHIP ENTIRE TOWN, 31,000 SQ YDS | HOLLAND, IA |  |  | 72884.58 | 814.12 | Fully Completed | $20,000 RUT FUND $43,000 GENERAL FUND $13,000 WATER FUND | 2009-09-03
Holstein | Project to be determined | Holstein, IA | 6420.52 | 7812.1 | 0 | 0 | Not Started | IJOBS funds not designated to a specific project yet | 2010-03-31
Holy Cross | leveling and overlay of street | Maple Rd | 942.9 | 1147.27 | 30615 | 942.9 | Fully Completed | $942.90 in I Jobs money | 2009-10-04
| Resurface Main St. Grind off old blacktop, level surface, and apply an additional 2 inches of new blacktop. INstall new curb and gutter and furnish base stone. | 917 Main St. |  |  | 42000 | 1147 | Fully Completed | I JObs -$1147.27 Road Use tax 42057.00 | 2010-10-22
Hopkinton | $3,619.08 is left to spend from IJOBS monies. Monies were spent repairing storm drainage issues on Locust Street. | Locust Street, Hopkinton, Iowa 52237 | 2974.41 | 3619.08 | 16501.87 | 3619.08 | Fully Completed | IJOBS, Road Use Tax, General | 2011-11-30
| Culvert Replacement/Repair | Walnut St SE |  |  | 5000 | 2974.41 | Fully Completed | Road Use Tax Monies | 2010-06-23
Hospers | Street improvements to 4th Avenue S and Cedar Street | Hospers, Iowa | 2935.1 | 3571.25 | 3195 | 2935.1 | Fully Completed | The $259.90 over and above the amount we received from IJOBS came from our Road Use Operation and Maintenance Department. | 2009-10-11
| We hired Sta-Bilt Construction Company to do some micro-resurfacing to 15 blocks of our City streets. | Block between Cedar St. & Elm St. on 4th Avenue S.; Block between Cedar St. & Elm St. on 3rd Avenue S.; Block between Cedar St. & Elm St. on 2nd Avenue S.; Block on Cedar St. between 2nd Avenue S. & 3 |  |  | 66033.9 | 3571.25 | Fully Completed | Our funding source came from the transfer of funds from Money Market accounts, money from our general account and IJOBS funding. | 2010-07-30
Houghton | materials for drainage system for new 4th street construction. | 4th Street | 500.08 | 608.47 | 1108.55 | 0 | Fully Completed | General fund | 2011-07-31
| Repair of manhole covers along hwy 16. (8 total) | 8 different locations along highway 16 in Houghton city limits. |  |  | 290 | 290 | Fully Completed |  | 2009-07-27
Howard County | The Epuipment has been delivered and paid for. | Cresco | 79810.22 | 98114.67 | 681300 | 177924.89 | Fully Completed | Secondary Road Fund | 2011-01-17
Hubbard | Constructed a box culvert to help with water run-off during heavy rains that was causing road erosion | West Elm St. | 3865.42 | 4703.2 | 24000 | 4703.2 | Fully Completed | Road Use Tax $19,297 and I-Job $4,703 | 2010-06-14
| Mill and resurface East Maple Street | East Maple St. from Iowa to State St. |  |  | 97013.03 | 3865.42 | Fully Completed | We used Road Use Tax $ along with I-JOB $ to fund this $130,590 street repair. | 2009-09-28
Hudson | Cedar Street Drainage Repair | Hudson, Iowa | 9246.43 | 11250.49 | 10300 | 9246.43 | Fully Completed | IJOBS $9,246.43 and operational expenses $1,053.57 | 2009-09-29
| In conjunction with IJOBS Disaster Funding, funding from this IJOBS source will be used to cover additional funding costs with this project to mitigate flooding in Hudson through the creation of detention ponds along Cedar Street | Cedar Street, Hudson, Iowa |  |  | 310000 | 11250 | 50% or More Complete | IJOBS funding Disaster Recovery $288,000. City of Hudson $32,000 (Reserves & IJOBS Road Funding) | 2011-08-01
Hull | Repair sunken sewer trench, tear out, repack, and put in new concrete. | West Second from Hayes Avenue, going east approximately 400 feet. | 8560.7 | 10416.14 | 38500 | 8560.7 | 50% or More Complete | General Fund; Sewer Fund | 2009-09-16
| Replace broken up asphalt on Brown Street with new concrete and put in a storm sewer line to drain area. | Brown Street going North from Center Street about 150 feet. |  |  | 23172 | 10416.14 | Fully Completed | Road Use Tax fund General Fund | 2010-08-06
Humboldt | 2010 NE Street Infrastructure Project, repair and maintenace of approximately 4 blocks of existing roadway, curb and gutter, sidewalk, storm sewers, manholes, and water valve boxes. | Humboldt | 19445.01 | 23659.51 | 273611.57 | 43104.52 | Fully Completed | Bond issue funds, I-Jobs | 2010-12-06
Humboldt County | Purchase roadstone for stockpile | Various locations throughout the county | 76004.4 | 90020.42 | 90020.42 | 90020.42 | Fully Completed | Ijobs and local | 2011-06-30
| Purchase roadstone for stockpile | Stockpiles throughout Humboldt County |  |  | 76004.4 | 76004.1 | Fully Completed | Local and I-Jobs | 2011-06-30
Humeston | resurface with oil and chips | Collins Street Summer Street | 2371.66 | 2885.69 | 8700 | 2371.66 | Fully Completed |  | 2009-09-11
Huxley | Single seal coat streets as listed below: | Timberlane from Oak to Hwy 69 Maple Dr: Timberlane to Oak Blvd Crestwood: Lynwood to N 5th Circle Dr: N 2nd to E 1st Shop Road: Oak Blvd to gravel | 12972.08 | 15783.64 | 24750 | 0 | Not Started | IJOBS AND Road Use Tax | 2009-11-01
Ida County | Remve bridge, 110th Street over Ashton Creek, and reconstruct. | 110th Street 0.8 miles west of US #59. | 69345.88 | 84326.43 | 101115.31 | 69345.88 | Fully Completed |  | 2009-09-23
Ida Grove | Asphalt removal and replacement. | The streets are Quimby between 5th and 7th; Warren between 1st and 2nd; 800 Block of Valley View Drive; Moorehead Street between 5th and 7th; and Circle Drive between 5th and 6th; and the alley betwee | 10264.1 | 12488.74 | 74161.37 | 12488.74 | Fully Completed | Road Use | 2011-06-30
| PCC Patching and HMA Overlay | Moorehead Avenue between 1st Street and Hwy 175 Ida Grove, IA |  |  | 262622 | 10264.1 | Fully Completed | Stimulus, I-Jobs, and Road Use Monies | 2009-10-07
Independence | Construct a salt shed hoop building | 1000 12th Street NE Independence, IA | 26477.01 | 32215.63 | 32215.63 | 32215.63 | Fully Completed | RUT & IJOBS | 2010-10-01
| Reconstructed several streets with base stone, double seal coat | 4th Ave Ne from 5th St NE to 10th St NE Lover's Lane from Hwy 150 going west for 160 feet Lover's Lane from previous to west end at 6th Ave SW 11th Ave NE from 10th St to RR tracks 9th St NE from | 26477.01 | 32215.63 | 68601.6 | 26477.01 | Fully Completed | IJOBS and RUT | 2009-09-24
Indianola | General repair and maintenance of city streets (operating and maintenance expenses) | Thoughout the City of Indianola, Iowa | 61877.25 | 75288.48 | 61877.25 | 10656.62 | Fully Completed | I-Jobs | 2010-06-30
| Materials & Supplies for repair and maintenance of city streets-snow and ice removal. | Indianola, Iowa |  |  | 70973 | 81137.14 | Fully Completed | I-Jobs | 2011-03-11
| Purchase of Asphalt from Grimes Asphalt & Paving for paving a portion of the Jerry Kelly Bike Trail in Indianola. | Indianola, Iowa |  |  | 61877.25 | 24182.89 | Fully Completed | I-Jobs | 2010-08-06
| Purchase of concrete for repair/maintenance of city streets | Indianola, Iowa |  |  | 9854.75 | 0 | Fully Completed | I-Jobs | 2010-12-17
| Repair & Maintenance of city streets-$5,778.50 Payroll Expenses-$129,326.91 | Indianola, Iowa |  |  | 135105.41 | 21189.08 | Fully Completed | I-Jobs & RUT | 2011-11-30
| Salary/wages for repair and maintenance of city streets | Indianola, Iowa |  |  | 31353.22 | 0 | Fully Completed | I-Jobs | 2011-05-31
Ionia | Repair Main Street City Sidewalk. | Main Street, Ionia, Iowa | 759.53 | 924.16 | 15000 | 1683.69 | Fully Completed | I-JOBS funds-- general & road use funds | 2010-10-29
Iowa City | 2400 square yards of concrete street pavement removed and replaced and 25 manhole casting removed and replaced. | Street Patching Locations: Governor St. from Jefferson St. to North St. Mormon Trek Blvd. from Dane Rd. to Eagle View Rocky Shore Dr. at Park Rd. Scott Blvd. at culvert and intakes Gilbert St. 75 | 276401.34 | 336308.39 | 245848.6 | 246725.63 | Fully Completed | IJOBS Road Use Tax | 2009-09-30
| Hot mix Asphalt(HMA) Overlay Project | Jefferson Street - Dubuque Street to Dodge Street Musactaive Avenue - Jefferson Street to Court Street Scott Boulevard - Rochester Avenue to Court Street 7th Avenue - Court Street to Muscatine Aven |  |  | 2200100.97 | 365984.1 | Fully Completed | IJOBS DOT Maintenance Funds Road Use Tax Water Utility Wastewater Utility | 2012-03-30
Iowa County | Full Depth Conrete Patching on all Concrete Roads in Iowa County | Iowa County | 107329.33 | 129510.59 | 226756.83 | 45953.12 | Fully Completed | Ijobs/Local | 2011-11-15
| Painting of Centerline Pavement Markings on all Hard Surface Roads in Iowa County | Iowa County |  |  | 40812.92 | 39000 | Fully Completed | Ijobs & Local Funds | 2011-10-14
| Railroad Flatcar Bridge | Located on SS Avenue in Section 31 of Greene Township, T-78N, R-9W, Iowa County, Iowa |  |  | 150000 | 151886.8 | Fully Completed | I-jobs | 2011-06-01
Iowa Falls | 7.5 TON OF 3/8 FINE ROCK........ | IOWA FALLS IOWA | 22681.48 | 27597.45 | 50.25 | 50.25 | Fully Completed | IJOBS | 2010-11-15
| 8FT STAINLESS STEEL SPREADER WITH INSTALL | IOWA FALLS IOWA |  |  | 4340 | 4340 | Fully Completed | IJOBS | 2010-12-20
| 9'6'' WESTERN POLLY V PLOW & DEFLECTOR | IOWA FALLS IOWA |  |  | 5270 | 5270 | Fully Completed | IJOBS | 2010-12-20
| CAP SCREWS/HEX NUTS FOR STREET SIGN | IOWA FALLS, IOWA |  |  | 11.36 | 11.36 | Fully Completed | IJOBS | 2010-08-16
| CONCRETE FOR CURB BY MAIN STREET | IOWA FALLS IOWA |  |  | 96 | 96 | Fully Completed | IJOBS | 2010-09-20
| Door openers, remotes, and weatherstipping in overhead doors | Iowa Falls, IA |  |  | 1760 | 3520 | Fully Completed | IJOBS Funds | 2010-06-21
| Dropped Tree at 922 Oak........... | Iowa Falls, IA |  |  | 100 | 100 | Fully Completed | IJOBS Road Funding | 2010-05-17
| FINE FILL ON MAIN........................ | IOWA FALLS IOWA |  |  | 48.58 | 48.58 | Fully Completed | IJOBS | 2010-08-16
| HEX NUTS & SCREWS FOR SIGNAGE | IOWA FALLS IOWA |  |  | 11.36 | 11.36 | Fully Completed | IJOBS | 2010-09-20
| MAINT SUPPLIES.............. | IOWA FALLS IOWA |  |  | 14.02 | 14.02 | Fully Completed | IJOBS | 2010-09-20
| New Tractor and mower for mowing and grading | Iowa Falls, Iowa |  |  | 80000 | 37633.34 | Fully Completed | IJOBS Road Funding and Road Use Tax | 2011-09-30
| Removal of trees in ROW................................. | Iowa Falls, IA |  |  | 1500 | 3000 | Fully Completed | IJobs Road Funding | 2011-06-20
| Remove trees..................................... | Iowa Falls, IA |  |  | 1820 | 1820 | Fully Completed | IJOBS Funding | 2010-06-21
| Removed tree on Rainbow Bridge | Iowa Falls, IA |  |  | 500 | 500 | Fully Completed | IJOBS Road Funding | 2010-05-17
| Road Stone for alleys..................... | Iowa Falls, IA |  |  | 81.11 | 81.11 | Fully Completed | IJOBS Road Funding | 2010-03-15
| road stone for maintaining alleys | Iowa Falls, Iowa |  |  | 327.01 | 327.01 | Fully Completed | IJOBS Road Funding | 2009-12-31
| ROAD STONE FOR SHOULDER WORK | IOWA FALLS, IOWA |  |  | 423.02 | 423.02 | Fully Completed | IJOBS | 2010-08-16
| ROAD STONE...................... | IOWA FALLS IOWA |  |  | 350.44 | 350.44 | Fully Completed | IJOBS | 2010-10-18
| ROAD STONE.......................... | IOWA FALLS IOWA |  |  | 545 | 545 | Fully Completed | IJOBS | 2010-09-20
| Road Stone............................................. | Iowa Falls, IA |  |  | 226.58 | 226.58 | Fully Completed | IJOBS Road Funding | 2010-05-17
| Road Stone............................................... | Iowa Falls, IA |  |  | 393.99 | 787.98 | Fully Completed | IJobs Road Funds | 2011-04-18
| Road stone/rock for alleys and shoulders | Iowa Falls, IA |  |  | 962.06 | 962.06 | Fully Completed | IJOBS Funds | 2010-06-21
| Rock for alleys | Iowa Falls, IA |  |  | 434.13 | 868.26 | Fully Completed | IJobs Road Funds | 2011-04-18
| SCREWS/WASHERS/PLYWOOD/GRINDING WHEELS | IOWA FALLS, IOWA |  |  | 118.83 | 237.66 | Fully Completed | IJOBS | 2011-03-21
| SIGNAGE AND HDW................... | IOWA FALLS IOWA |  |  | 3819.9 | 3819.9 | Fully Completed | IJOBS | 2010-10-18
| Signage for streets..................................... | Iowa Falls, Iowa |  |  | 536.47 | 1072.94 | Fully Completed | IJOBS Road Funding | 2011-07-18
| SIGNS AND POSTS................................... | IOWA FALLS, IA |  |  | 2799.9 | 2799.9 | Fully Completed | IJOBS | 2010-07-19
| Signs for streets................................................................................................................. | Iowa Falls, Iowa |  |  | 2356.95 | 2356.95 | Fully Completed | IJOBS road funds | 2010-02-16
| Signs from Iowa Prison Industries | Iowa Falls, Iowa |  |  | 1806.3 | 3612.6 | Fully Completed | IJOBS | 2011-01-31
| Steel for brackets....................................... | Iowa Falls, IA |  |  | 106.2 | 106.2 | Fully Completed | IJOBS Road Funding | 2010-05-17
| STEEL FOR SIGN MOUNTS................ | IOWA FALLS, IA |  |  | 37.6 | 37.6 | Fully Completed | IJOBS | 2010-12-20
| STEEL PLATE...................... | IOWA FALLS IOWA |  |  | 37.6 | 37.6 | Fully Completed | IJOBS | 2010-12-20
| STEEL PLATES & PIPES...................... | IOWA FALLS IOWA |  |  | 36 | 36 | Fully Completed | IJOBS | 2010-08-16
| STEEL PLATING & TUBING FOR SIGNS | IOWA FALLS IOWA |  |  | 87.2 | 87.2 | Fully Completed | IJOBS | 2010-09-20
| TREE REMOVAL FROM STORM DAMAGE | IOWA FALLS, IA |  |  | 100 | 100 | Fully Completed | IJOBS | 2010-07-19
| Tree Removal in ROW AT JULIE ONEAL | Iowa Falls, IA |  |  | 245 | 245 | Fully Completed | IJOBS Road Funding | 2010-04-20
| Tubing for Leaf Box extention | Iowa Falls, Iowa |  |  | 49.4 | 98.8 | Fully Completed | IJOBS | 2011-02-21
| USED John Deere push mower for Streets Dept | Iowa Falls, IA |  |  | 60 | 60 | Fully Completed | IJOBS Road Funding | 2010-05-17
Ireton | 2010 Seal coating on selected streets | Selected streets thruout City limits | 2555.11 | 3108.9 | 3108.9 | 3108.9 | Fully Completed | I-Jobs / Road Use Tax | 2010-07-13
| Seal Coating Street. Approximately 23476 sq. yards | Streets thruout the City |  |  | 27466.92 | 2555.11 | Fully Completed |  | 2009-07-27
Irwin | PURCHASED COLD PATCH AND ROCK FOR STREET MAINTENANCE AS NEEDED. STA-BILT CONSTRUCTION - 7/01/10-COLD PATCH- $296.94 MURRAY TRUCKING - 8/31/10- ROCK - $531.30 STA-BILT CONSTRUCTION -10/06/10-COLD PATCH- $233.24 STA- | CITY OF IRWIN - VARIOUS LOCATIONS | 1022.05 | 1243.56 | 1499.04 | 1243.56 | Fully Completed | I-JOBS | 2010-10-06
| THE PROJECT OF CLEANING AND FILLING CRACKS AS NEEDED WITHIN THE CITY LIMITS OF IRWIN HAS BEEN COMPLETED. | VARIOUS STREETS WITHIN THE CITY OF IRWIN |  |  | 5873.4 | 1022.05 | Fully Completed | I-JOBS FUNDS 1022.05 INTEREST FROM CD 4.04 CITY ROAD USE FUNDS 4847.31 TOTAL $5873.40 | 2010-05-06
Jackson County | Ion Bridge Road Approximately 3 miles east of hwy 62. Three areas to be patched #1 is 26'x1035' #2 is 26'x850' #3 is 26'x1000' Contractor is 4" of HMA and replace pavement markings | iron Bridge Road 3 miles east of hwy 62 | 111074.84 | 133665.19 | 102049.85 | 0 | Fully Completed | I-Jobs and Local | 2009-11-15
| patch 26'x1000' area with 4" HMA replace striping and 2' rock shoulder edge | Jackson County near intersection of bernard Road and S. Garryowen Road |  |  | 33879.5 | 0 | Fully Completed | I-jobs and local | 2009-11-15
| PCC Paving 17th St. from E. Preston City Limits to 450th Ave. | 17th St. from E. Preston City Limits to 450th Ave. |  |  | 364850.14 | 108810.68 | Fully Completed | I-Jobs | 2010-09-30
Jackson Junction | deliver and spread 60.9 tons of road rock | 330TH AVENUE | 252.26 | 306.94 | 252.26 | 252.26 | Fully Completed | I-JOBS AND ROAD USE TAX | 2009-08-03
Janesville | Remove Damaged/Dead Trees in Street Right-of-Way | Within City Limits | 3620.83 | 4405.6 | 6632.43 | 800 | Less than 50% Complete | I-JOBS | 2012-06-29
| To be determined | To be determined |  |  | 1394 | 1394 | Fully Completed | I-JOBS Funds | 2009-10-01
Jasper County | Placing granular surfacing on various roads through out the county with county employees. Material will be purchsed from the quarry. | Jasper County Rural Roads | 149817.39 | 179033.58 | 250000 | 149500 | Fully Completed | Local Funding | 2011-06-30
| Resurfacing on granular roads | Through out Jasper County |  |  | 400000 | 179350.97 | Fully Completed | Local | 2011-09-30
Jefferson | Repair the bridge approach and the back wall on the bridge. The road is a major arterial for the city and county. | Bridge on Grimmell Road within the city of Jefferson | 20204.99 | 24584.21 | 110000 | 44789.2 | Fully Completed | I-Jobs, Local Option Sales Tax | 2011-07-29
Jefferson County | Applied GSB Sealer Binder 83,893 SY | Glasgow Rd- E Madison St(Fairfield) to Stockport Rd | 79055.95 | 95538.31 | 85743 | 79055.95 | Fully Completed | jefferson co local construction funds | 2009-09-09
Jesup | Replace 1800 lin ft water main and sanitary sewer along with Tenth Street full width street removal and replacement. 13" of crushed stone base and excess coreout excavation. | Tenth Street from Ainsworth Street to Duroe Street, along Duroe Street from Tenth Street, one block east and along Prospect Street from Tenth Street East one block. | 9661.36 | 11755.35 | 314363.89 | 11755.35 | 50% or More Complete | Community Development Funds, Road Use Tax Funds, Water and Sewer Revenues and I-Jobs Grant | 2010-10-30
| SEAL COAT, 3/8" AND 1/2" SEAL, ON NEW ROAD TO INDUSTRIAL PARK | STARTING AT NORTH END OF 12TH STREET ENDING AT EAST END OF STEVENS STREET |  |  | 9661.36 | 9661.36 | Fully Completed |  | 2009-08-06
Jewell | The State of Iowa is resurfacing Highway 175 that goes through parts of the City of Jewell. | This project starts at the south City limits to Highway 175 east. | 5411.58 | 6584.49 | 92256.24 | 11996.07 | Fully Completed | I Jobs money along with Road Use money | 2010-01-29
Johnson County | Gravel on eligible county roads | throughout Johnson County | 158011.88 | 192238.26 | 615000 | 350250.14 | Fully Completed | RUTF and I-jobs | 2011-05-04
Johnston | Continued shoulder erosion on NW 70th. This project was to asphalt the shoulders. This was added to the scope of another project which was not funded with I-JOBS funds. | NW 70th Avenue, Johnston | 59383.29 | 72253.98 | 125000 | 93782.85 | Fully Completed | I-JOBS Funds | 2010-12-01
| New concrete street build as per Statewide Urban Design and Specficiation | Extension of NW 48th Street from just north of NW 64th Avenue to just south of NW 65th Avenue (approximately 400) |  |  | 274900 | 37854.42 | Fully Completed | In addition to I-Jobs funding, we will be using General Obligation Debt money | 2010-10-29
Joice | 3/4" road stone 32 tons and rental of tractor and blade to spread the gravel | between Main Street and Lake Street approach to the grain elevator | 562.18 | 684.03 | 438.02 | 438.02 | Fully Completed | I-Jobs money | 2009-09-10
Jolley | Hot Mix in holes | various streets in City of Jolley | 177.42 | 215.87 | 177.42 | 177.42 | Fully Completed |  | 2009-09-29
| Snow Removal in Jolley, Iowa | Jolley, Iowa |  |  | 215.87 | 96 | Fully Completed | IJOB | 2011-03-31
| Snow Removal in the City of Jolley | City of Jolley, Iowa |  |  | 23.87 | 23.87 | Fully Completed | I-JOBS and RUT | 2012-03-31
Jones County | Project consists of 1.4 miles of HMA resurfacing and associated work on Hardscrabble Road. The work starts at intersection of 11th Street and Hardscrabble Road in the NW Corporation limits of the City of Monticello in Section 16, T86N, R3W and continues | Hardscrabble Rd | 102243.07 | 122856.81 | 647955.88 | 225099.88 | Fully Completed | Secondary Road Fund | 2011-10-30
Kalona | UPON DETERMINING THE PROJECT TO BE COMPLETED AN ACCURATE DESCRIPTION WILL BE GIVEN ON SAME | TO BE DETERMINED | 10015.14 | 12185.82 | 0 | 0 | Not Started | TO BE DETERMINED | 2009-12-31
Kamrar | Add rock to current road in city | Hill Street City of Kamrar | 529.36 | 644.1 | 529.36 | 529.36 | Fully Completed |  | 2009-08-30
| Repair of Tractor for road maintenance | Within City of Kamrar to be Determined |  |  | 0 | 0 | Not Started | IJOBS | 2011-06-30
Kanawha | 6 manholes rebuilds and frames, covers and concrete | W 4th & Elm, Main & 7th, W 2nd & Elm, W 4th & Elm, E 6th & Main, E 3rd & Linden | 3227.73 | 3927.31 | 4700 | 7079.63 | Fully Completed | iJobs | 2011-04-20
| No new projects identified at this time. | kanawha |  |  | 0 | 0 | Not Started | ijobs | 2010-12-22
| Street Repair at 6th & Main, Sidewalk Repair on 5th St, Cut-Knock Out-Form-Place & Finish Concrete-Crack Control Cut-Back Fill with Black Dirt | 6th and Main, Kanawha |  |  | 2463.2 | 2463.2 | Fully Completed | IJOBS | 2010-08-28
Kellerton | tore old seal coat up and reworked road and graveled. four blocks on east 1st avenue. | east 1st ave | 1166 | 1418.71 | 2647.94 | 2584.71 | Fully Completed | IJOBS and road use tax | 2010-09-17
Kelley | Replace sidewalk on Grace Street running north and south of on the city property | City of Kelley | 849.35 | 1033.45 | 0 | 0 | Not Started | I-Jobs | 2010-06-30
Kensett | Re-surface roads from sealcoat to asphalt. Planning on doing the whole town, a few blocks at a time. | Between 7th & 8th and 3rd & 4th on Walnut, between Elm & Walnut on 4th, between Walnut & Elm on 2nd and 1st, between Hwy 65 and Elm on 6th and 7th, between 6th & 7th on Ash, NW radious at Ash & 8th, b | 1002.87 | 1220.23 | 20697 | 2223.1 | Fully Completed | Road Use Tax | 2010-08-25
Keokuk | Asphalt to repair Park Lane due to wet weather damage | Park Lane, Keokuk, Iowa | 49909.74 | 60727.15 | 820 | 0 | Fully Completed | IJOBS | 2010-08-24
| Pavement removal and replacement | Washington Street and Messenger Road, Keokuk,Ia |  |  | 60096.44 | 60096.44 | Fully Completed | IJOBS and LOST funds | 2010-10-29
| Pavement removal and replacement at Carbide Lane | Carbide Lane, Keokuk, Iowa |  |  | 69411.68 | 49909.74 | Fully Completed | Local Option Infrastructure Sales Tax (LOST) | 2009-10-05
Keokuk County | Purchase of new motor grader for road maintenance activities | Hedrick route, Keokuk County, IA | 90702.52 | 109867.95 | 137430 | 109867.95 | Fully Completed | I-jobs, road use tax | 2010-12-31
| Purchase of new motor grader for road maintenance activities | Richland route, Keokuk County, Iowa |  |  | 163000 | 90702.52 | Fully Completed | I-Jobs, Road Use Tax | 2010-01-31
Keomah Village | Asphalt resurfacing for Keomah Village | Keomah Village excluding North Dr. | 423.67 | 515.49 | 22841.58 | 423.67 | Fully Completed | IJOBS and road use tax | 2010-08-08
| Winter maintenance of City streets | Keomah Village |  |  | 2115 | 515.49 | Fully Completed | I-Jobs and road use tax | 2010-12-31
Keosauqua | Seal coat streets located at 5th, Louis, Market, Harrison, Des Moines, Timber Ridge and Front Streets | 5th, Louis, Market, Harrison, Des Moines, Timber Ridge and Front Streets. | 4655.97 | 5665.1 | 24977.9 | 4655.97 | Fully Completed | Road Use Tax | 2009-07-07
| Seal coat streets located at 6th, 7th, Division and Dodge Streets. | 6th, 7th, Division and Dodge Streets |  |  | 35112.75 | 5665.1 | Fully Completed | Road Use Tax | 2010-09-17
Keota | Asphalt resurfacing - Type B Seal Coat Work Patch Mix Delivered & Placed | Washington St. - Hoover to Davis North Jefferson St. - Keokuuk - South Cemetery Road - Gate-North; Shed-West;Shed-North (Loop); Davis-West South Fulton St. - Park Avenue - South Park Avenue - Keok | 4476.9 | 5447.21 | 29719.6 | 4476.9 | Fully Completed | Road Use Tax | 2009-05-20
| Replacing the water main on all of Davis Street and part of Centennial Avenue. | Keota, Iowa |  |  | 385315 | 0 | 50% or More Complete | SRF Loan and I-Jobs | 2011-10-31
| Type B Seal Coat Work Patch Mix Delivered and Placed | Iowa Street- sewer reapair, Corp. Line north Green Street- Park Ave south Hamilton Street- Lafeyette to Rock Island South Fulton Street- Centennial Street north, Broadway south (westside), Keokuk s |  |  | 31284.8 | 0 | Fully Completed | IJobs Road Use Tax Fund | 2010-05-17
| Type B Seal Coat Work Patch Mix Delivered and Placed | Iowa Street-sewer repair, Corp. Line noth Green Street-Park Ave South Hamilton Street-Lafayette to Rock Island South Fulton Street-Cenntenial Street North Broadway south (westside), Keokuk s |  |  | 31284.8 | 5447.21 | Fully Completed | I-Jobs Road Use Tax Funds | 2012-03-27
Keswick | fixed cement patches on various roads Concerte cement Road Patch | All over city | 888.3 | 1080.82 | 9408.05 | 291.75 | Fully Completed | Roads/IJOBS | 2009-07-20
| Fixed concerte slabs in city roads | All of city |  |  | 10168 | 1080.82 | Fully Completed | Roads/IJOBS | 2010-09-20
| Multi County Oil:Gravel for various alley ways | Various Alley ways |  |  | 320.55 | 320.55 | Fully Completed | I-Jobs money | 2009-07-15
| Ogden Oil:Dust Control for gravel road | 140th street |  |  | 276 | 276 | Fully Completed | I-Jobs money | 2009-08-03
Kimballton | 1500 watt mh fixtures for the ball park | Kimballton ball park | 1352.83 | 1646.05 | 0 | 0 | Fully Completed | I-Jobs | 2009-11-03
Kingsley | Cement driveway and parking for new city maintenance building. | 319 East 1st St. Kingsley, IA | 5437.79 | 6616.37 | 3937 | 3937 | Fully Completed | I-Jobs and building loan. Used $3,937.79 I-Jobs $3,562.21 building loan | 2010-05-10
| Milling and patching was done in the following locations. | Sections of Barre Street, Third Street and west of school. |  |  | 1500 | 1500 | Fully Completed | I-Jobs $1,500.00 | 2009-12-01
| Reconstructed a portion of a street. | Brookside Drive. |  |  | 7083 | 2209 | Fully Completed | 2,209.37 - I Jobs 4,873.63 - Road Use | 2012-06-08
| Repair of Brandon Street where a section of the street was sinking. Cut out section, repaired and poured new concrete. This should have been reported in the 4th quarter 2011. | Intersection of Brandon Street and Third Street. |  |  | 4407 | 4407 | Fully Completed | I-Jobs $4,407.00 | 2011-11-15
| To be determined at a later date. | To be determined at a later date. |  |  | 0 | 0 | Not Started | I-Jobs | 2009-10-06
| We do not have a planned expense for the $6,16.37 that was received in August 2010. | Kingsley |  |  | 0 | 0 | Not Started | We will be using the I-Jobs money plus city money to complete the project when we plan it. | 2011-09-09
Kiron | repair culverts to correct drainage and grade and re-surface streets and alleys. Work will be done when weather permits. No gravel will be put on this fall. Snow removal will destroy any new rock placed at this time/ | all strret and alleys within the city limits | 973.29 | 1184.24 | 1184.24 | 1184.24 | Fully Completed | RUT | 2011-05-30
Klemme | resurfacing/overlayment of 11 blocks of streets in Klemme, IA | Klemme IA | 2590.05 | 3151.41 | 46706 | 5741 | Fully Completed | IJobs Money of $5,741.00. Balance of $40,965 was taken from General Street Budget. | 2010-08-12
Knierim | add rock in alley between 1st ave west and centre | between 1st ave west and centre ave | 154.88 | 188.45 | 155 | 155 | Fully Completed | I-JOBS | 2009-08-30
| rock | north end between ist ave west and centre |  |  | 188 | 188 | Fully Completed | I-JOBS | 2010-07-16
Knoxville | resurfacing project in various areas of the city | various city locations | 33766.71 | 41085.29 | 83882.1 | 23443.9 | Fully Completed | I-JOBS | 2010-08-30
| Resurfacing project in various areas of the City | Various City locations |  |  | 0 | 0 | Not Started | I-JOBS | 2009-12-31
| Resurfacing project in various areas of the City | Various City locations |  |  | 75000 | 0 | Not Started | I-JOBS | 2009-12-31
Kossuth County | Maintenance Seal Coat (chip seal) of various hot mix asphalt surfaced roads in Kossuth County. | MSC-1-10 - P-20 from Humboldt/Kossuth County line north 11 miles to B-40. MSC-2-10 - B-60 from Highway #15 east 3 miles to P-20. MSC-3-10 - B-30 from Highway #15 east 9.5 miles to Highway #169. MSC | 168590.58 | 207849.15 | 302860 | 207849.15 | Fully Completed | Local Funding | 2010-09-10
| Maitenance Seal Coat (chip seal) of various hot mix asphalt surfaced roads in Kossuth County. | MSC-1-09 - On P66 from A42 north 7 miles to IA 9. MSC-2-09 - On A42 from P64 east 4 miles to the east county line. MSC-3-09 - On A21 from P30 east 7 miles to P50. |  |  | 240017.06 | 168590.58 | Fully Completed | Local Funding | 2009-09-03
La Porte City | Street Overlay of Cedar Street from Third St to railroad tracks, including concrete intersection at Fourth St | Cedar St from Third St to railroad tracks | 10137.44 | 12334.62 | 162905 | 22425 | 50% or More Complete | Road Use Tax Fund | 2010-09-30
Lacona | Snow removal for City streets | City streets in Lacona | 1293.68 | 1574.07 | 1293.68 | 1293.68 | Fully Completed | I jobs money and Road Use Tax money | 2010-02-26
Ladora | Seal coat | Fire Station Alley, Short St, High St, East St | 1007.94 | 1226.4 | 14035.95 | 2234.34 | Fully Completed | Ijobs Money & Road Use Tax | 2010-07-15
Lake City | Seal coating and patching | Various Locations in Lake City, Iowa | 7979.79 | 9709.33 | 60000 | 17689.12 | Fully Completed | Road Use Tax | 2011-08-31
Lake Mills | 2010 Street Maintenance - Patching and Seal Coating | Streets in the City Limits - S 12th Ave W,, Washington Court, South Lake Street, North Western Street, South Lincoln Street | 9346.88 | 11372.72 | 36922.58 | 20719.6 | Fully Completed | I Jobs and Road Use Tax | 2010-10-12
Lake Park | Asphalt strengthening and leveling; and oil & chip single seal on various streets. Approximately 16 hours for project. | Lake Avenue-3 blocks; South 3rd St-1 block; Chestnut Ave-1 block; South 2nd St-1 block; and 8'X60' asphalt on Market Street on railroad tracks that were removed. | 4468.16 | 5436.59 | 34671.8 | 5436.59 | Fully Completed | General fund and I-Jobs funding. | 2010-07-23
| Sealcoat and patchwork on various streets listed below. | North Market St from Ave B thru Ave F; Railroad Ave from Market St to East 1st Street; West 2nd St from Ave A to Railroad Ave; and Ave B from West 2nd St to West 3rd St. |  |  | 15785.28 | 4468.16 | Fully Completed | General Fund | 2009-12-31
Lake View | Planed asphalt overlay and curb & gutter repair project for 2010 | 2nd Street & 4th Street | 5752.26 | 6999.01 | 130000 | 0 | Not Started | Road Use Tax & additional I-JOBS funding | 2010-08-31
Lakeside | repair and replace storm sewers | Daphne St.,Cedar St., and Birch St. | 2113.97 | 2572.15 | 6262.5 | 2113.97 | Fully Completed | federal ijobs and rut fund | 2010-05-07
| routing, cleaning of all random cracks followed by furnishing and installation of a rubber sealant (2200 pounds ) | all streets in City (approximately 40 city blocks) |  | 2572.15 | 7980 | 2572.15 | Fully Completed | Ijobs and road use tax. | 2011-05-10
Lakota | Fill and patch holes in streets | Brewer Street between 1st Avenue and P-60 Clark Street between 1st Avenue and P-60 Graham Street between 4th Avenue and P-60 | 861.53 | 1048.26 | 861.53 | 861.53 | Fully Completed |  | 2009-08-11
| Repair and patch holes in streets | Brewer Street, Clark Street and 3rd Street |  |  | 1048.26 | 1048.26 | Fully Completed | I-Jobs monies | 2010-09-28
Lambs Grove | Purchase of new grates for storm sewers. | City streets | 872.17 | 1061.21 | 7500 | 0 | Not Started | I-Jobs | 2012-03-31
Lamoni | Sidewalk Repair at Street Dept. Shop/Police Station | S. Linden | 10674.67 | 12988.29 | 26336.75 | 23662.96 | Fully Completed | Road Use Tax | 2011-05-09
Lamont | install french drain, culvert and 600' drainage tile to eleviate standing water issues | 225 Concord Street to 405 Concord Street | 2196.95 | 2673.12 | 2168.42 | 858.67 | Fully Completed | 858.67 IJOBS street funds 1309.75 General fund | 2011-06-20
| remove and replace 3 inches hot mix | 624-628 Bush Street; 610 Pine Street |  |  | 5172.9 | 4011.4 | Fully Completed | IJOBS Funds; Public Works (General)Fund | 2010-06-30
Lansing | Line approximately 530' of 24" storm sewer | 300 Block of Main Street | 4420.11 | 5378.13 | 48760 | 4420.11 | Fully Completed | Local Option Sales tax & I-Jobs funds | 2009-10-30
Larchwood | Dug up caved in street, found water leak and fixed, filled with red rock and concrete | Intersection of Blaine and Holder Streets | 3441.75 | 4187.71 | 2905.94 | 2905.94 | Fully Completed | I-Jobs | 2011-06-06
| Installation of sewer line required red rock for the street. | Railroad Street |  |  | 600 | 210.8 | Fully Completed | I-Jobs | 2012-01-13
| Installed new sewer line on Railroad and Broadway. Needed Concrete replacement at the lumberyard and gravel on Williams Street intersection with Railroad Street. | Railroad & Broadway |  |  | 0 | 0 | Not Started | I-jobs | 2011-12-01
| Not sure yet | Larchwood City Street |  |  | 0 | 0 | Not Started | none | 2009-12-10
| Repair of alligatored roadway caused by tractors and semi's using the road to access the elevator | Broadway Street |  |  | 3683.1 | 7217 | Fully Completed | I-Jobs | 2010-11-03
| Will discuss at October Council Meeting | Larchwood City Streets |  |  | 0 | 0 | Not Started | None | 2009-12-30
Larrabee | Fix sinkhole in Larrabee, Iowa | Main Street | 611.82 | 744.42 | 811 | 744.42 | Fully Completed | I-JOBS | 2010-09-30
| Resurface and widen appoach into town off Hwy. 59 | Hwy. 59 & Depot St. |  | 744.42 | 14260 | 611.82 | Fully Completed | We used the I-Job money for this as well as other money from the road use tax account. | 2009-09-17
Latimer | Street repairs in Latimer | Various streets in Latimer | 2336.72 | 2843.18 | 9132 | 2843.18 | Fully Completed | I-Jobs Road Funding and Local Option Sales Tax Street Improvement Funding | 2010-08-26
| Street Repairs in Latimer | various streets |  |  | 6000 | 2336.72 | Fully Completed | rOAD uSE fUND | 2010-05-31
Laurel | Tools and storage system for Street Dept. | Laurel, Iowa | 930.37 | 1132.02 | 1309.81 | 1132.02 | Fully Completed | Road Use Tax Fund, General Fund | 2010-11-30
| TREE REMOVAL ON RIGHT OF WAY | NE CORNER OF MAIN ST AND WEISSENBURGER. (1-TREE) NW CORNER OF WEISSENBURGER AND 1ST AVE. (2-TREES) |  |  | 1600 | 930.37 | Fully Completed | I-Jobs Fund Road Use Tax Fund | 2009-10-29
Laurens | Repaired CAT road grader - | City of Laurens | 6446.73 | 7843.99 | 24971.33 | 6446.73 | Fully Completed | IJOBS, reserve funding | 2009-07-31
Lawler | remove concrete and pipe, replace culvert, apron ties, reshape ditches and fill, tie all joints together | South Center Street | 1704.65 | 2074.12 | 1704.65 | 1704.65 | Fully Completed | I-JOBs and Road Use Tax | 2009-10-22
Lawton | Clean, tack and mill oak Street, lay hot mix asphalt 2" thick | 300 block, Oak Street | 3044.29 | 3704.11 | 29050.05 | 3704.11 | Fully Completed | I-JOBS, RUT | 2010-12-31
| Street overlay project covering approximately 4,500 sf with 2" hot mix asphalt | Cedar Street & Maple Street intersection |  |  | 3987.5 | 3044.29 | Fully Completed |  | 2009-08-20
Le Claire | Purchase of street maintenance materials; i.e., deicing salt | City-wide | 12526.57 | 15241.57 | 75000 | 12526.57 | Fully Completed |  | 2009-09-30
Le Grand | HMA Leveling and 5" HMA Full Depth Patching on City Streets | Various City Streets | 3856.68 | 4692.58 | 2107.87 | 2107.87 | Fully Completed | Stimulus $ | 2009-11-02
Le Mars | 3rd Ave SE Whitetopping - 4" PCC Whitetopping & Driveway/Sidewalk replacements | 3rd Ave SE from 2nd Street to 5th Street South | 40344.47 | 49088.71 | 112046.24 | 89433.18 | Fully Completed | I-Jobs & Road Use Tax Fund | 2010-07-08
| To Be Determined At a Later Date | To Be Determined |  |  | 0 | 0 | Not Started | RUT, I-JOBS | 2010-06-30
Le Roy | Fill potholes in city street | 6th Avenue between 4th and 5th Streets | 21.19 | 25.78 | 300 | 0 | Less than 50% Complete | I-Jobs money and city street fund | 2010-10-29
Ledyard | Crack seal streets North Division Street, Blake between Division and Logan, Arther between Division and Logan, Division between Arther and Richland. Cost 4175.00 to | North Division Street, Blake between Division and Logan, Arther between Division and Logan, Division between Arther and Richland. | 494.76 | 601.99 | 4175 | 494.76 | Fully Completed | Road Use Fund | 2009-10-07
Lee County | Materials used for maintaining seal coat roads. | Multiple roads throughout Lee County. | 105562.34 | 128268.11 | 216300.15 | 128268.11 | Fully Completed | I-Jobs | 2010-10-19
| Resurfacing and patching seal coated roads | Various roads throughout Lee County |  |  | 193479.27 | 105562.34 | Fully Completed |  | 2009-09-10
Lehigh | 1" Roadstone & work on Alley behind East Main | Clayworks Drive, East Main Street & other Streets that need Rock. | 1812.33 | 2205.14 | 4000 | 211.36 | Less than 50% Complete | Road Use Tax Fund | 2011-10-31
Leland | 1" asphalt overlay - 145x26x419; 1" asphalt overlay - 525x21x1225; asphalt leveler; Mill header joint N. end - 56x3x19; Mill header joint S End - 20x3x7; 3" asphalt patch - 30x2x7 - 1 ton; $220.00 | S Walnut St, Broadway, W 5th Avenue | 895.48 | 1089.56 | 220 | 0 | Fully Completed | Road use funds | 2009-11-13
| 3" asphalt mat - 12 ton; Sawcut and remove pavement - 71 S.Y.; Install 6" rock base; $2101.75 | City Hall parking area on South Walnut Street |  |  | 2101.75 | 15.48 | Fully Completed | Road use funds | 2009-11-13
| 3" asphalt patching - 3 x 3 x 1 - 1 ton - $220.00 | East side of intersection of 4th Avenue and Hwy 69 |  |  | 220 | 220 | Fully Completed | Road use funds | 2009-11-13
| 4" asphalt patching - 36 x 5 x 20 - 5 ton - $1100.00 | 4th Ave & "D" St patch |  |  | 1100 | 0 | Fully Completed | Road use funds | 2009-11-13
| 4" asphalt patching, 10 X 10 X 11, 2 TON - water valve repair patch - $440.00 | NE corner of intersection of C Street and Broadway Avenue, Leland, Iowa |  |  | 440 | 0 | Fully Completed | Water account | 2009-11-13
| Patch on North side of drive to garage on East side of street, 4" asphalt patching - 25 x 5 x 14 - 3 ton - $660.00 | East D Street, Leland, Iowa |  |  | 660 | 660 | Fully Completed | Road use funds | 2009-11-13
| Rout, Clean and Fill cracks 1/4" or wider, with a Craftco hot pour rubberized crackfiller | River Road, E. Broadway, North "A" St, W. Broadway and 2nd Ave W. |  |  | 5332.8 | 0 | Not Started | IJobs and RUT | 2011-06-30
| To be determined by city council | Leland, Iowa |  |  | 0 | 0 | Not Started | IJOBS funds | 2011-06-30
| To be determined by city council | City of Leland, Iowa |  |  | 0 | 0 | Not Started | The project has not yet started and no I-JOBS have been expended. | 2011-06-20
Lenox | Repairs to streets including pot holes and overlay project. | To be determined | 6119.15 | 7445.41 | 184000 | 13564.56 | Fully Completed | City revenue road use tax and I-jobs money. | 2010-06-30
Leon | Hot mix asphalt resurfacing on a portion of Little River Lake Road. | Little River Lake Road, Leon, Iowa 50144 | 8661.16 | 10538.37 | 7000 | 7000 | Fully Completed | I-Jobs Funding $7,000.00 | 2009-08-27
| Repairing and replacing the Concrete Paving on Q Street and Highway 2. | Q Street and Highway 2 in Leon, Iowa 50144. |  |  | 3458.29 | 1661 | Fully Completed | I-JOBS Road Funding in the amount of $1,661.00 and City Transportation Funds in the amount of $1,797.29. Total project cost of $3,458.29. | 2009-09-19
| Street Grinding and Laying of New Ashalt. | NW 4th Street between NW Church Street and N Main Street in Leon, Iowa 50144. |  |  | 19933.13 | 10538.53 | Fully Completed | I-Jobs Funding $10,538.53 and Street Improvement LOST $9,394.60. | 2010-10-29
Lester | Repair and improve box culvert entry. | Corner of Main St and Hastings St. | 843.46 | 1026.28 | 1280 | 843.46 | Fully Completed | IJOBS funds of $843.46 and road use money in account of $420.97. | 2009-10-21
| Shoulder work on Clinton St and Hastings | Hastings and Clinton Streets |  | 1026.28 | 1215 | 1026.28 | Fully Completed | IJOBS money of $1,026.28 and balance of money from General Fund. Project completed October 2011 by Paul Metzger COnst. Paid $1,026.28 fro IJOBS and $188.72 from RUT a/c. | 2011-08-31
Letts | We used the $1381.22 for cleaning ditches | all though out the city | 1381.22 | 1680.59 | 1381.22 | 1381.22 | 50% or More Complete | I-jobs funds 1381.22 | 2009-08-31
Lewis | Asphalt Patching of City Streets in Lewis, Iowa | Six separate locations in Lewis, Iowa | 1707.81 | 2077.96 | 2125 | 1213.43 | Fully Completed | I-Jobs Revenue and Road Use Revenue | 2011-06-08
| Concrete Saw and saw blade | Lewis, Iowa |  |  | 1102.62 | 1102.62 | Fully Completed | I-Jobs revenue | 2011-12-31
| Street Grindings on miscellaneous streets | Webster, Market, Clark, and Fifth Streets |  |  | 2000 | 1469.72 | Fully Completed | I-JOBS Funding | 2010-04-30
Libertyville | Graveling of alleys within the City | Within the City limits | 759.18 | 923.72 | 2077.03 | 759.18 | Fully Completed |  | 2009-08-11
Lidderdale | Continuing to put rock in alleys and rocked roads as needed | 4th Street and alleys | 437.93 | 532.85 | 660 | 0 | Fully Completed | street funds of 659.73 all ijob funds have been used completely | 2011-08-31
| PURCHASE OF ROCK FOR FILLING OF HOLES IN STREETS AND ALLEYS UNTIL WE DECIDE WHAT TO DO WITH WATERMAIN IMPROVEMENTS AND HAVING TO TEAR UP THE STREETS SO JUST TEMPORARY DOING REPAIRS | STREETS IN THE CITY OF LIDDERDALE |  |  | 2100 | 437.93 | Fully Completed | USED 437.93 IN I JOBS FUNDING AND 258.04 FROM THE STREET FUNDS | 2010-08-30
| Putting Rock in some alleys in Lidderdale that are needed it, has not been done in years and will continue to see if they need more after the winter | alleys in Lidderdale |  |  | 1040 | 532.85 | Fully Completed | I jobs 532.85 Street fund 503.68 to date | 2011-06-30
Lime Springs | blade work on gravel road by Travel Plaza--Lime Springs City Street | gravel road by Travel Plaza | 1591.83 | 1936.85 | 500.88 | 500.88 | Fully Completed | I Jobs | 2010-07-22
| purchased salt/sand mix for use on city streets | all city streets |  |  | 636.6 | 903.34 | Fully Completed | I-Jobs and road use tax fund | 2011-03-31
| resurface street after water main repair | junction of Jackson St and Miller St |  |  | 5600 | 1591.83 | Fully Completed | I Jobs and Road Use Fund | 2009-09-11
| rock for repairing city streets | various washed out streets in city limits |  |  | 153.83 | 307.66 | Fully Completed | I-Jobs | 2010-10-15
| rock for repairing holes and washouts on our city gravel streets | various gravel streets in city limits |  |  | 830.47 | 830.47 | Fully Completed | I Jobs | 2010-07-09
Lincoln | sealcoating | Main Street | 613.71 | 746.72 | 613.71 | 613.71 | Fully Completed |  | 2009-09-17
| Sealcoating | East Railroad Street |  |  | 9500 | 746.72 | Fully Completed | I-JOBS and Road Use Tax | 2010-09-09
Linden | 31.52 tons of 1" Road Stone rock | spread on E. Dallas Street | 503.12 | 612.16 | 572.68 | 503.12 | Fully Completed | I-Jobs road funding money | 2009-11-30
Linn County | PCC paving on C Ave Ext & Echo Hill Road | C Ave Ext from County Home Road south to Echo Hill Road & Echo Hill Road from C Ave Ext to Alburnett Road. | 185497.54 | 228637.25 | 531821.54 | 414134.79 | Fully Completed | Local | 2010-10-15
Linn Grove | Sealcoating a portion of East High St | East High St | 765.23 | 931.08 | 931.08 | 931.08 | Fully Completed | I-Jobs RUT | 2011-08-31
| Sealcoating streets | Linn Grove West High Street and East High Street |  |  | 3203.25 | 765.23 | Fully Completed |  | 2009-07-10
Lisbon | South Washington Pavement Patching Improvements for the City of Lisbon | South Washington | 8289.9 | 10086.65 | 23046.5 | 8289.9 | Fully Completed | I Job and Road Use or General Funds | 2009-09-14
Liscomb | Install drainage after asphalt has been laid | Park St | 728.34 | 886.2 | 755.5 | 728.34 | Fully Completed |  | 2009-09-14
Little Rock | Repair streets using Dura-patching | Various streets in Little Rock | 1352 | 1645.02 | 2603.62 | 1352 | Fully Completed |  | 2009-09-22
Little Sioux | Patch holes in the roads through out town . | City limits of Little Sioux | 861.31 | 1048 | 3924.46 | 0 | Fully Completed | Road Use Tax Fund | 2012-04-30
Livermore | Grading streets and creating new driveways and culverts | 3rd Avenue, 4th Street | 1467.8 | 1785.93 | 5000 | 1467.8 | Less than 50% Complete | I JOBS | 2009-12-31
| Repair manholes and drainage | located throughout city |  |  | 5000 | 0 | Not Started | IJOBS money and road use money | 2010-12-31
Lockridge | Mill and resurface with asphalt | S Broadway and S First in front of fire station | 681.59 | 829.31 | 85270 | 681.59 | Fully Completed | Loan of $77,000 from bank along with $681.59 from I-Jobs and $7588.41 of road use tax funds. | 2009-10-02
Logan | Mill and pave 6" on East 6th Street from North 5th Ave. thru North 6th Ave. | East 6th Street from North 5th Ave. thru North 6th Ave. | 6748.1 | 8210.68 | 21653.4 | 14958.78 | Fully Completed | IJobs, Street Road Use. This was postponed due to too much rain. | 2010-05-31
Lohrville | Remove and replace concrete street and storm drains. | Intersection of Oak and 4th. | 1665.76 | 2026.79 | 3375 | 1665.76 | Fully Completed |  | 2009-08-09
Lone Rock | fILL IN CRACKS AND RESURFACE | LONE ROCK STREETS | 587.3 | 714.59 | 17500 | 587.3 | Fully Completed | I-JOB AND ROAD USE TAX FUNDS | 2010-06-09
| To be determined at later date. | various locations |  |  | 0 | 0 | Not Started | Federal I-Jobs | 2010-03-17
Lone Tree | DeVoe Street Project 2009 | DeVoe Street | 5027.23 | 6116.82 | 700000 | 11144.05 | Fully Completed | Bonding | 2010-10-01
Lorimor | Purchase of 1991 F-8000 Ford truck | Lorimor, IA 50149 | 1626.79 | 1979.38 | 6900 | 1414.38 | Fully Completed | LOST funds and I-Jobs funds | 2011-11-14
| Re-grade and road rock and oil application | 600 block of Main Street, 200 and 300 block of Nebraska Ave. |  |  | 6300 | 1626.79 | Fully Completed |  | 2009-09-03
| Scarify, regrade, and lay rock base | 800 block of 3rd Street Lorimor, IA |  |  | 565 | 565 | Fully Completed | Road use tax funds, I-Jobs funds | 2011-07-20
Lost Nation | crack sealing | South Avenue | 1784.24 | 2170.96 | 3420 | 1784.24 | Fully Completed |  | 2009-09-08
Louisa County | Bridge patch on damaged pavement | Bridge 034170 over Iowa River near Oakville | 72801.54 | 88366.7 | 7500 | 0 | Fully Completed | I-Jobs | 2009-10-07
| Concrete repairs on G28-X14 | From X14 at North County line to G28 at East County line about 3 miles. |  |  | 75000 | 74612.92 | Fully Completed | I-Jobs | 2010-09-14
| Crack sealing and patching of various roads | Varios roads and locations |  |  | 9412 | 0 | Fully Completed | I-Jobs | 2010-10-29
| Culvert repair and slab jacking | X99 - G36 - G62 and X61 |  |  | 65000 | 37961.15 | Fully Completed | I-Jobs | 2010-09-10
| PCC joint reseal concrete repairs | County Road G62 from Wapello to intersection at X37 |  |  | 48594.17 | 48594.17 | Fully Completed | I-Jobs | 2009-10-12
Lovilia | Asphalt Cold Patch. | Lovilia | 2546.37 | 3098.27 | 1400 | 1182.14 | Fully Completed | I Jobs | 2011-09-27
| Street Sweeping - balance of Project 2. | Lovilia |  |  | 156.13 | 0 | Fully Completed | I jobs | 2010-06-30
| Street Sweeping. Cleaning streets of sand & debris-winter cleanup. | City streets. |  |  | 510 | 510 | Fully Completed | I Jobs | 2011-06-30
| Street sweeping. Clean-up of city streets of winter sand and debris. | E Avenue, W. 16th St., W. 17th St., W. 18th St, W. 19th St. |  |  | 702.5 | 546.37 | Fully Completed | I Jobs | 2010-05-01
| Tear out and replace 500 Sq. ft. of sidewalk. | 1602 E Avenue South |  |  | 2000 | 2000 | Fully Completed | I Jobs | 2010-04-22
| Tree removal from right-of-way. | 902 F Avenue South, Lovilia |  |  | 1250 | 1250 | Fully Completed | I jobs. | 2011-10-03
Low Moor | NOT STARTED | CITY OF LOW MOOR | 745.32 | 906.86 | 0 | 0 | Not Started | GOVERNMENT FUNDING | 2010-09-01
Lowden | Seal coating on streets in Lowden | Lowden streets | 3467.96 | 4219.6 | 49000 | 4219.6 | Fully Completed | IJOBS and road use funds | 2011-10-07
| Seal coating on streets in Lowden | Lowden streets |  |  | 49541.85 | 4219.6 | Fully Completed | Road use tax and IJOBS funding | 2010-08-30
| Seal coating on streets in Lowden. | 5th St. Place |  |  | 51477 | 3467.96 | Fully Completed | Road Use Funds | 2009-07-21
Luana | Adding two feet to width of road and adding curb and gutters. 11/1/2009 and 11/29/2009 | 511 Main Street to 521 Main Street | 483.9 | 588.78 | 36828.8 | 483.9 | Fully Completed | $483.90 From I-Job Stimulus, remaining balance from road use tax. | 2009-10-05
Lucas | NO PROJECT HAS BEEN IDENTIFIED/INITIATED AT THIS TIME | TO BE DETERMINED | 963.28 | 1172.07 | 0 | 0 | Not Started | TO BE DETERMINED | 2011-06-30
| No project has been initiated at this time | N/A |  |  | 0 | 0 | Not Started | Not determined at this time | 2011-06-30
| The majority of our city streets are gravel, and there are several sites that need repaired/graded with gravel added | City of Lucas |  |  | 2136 | 1024.03 | Fully Completed | IJOBS for 2010 and 2011 | 2011-06-25
| The majority of the streets in our town are gravel and we have used the funding to grade/repair/add gravel/maintain several streets | City of Lucas |  |  | 1111 | 1111 | Fully Completed | IJOBS | 2012-06-30
Lucas County | Lucas County purchased granular surfacing material from Bruening Rock Products in Knoxville during the winter of 2011. The material was hauled to the Lucas County Maintenance Facility in Chariton where it was stockpiled. The material was used in the spr | Lucas County Maintenance Facility in Chariton, Iowa. Then to various Lucas County Roads. | 65634.83 | 80939.1 | 97703.28 | 80939.1 | Fully Completed | 82.84% IJOBS 17.16% Local Funds | 2011-02-28
| Replaced 16'x37' Pony Truss Bridge that was closed with a 24'x50' Beam-In-Slab Bridge. | Section 23 of Liberty Township (T-73N, R-22W) 20,000th Block of 550th Street |  |  | 84083.92 | 65634.83 | Fully Completed |  | 2009-08-13
Luther | To be determined at a later date | To be determined | 448.56 | 545.79 | 836.85 | 0 | Fully Completed | I-Jobs Funds | 2010-06-30
Luverne | single seal coat | Community Center Alley Quincy Street Fourth Street Sixth Street North Street Park Street | 977.77 | 1189.7 | 10124 | 1189.7 | Fully Completed | Road Use Tax Fund | 2010-08-02
| single seal coating, hot mix patching | Broadway from county road to 4th St. S. 3rd St. from Hanna Ave. to Prospect St. 4th St. from DeWitt St. to Prospect St. 5th St. N. from Hanna Ave. to Prospect St. Hot Mix Patching misc. locations |  |  | 9648.52 | 977.77 | Fully Completed | roads and streets fund | 2009-10-05
Luxemburg | Repaired catch basin that was in need of repair. | 106 1st Street East | 1074.45 | 1307.33 | 2712.5 | 1074.45 | Fully Completed | I-Jobs | 2009-09-03
Luzerne | Constuct city maintenance shed to be used to house the city tractor. | Luzerne | 287.89 | 350.28 | 16670 | 638.17 | Fully Completed | I-JOBS and the City of Luzerne | 2010-09-30
Lyon County | Slurry leveling with slurry surfacing and/or slurry leveling with chip seal | County wide with exact location to be determined in the spring after the freeze thaw cycle | 111173.61 | 136520.14 | 400000 | 247693.75 | Fully Completed | Secondary road fund | 2010-08-27
MacEdonia | Complete rebuild, sandblast and painting of truck sander. | 322 Main St, Macedonia IA 51549 | 1096.89 | 1334.63 | 1357 | 1334.63 | Fully Completed | I-JOBS | 2010-12-01
| Rout existing cracks (that have not been previously sealed) in asphalt pavement 3/4" by 3/4", blow with compressed air and seal with hot pour crack sealant material. Over band approx. 2" on both sides of crack. The cracks that have been previously seale | All City Streets in Macedonia. |  |  | 9000 | 1096.89 | Fully Completed |  | 2009-08-25
Macksburg | MAINTENANCE OF STREET 70.83 TON ROAD STONE AND HAULING TOTAL INVOICE $1,027.04 | W. GRANT STREET | 407.54 | 495.88 | 1027 | 407.54 | Fully Completed | $407.54 ROAD USE TAX $619.50 ROAD USE TAX | 2009-08-03
| MAINTENANCE OF STREET 32.8200 TON ROAD STONE Schildberg Construction Company Invoice $264.20 Beeler Trucking Hauled Invoice $164.10 | W. Grant Street |  |  | 500 | 482.3 | Fully Completed | $264.20 ROAD USE TAX $164.10 ROAD USE TAX | 2012-08-31
| purchased, hauled and spread 399 tons of rock to gravel roads. | around perimeter of city |  |  | 5132 | 0 | Fully Completed | road use tax | 2011-09-28
| replace 2 culvert and clean street ditches. | east north st |  |  | 3020 | 0 | Fully Completed | road use tax | 2011-09-16
Madison County | All edges of pavement need edge ruts filled with rock. | All paved routes in Madison County. | 103271.09 | 123993.13 | 8759.17 | 6414.18 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2009-10-20
| BRIDGE REPAIR - REPLACED 2 PIER CAPS AND 15 PIER PILING TO BRING THE BRIDGE BACK TO A LEGAL LOAD CAPACITY. | 15B-370-150 LOCATED IN SECTION 10-74-27 |  |  | 33487.82 | 33487.82 | Fully Completed | MADISON COUNTY SECONDARY ROAD DEPT | 2010-08-31
| Culvert under pavement rusted out causing hole in shoulder. Install plastic liner and grout. | 800 ft. East of Holliwell Bridge Rd on the St. Charles Rd (G50). Scott Twp, Section 10, Madison County |  |  | 16181.99 | 16181.99 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2009-08-03
| Flood waters eroded South abutment and wings exposing wood piling. Replace wood piling and cap on South abutment both wings. Replace backing boards to an elevation 5 ft. below streambed. Place engineering fabric and riprap to prevent further erosion. | 1B-500-240 - Bridge over Jim Creek on Fawn Avenue between 120th St. and 130th St. - Section 13-77-29 |  |  | 65862.53 | 65862.53 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2009-09-25
| PURCHASE 140M MOTORGRADER | MADISON COUNTY |  |  | 200000 | 64537.31 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2011-01-26
| PURCHASE CAT COMPACTOR PLATE, MODEL CVP110 | ZIEGLER CAT |  |  | 9000 | 9000 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2009-10-22
| RE-GRADE SECTION OF ROADWAY TO IMPROVE DRAINAGE. | ON 201ST TRL. AND 200TH TRL. EAST OF SUMMERHILL DR. IN SECTION 20 OF CRAWFORD TWP. |  |  | 12000 | 10076 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2010-09-09
| RE-GRADE SECTION OF ROADWAY TO IMPROVE DRAINAGE. | SECTION OF HOLLIWELL BRIDGE RD. EAST AND SOUTH OF NORWOOD AVE. IN SECTIONS 4 & 5 OF SCOTT TWP. |  |  | 16000 | 15892 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2010-11-04
| REPLACE TIMBER ABUTMENT PILING ON BRIDGE. | 4B-000-595: 1/4 MILE EAST AND SOUTH OF CUMMING RD (G4R) ON SETTLERS AVE. - LEE TWP, SECTION 31, MADISON COUNTY |  |  | 5812.39 | 5812.39 | Fully Completed | MADISON COUNTY SEC RD DEPT | 2009-10-21
Madrid | Repair and maintenance of a drainage ditch that traverses the community from northwest to southeast. Funds will be used to remove sediment and debris; as well as the removal of a wooden traffic bridge on Third Street. We will also use any remaining funds | Throughout the central portion of the community as described in the project description. | 10561.11 | 12850.11 | 45000 | 10000 | 50% or More Complete | IJOBS Funds and borrowed funds from a General Obligation Bond. | 2010-11-30
Magnolia | Gravel work for alleys | City of Magnolia | 746.63 | 908.46 | 6092.58 | 908.46 | Fully Completed | Ijobs and RUT | 2011-06-30
| roads were recently seal coated. Now pea gravel will be swept and removed. The date below is an estimate. | Magnolia, Iowa |  |  | 3640 | 746.63 | Fully Completed | IJOBS money and RUT funds or farm to market funds | 2009-10-30
Maharishi Vedic City | Add road stone to gravel road. | Maharishi Center Ave. | 518.17 | 630.47 | 630.47 | 630.47 | Fully Completed | FHWA & State Road Use monies | 2011-04-19
| Maintain existing gravel road, grading & road stone | Maharishi Center Ave. (formerly Juniper Ave.) |  |  | 3336 | 518.17 | Fully Completed | Road Use Fund | 2009-10-16
Mahaska County | Reconstruction of box culvert on 245th St. 8x12x45 RCB | 245th Street, Evans, Mahaska County | 105887.12 | 127275.39 | 31495.54 | 28949.43 | Fully Completed | ARRA Block Grant | 2011-06-30
| Road to Lacey Rec Complex | Sec 11-T75N-R16W |  |  | 204213.08 | 204213.08 | Fully Completed | RIIF | 2012-06-30
Malcom | 2" overlay on Washington St 6" patch at Washington & 4th Streets 8" patch at Washington & 1st Streets | Washington St & 4th St intersection Washington St & 1st St intersection Washington St from 1st to 8th St | 1309.01 | 1592.72 | 15995.4 | 0 | Fully Completed | Road Use Tax Fund | 2010-06-17
| Seal coating of the following locations | 8th Street from Hwy 63 to Washington Street 7th Street from Washington to Clay Street 6th Street from Washington to Hwy 63 5th Street from Lincoln to Clay Street 5th Street from Hwy 63 to Chapman |  |  | 37884.6 | 1309.01 | Fully Completed | Road Use Tax Fund | 2009-06-09
Mallard | Repair of street and RR crossing. | 511 Miller Street Mallard, Iowa 50562 | 1192.39 | 1450.82 | 0 | 0 | Not Started | I-Jobs money and Road Use Tax | 2010-07-29
| Repair of street and RR crossing. | 511 Miller Street Mallard, Iowa 50562 |  |  | 8000 | 0 | Not Started | I-Jobs money and Road Use Tax | 2010-07-29
| Repair road | 511 Miller Street |  |  | 0 | 0 | Not Started | I-Jobs and Streets | 2010-07-31
| Repair road | 511 Miller Street |  |  | 8000 | 0 | Not Started | I-Jobs and Streets | 2010-07-31
| Seal Coated 80% of streets south of Inman St. | Streets south of Inman Street |  |  | 20000 | 2643.21 | Fully Completed | used all of the I-Jobs monies and rest out of Road Use | 2010-07-13
Malvern | Breaking out of old concrete, level fill rock, supply and install 1/2" rebar on 12" centers eacy way, pour and finish new concrete to depth of one foot. | 3rd & Main Street | 5485.83 | 6674.83 | 2684 | 2684 | Fully Completed | I-Jobs $2684.00 | 2010-11-09
| New asphalt on 2nd Avenue | City Streets |  |  | 39628.87 | 3990.83 | Fully Completed | I-Jobs & Road Use Funds | 2011-05-28
| Remove and replace new asphalt on Marion Avenue | Marion Avenue, Malvern, IA |  |  | 68173.65 | 5485.83 | Fully Completed | Road Use Tax Funds | 2009-08-05
Manchester | 2010 Street Improvement Project: Reconstruction of Prospect Street from Williams Street to Anderson Street, including Millam Heights and Prospect Court | City of Manchester, Iowa | 22961.01 | 27937.57 | 891140 | 50898.58 | Fully Completed | IJOBS Funds, Local Option Sales Tax Funds, General Obligation Bonds, Water & Sewer Funds, Special Assessments | 2010-10-31
Manilla | 1998 International Dump Truck | Manilla, Iowa | 3664.5 | 4458.75 | 20151 | 3664.5 | Fully Completed | Road Use Taxes | 2009-12-03
| Seal coat and rock 12 Blocks of streets in Manilla in 05/02/2010 | 4 blocks of 3rd Ave, 2 blocks of 7th St, 2 blocks of 6th St, 2 blocks of 5th St, and 2 blocks of 4th St. Manilla, Iowa |  |  | 0 | 0 | Not Started | I Jobs and Road Use Funds | 2011-05-13
| Seal coat and rock 12 Blocks of streets in Manilla in 05/02/2010 | 4 blocks of 3rd Ave, 2 blocks of 7th St, 2 blocks of 6th St, 2 blocks of 5th St, and 2 blocks of 4th St. Manilla, Iowa |  |  | 9250 | 0 | Not Started | I Jobs and Road Use Funds | 2011-05-13
| Seal Coat city streets with oil and gravel | Manilla, Iowa |  |  | 9250 | 0 | Not Started | Ijobs money and Road Use Taxes | 2011-05-06
| Seal Coat city streets with oil and gravel | Manilla, Iowa |  |  | 10560 | 0 | Not Started | Ijobs money and Road Use Taxes | 2011-05-06
Manly | INSTALLATION OF 3-4" PATCH,INSTALL LEVELERS,ADJUST MANHOLES AND WATER RISERS, INSTALL CURB BETWEEN ELMORE AND SPRING TO PREVENT WATER RUNNING ONTO OWNERS' PROPRTIES | W SPRING ST. FROM GRANT TO S LINDEN ST | 5861.46 | 7131.87 | 15237 | 5861.46 | Fully Completed | RUT $8949.74 | 2009-10-13
| N.Blanch St. from W.Harris St. to W. North St. | City of Manly |  |  | 7088.06 | 0 | Fully Completed | I-Jobs | 2011-06-29
Manning | May Street Reconstruction | From Madison to Nameless | 6507.88 | 7918.39 | 24102.29 | 6507.88 | Fully Completed |  | 2009-08-26
| Reconstruct bridge | West street bridge crossing over the West Nishnabotna |  |  | 47030.75 | 7918.39 | Fully Completed | 80% Federal; 10% County; 10% City made up of IJobs and RUT | 2011-07-30
Manson | Main Street railroad crossing approaches | Main Street between 8th and 9th Ave. | 8268.06 | 10060.08 | 0 | 0 | Not Started | road use tax funds | 2012-06-01
| Main Street railroad crossing approaches | Main Street between 8th and 9th Ave. |  |  | 21639 | 0 | Not Started | road use tax funds | 2012-06-01
| street improvement project - asphalt resurfacing | 9th Ave from Main St to 15th St, 10th Ave from 8th St to 10th St, 12th Ave from 8th St to 16th St, 12th Ave from 8th St to 16th St, 13th St from 9th Ave to 12th Ave, 11th St from 10th Ave to 15th Ave, |  |  | 712000 | 8268.06 | Fully Completed | general obligation bonds | 2009-10-15
Mapleton | Pavement patching and crack and joint cleaning and filling on Ohm Drive east of Chamberlain Street, curb and gutter and sidewalk replacement on 4th Street from Courtright Street to Main Street and pavement patching in the east half of the intersection of | Ohm Drive east of Chamberlain Street 4th Street from Courtright to Main Street Elm Street and 7th Street intersection | 5774.1 | 7025.58 | 84620.6 | 12799.28 | Fully Completed | Road Use Tax Fund | 2011-09-01
Maquoketa | Washington Street: The City Council decided to use it two I-Jobs allocations on the reconstruction of 1 block (770 lineal feet) of Washington Street. The project is now completed. It cost $108,000. (Entered 9/17/2010) | This section of Washington Street is from S Vermont to S 5th Street. It mainly abuts property that is owned by the Maquoketa Community School District. | 26695.4 | 32481.34 | 118165.6 | 59176.74 | Fully Completed | Sources: I-Jobs $59,000; Maquoketa School District $15,000; City RUT budget $34,000. | 2010-08-16
Marathon | partial payment for dumptruck/snowplow replacement | Within the City of Marathon | 942.18 | 1146.39 | 11000 | 942.18 | Fully Completed |  | 2009-10-01
| repairs on dump truck at City of Marathon. | 306 West Attica Marathon, IA 50565 |  |  | 3112.6 | 1146.39 | Fully Completed | i jobs | 2010-07-02
Marathon | seal coating of some streets | within City of Marathon |  |  | 3950 | 0 | Fully Completed | I-Jobs | 2011-07-07
Marble Rock | Filling potholes in blacktop in various places. | On all streets that have potholes. | 979.64 | 1191.97 | 1000 | 0 | Not Started | Road Use Tax Fund | 2010-04-13
Marcus | Asphalt strengthening on one block at west second st from walnut to ample street. | west second st from walnut to maple street | 4974.81 | 6053.05 | 13351 | 952.64 | Fully Completed | $476.32 from I-Jobs and the rest from Road Use Tax | 2011-07-31
| Did some repairs on one block of Main Street. Used Nuvo Gap in the cracks on that block. | One block of North Main Street, between Pine and Spruce. |  | 6053.05 | 4974.81 | 4974.81 | Fully Completed | $4,974.81 was from I-Jobs. The rest was from Road Use Tax in the amount of $1588.31 | 2009-10-07
| Tore up the old asphalt and turned the street back into a gravel street. Incorporated the old asphalt into the street along with gravel. This project will not be totally completed until next Spring, so we can work on the soft spots. | Section Street |  | 6053.05 | 5576.73 | 5576.73 | Fully Completed | I-Jobs and Road Use Tax Money. $5576.73 was use from I-Jobs. for this project. | 2010-10-15
Marengo | Install curb and gutter and seal coat. | Curb and gutter will be on the east side of Marengo Ave. between Main St. and May St. Seal Coat will be various locations of varying length and scope. | 11072.13 | 13471.89 | 62000 | 24544.02 | Fully Completed | Local Option Sales Tax | 2011-06-20
Marion | 29th Avenue partial reconstruction project including reconstruction of the slab and gutter east of Alburnett Road. | 29th Ave east of Alburnett Road | 114844.38 | 139735.68 | 14996 | 14996 | Fully Completed | IJOBS | 2010-08-06
| Asphalt overlay project on 7th Avenue. | Intersection of 7th Avenue and 35st Street. Intersection of 7th Avenue and 3rd Street. |  |  | 63113 | 63113 | Fully Completed | I-JOBS | 2009-11-18
| Intelligent Transportation Systems project | Various locations |  |  | 139382.26 | 139382.26 | Fully Completed | I-Jobs Funds | 2011-03-18
| Paving a deteriorated stretch of Winslow Road. | Winslow Road |  |  | 37088.8 | 37088.8 | Fully Completed | I-JOBS Funds | 2009-10-30
Marion County | 6X6 RCB cost shared with Mahaska County. | 250th 1600' South of Hwy G71 | 117569.34 | 140974.36 | 15000 | 2400 | Fully Completed |  | 2009-06-27
| Ditching, culvert repair | G76 and S45. |  |  | 2080 | 2080 | Fully Completed |  | 2009-07-08
| Outlet caved off 42" pipe on inlet & outlet of RCB | 370 Feet South of Hse 2366 on 140th. Sec 18, TWN 74, RNG 19 |  |  | 10000 | 4275 | Fully Completed |  | 2009-06-30
| Purchase of rock for roads in Marion County. | Marion County |  |  | 80997.69 | 76742.5 | Fully Completed | I-JOBS | 2012-04-30
| RCP needs to be relaid and tied together. | 222nd just South of Jesup Drive. Sec 27, Twn 76, Rng 18 |  |  | 15000 | 3260 | Fully Completed |  | 2009-07-07
| RCP-Boiler Pipe-No Outlet | 200 Feet South of house 2074 (Corwin Fee)\ SEC7, TWN 74, RNG 19 |  |  | 20538 | 20538 | Fully Completed |  | 2009-07-22
| Replace existing box culvert | 130th South of Knoxville |  |  | 76000 | 75994.8 | Fully Completed | Ijobs | 2010-09-30
| Replace existing twin 60"X46' with the same plus HD Walls. 2-54"X24' & 2-60" X 2' CMP | 1400 Feet North of House 2083 - North of Bauer on 20th |  |  | 25000 | 10263 | Fully Completed |  | 2009-08-09
| Replace North and South Culvert on 40th Pl | 40th Pl |  |  | 57143.4 | 57143.4 | Fully Completed | Ijobs | 2010-09-30
| South Abutment washing out 51264160 & 51266196 | Bridge over Whitebreast North of Melcher |  |  | 5847 | 5847 | Fully Completed |  | 2009-08-01
Marquette | Salt Shed Concrete Floor | City shop 420 Pleasant Drive | 1812.62 | 2205.48 | 3644.07 | 1812.62 | Fully Completed | I-Jobs and Capital Project Funds | 2009-09-03
| Salt Shed Expansion Project | City Shop 420 Pleasant Drive |  |  | 3561 | 1812.62 | Fully Completed | I-jobs and General Fund | 2009-09-03
Marshall County | Will be used to purchase either crushed rock or crushed gravel of the 40,000 ton annual use. | To be used in one of four surfacing divisions in Marshall Co.. | 116036.7478 | 138313.15 | 305000 | 116036 | Fully Completed | Local Funds will be used on all four divisions of rock surfacing. | 2010-06-24
| Will be used to purchase either crushed rock or crushed gravel of the 40,000 ton annual use. | To be used in one of four surfacing divisions in Marshall County. |  |  | 310000 | 138313.89 | Fully Completed | Local Funds will be used on all four divisions of rock surfacing. | 2011-06-30
Marshalltown | Slurry Seal 5.9 miles of street, 1852 SY of pavement replacement | State St from N. 13th St. to N. 7th Ave. and Main St. from Highland Acres Rd. to 13th St. also from 3rd St. to 12th Ave | 113599.59 | 138221.09 | 547286 | 251820.68 | Fully Completed | Local Option Sales Tax will fund the rest of the project not covered by the I-jobs funds. | 2010-06-30
Martelle | Asphalt Resurfacing Street | Military Street | 944.42 | 1149.11 | 1025 | 944.42 | Fully Completed |  | 2009-09-02
Martensdale | Resurfacing of city streets | City of Martensdale, Iowa Ave., Burlington Ave., and Center St. | 2039.72 | 2481.8 | 2481.8 | 2481.8 | Fully Completed | IJOBS funds for 2010 - $2039.72 | 2010-10-15
Martinsburg | Street Maintenance | Martinsburg, IA | 405.14 | 492.95 | 18359.08 | 492.95 | Fully Completed | Road Use & Stimulus Funds | 2010-10-31
| Street supplies to maintain and improve streets. | Martinsburg, IA |  |  | 979 | 405.14 | Fully Completed | Road Use Tax, I-Jobs Fund | 2010-03-31
Marysville | Rock hauling. | city streets | 145.79 | 177.39 | 23.18 | 23.18 | Fully Completed | I jobs | 2011-09-16
| Street drainage improvement. | Marysville Iowa |  |  | 150 | 150 | Fully Completed | I Jobs | 2010-06-30
| Street Drainage improvement-Rock. | Marysville |  |  | 150 | 150 | Fully Completed | I Jobs | 2011-06-30
Mason City | 15th Street SW Bridge over Cheslea Creek-Approach Replacement. The IJOBS cost of the project was $102,003.70. | 15th Street SW Bridge over Cheslea Creek-Approach | 127414.63 | 155030.39 | 110200 | 102003.7 | Fully Completed | IJOBS-RUT | 2010-11-16
| Construction of rehabilitation of the west approach on the 12th Street NW Overpass. IJOBS fuds to be used for the project is $65,572.07. | 12th Street NW Overpass |  |  | 79441.75 | 65573.49 | Fully Completed | I-JOBS | 2012-06-29
| Engineering for rehabilitation of the west approach on the 12th Street NW Overpass. The contract for these services is in the amount of $24,725.00. | 12th Street NW Overpass |  |  | 24725 | 24723.58 | Fully Completed | I-JOBS | 2012-06-29
| North Taft Avenue Culvert Replacement. The IJOBS cost of the project was $64,764.25. | North Taft Avenue |  |  | 62764.25 | 62764.25 | Fully Completed | IJOBS- RUT | 2010-11-16
| Route and seal and crack filling on designated streets within Mason City. The IJOBS cost of the project was $27,380.00. | Mason City |  |  | 30671 | 27380 | Fully Completed | IJOBS-RUT | 2011-11-21
Masonville | Putting rock and hot mix on roads to fill in potholes before winter weather | various Masonville city street | 405.4 | 493.26 | 250 | 250 | Fully Completed | Ijobs funds - city of masonville | 2009-10-15
| repair city streets with tar and chips | Masonville |  |  | 10300 | 493.26 | Fully Completed | road use money, city funds and I-jobs funds | 2010-07-10
| Rock added to fill potholes. Add rock to roads and graded them to bring crown back. | John Street and Bernhart Street |  |  | 1670 | 0 | 50% or More Complete | IJobs and Road Use Funds | 2011-09-30
Massena | Asphalt Seal Coat and Patching | Seal Coat: Alley from Main To Pine, Spruce from Clark to 6th, 6th from E.Cedar to Main, W.Cedar from 1st to 5th, Pine from 5th to 3rd, 3rd&4th from Main to Spruce, patch on Main, Mulberry,W.Ced | 1389.25 | 1690.35 | 17403 | 1690.35 | Fully Completed | Road Use Taxes & I-JOBS Funding | 2010-07-08
| Replacement of Sidewalks, Curbs, and Gutters on Main Street from 1st Street to 2nd Street | Main Street from 1st Street to 2nd Street |  |  | 60967 | 1389.25 | Fully Completed |  | 2009-09-01
Matlock | Snow removal of city streets. | City streets of Matlock | 230.35 | 280.28 | 1801 | 510.63 | Fully Completed | I-Jobs, including Road Use Tax Income | 2011-03-15
| To be determined. Will be used for future city street maintenance. | To be determined. |  |  | 400 | 0 | Not Started | I-Jobs, including Road Use Tax Income | 2009-12-31
Maurice | Replace broken culvert and repair street | Oak Street north of intersection with 4th Street | 856.2 | 1041.78 | 2200 | 1897.98 | Fully Completed | Road Use Tax Funds | 2010-06-30
Maynard | Erosion Abatement Project for alley/culvert due to dry run creek issues. | 3rd St. N. alley between Main Street W and Maynard Street | 2183.85 | 2657.18 | 22954.25 | 2183.85 | Fully Completed | This progject was funded with Donations in the amount of $13,300, FEMA, and IJOBS funds. | 2010-09-30
| High Performance Pothole Patch Maintenance Program. | City Streets of Maynard |  |  | 3780 | 2657.18 | Fully Completed | I Jobs Stimulus Monies and Rut Fund | 2010-11-15
Maysville | repair pothole in public streets where needed in town | Northeast of New Liberty Road | 547.65 | 666.34 | 6770 | 1213.99 | Fully Completed | Road Use Tax Fund | 2011-09-06
McCausland | clean out and repair drainage ditches | through out town | 709.67 | 863.48 | 5000 | 0 | Not Started | i-jobs | 2010-05-31
McClelland | Reseal City Streets in McClelland | Within City Limits | 444.69 | 541.07 | 35000 | 985.76 | Fully Completed | I-JOBS and Road Use Tax | 2010-07-08
McGregor | Engineering of alley extension to connect Main Street to municipal parking lot on 1st Street | Front St. from Main Street to 1st Street Parking Lot | 3804.27 | 4628.8 | 5600 | 4628.8 | 50% or More Complete | I-Jobs | 2011-08-31
| street resurfacing | City of McGregor |  |  | 3804.27 | 3804.27 | Fully Completed | I Jobs | 2009-12-31
| Undecided-project not started | City of McGregor |  |  | 0 | 0 | Not Started | I Jobs | 2009-09-30
Mechanicsville | Details not yet identified | Mechanicsville | 5123.32 | 6233.74 | 0 | 0 | Fully Completed | IJobs 2009-2010 | 2010-12-31
| Street Seal Coat Work | Oak Street from Pavement East to Second Street; John Street from 1st to 2nd; Oak & 1st Street; Approach to Oak St; and First Street (West) |  |  | 12043.55 | 11357.06 | Fully Completed | I-Jobs & RUT | 2010-08-19
Mediapolis | Money will be spent for an addition to the Main Street Improvements Project Phase III. STP funds have been awarded for some portions of the project. Additional work on Orchard Street from Main to Middle is not funded and the IJOBS money will be used for t | Orchard Street from Main to Middle | 7180.5 | 8736.8 | 0 | 0 | Not Started | Ciy Funds will be used-proceeds from a G.O. Bond | 2011-06-06
| Money will be spent for an addition to the Main Street Improvements Project Phase III. STP funds have been awarded for some portions of the project. Additional work on Orchard Street from Main to Middle is not funded and the IJOBS money will be used for t | Orchard Street from Main to Middle |  |  | 212429 | 0 | Not Started | Ciy Funds will be used-proceeds from a G.O. Bond | 2011-06-06
Melbourne | restructuring of intersection where heavy truck traffic had torn up road Invoice amount $4,000.00 (remaining IJobs money $219.60) | 4th Street and Hart Avenue | 3467.96 | 4219.6 | 4000 | 4000 | Fully Completed | I Jobs | 2010-10-15
| We have only $219.60 left of our I Jobs monies. This spring we use the money to buy items to repair pot holes and gravel where necessary | Spots thru out city |  |  | 0 | 0 | Not Started | City will use all the money from I Jobs and also some from our street money (RUT) | 2011-04-29
| We used the IJobs monies to help repair our streets. 5" HMA Full Depth patching, 2" HMA resurfacing, 3" HMA resurfacing, HMA surface patch w/curb, 1 1/2" Milling and HMA resurfacing (Mousehole). Total bid was $65,349.13 we used all of our IJobs $3,467.96 | Several streets in the city were resurfaced and patched. |  |  | 65349.13 | 3467.96 | Fully Completed |  | 2009-08-28
Melcher-Dallas | filling cracks in blacktop streets | West 2nd Street, West and East Center Street, West 1st Street, Church Street, North B Street, D Main Street, | 5669.28 | 6898.03 | 7342.68 | 5669.28 | Fully Completed |  | 2009-08-28
Menlo | storm sewer tiling around city park & residential area | city park & side streets | 1594.21 | 1939.74 | 7057.75 | 3533.95 | Fully Completed | I Jobs funding & city funds | 2011-07-18
Meriden | Seal Coat 3rd Street | City of Meriden, 3rd Street to county line | 803.66 | 977.84 | 1559.5 | 803.66 | Fully Completed | Road Use Tax Fund & Local Option Sales Tax | 2009-08-21
Merrill | Repair broken concrete due to heavy equipment use during new house project | Corner of Grant & Lynn Sts | 3293.25 | 4007.02 | 6000 | 3293.25 | Fully Completed | LOCAL OPTION TAX & I JOBS | 2009-10-12
Meservey | Blacktopped six streets in Meservey. | Meservey, IA | 1043.45 | 1269.61 | 22000 | 1043.45 | Fully Completed | IJobs money of $1043.45 | 2009-09-10
| Blacktopped the final 8 blocks in Meservey | Meservey IA |  |  | 40000 | 1269.61 | Fully Completed | IJOBS Money and General Street Fund | 2011-06-22
| Repaired and Blacktopped streets in Meservey | Meservey IA |  |  | 0 | 0 | Fully Completed | I Jobs Money of $1043.45 was used to help pay for the streets that were blacktopped in Meservey. The bill was paid in October 2009. | 2009-12-31
| We have black topped six streets in Meservey but have not received the bill as yet. It will be paid sometime in October 2009. | Meservey, IA |  |  | 0 | 0 | Fully Completed | IJobs Money of $1043.45 | 2009-10-13
| We have not determined what the IJobs money will be used for at this time | Meservey IA |  |  | 0 | 0 | Not Started | The IJob money of $674.18 will be used for any project yet to be determined. | 2011-06-30
Middletown | Street Sealcoating | Boundary Avenue between Main Street and Louisiana Street | 2336.72 | 2843.18 | 4721 | 2336.72 | Fully Completed |  | 2009-08-25
Miles | patching and seal coating streets | various streets in Miles | 1296.89 | 1577.98 | 20167.6 | 2874.87 | Fully Completed | to be used with RUT funds | 2010-07-22
Millersburg | Repair and sealcoat streets | Ballard St, Fremont St, Main St, Jackson St, Fremont St | 605.71 | 736.99 | 8128.46 | 605.71 | Fully Completed | Road Use Tax | 2009-07-16
| Repair and sealcoat streets | Jackson St, Main St, Fremont St, Miller St, Bush St, Washington St, Ballard St |  |  | 9820.96 | 736.99 | Fully Completed | Road Use Tax | 2010-07-01
Mills County | Replacement of drainage culvert. Repair road grade and surface. Reseed foreslopes and borrow area. | Pease Rd. S26 T71 R43 | 84436.31 | 102829.56 | 67402.83 | 0 | Fully Completed |  | 2009-08-21
| spot rock on various county roads | 408 on Applewood Ave & Brothers Ave. 402 on Gaston Rd. |  |  | 17033.48 | 17033.48 | Fully Completed |  | 2009-09-09
Millville | Application of Dust Control | Gravel Roads in City of Millville | 69.41 | 84.45 | 650 | 69.41 | Fully Completed | city budget | 2010-04-30
| Apply Dust Control on gravel roads in city limits | Gravel Roads in City of Millville |  |  | 850 | 84.45 | Fully Completed | Budget | 2012-06-30
Milo | TO BE DETERMINED | TO BE DETERMINED | 3664.5 | 4458.75 | 0 | 0 | Not Started |  | 2010-02-25
Minburn | Asphalt Patching Repair | Portions of North Street, 3rd Street, Walnut Street, 5th Street and F31 | 1270.69 | 1546.1 | 2660 | 1270.69 | Fully Completed | Road Use Tax | 2009-10-20
| Single seal coat to cover aggregate to include compaction | 6th Street |  |  | 14813.85 | 1546.1 | Fully Completed | I-Jobs | 2010-06-30
Minden | Removed and repaired damaged curbs throughout the community | 1st, 4th st, Brady, Perry | 2463.38 | 2997.3 | 5400 | 2463.38 | Fully Completed | IJobs | 2009-09-01
| Repaired alley entrance to help vehicle access | 4th Street from Brady Street to Perry Street |  |  | 5019.99 | 2997.3 | Fully Completed | IJOBS Road Fund Stimulus | 2010-10-13
Mingo | Clean, tack and lay 2" average depth of type A asphalt | South Station, Mohawk, Main Street, Theodore St. | 922.91 | 1122.94 | 16385.4 | 2045.85 | Fully Completed | I Jobs and General Fund | 2010-10-16
Missouri Valley | concrete paving on Third Street from Huron to Summit Street | Third Street from Huron St to Summit Street | 13068.17 | 15900.55 | 801564.08 | 28968.72 | Fully Completed | local sales tax revenue, RUT, I-JOBS | 2010-09-16
Mitchell County | Purchase salt and sand for winter roadway maintenance. | Mitchell County Secondary Roads, Osage Shop | 84992.67 | 105042.64 | 121057.72 | 105042.64 | Fully Completed | Secondary Road Budget | 2010-12-31
| Purchased salt for FY 2010 | Mitchell County Storage Facility, Osage, IA |  |  | 104385 | 84992.67 | Fully Completed | Secondary Road Funds | 2009-10-30
Modale | Asphalt Prime Coat to West Anderson Street - 3,124 SY Single Sealcoat to West Anderson Street - 3,124 SY | West Anderson Street, Modale, IA | 771.17 | 938.32 | 5060.88 | 771.17 | Fully Completed | $771.17 from I-Jobs Funds $4,289.71 from Road Use Tax | 2009-06-30
Mondamin | Asphalt repair of intersections on Maple Street | City of Mondamin; Maple Street and Main Street | 1847.54 |  | 2200 | 1847.54 | Fully Completed |  | 2009-09-25
| Repair Sub-base and surfacing of existing city streets | Granular surfaced streets & alleys south of Maple Street |  |  | 2820 | 2247.97 | Fully Completed | I-Jobs Road Funding | 2010-11-02
Monmouth | Repair culvert | South Division Street | 599.92 | 729.94 | 1490 | 599.92 | Fully Completed |  | 2009-09-09
| Repair streets by covering with slurry or Seal Coat | Residential Streets |  |  | 0 | 0 | Not Started | LOT, RUT, IJobs | 2011-06-01
| Repair streets by covering with slurry or Seal Coat | Residential Streets |  |  | 14500 | 0 | Not Started | LOT, RUT, IJobs | 2011-06-01
Monona | Street Maintenance - Crack Sealing | City of Monona | 6769.94 | 8237.25 | 9993.05 | 8237.25 | Fully Completed | RUTF | 2011-04-30
Monona County | County Wide PCC Pavement Patching | County Wide | 105624.5 | 127573.97 | 242354.9 | 233198.47 | Fully Completed | I-Jobs/Local Funds | 2010-08-31
Monroe | Adding rock to streets repairing of pot holes due to winter. | Numerous Streets in town, Commerce, Sherman, Zickel, Taylor, Rose Lane, etc | 7896.81 | 9608.36 | 1060.3 | 1030 | Fully Completed | I Jobs fund | 2010-10-13
| Patch, base repair and seal coating on Cemetery Road, from Beverly Circle to Taylor, Level and double seal bad area on Marion Street 5 ton of patch furnished and placed. City Hall Drive also. | Cemetery Roard from Beverly Circle to Taylor Street, Marion Street repair and City Hall Drive. |  |  | 12079.85 | 9505.45 | Fully Completed | IJOBS total cost $12079.85 | 2011-06-17
| Repair of culvert on South side of road | West County Line Road, Monroe IA |  |  | 7500 | 6736.72 | Fully Completed | IJOBS Funds/City of Monroe Funds | 2009-10-15
| Rock for City Hall Drive balance of IJOBS funds used. | 206 W Sherman, Monroe IA |  |  | 233 | 233 | Fully Completed | I-JOBS / CITY BUDGET | 2011-08-29
Monroe County | Improve Existing Roads (High Volume) BY: 1. Re Establish ditches to improve drainage 2. Re Shape the road surface to provide an appropriate crown. 3. Incorporate an additive such as "flyash" or "c-Stone" to improve the subgrade stability. 4. Re s | 1. From end of pavement on 653rd to 220th street (2 MI) 1A. 653rd Ave. from 220th to 235th Street. 2. 623rd Ave. from 206th Pl to 227th Street (2MI) | 64738.99 | 78133.76 | 65288 | 64738.99 | Fully Completed | Secondary Road Fund | 2010-06-30
| Reshape road surface and add surface material. | Numerous Secondary Roads |  |  | 78133.76 | 78133.76 | Fully Completed | Secondary Roads | 2012-06-30
Montezuma | sealcoating streets | multiple streets | 6363.74 | 7743.02 | 14397 | 6363.74 | Fully Completed |  | 2009-09-18
Montgomery County | Apply road rock to local and farm to market secondary roads rock wide spread areas through out the county coounty or contracted rock hual to be determined | County wide, 12 Townships in Montgomery County Spot locations damaged by the Winter Storm of 2009-2010 | 74101.21 | 90608.02 | 150000 | 0 | Not Started | TO BE DETERMINED | 2010-08-01
| Bridge Replacement 24'x50' Slab and Beam Bridge | Section 21 in East Township Montgomery County Iowa |  |  | 125000 | 0 | Not Started | Local Funds | 2010-07-22
| Remove and replace two bridges on L Ave. with culverts | Section 18 and 19 in Frankfort Township in Montgomery County On L Ave between 180th and 200th Street |  |  | 90000 | 0 | Not Started | local Funds | 2011-06-15
| Remove failed multiplate culvert and Replace with 10'x10' twin RCB Culvert Division II is Roadway Grading and Channel Excavation | 1/4 South of State Highway 34 on T Ave., in Section 12 of East Twp., in Montgomery County |  |  | 300000 | 0 | Not Started | Local Farm to Market/FEMA Alternate Project | 2010-12-30
Monticello | E 2nd Street Rehab & adding storm sewer- design phase | E 2nd Street between Maple and Mains Street and a small section on Maple Street | 15789.25 | 19211.4 | 52137 | 19409.64 | Fully Completed | ijobs and bonding | 2012-05-31
| Repair alley that caved in from defective storm sewer | Between South Main Street to Elm Street |  |  | 20000 | 15591.01 | Fully Completed | Ijobs and bonding | 2010-05-31
Montour | Barier for Road sand and salt | City of Montour | 902.21 | 1097.76 | 902.21 | 902.21 | Fully Completed | Ijob did not use I-Jobs money | 2010-12-08
| Build box blade for snow plow for snow removal | City of Montour |  |  | 37.77 | 37.77 | Fully Completed | I-Jobs $939.98 | 2011-12-15
| rerock residential gravel roads | various |  |  | 1059.99 | 1059.99 | Fully Completed | ijobs $1059.99 | 2011-12-31
Montrose | Adding dirt to raise the ground to mitigate future flooding along the south slough. | City of Montrose south slough. | 4179.89 | 5085.84 | 9265.73 | 7011.22 | 50% or More Complete | I-Jobs funding | 2010-04-29
Moorhead | Minor street and alley maintenance. | City of Moorhead | 926.21 | 1126.95 | 2152.52 | 2053.16 | Fully Completed | I-JOBS funds | 2011-06-30
Moravia | rock for culvert replacement | south side of Montgomery Street | 3114.17 | 3789.14 | 1500 | 1367.33 | Fully Completed | I-Jobs | 2009-12-01
Morley | Additional repair work had to be done to culvert on Wurzbacher St. that had not been planned on. | Wurzbacher St. near intersection of Rohrbach St. | 244.59 | 297.6 | 418.88 | 297.6 | Fully Completed | I-Jobs Monies $297.60 Reg. Road Use Funds $121.28 | 2010-08-23
| Install culvert and do repair work to hole in street | On Wurzbacher St. near intersection of Rohrbach St. |  |  | 2634.2 | 245 | Fully Completed | I-Jobs Monies | 2010-06-21
Morning Sun | Sealcoat on city streets. | North Elm - Division to North 1st, North 1st to North 2nd North Maple - 1st to Division South East 6th - Church street to Main | 3808.64 | 4634.12 | 47700.15 | 4634.12 | Fully Completed | I-Job Funds | 2010-07-16
| Sealcoat streets | North Church St. - 1st St. to Division St. North Blair St. - 3rd St. to 2nd St. Manor Road - Main - West |  |  | 40748.4 | 3808.64 | Fully Completed |  | 2009-09-14
Moulton | resurfacing the city parking along Hwy 202. DOT will be resurfacing the Hwy at this time. | Between Second Street and Broadway on both sides. There will also be some curb and gutters that will have to be replaced. | 2873.95 | 3496.85 | 100000 | 0 | Fully Completed | loan | 2010-10-30
Mount Ayr | Repairs to Jefferson Street a concrete street by replacing sections of concrete as needed. | West Jefferson Street from N Fillmore St to N West Street | 7957.95 | 9682.76 | 17655 | 17556.94 | Fully Completed | I-Jobs Funds | 2010-11-30
Mount Pleasant | Alley reconstruction from Washington Street to Monroe Street. | Alley between Jefferson Street and Jackston Street. | 38221.77 | 46505.93 | 65000 | 46505 | Fully Completed | I-Jobs | 2010-07-09
| PCC paving removal and replacement | Armstrong Court at Aldrin and Shepard Drive & Shepard Court |  |  | 45696.14 | 38221.77 | Fully Completed | I-JOBS road funding | 2009-10-15
Mount Vernon | U.S. Highway 30 Corridor Pre Design | Cedar Rapids, Iowa | 18217.69 | 22166.18 | 44500 | 40383.87 | 50% or More Complete | RUT Funds & Street Funds | 2010-12-30
Murray | continue to repair City streets | City of Murray | 3345.66 | 4070.8 | 6000 | 3215.68 | Less than 50% Complete | Road Use and general funds | 2011-06-30
| Due to weathercontions over the years the streest have deteriated. The base needs to be rebuilt before we can resurface the streets. We contioue to haul rock to rebuild the base. | streets of the City of Murray |  |  | 5000 | 3345 | Less than 50% Complete | Road Use Funds and General Funds | 2011-06-30
Muscatine | Bidwell Road Asphalt Resurfacing including related concrete patching and handicapped ramps | Bidwell Road between Isett and Wier Streets | 99133.75 | 120619.94 | 229410.74 | 219753.69 | Fully Completed | IJOBS Funding | 2009-11-30
Muscatine County | Maintenance Pavement Markings | Various secondary roads in Muscatine County | 93129.2 | 111238.21 | 138907.32 | 111238.21 | Fully Completed | Secondary Road Fund | 2011-08-25
| RCB box culvert extensions. | Hampton Avenue and Independence Avenue, Muscatine County, IA. |  |  | 556316.19 | 93129.2 | Fully Completed | Local Secondary Road Fund | 2010-05-28
Mystic | Going to blade and add class A rock to 1,905 feet of road going around Mystic Reserivor. Add a 16 inch X 20 foot culvert at entrance to Reserivor. | Mystic Reservior | 2568.21 | 3124.84 | 2599.07 | 2568.21 | Fully Completed | ARRA Block Grant | 2009-10-19
| Rock for Road and major repair on road grader | roads graveled in City of Mystic and City Shop |  |  | 3470.6 | 3124.84 | Fully Completed | I-Jobs | 2010-11-08
Nashua | Lexington Ave. repair to include grinding of raised portions of the street. | Nashua | 7066.94 | 8598.63 | 16000 | 15455.27 | Fully Completed | I-Jobs funging will used to partially pay for the cost of the repairs | 2010-09-30
Nemaha | dust control on RailRoad Street | RailRoad Street | 357.56 | 435.04 | 555 | 357.56 | Fully Completed |  | 2009-08-27
Neola | Patching sections of Second Street & Pearl Street with asphalt | Sections of Second Street and Pearl Street | 3690.71 | 4490.63 | 6624 | 4490.63 | Fully Completed | Used from General Street Budget | 2010-10-29
| Street repairs at Second and Garfield | Second and Garfield, Neola, Iowa |  |  | 3711 | 3690.71 | Fully Completed |  | 2009-08-10
Nevada | Purchase of Used Boom Truck | 8th Street and N Avenue | 29080.17 | 35382.98 | 26497 | 1211.98 | Fully Completed | RUT & I-Jobs | 2011-04-25
| Salt Purchases for 11/12 Snow & Ice Removal | 8th Street & N Avenue |  |  | 9608.75 | 9571.86 | Fully Completed | I-Jobs | 2011-06-01
| Snow and Ice control materials | All city streets |  |  | 29080.17 | 29080.17 | Fully Completed | Road Use Tax - I-Jobs | 2010-06-01
| Snow Removal supplies, storage | 8th Street and N Avenue |  |  | 24599.14 | 24599.14 | Fully Completed | IJOBS | 2011-03-31
New Albin | Repair and Maintenance of public alleys. | City of New Albin | 2301.78 | 2800.67 | 2301.78 | 2301.78 | Fully Completed | I-Jobs | 2011-06-30
New Hampton | Street Restoration Project | 42,000 square yards of seal coat on various City Streets | 16125.56 | 19620.6 | 57262 | 35746.16 | Fully Completed | I-Jobs funds, the rest from Road Use Tax Funds | 2010-07-29
New Hartford | 2 1/2 asphalt overlay for street repairs and upgrades | East, York, Water, Mill, Maple and Beaver | 2878.32 | 3502.16 | 50673 | 2878.32 | Less than 50% Complete | Road Use Funds and Reserve Road Funds | 2010-07-30
New London | Lay 735' asphalt on Newland St. where the road was tore up to install a new storm sewer line. | The 300 block of Newland St. from McKinley St. to Adams St. | 8460.24 | 10293.91 | 33550 | 18754.15 | Fully Completed | I-Jobs & Local Funds | 2010-08-11
New Market | Asphalt patch & Leveling and single seal coat | Adams Street, Washington Street, 7th Street, Lafayette, 5th Street, West 9th Street, 4th Street, B Street, 3rd Street and 8th Street in New Market. | 1720.25 | 2093.1 | 41956.45 | 1720.25 | Fully Completed |  | 2009-08-10
New Providence | asphalt Grape Dr. and patches on W. Main St. and Walnut St. | New Providence | 538.14 | 654.78 | 14817 | 654.78 | Fully Completed | Local option Tax | 2010-07-26
| replacing and repairing snow plow truck parts | Eldora |  |  | 984.05 | 538.14 | Fully Completed | Road Use Tax Fund | 2009-09-21
| to be determined just setting up this report | to be determined |  |  | 0 | 0 | Fully Completed | Road Use Tax Fund | 2009-10-29
New Sharon | Planning to purchase a dump truck. | New Sharon | 5682.38 | 6913.98 | 0 | 0 | Not Started |  | 2011-06-30
New Vienna | Asphalt repair of city streets | North Washington Street - 175 sq.ft. East Harrison Street - 72 sq.ft. Pleasant View Dr. - 974 sq.ft. | 1465.43 | 1783.05 | 5000 | 1783.05 | Fully Completed | Road Use Tax Other Street Monies | 2010-07-20
| Crack sealing of streets | various streets |  |  | 4999.68 | 1465.43 | Fully Completed |  | 2009-07-07
New Virginia | Lions Park alley work & ditch work: Pull old culverts & replace, clean ditch north of alley, install intake & tube at top of alley, fill ditch & yard area, grade & slope alley, spread & grade rock - 3 loads. | Alley between West Street & Border Street on the north side of Lions Park. | 1618.18 | 1968.91 | 3907.45 | 1618.18 | Fully Completed | I-Jobs funds & City Road Use funds. | 2010-11-06
| Repair cut-outs in asphalt street surface. | Main Street |  |  | 5500 | 1618.18 | Fully Completed | I-JOBS funds and from City Road Use Fund | 2009-11-12
Newell | Black Top Service Inc pored 1 inche of asphalt on E Chaney Street and then seal coated over the top of that. They also did some patching with 1-3 inches of asphalt and then seal coated on a part of W Third Street and Williams Street. | E Chaney Street and part of W 3rd Street & Williams Street | 3874.15 | 4713.83 | 38500 | 4713.83 | Fully Completed | Street Fund | 2010-07-06
Newell | Cold Mix to repair streets | Fulton St, E Chaney St, 3rd St and Williams St |  |  | 349.58 | 0 | Fully Completed |  | 2009-07-30
Newell | Dust control on gravel roads | W Jensen St, W Chaney St, and pool road |  |  | 2365.49 | 0 | Fully Completed |  | 2009-08-31
Newell | Gravel for road | W Jensen St |  |  | 598.55 | 598.55 | Fully Completed | Street fund | 2010-05-10
Newell | White Rock for alleys | all alleys that needed white rock to fill holes |  |  | 560.53 | 0 | Fully Completed |  | 2009-08-31
Newhall | Purchase mower/snowblower for snowremoval in smaller locations | will be used all over town | 3869.78 | 4708.52 | 9216 | 3869.78 | Fully Completed | stimulas money and rut money | 2010-03-31
Newton | Resurfacing road and paving | W 9 St S, 800 Block to 1100 block | 68044.44 | 82792.35 | 210026.5 | 150836.79 | 50% or More Complete | I jobs money | 2010-10-15
Nichols | Repair and sealcoat portions of Adams St, Grand St, Broadway St, Main St and Short St. | City of Nichols | 1633.52 | 1987.57 | 1633.52 | 1633.52 | Fully Completed | Road Use Funds | 2010-09-23
| Repair and sealcoat streets | Portions of Adams St,Grand St, Broadway St, Main St, and Short St in the City of Nichols |  |  | 11074.03 | 1987.57 | Fully Completed | Road Use Fund | 2011-07-15
| Type B Seal Coat Work/Materials | Grand Ave. from Main St. to Adams St. and Short St from Ijem Ave. to Grand Ave. |  |  | 1633.52 | 1633.52 | Fully Completed | Road Use Fund | 2010-06-15
Nodaway | repair guttering and roof at community building | Nodaway community building nodaway iowa | 424.82 | 516.89 | 1633.52 | 424.82 | Fully Completed |  | 2009-06-01
Nora Springs | Asphalt resurfacing-Beginning at the eastern most city limits on Congress Street and west to the alley between N. Hawkeye Avenue and N. Boulder Avenue | Resurfaced East Congress Street-Beginning at city limits from the east side of Congress Street and completion at the alley just west of North/South Hawkeye Avenue.\ | 6691.32 | 8141.59 | 142030.19 | 6691.32 | Fully Completed | Local Option dollar, Tax Increment Finance dollars and I-Job funding | 2009-08-12
| Curb repairs in various locations | Along S. Quinby Ave.; on 2nd St. SE; on 4th St. NW; and along 3rd St. NE |  |  | 1632 | 3264 | Fully Completed | I-Job Funding | 2010-09-10
| Salt/Sand Purchase for FY 2010-11 winter | Coverage for entire community |  |  | 5000 | 759.59 | Fully Completed | IJOBS | 2011-04-15
| Used John Deere Lawn mower | For Parks and City Property |  |  | 10500 | 5750 | Fully Completed | IJOBS and Road Use funds | 2011-01-13
North Buena Vista | Road rock and use of skidloader for culvert and street resurfacing | 200 Block, Main Street | 324.3 | 394.59 | 450 | 324.3 | Fully Completed | I Jobs funding | 2008-07-12
North English | 2009 SEALCOAT WORK | 1. By Larson's on W. Clark St. 2. Corner of Lakeview and East St. 3. Woodland Dr. From Woodbine to Cement 4. North St. By Water Tower 5. Maple Lane House #423 6. L Avenue 7. Woodbine Dr. & Mai | 4328.39 | 5266.53 | 4328.39 | 4328.39 | Fully Completed |  | 2009-07-15
| 2010 TYPE B SEALCOAT WORK | 1. WASHINGTON ST. NORTHSIDE 2. NORTH STREET 3. LAKEVIEW ST. 4. EAST ST. 5. WOODBINE HS #125 & #130 6. REDWOOD AVENUE |  |  | 4328 | 4328 | Fully Completed | I-JOBS | 2010-06-04
North Liberty | Asphalt Paving on 230th STreet from Highway 965 to railroad | 230th Street - Highway 965 to railroad | 31574.12 | 38417.48 | 10230 | 5262.35 | Fully Completed | Future bond proceeds. | 2009-11-30
| Asphalt Paving on 230th Street from the railroad to lift station | 230th Street railroad to lift station |  |  | 32670 | 5262.35 | Fully Completed | Future bond proceeds. | 2009-11-30
| Base Repair and Double Sealcoat on Forevergreen Road from Jones Boulevard to West City Limit. Project had to be redone in FY11 due to issues with base. | Forevergreen Road - Jones Blvd to West City Limit |  |  | 54255.5 | 5262.35 | Fully Completed | Future bond proceeds & IJOBS revenues | 2010-08-24
| Mill & overlay on Dubuque Street | Dubuque Street |  |  | 53077.75 | 5262.35 | Fully Completed | Future bond proceeds | 2009-11-30
| Mill and overlay on North Front Street from Cherry Street to Penn Street | North Front Street - Cherry Street to Penn Street |  |  | 45613.75 | 5262.35 | Fully Completed | Future bond proceeds | 2009-11-30
| Milling of HMA and installation of HMA on Scales Bend Road. | Scales Bend Road from Highway 965 north to the northern city limits in North Liberty |  |  | 154402 | 34817.47 | Fully Completed | IJOBS and bond proceeds. | 2010-08-24
| Repair and sealcoat of West Penn Street - West of Herky to west City maintenance limits | West Penn Street - West of Herky to west City maintenance limits |  |  | 27804.3 | 5262.35 | Fully Completed | Future bond proceeds | 2009-11-30
North Washington | Dust control application on farm to market road. | 170th street | 243.57 | 296.36 | 637 | 243.57 | Fully Completed | city funds | 2010-08-15
| Repaired section of road and recoated. | Wapsie Street |  |  | 975 | 243.57 | Fully Completed | City funds | 2009-09-14
Northboro | Repair of Northboro City Streets | Various Locations | 197.06 | 239.77 | 1794.5 | 197.06 | Fully Completed |  | 2009-08-22
Northwood | MP41R12-ISCT Snowplow, MC7082 Hitch with MC6000 Quick Hitch and MC50 Thrust Arms | Lake Crystal, MN | 8953.79 | 10894.43 | 10920 | 10894.43 | Fully Completed | I-JOBS and General Fund/Streets/Equipment | 2010-11-30
| Vac and televised sewer lines; repaired entire manhole structure; installed new surface castings for access; cleaned box culvert going under Highway 65 S./10th Street S., all needed prior to IDOT project scheduled for FY10 | Highway 65 S./10th Street S. |  |  | 9047.13 | 8953.79 | Fully Completed | In addition to I-JOBS funding, sewer funds were also used on this project | 2009-09-04
Norwalk | repair dip in the intersection | High Road & Holly Drive | 36103.43 | 43928.47 | 0 | 0 | Not Started |  | 2010-05-31
Numa | Snow removal | Numa Streets | 332.36 | 404.39 | 1250 | 404.39 | Fully Completed | Road Use Tax | 2011-02-07
| Used toward purchase of gravel. | All streets in Numa received gravel. |  |  | 5338.27 | 332.36 | Fully Completed |  | 2009-08-01
Oakland | Asphalt resurfacing | Brown Street to Kelsay Ave, Alleyway between Elm Street and Walnut Street, Center Street from Vine to Linden, Patch on North Vine Street, Palmer Street, Alleyway between Fire Station and Congregationa | 6494.77 | 7902.45 | 122826.48 | 6494.77 | Fully Completed |  | 2009-08-10
| Grind and patch areas with hot asphalt in streets and crackfill | Oakland Avenue in front of Fire Station, intersection of Gates and Brown, intersection of Glass and Brown, Walnut Street, Pullen Avenue |  |  | 13325 | 7902.45 | Fully Completed | IJobs and Road Use Tax Funds | 2010-09-17
Oakland Acres | Curb, street patch, intake, driveway, backfill, and asphalt overlay. | Intersection of Oakridge Drive & Fore Seasons Drive. | 725.04 | 882.18 | 15699 | 725.04 | Fully Completed | Road Use Tax Fund | 2010-04-22
| Materials and labor for trimming trees along the road near the entrance. Purchase new barrier and street signs. | Entrance |  |  | 1035.55 | 882.18 | Fully Completed | Road Use Tax Fund | 2010-09-15
Oakville | reconstruction of alley adjacent to Community bldg/firestation in which a generator has been installed as Hazard Mitigation folllowing the flood of 2008. The project was leveliing, filling and rocking to road bed to provide access. | alley between Russell Street and 2nd Street in the 600 block of Oakville. | 1614.67 | 1964.63 | 6594.6 | 3579.3 | Fully Completed | IJobs and Road Use Tax funds | 2011-04-27
O'brien County | Bridge approaches and PCC Paving | B-40 between Polk Avenue and Redwing Avenue | 99623.96 | 123659.56 | 195140.75 | 123659.56 | Fully Completed | I-Jobs | 2010-11-29
| Seal Coat on M-12 from B-40 west, south to Hwy 10 | M-12 from B-40 west, south to Hwy 10 |  |  | 120232.36 | 99623.96 | Fully Completed | Federal I-Jobs | 2009-08-07
Ocheyedan | Sealcoating city streets in July of 2010. | East side of town | 2341.09 | 2848.5 | 30374.6 | 5189.59 | Fully Completed | Road Use Tax | 2010-07-14
Odebolt | ROADWAY REPAIR AND RESURFACING | 4TH STREET FROM WILLOW TO LOCUST TO PARK TO HWY 39 5TH STREET FROM PARK TO HWY 39 PATCH AREA ON N MAIN | 5035.96 | 6127.45 | 36823.8 | 5035.96 | Fully Completed | ROAD USE TAX FUND | 2009-07-29
| ROADWAY REPAIR AND RESURFACING | WALNUT STREET FROM 2ND TO 5TH AND ONE BLOCK ON 5TH STREET |  |  | 38988 | 0 | Fully Completed | ROAD USE TAX FUND AND IJOBS ROAD FUNDING | 2010-08-17
Oelwein | 2011 Ford Super Duty F-250 4 WD truck | 20 2nd Ave SW Oelwein, IA 50662 | 29228.67 | 35563.67 | 22393 | 22393 | Fully Completed | I Jobs | 2011-06-14
| 3rd street and 3rd avenue NE intersection 42 well storm sewer replacement | 3rd street and 3rd avenue NE |  |  | 609.34 | 609.34 | Fully Completed | I jobs | 2010-09-06
| intersection of lst street and 3rd avenue SE, Curb,handicap ramp, sidewalk and gutter repair to improve drainage and meet new elevations. | intersection 1st street and 3rd avenue SE, Oelwein |  |  | 9929 | 9929 | Fully Completed | I-Jobs money | 2010-06-30
| John Deere 310 SG | 20 2nd Ave SW Oelwein, IA 50662 |  |  | 28000 | 56000 | Fully Completed | IJobs funds and local trade | 2012-03-09
| Model CPM8 Gas powered Concrete Scarifier 78 New Tungsten Stars for CPM-8 | 20 2nd Ave SW, Oelwein, IA 50662 |  |  | 3861 | 3861 | Fully Completed | I Jobs funds | 2012-04-10
| to be determined at a later date | 20 2nd Ave SW |  |  | 0 | 0 | Fully Completed | I Jobs Street | 2011-12-30
| To Be Determined at a Later Date. | Oelwein |  |  | 0 | 0 | Fully Completed | IJobs | 2011-12-31
Ogden | Full-depth patching | West Chestnut, West Cherry, West Elm, NE 3rd, SW 5th, SW 8th, Haw's Circle | 8835.86 | 10750.94 | 8835.86 | 8835.86 | Fully Completed |  | 2009-08-21
| Widened South 1st Street from Walnut to Veteran's Dr | S. 1st St from Walnut to Veteran's Dr. |  |  | 10750.94 | 10750.94 | Fully Completed | I-Jobs | 2010-08-18
Okoboji | Garbage truck and sweeper repair | Spirit Lake, Iowa | 3581.52 | 4357.77 | 1141.19 | 1141.19 | Fully Completed | I-JOBS | 2009-09-20
| Repair and replacement of storm sewer pipe, erosion control measures due to failure of pipe from street water | 2509 Lakeshore Drive Okoboji, Iowa 51355 |  |  | 4357.77 | 4357.77 | Fully Completed | I Jobs | 2011-06-01
| To be determined, funds have not been spent for projects at this time and date | To be determined |  |  | 0 | 0 | Not Started | I Jobs | 2011-03-31
| To be determined,Funds have not been spent for projects as this time and date | To be determined |  |  | 0 | 0 | Not Started | I JOBS | 2010-12-31
| Traffic cones, sign posts | Omaha, NE |  |  | 2158.33 | 2158.33 | Fully Completed | I-JOBS | 2009-07-15
| Vehicle and truck parts, wipers blades, battery & Miscellaneous | Spirit Lake, Iowa |  |  | 441.16 | 282 | Fully Completed | I-JOBS | 2009-08-25
Olds | The city has not yet spent this money. | Olds, IA | 1087.56 | 1323.27 | 2410.83 | 0 | Fully Completed | I-Jobs | 2010-03-01
Ollie | snow removal | all city streets | 600.49 | 730.64 | 2500 | 0 | Not Started |  | 2010-03-15
Onawa | Iowa Avenue Redesign -- engineering services to redisign State HWY 175 through Onawa. | Onawa, Iowa | 13500.57 | 16426.67 | 45000 | 1243.83 | Less than 50% Complete | IJOBS funds of $29,951. | 2012-12-01
Onslow | Maintenance of city streets by contractor to include seal coat and patch. | Summit Street, 3rd Street, 2nd Street, 1st Street, Church Street, North Street, Pine Street. | 800.47 | 973.96 | 10083.4 | 800.47 | Fully Completed |  | 2009-08-31
Orange City | Remove five blocks of asphalt and replace with concrete. We are also replacing the water line and all water services along the street. We are also placing new street light bases and fixtures along the downtown street. | The 2009 street project runs along central Ave for four blocks and one block along first and central running east towards Albany Ave. | 24411.09 | 29701.94 | 1400000 | 54113.03 | Fully Completed | General Obligation Bonds | 2010-03-01
Orchard | Repairing Pump House | City of Orchard | 237.4 | 288.85 | 500 | 237.4 | Fully Completed |  | 2009-11-10
| Scrapping & painting the City Hall | Bank Street, Orchard, IA 50460 |  |  | 300 | 0 | Not Started | City $300.00 | 2010-06-28
| Well Casings Reapirs at Pump House | Pump Staition, Orchard, IA 50460 |  |  | 3486 | 0 | Fully Completed | City Of Orchard $3486.00 | 2009-11-10
Orient | SEALCOATING OF CITY STREETS - I-JOBS funding assisted in paying for this street project. Total cost - $7,079 | East 2nd & Batie Streets | 1458.63 | 1774.77 | 7079 | 1458.63 | Fully Completed | Street Surface Maint/Drainage Fund | 2009-07-13
Orleans | Engineering fees for reconstruction of 140th Street | 140th Street from Hill Avenue to Peoria Avenue | 2738.55 | 3332.1 | 22750 | 6070.65 | 50% or More Complete | I-jobs funds and general funds | 2010-10-31
| Engineering fees for reconstruction of 140th Street | 140th Street from Hill Avenue to Peoria Avenue |  |  | 45000 | 6070.65 | 50% or More Complete | I-jobs funds and general funds | 2010-10-31
Osage | Cherry Street improvements, widen to platted width, improve road surface and drainage. | Cherry Street | 15120.99 | 18398.3 | 0 | 0 | Not Started | Combination of I-Jobs, RUT and Street Improvements Reserve Fund | 2011-08-31
| Seal Coat several streets | Primarily 3rd Ward |  |  | 18000 | 15120.99 | Fully Completed | IJOBS | 2009-11-01
Osceola | STREET IMPROVEMENTS 2009/2010 | CLARKE STREET, SOUTH RIDGE ROAD, LAKE STREET, W. CASS, JEFFERSON STREET | 20349.13 | 24759.59 | 1769990.34 | 45108.72 | Fully Completed | general obligation bonds | 2010-10-01
Osceola County | crushing of gravel at pit | Leinen Pit | 73096.28 | 90646.35 | 57350 | 45259.28 | Fully Completed | Secondary Road Fund | 2009-11-05
| joint repair and crack sealing | various |  |  | 100000 | 90646.35 | Fully Completed | Osceola County | 2010-10-15
| Pavement Striping | various locations |  |  | 28000 | 27837 | Fully Completed |  | 2009-08-21
Oskaloosa | 2011 Elgin Pelican Sweeper with 5 year/5,000 hour extended warranty for JD Engine. | For use on all Oskaloosa Municipal Streets | 48206.34 | 58654.55 | 157019 | 45759 | Fully Completed | I-Jobs for $45,758.68 and Storm Water Utility Fund for $110,709.53. | 2011-04-15
| Construct 25 feet long concrete payment at westbound approach leg. | 4th Avenue E/Market Street |  |  | 3181.61 | 3181.61 | Fully Completed | I-Jobs | 2010-11-01
| Construct 60 feet long concrete pavement at westbound approach leg. | 3rd Ave E/Market Street |  |  | 4764.6 | 4764.6 | Fully Completed | I-Jobs | 2010-10-21
| Mix salt/sand, haul sand, prepare/spread brine, spread salt/sand | City streets in Oskaloosa |  |  | 44100 | 27498.15 | Fully Completed | I-Job funds purchased the materials and street employee hours were paid through road use funds. | 2010-07-30
| Professional services to design 2010 Street Rehabilitation Project (Iowa 432 & C Avenue West) | Oskaloosa-Iowa 432 & C Avenue West |  |  | 3985.9 | 0 | Fully Completed | I-Jobs Funding | 2010-01-31
| Seal Coat Maintenance for 2010 Process is to sweep the street clean, patch holes and apply HFE-90 liquid asphalt and cover with a washed chip rock. | J Avenue, North Park & South Park |  |  | 35241.75 | 20707.85 | Fully Completed | I-Jobs for $20,707.85 and road use funds for $14,533.90 | 2010-06-30
| Used, pusher plow, Bonnell LDP-5100-16FB, new rubber cutting edge, 16 feet long x 48 inches tall, flat back with bucket hook-up, painted new cat yellow, excellent paint. | Used for city streets and parking lots in Oskaloosa, Iowa. |  |  | 4950 | 4950 | Fully Completed | I-Jobs | 2010-12-03
Ossian | Ashphalt Resurfacing was done to both streets. Previously they were tar and chipped | Hill Street and Kuhn Drive | 3725.65 | 4533.15 | 29321.5 | 4533.15 | Fully Completed | I-Jobs and Road Use Tax | 2010-07-30
| Asphalt resurfacing. | Kuhn Drive and Hill Street |  |  | 29321.5 | 3725.65 | Fully Completed |  | 2009-08-17
Otho | MILL AND LEVEL UP DIPS THEN OVERLAY WITH 3" OF ASPHALT ON AREA 975' BY 21' | SCHOOL STREET FROM HIGHWAY STREET GOING EAST | 2493.96 | 3034.5 | 46320 | 5528.46 | Fully Completed | ROAD USE TAX LOCAL OPTIONS SALES TAX IJOBS | 2010-07-02
Oto | To Be Determined | To Be Determined | 586.75 | 713.92 | 0 | 0 | Not Started | I-JObs | 2012-05-01
Ottosen | 14.64 ton Class A road stone | 1st street from Highway C20 to Wehrspann Ave. | 158.69 | 193.09 | 220.33 | 158.69 | Fully Completed | IJOBS | 2009-09-02
| 15.10 ton Class A rock 14.99 ton Class A rock 8.22 ton 3/8 W Chip | 1st Street from Highway C20 to Wehrspann Ave and various bad spots where town roads needed repairing |  |  | 633.41 | 193.09 | Fully Completed | IJOBS and remaining coming from the City Funds | 2010-09-28
Ottumwa | Asphalt Resurfacing on Ferry Street from Finley to Mary Street | Ferry Street from Finley to Mary Street | 109183.84 | 132848.27 | 1086707 | 242032 | Fully Completed | IJOBS and Bond Debt from CIP Funding | 2011-04-30
Oxford Junction | Asphalt paving of railroad crossing-1500 sq ft | 1st Ave S Near Hwy X-64 | 2502.69 | 3045.13 | 6345 | 5547.82 | Fully Completed | I-Jobs money and City funds | 2010-08-13
Oyens | seal city streets | Lincoln St | 453 | 551.17 | 1991.08 | 0 | Fully Completed | Road Use Tax Fund | 2009-09-16
| Seal cracks in city streets with tar | Oyens Ia |  |  | 1991 | 453 | Fully Completed |  | 2009-09-16
Packwood | culvert & storm drain repair | West 1st St. | 604.47 | 735.48 | 750 | 604.47 | Fully Completed | RUTF | 2009-09-30
Page County | Base Stabilization, Asphalt prime coat & Single seal coat | Various locations(332St,212Place,J-55,M-60&M-56) | 95847.88 | 116381.61 | 106823.4 | 95847.88 | Fully Completed | Secondary Road Fund | 2009-09-28
| Granular Surfacing of 28.75 miles of Secondary Roads | Various locations within Page County |  |  | 124631.25 | 0 | Fully Completed | Secondary Road Fund | 2010-08-17
| Granular Surfacing of 28.75 miles of Secondary Roads | Various Locations |  |  | 124676.33 | 116381.61 | Fully Completed | Secondary Road Fund | 2010-08-17
Palmer | Installed new driveway and culvert for an expanding bussiness in town off of our City Street | Palmer, IA | 531.91 | 647.2 | 1604 | 531 | Fully Completed | $531.91 I-Job money and $1,072.15 City RUT money Total project $1,604.06 | 2009-11-12
| Maintain alleys, resurface a couple streets, repair a corner cut down the hump and level it out | Palmer Iowa |  |  | 20000 | 0 | Fully Completed | I job money ($647.20) and RUT money ($9379.80, and general fund money ($10,000.00) | 2012-06-12
Palo Alto County | mining and crushing of gravel for road surfacing | 3 miles North of Cylinder in Section 18 of Fairfield Township (T96N, R31W) | 89474.35 | 109158.14 | 164095.53 | 109158.14 | Fully Completed | local funds | 2010-11-19
| Rehabilitation of existing high truss bridge. | Over West Branch of the Des Moines River in Section 21 of Nevada Township, Palo Alto County, Iowa |  |  | 265153 | 178948.7 | Fully Completed | local funds | 2010-11-01
Panama | FY2009 - Grading and Rock for preparation for Paving in FY2010 | South 4th Street | 925.95 | 1126.64 | 1207.74 | 2052.58 | Less than 50% Complete | RIIF - $672.80 ARRA Block Grant - $253.15 Street Construction - $281.79 | 2009-04-30
| FY2010 - Paving of South 4th Street | South 4th Street, Panama, IA |  |  | 5000 | 0 | Not Started | RIIF ARRA Block Grant Street Construction TIFF | 2010-06-30
Panora | Repairing and adding to existing culverts. | City of Panora | 5132.05 | 6244.37 | 2500 | 2382.26 | Fully Completed | I Jobs Money-Road Use Money | 2010-08-02
| Street Patching/seal coat | city streets |  |  | 21000 | 3540.56 | Fully Completed | I Jobs and Road use funds | 2011-09-01
| Street patching/seal coat | Panora Streets |  |  | 25000 | 10907.2 | Fully Completed | Road use money and I job money | 2010-09-06
Parkersburg | DESGINING, ENGINEERING, AND PLANNING FOR THE CONSTRUCTION OF STORM SEWER PROJECT IN JOHNSON HEIGHTS, INSTALLING A NEW CULVERT ON WEMPLE STREET, WITH ROADWAY RESURFACING. | JOHNSON HEIGHTS ADDITION, PARKERSBURG | 8250.59 | 10038.82 | 11828 | 10038.82 | Fully Completed | IOWA ECONOMIC EMERGENCY FUND | 2011-06-30
| DESIGNING, ENGINEERING, AND PLANNING FOR THE CONSTRUCTION OF STORM SEWER PROJECT IN JOHNSON HEIGHTS, INSTALLING NEW CULVERT ON WEMPLE STREET, AND STORM SEWER AND RETETION BASIN IN PARKERSBURG INDUSTRIAL PARK. | JOHNSON HEIGHTS ADDITION FROM NORTH JOHNSON STREET TO EASTVIEW DRIVE, WEMPLE STREET FROM NORTH JOHNSON ROAD TO BROOKSIDE DRIVE, PARKERSBURG INDUSTRIAL PARK |  |  | 24598 | 8250.59 | Fully Completed | IOWA ECONOMIC EMERGENCY FUND | 2010-06-30
Paton | Asphalt Street Repair. | 1. South end of South Wise Street 2. South Main Street 3. 508 South Wise Street 4. 516 South Park Street 5. South end of South Park Street 6. North Main Street | 946.21 | 1151.29 | 5100 | 0 | Fully Completed | Road use tax fund. | 2009-10-29
| Re-paving of Main Street | Main Street from E18 South to Tallman Street |  |  | 20000 | 0 | Not Started | Road Use Tax Funds. No Vendor Estimate received as of this date (3-30-2012) | 2012-05-31
| Use of Road Tax not yet determined. | Paton |  |  | 0 | 0 | Not Started | Road Use Tax Fund | 2011-06-30
Patterson | Snow removal for City streets | Patterson | 431.19 | 524.64 | 431.19 | 431.19 | Fully Completed | I-Jobs money and Raod use tax | 2010-02-25
| street maintenances | Patterson |  |  | 324.64 | 324.64 | Fully Completed | IJobs | 2011-05-31
| Street repair and sealcoating | Patterson |  |  | 200 | 200 | Fully Completed | IJOBS | 2011-06-30
Paullina | Cemented a cul de sac on the north end of Mickley Street. | North Mickley Street in 400 block. | 4909.3 | 5973.34 | 83600 | 4909.3 | Fully Completed | City is funding the project with Road Use Tax Funds and I-jobs Funding. $4909.30 - I-Jobs, $47280.50 Special Assessment and balance paid by Road Use Tax Fund. | 2009-09-18
| Plans to tear out Maple Street and replace it with a new concrete street with new curb and gutter.Have received Federal Funding for 2014. Currently we are tearing out the bad sections and replacing it with cement patches. | North and South Maple Street |  |  | 1170000 | 488 | Less than 50% Complete | G.O. Bonds and I- Jobs, CDBG, Special assessment, Federal Funding | 2011-06-30
| Plans to tear out Maple Street and replace it with a new concrete street with new curb and gutter.Have received Federal Funding for 2014. Currently we are tearing out the bad sections and replacing it with cement patches. | North and South Maple Street |  |  | 11700000 | 488 | Less than 50% Complete | G.O. Bonds and I- Jobs, CDBG, Special assessment, Federal Funding | 2011-06-30
Pella | Engineering Design Services - North Main Reconstruction | North Main from Washington Street to Elm Street | 43279.57 | 52659.95 | 99500 | 95939.52 | Fully Completed | I-Jobs, STP and Local | 2010-06-30
Peosta | Install storm sewer and widen shoulders | 8558 to 8760 Kapp Drive | 4594.82 | 5590.7 | 32700 | 4594.82 | Fully Completed | Road Use Tax | 2009-10-15
| Remove and replace concrete street panels | Enterprise Drive and Kapp Drive |  |  | 6500 | 5590.7 | Fully Completed | IJobs | 2010-10-25
Perry | Reconstruction of 26th Street including 3,700 CY of Excavation, Storm Sewer, Subgrade Preparation, Granular Subbase, 2,300 SY of 8" P.C.C. Paving, erosion control and seeding. | 26th Street, Iowa Street to 790 feet North, Perry, Iowa | 33338.68 | 40564.48 | 250185.2 | 33338.68 | Fully Completed | IJOBS, RISE Grant, TIF Funds | 2010-05-10
| Roadway extension of Southgate Drive into commercially zoned area to allow for access to new recreational trail and future site development. | Southgate Drive, south of Highway 141 |  |  | 47783 | 40564.48 | Fully Completed | I-Jobs, Local Option Sales Tax | 2010-12-31
Persia | Installed curbing | East side of south end of first block of Second Street,located between First Avenue and Second Avenue. | 1311.16 | 1595.33 | 0 | 0 | Fully Completed | I-Jobs - $1,311.16 RUTA Funds - 1806.34 | 2009-06-16
| Street wideing and Curb installation | 3rd St. & Main |  |  | 5000 | 1595.33 | Fully Completed | Ijob-1595.33 RUTA 3208.84 | 2010-11-15
Peterson | Hot Patching City Streets Single Seal-Coating Streets | East & West City Streets | 1410.12 | 1715.74 | 16000 | 3125.86 | Fully Completed | Road Use Tax | 2010-07-01
Pierson | man hole rehabilitation | intersection of main and front street intersections of main and 4th street | 1291.32 |  | 2000 | 1291.32 | Fully Completed |  | 2009-08-30
| Man Hole Rehabilitation repair man holes and repour concrete to grade. | Lower 4th Street Second Street by 200 Main |  |  | 1571.2 | 1571.2 | Fully Completed | i-jobs | 2010-08-30
Pilot Mound | Mowing roadways & Haul gravel and spread in alley's & drives spraying weeds in road ways. | City of Pilot Mound | 596.42 | 725.69 | 270 | 270 | Fully Completed | I-JOBS | 2010-09-06
| Purchase stop signs and posts. | City of Pilot Mound |  |  | 733.18 | 596.42 | Fully Completed | IJobs funding | 2010-12-31
| Tractor Repair - Replace Injector Pump | Repaired at City Shed |  |  | 1281.07 | 455.69 | Fully Completed | I-Jobs | 2010-10-21
Pisgah | Rock and hauling alley way. | Between Pine and Oak Street | 1014.36 | 1234.21 | 1062 | 1014.36 | Fully Completed | General Fund | 2009-11-07
| super patch/ rock | Jaclson St. between Ideal Ave and 2nd St. super patch 2nd St. rock pot holes |  |  | 1435.85 | 1234.21 | Fully Completed | general fund | 2011-09-09
Plainfield | Asphalt resurfacing with a single sealcoat | Plainfield | 1913.05 | 2327.69 | 20000 | 4240.74 | Fully Completed | IJOBS and City funds | 2010-06-02
| Asphalt resurfacing with a single sealcoat | The exact streets to be resurfaced have not been determined yet. |  |  | 20000 | 0 | Fully Completed | Road Use Tax Fund | 2010-06-02
Plano | Repair and Maintenance to City Streets from snow and freezing and thawing | Plano City Streets | 186.43 | 226.83 | 226 | 226 | Fully Completed | I Jobs | 2011-02-14
| REPLACED A CULVERT IN A STREET | 4TH AND WAKEFIELD |  |  | 1054 | 186.43 | Fully Completed |  | 2009-08-10
Pleasant Hill | Coreout and replace asphalt, clean ditches and reestablish drainage. The City of Pleasant Hill purchased 50% of asphalt mix, participating with Polk County. | South Shadyview Blvd. Pleasant Hill, Iowa | 30403.58 | 36993.23 | 9018.97 | 9018.97 | Fully Completed | I-Jobs Funds | 2010-07-15
| Street Maintenance and/or construction | City of Pleasant Hill |  |  | 58377.84 | 30404 | 50% or More Complete | I-JOBS Funds | 2012-06-30
Plymouth | Core rock out of sink hole patch area and haul away. Compact subbase and furnish and install 6" asphalt patch. | West of city hall on Main Street bridge deck. | 1253.59 | 1525.3 | 2000 | 1253.59 | Fully Completed | $746.41 Road Use Funds $1,253.59 I-Jobs Funds | 2009-10-16
| Resurface asphalt street and raise manholes | Grove Street from Main Street south to South Street |  |  | 29241.1 | 1525.3 | Fully Completed | I-Jobs and Road Use Tax Funds | 2010-07-19
Plymouth County | REMOVE A 15'X20'WOODBRIDGE AND INSTALL A 12'X7'X46' PRECAST CONCRETE BOX CULVERT | ON 240TH ST. NEAR THE N1/4 CORNER OF SECTION 26, T-91N, R-44W OF UNION TOWNSHIP | 167617.58 | 203424.08 | 78933 | 30119.85 | Fully Completed | SECONDARY ROAD FUND HUNGRY CANYONS ALLIANCE NRCS | 2010-11-18
| REMOVE A 20'X20' WOOD BRIDGE AND INSTALL A 84"X64' CORRUGATED METAL PIPE | ON 240TH ST. NEAR THE N1/4 CORNER OF SECTION 13, T-90N, R-44W, UNION TOWNSHIP |  |  | 45738.45 | 37638.45 | Fully Completed | SECONDARY ROAD FUNDS HUNGRY CANYONS ALLIANCE | 2010-09-16
| remove a 79' x 20' i-beam bridge and replace with a 130' x 30' continuous concrete slab bridge | on Noble Ave. sec. 31, T-93N, R-44W, Fredonia Twp. |  |  | 367344.6 | 59507.25 | Fully Completed | Federal I-Jobs Federal Bridge Replacement Funds | 2011-08-19
| REMOVE EXISTING WOOD BRIDGE AND INSTALL A 59'X30' CONTINUOUS STEEL BEAM BRIDGE | NEAR THE NE CORNER OF SECTION 21, T-93N, R-45W, ELGIN TOWNSHIP |  |  | 146096.8 | 146096.8 | Fully Completed | SECONDARY ROAD FUND | 2010-11-09
| Replacement of existing wooden bridge with a concrete slab bridge | North of Section 4 Lincoln Twp on 280th St . |  |  | 229906.53 | 45981.31 | Fully Completed | Federal I-Jobs Federal Bridge Replacement Funds | 2010-07-30
| RESTOCK COUNTY SUPPLY OF VARIOUS CORRUGATED METAL PIPE | LE MARS COUNTY YARD |  |  | 51698 | 51698 | Fully Completed | SECONDARY ROAD FUND | 2011-03-30
Pocahontas | -We will be using the I-Jobs funds to do road construction in fiscal year 2010. The proposed start date is tentativley May 2010. | City of Pocahontas | 8604.38 | 10469.28 | 8604.38 | 0 | Less than 50% Complete | -We will be using the I-Jobs grant along with funds from our Road Use Taxes | 2010-05-31
Pocahontas County | Clean out and tie separated concrete culverts. Also pressure grout voids over and around these culverts. Grout rip rap at five locations and slab jack two bridge approaches | Various locations in County | 98259.31 | 118229.68 | 75293.3 | 75293.3 | Fully Completed | Secondary Roads Fund | 2009-11-02
| Replace timber box culvert with 78" CMP | Lincoln 16/17 |  |  | 18055.35 | 20593.2 | Fully Completed | Secondary Roads Fund | 2011-08-04
| Replace timber box culvert with 84" CMP | Lincoln 21/28 |  |  | 20494.22 | 1956.19 | Fully Completed | Secondary Roads Fund | 2011-08-04
| Replace timber box culvert with triple 72" CMP | Cummins 20/29 |  |  | 41352.6 | 52878.48 | Fully Completed | Secondary Roads Fund | 2011-07-15
| Replace timber box culvert with twin 42" CMP | Powhatan 1/12 |  |  | 5632.06 | 5632.06 | Fully Completed | Secondary Roads Fund | 2011-05-17
| Temporary employees hired to assist clearing roads of snow and ice. Also includes County equipment cost. | Countywide |  |  | 7857.4 | 7857.4 | Fully Completed | Secondary Roads Fund | 2012-02-24
| Temporary employees hired to assist clearing roads of snow and ice. Also includes County equipment cost. | Countywide |  |  | 29312.35 | 29312.35 | Fully Completed | Secondary Roads Fund | 2011-03-10
| Temporary employees hired to assist clearing roads of snow and ice. Also includes County equipment time at IDOT rental rates. | Whole County |  |  | 121828 | 22966.01 | Fully Completed | Secondary Roads Fund | 2010-03-04
Polk County | HOT MIX ASPHALT RESURFACING 5.42 MILES | SE 6 AVE/SE 124 ST AND SE 40 AVE | 177616.27 | 211287.78 | 784000 | 388904.05 | Fully Completed | IJOBS FUNDING AND LOCAL SECONDARY ROAD FUNDS | 2010-07-27
Pomeroy | Purchase new street signs | in city limits | 3101.07 | 3773.19 | 0 | 0 | Not Started | Remainder of I-Jobs money the rest from RUT Funds | 2011-06-30
| Purchase new street signs | in city limits |  |  | 2000 | 0 | Not Started | Remainder of I-Jobs money the rest from RUT Funds | 2011-06-30
| Purshase 97 Ford F-250 for plowing street corners and alleys in town | Pomeroy |  |  | 6000 | 5285 | Fully Completed | I-Jobs for 5285.00 | 2010-12-14
| Replace street and sidewalk from intake repair | 115 Main St, 313 S East St, and 415 Cayuga St. |  |  | 4500 | 4378.52 | Fully Completed | I-Jobs and RUT | 2011-12-31
Popejoy | Alliant bill for Street Lights | City of Popejoy | 217.6 | 264.77 | 274.76 | 217.6 | Fully Completed | I-jobs & RUT money | 2009-12-07
| Alliant Energy - Street Lights | Street Lights |  |  | 264.77 | 264.77 | Fully Completed | Rut & I-jobs funds | 2011-08-10
| Street Lights/ Alliant Energy | Popejoy Street Lights |  |  | 271.23 | 0 | Fully Completed | RUT & I-JOBS | 2011-08-23
Portsmouth | Resurfaced 2nd St. from 4th Ave. to 5th Ave. | 2nd Street on North side of city limits. | 773.72 | 941.41 | 50000 | 773.72 | Fully Completed | CITY FUNDS | 2009-09-21
Postville | Project will be improvement to West Alley | Postville Iowa | 9927.79 | 12079.53 | 100000 | 22007.32 | 50% or More Complete | I-Jobs RUT Funds and LOST Dollars | 2010-09-30
Pottawattamie County | Project Rock for various roads in Pott Co. | Various Gravel Roads in Pott Co. | 187947.3 | 235054.16 | 900000 | 235054.16 | Fully Completed | Pottawattamie County | 2010-09-16
| Rock purchased to use on various county roads. | Various county roads. |  |  | 125000 | 121000 | Fully Completed | Pott county Fund 20 | 2009-09-24
| Rock purchased to use on various county roads. | Various roads in the county |  |  | 75000 | 66947.3 | Fully Completed | Pottawattamie County | 2009-10-30
Poweshiek County | Winter operations, including labor & materials for snow & ice removal | Countywide | 94967.05 | 116570.43 | 330838.28 | 116570.43 | Fully Completed | I-Jobs and operational funds | 2012-03-31
| Winter Operations, including labor & materials for snow & ice removal. | County-wide |  |  | 469496.49 | 94967.05 | Fully Completed | General Operational (Local) Funds | 2010-03-31
Prairie City | Additional maps from GIS project #111-2 | City wide - City of Prairie City | 5961.91 | 7254.1 | 2000 | 841.75 | Fully Completed | I-jobs | 2011-06-30
| Additional street seal coat and repair. | N Dewey to East Jefferson |  |  | 28612.31 | 3942.76 | Fully Completed | Roade Use & IJOBs | 2011-07-22
| Geographic Information Systems support street condition survey and pavement analysis. Database would be created based on industry standards and city's specific requirments. | Prairie City |  |  | 10000 | 8431.5 | Fully Completed | Water and Sewer Funds | 2011-03-31
Prairieburg | City street repair. | 1. 306 East Main Street 2. North Maple Avenue 3. 305 West Main; 500 West Main; 513 West Main 4. Parsons Street at West Avenue & Locust Avenue 5. 210 Boulder Street & West Avenue by Hakes Street 6 | 490.79 | 597.16 | 6964 | 1087 | Fully Completed | Road Use Fund (I-JOBS Money deposited to this fund.) | 2010-08-26
Prescott | gravel for streets | Prescott Streets 7th Avenue | 1031.71 | 1255.32 | 5000 | 1031.71 | Fully Completed |  | 2009-06-30
Primghar | Cobblestone town square reconstruction design services. | Rock Rapids | 3891.62 | 4735.09 | 190700 | 3891.62 | Less than 50% Complete | I-Jobs | 2010-07-12
| To Be Determined | To Be Determined |  |  | 0 | 0 | Not Started | I-Jobs | 2011-06-30
Princeton | Design and plan 3 inch overlay on Lost Grove Road. | Lost Grove Road west from Highway 67 | 4131.85 | 5027.38 | 23000 | 4131.85 | Fully Completed | RPA/MPO Recovery Act | 2010-01-21
Promise City | Repair streets following installation of sewer lines | North Center Street, Depot Street east, South Center Street, | 431.5 | 525.02 | 3000 | 0 | Not Started | I-Jobs funding, Road Use Taxes | 2011-05-31
Protivin | For supplies and maintenance of the city streets | The streets in Protivin | 976 | 1187.54 | 1187.54 | 1187.54 | Fully Completed | I Jobs total of $1187.54 | 2011-03-31
| For the supplies and maintenance of the city streets | The streets in Protivin |  |  | 1106.25 | 976 | Fully Completed | I Jobs total of 976.00 | 2010-05-31
Quasqueton | Filling of cracks on Water Street (an asphalt street) | Water Street from Locust to Linn Streets. Approximately 7580 linear feet | 2507.06 | 3050.44 | 4650 | 2052 | Fully Completed | I-Jobs | 2009-08-06
| Single Seal and cold patch of Street | Spruce Street starting at Fourth Street and going 95' east |  |  | 456.95 | 455.06 | Fully Completed | I-Jobs and Road Use funds | 2010-06-11
| Spring repair of street in Quasqueton, Iowa. | Dubuque and Walnut Streets |  |  | 3050.44 | 3050.44 | Fully Completed | IJOBS AND RUT | 2011-07-29
Quimby | Form and pour concrete pads in front of city mainenance buildings. | 101 West 1st Avenue, Quimby, IA | 1346.07 | 1637.81 | 1637.81 | 1637.81 | Fully Completed | I-JOBS and Road Use Tax funds | 2010-06-21
| Purchase a new furnace for city garage building | city garage building at 101 W 1st Ave. |  |  | 3147 | 1346.07 | Fully Completed | I-JOBS and Road Use Tax funds | 2009-09-23
Radcliffe | Repair on Isabella Street | Radcliffe, IA | 2651.2 | 3225.81 | 52787 | 2651.2 | Fully Completed | Road Use tax money and I-Jobs road funding | 2009-10-01
| Repair on Minnie Street in Radcliffe, Iowa. | Minnie Street |  |  | 49997.25 | 3225.81 | Fully Completed | Road Use Money and I-Jobs Road Funding | 2010-08-04
Rake | Excavate frost bite areas. Furnish and place subgrade fabic, rock and aspalt. 1054 additional sq ft. Total sq. ft. 12,875 - Material and Labor | Block west of Main 1st Street SW 4800 sq ft Florence Steet West End 1465 sq ft 1st Street SE 5200 sq ft 2nd Street NE 400 sq ft 2nd Street NE 2450 sq ft 2nd Street NE 4080 sq ft | 612.04 | 744.7 | 36213 | 1356.74 | Fully Completed | State Savings Bank, Rake IA 50465 1-641-566-3321 | 2010-07-13
Ralston | not determined at this time | undetermined | 105.59 | 128.48 | 283.89 | 234.07 | Fully Completed | IJOBS AND RUT FUNDING | 2010-08-01
Randalia | resurface and repair asphalt road | 1 block each Oak st, N 2nd street, Bank street | 191.32 | 232.79 | 423.79 | 0 | Fully Completed | federal I jobs | 2010-04-28
Randall | repair or replace tile to drain corner of Main Street and First Street. | SE corner of Main and First Street | 364.91 | 444 | 1500 | 364.91 | Fully Completed |  | 2009-08-14
| Snow removal on city streets during winter season | City of Randall |  |  | 3401.88 | 440 | Fully Completed | IJOBS | 2011-01-31
Randolph | Resurfacing the east and west streets in Randolph | From B Street to H Street | 892.02 | 1085.36 | 23636.6 | 1977.38 | Fully Completed | General Fund | 2010-07-16
Rathbun | Replaced culvert for proper drainage of street ditch | Elm St. | 265.13 | 322.59 | 300 | 265.13 | Fully Completed | Ijobs | 2009-08-20
Readlyn | Crack fill City Streets - repairs to City Streets | Within Corp. limits of Readyln | 3433.01 | 4177.08 | 6997.4 | 4177.08 | Fully Completed | I-Jobs Road Use Tax | 2010-08-12
| Crack filling city streets within city limits of Readlyn, Iowa. | Readlyn, Iowa |  |  | 6691.44 | 3433.01 | Fully Completed | IJOBS funding and Road Use Tax money. | 2009-09-04
Reasnor | 3" asphalt patching on misc. streets as needed. | 3 patches on Main Street 1 patch on West St. Light surface patching | 393.74 | 479.08 | 7260 | 393.74 | Fully Completed | Road Use Tax Fund and I-Jobs fund | 2009-08-27
| Patching 15 tons patch in place/compacted - edges, low areas | 2nd, 3rd, Broad and East Streets |  |  | 17989.05 | 479.08 | Fully Completed | Street Fund and I-Jobs fund | 2011-10-06
Red Oak | a 2012 model 544k Wheel Loader at $114,410.00 has been ordered - awaiting delivery | Red Oak City | 27066.65 | 32933.06 | 114410 | 0 | Less than 50% Complete | I-jobs and city monies | 2012-08-15
| Highland/Coolbaugh Bridge and railing | intersection of Highland and Coolbaugh streets |  |  | 17600 | 35200 | Fully Completed | have not finalized out the railing part of the project - DOT project and city funds - PROJECT HAS BEEN FINALIZED | 2010-05-01
Redding | Rip up and replace gravel on Fourth Street to get rid of pot holes | Redding Ia | 267.04 | 324.92 | 1200 | 0 | Less than 50% Complete | State of Ia | 2009-12-31
Redfield | Street repairs to River-to-River Rd. | City of Redfield | 3638.3 | 4426.86 | 10000 | 8065.16 | Fully Completed | street monies | 2010-09-30
Reinbeck | Reline manholes and replace one flush pot with manhole | 500 block of Pine Street | 7647.85 | 9305.44 | 8800 | 8650 | Fully Completed | I-jobs money and RUT | 2010-10-19
| Repair curb and gutter along highway 175 | Highway 175 Reinbeck, iowa |  |  | 19164.6 | 7647.85 | Fully Completed | Road Use Tax | 2009-10-29
| repair manhole and intake | Main and Blackhawk and 122 Park |  |  | 3600 | 1310.88 | Fully Completed | I-Jobs | 2011-09-08
| replace bad sewer line on Pine Street, replace Manhole and reconnect main to service line. Replace orange from main to back of curb | 500 block of Pine Street |  |  | 33000 | 0 | Fully Completed | I-jobs, wastewater fund and RUT | 2010-10-19
Rembrandt | to be determined not yet started | within city limits | 795.89 | 968.38 | 0 | 0 | <not selected> |  | 2010-06-30
Remsen | The City of Remsen's IJOBS allocation will more than likely be used to either overlay a portion of the street or repair street cracks. | City of Remsen | 7695.89 | 9363.89 | 20000 | 16725.64 | Less than 50% Complete | Road Use Tax Fund | 2010-09-01
Renwick | Asphalt Hot Mix Leveler and Single Seal Coat | Various Streets in Renwick, Iowa | 1078.8 | 1312.61 | 19884 | 1078.8 | Fully Completed | RUT Funds | 2009-09-18
Rhodes | Repair area in road at the north end of Newton Street | North end of Newton Street | 925.85 | 1126.52 | 853.23 | 853.23 | Fully Completed | IJob money | 2009-10-20
| Repaired streets on Maple and Main Street and Dead end off of Cherry Lane and West end of Cherry Lane | On Maple, Main and Cherry Lane |  |  | 4189 | 1199.14 | Fully Completed | RUT and I-Jobs | 2010-10-13
Riceville | make repairs to Ninth Street | 9th Street | 3668.87 | 4464.06 | 6500 | 3668.87 | Fully Completed | street reserves/ijobs funds | 2009-12-01
Richland | to be determined | to be determined | 2563.84 | 3119.53 | 0 | 0 | Not Started | I-Jobs money | 2010-02-26
| To be determined at later date | To be determined |  |  | 0 | 0 | Not Started | I-Jobs Money | 2009-11-17
Rickardsville | Snow Removal Services contracted through Dubuque County Highway Department. | 2.86 lane miles consisting of St. Joseph's Drive, Diagonal Street, James Road, Five Points Road, South Mound Road and Hilltop Court. | 747.93 | 910.04 | 2575.92 | 747.93 | Fully Completed | Road Use Tax Fund | 2010-03-05
Ricketts | 17.25 Tons of Rock, Catloader to spread rock, packed with roller OK Construction Inc. did the work | Oak Street | 400 | 486.7 | 484 | 400 | Fully Completed | $400.00 I-Jobs Fund 84.00 Roaduse Fund | 2009-07-09
Ringgold County | There are four bridges that we have decided to replace with CMP. The funds are being used to buy pipe, aggregate and labor and equipment cost. | Pipe #1 250th St between 310th Ave and P-68. Pipe #2 310th St is just west of the intersection of 300th Ave. Pipe #3 on 260th St is between 270th Ave and 280th Ave. Pipe #4 is on 140th St between 3 | 82361.9 | 101011.09 | 90000 | 82361.9 | Fully Completed | Road Use Tax Fund | 2010-05-10
| We are planning to use I Jobs funding to do repairs and maintain to our aggregate roads. | Ringgold County |  |  | 102000 | 101011.09 | Fully Completed | Road Use Tax Fund | 2011-06-24
Ringsted | 2009 Street Construction consists generally of 1526 ton of HMA Paving with 2160 lineal feet of 6" X 30" P.C. Concrete Curb & Gutter, 372 ton Class "C" Gravel driveway removal & replacement seeding & fertilizing. | N. Railroad Street; Walnut Street and E Maple Street from N. Railroad Street to Beech Street | 1632.27 | 1986.05 | 220000 | 1632.27 | Fully Completed | Emmet County State Bank Loan And Road Use Taxes and I-Jobs | 2010-05-10
| 2009 Street Construction consists generally of 1526 ton of HMA Paving with 2160 lineal feet of 6" X 30" P.C. Concrete Curb & Gutter, 372 ton Class "C" Gravel, driveway removal & replacement, seeding & fertilizing. | N. Railroad Street, Walnut Street and E. Maple Street from N. Railroad Street to Beech Street |  |  | 215000 | 0 | Fully Completed | Emmet County State Bank Loan And Road Use Taxes And I-Jobs | 2010-05-10
| 2011 Street Construction consists generally of HMA Paving with P.C. Concrete Curb & Gutter on E. Maple Street and Larch Street | E. Maple Street from Heritage Street to S. 550th Avenue Larch Street from Heritage Street to E. Maple Street |  |  | 295000 | 1986.05 | 50% or More Complete | I-Jobs, Road Use Taxes, Interfund Loan, Emmet County State Bank Loan | 2011-12-12
Rippey | Evaluation of maintenance need for Street Lights repair and replacement of old light poles. Advise Alliant Energy of all Street Lights needing maintenance or pole replacement. Alliant Energy dispatched to repair/replace Street lights and/or poles. | Every City Street in Rippey IA | 807.41 | 982.41 | 2300 | 1789.82 | Fully Completed | Road Use Tax Fund | 2011-06-30
Riverdale | Cut out and remove existing deteriorated asphalt areas approx.+or- 1,032 sq. ft. and install 4" thick compacted hot mix asphalt patches in same cut out area. | Street Repair on Elmhurst Lane, Riverdale, Iowa | 2852.11 | 3470.27 | 4845 | 2852.11 | Fully Completed | I-Jobs, $2,852.11 Total Project Cost $4,845.00 | 2010-09-29
| To Be Determined at a later date | To Be Determined |  |  | 0 | 0 | Not Started | To Be Determined at a later date | 2012-06-05
Robins | Crack Seal Several Robins streets. | Miscellaneous Robins streets. | 10635.36 | 12940.46 | 2305.82 | 2305.82 | Fully Completed | I-jobs | 2011-08-15
| Improve North Troy Road by double coating with seal-coat. | North Troy Road in Robins, Iowa |  |  | 21270 | 21270 | Fully Completed | I-job receipts | 2010-10-15
| Seal Coat existing Robins' streets. | In the Robins City Limits |  |  | 10000 | 0 | Not Started | I-Jobs | 2010-06-07
Rock Falls | new Street Signs and poles were installed to replace worn and broken signs and posts | Rock Falls | 362.75 | 441.38 | 581.15 | 362.75 | Fully Completed | ijobs and the city of rock falls road use tax money | 2010-03-10
| replace roof on shelter house in city park..Installing metal roofing and closing the north end of the shelter house to eliminate children crawling on top of the roof | City park Rock Falls, Iowa |  |  | 798.85 | 0 | Fully Completed | City of Rock Falls park fund | 2010-10-31
Rock Rapids | Reconstruct 10 blocks of PCC concrete street in residential areas of the City. | Sections of Dickinson Street, Randall Street, Bradley Street, 4th Avenue, 5th Avenue, and 6th Avenue, all located west of Union Street. | 11238.1 | 13673.84 | 2362008.5 | 11238.1 | Fully Completed | G.O. Bonds; I-Jobs | 2009-08-31
| Seal Coat 30 blocks of asphalt street. | Streets located South of 6th Avenue, North of 12th Avenue, East of Union Street, West of Tama Street. |  |  | 52608.05 | 0 | Fully Completed | General Obligation Bonds, IJobs | 2010-09-10
Rock Valley | Replace broken concrete on 16th Street, 15th Street, 10th Street, Riverview Drive, and 18th Avenue. | 16th Stree, 15th Street, 10th Street, Riverview Drive, and 18th Avenue. | 11801.53 | 14359.39 | 15000 | 8000 | 50% or More Complete |  | 2009-10-29
Rockford | Insulating and repair of maintenance facility used for maintenance and storing of street equipment. | 403 2nd Ave. N.E. | 3961.51 | 4820.12 | 4930.41 | 3961.51 | Fully Completed | I-Job Funding | 2010-04-01
Rockwell | Repairs on Oak Street North and Main Street East | Oak Street North and Main Street East | 4319.66 | 5255.9 | 59958.15 | 4319.66 | Fully Completed | Road Use Tax Local Option I-Jobs funds | 2009-10-15
Rockwell City | 3rd Street from Main Street to High Street - Mill Areas to Install 2 1/2" Asphalt Overlay | 3rd Street from Main to High Street | 9713.77 | 11819.13 | 30675 | 11819.13 | Fully Completed | Road Use - I jobs | 2011-08-31
| Mill Out area 245' X 20' to install 3" of asphalt | 6th Street - Court to Richmond |  |  | 10200 | 9713.77 | Fully Completed | Road Use tax Fund | 2010-06-25
| To be determined....................... | To be determined |  |  | 0 | 0 | Not Started | To be determined | 2009-12-01
Rodney | Seal-coating of city streets and pothole filling | Main Street | 159.79 | 194.42 | 5000 | 0 | Not Started | State of Iowa | 2010-07-29
Roland | Crack sealing | Several street in town | 5782.84 | 7036.21 | 4960 | 4960 | Fully Completed | ijobs revenue | 2009-07-06
| I-JOBS Project not determined yet. | w/in the city limits of Roland |  |  | 0 | 0 | Not Started | I-jobs | 2011-06-30
| Storm sewer intake repairs | Main & Locust Street |  |  | 2300 | 822.84 | Fully Completed | ijobs and rut funds | 2009-11-17
Rolfe | Used to sealcoat a section of city street. | City of Rolfe | 2948.2 | 3587.19 | 29457.93 | 4457.93 | Fully Completed | I JOBS Steet funding | 2010-08-31
| We used the remaining money to purchase new street signs for the City of Rolfe | The whole town |  |  | 2100 | 2077.46 | 50% or More Complete | I-Jobs street money | 2011-06-30
Rome | alley in need of scouring and resurfacing | repair alley between Broadway and Fairchild, 3rd and 4th streets | 336.03 | 408.86 | 1370.42 | 336.03 | Fully Completed | I-JOBS and road use funds | 2009-08-30
Rose Hill | cold patch in pot holes in streets | various streets in Rose Hill | 723.44 | 880.24 | 400 | 23.44 | Less than 50% Complete | Roads, Bridges, Sidewalks: Street Repairs | 2009-11-30
| culvert work and roadway repairs, road washing out | Corner of Jackson and Washington Street |  |  | 700 | 700 | Fully Completed | Roads, Bridges, Sidewalks: Street Repairs | 2009-09-09
Rowley | Double Seal Coat Rainbow St | Rainbow Ave between Rowley St and Ely St | 906.97 | 1103.55 | 2115 | 2010.52 | Fully Completed | State Money for Roads | 2010-09-30
Rudd | 1995 Intnl 4700 truck 6cyl 4spd AT | City of Rudd | 1335.25 | 1624.65 | 15500 | 1335.25 | Fully Completed | I-Jobs and Road Use Tax | 2009-08-12
| Tearing up and replacing concrete on street. | 5th and Chickasaw ST. |  |  | 2295 | 1624.65 | Fully Completed | I-JOBS & Road use tax | 2010-11-20
Runnells | Repair Sidewalk | Between Brown St and Hancock St | 1537.43 | 1870.65 | 1250 | 1250 | Fully Completed |  | 2009-08-15
| The plan is to continue repairing the city sidewalks and public areas. | Brown St and W. McKinney area. |  |  | 1683.5 | 1683.5 | Fully Completed | I-Job | 2011-04-29
Russell | Repair streets, seal coating, | City of Russell | 2441.55 | 2970.72 | 167010 | 5350.21 | Fully Completed | I-Jobs, FEMA Funds | 2010-07-19
Ruthven | Installing 200 foot of 8 inch Storm Sewer and installing 100 foot of 6 inch storm sewer | Rolling Street from Gowrie Street to Ruthven Street and 1300 Block of Ruthven Street | 3341.29 | 4065.48 | 8040 | 7406.77 | Fully Completed | Road Use Tax | 2010-08-01
Ryan | The city will be using the funds towards repair and maintenance of streets. | Various street improvements as well as Main Street Improvement Project | 1417.12 | 1724.26 | 220000 | 3141.38 | Less than 50% Complete | General Obligation Loan, Local Option Sales Tax Funds for Street Use, IJOBS Funds | 2010-07-01
Sabula | Emergency Watershed Protection Program. The contractor shaped the existing slope as shown in the plans, placed geotextile fabric, and installed the rip-rap material. This work was completed to prevent future natural disasters that caused flooding events | Section 29, Union Township, Jackson County. South Avenue,. Sabula, IA. | 2926.36 | 3560.62 | 66342 | 2926.36 | Fully Completed |  | 2009-06-30
Sac City | Street Improvement/Repair Project | Sac City, Iowa | 10342.72 | 12584.4 | 10048.5 | 20097 | Fully Completed | Special Assessment/General Obligation | 2012-11-02
| This project includes 3 phases: 1. Sanitary Sewer Lining 2. Sanitary Sewer Line Improvements 3. Wastewater Treatment Plant Improvements | Phase 1 - South 13th Street through South 11th Street and Chautauqua Park Line. Phase 2 - East/West between South 5th Street and South 11th Street. Phase 3 - Repair Main Pump Station, Retro-Fit WWTP |  |  | 7400000 | 2830.12 | Fully Completed | CDBG, ARRA, & Revenues | 2011-12-31
Sac County | 2010 Cat 140M all wheel drive motorgrader | Sac City | 97958.56 | 121367.13 | 263000 | 121367.13 | Fully Completed | RUTF | 2010-10-26
| PCC patching on various paved county roads | on county roads M27, M43, M55, M68, N14, and D46 |  |  | 282351.44 | 97958.56 | Fully Completed | Secondary Road Fund | 2009-10-30
Sageville | Fill in cracks and minor repairs of entire street. | Leiser Lane | 404.58 | 492.27 | 2932 | 809.16 | Fully Completed | Road use tax for anything above IJOBS amount. | 2010-05-28
| We are not sure yet what we will be doing. | Not sure which street will be worked on. |  |  | 0 | 0 | Not Started | I-Jobs and road use tax. | 2011-08-01
Saint Ansgar | 3 INCH ASPHALT PATCH W/2 INCH ASPHALT OVERLAY | EAST 5TH STREET FROM SOUTH SUMMER STREET TO EAST DEAD END | 4503.1 | 5479.1 | 19489.26 | 9982.2 | Fully Completed | ROAD USE FUNDS WILL SUBSIDIZE FUNDING FROM THE I-JOB ROAD FUNDING | 2010-06-10
Saint Anthony | Replacement of culvert under city street (Howard) due to deterioration. | Howard St., St Anthony, IA | 237.27 | 288.7 | 2548.57 | 237.27 | Fully Completed | LOST funds, RUT funds, IJOBS funding | 2010-10-01
Saint Charles | 15" cement storm drain to keep water from backing up and causing further damage to street | north and south under W. Carpenter Street | 2703.61 | 3289.59 | 10000 | 0 | Less than 50% Complete | I-Jobs | 2010-06-30
| Removing a storm sewer drain under the street that has caused damage to the street requiring repair. | corner of Market on Lumber to Vine street | 2703.61 | 3289.59 | 7000 | 1860.84 | Fully Completed | I-Jobs | 2009-11-30
Saint Lucas | SPRAY PATCHING | SPRING STREET | 339.62 | 413.24 | 1910.89 | 752.86 | Fully Completed | ROAD USE TAX | 2011-06-24
Saint Marys | Road Re-surfacing | Iowa Street, Main Street, St James Street, St Johns Street | 406.71 | 494.86 | 33000 | 0 | Not Started | Road Use Tax, I-Jobs Funds | 2010-08-31
Saint Olaf | An access driveway was built at the St. Olaf Wastewater facility. | 111 North Main Street | 164.56 | 200.22 | 300 | 164.56 | Fully Completed | I-Jobs Funds = $ 164.56 Sewer Fund = $135.44 | 2010-05-25
Saint Paul | No project plans at this time | City of St. Paul | 124.64 | 151.65 | 0 | 0 | Not Started | RUT funds/I-Jobs funds | 2011-01-01
Salix | Repair and replace 10'x 20' area at water curb stop area in front of fire station. Removed old paving, installed tie bars and steel mat, re-paved with 8" portland concrete cement pavement. | 315 Tipton Street | 1242.76 | 1512.11 | 2496 | 1242.76 | Fully Completed |  | 2009-08-02
Sanborn | Asphalt resurfacing & seal coating | Sibley Street - between 1st & 4th & between 4th & 7th street. Carroll Street - between 1st & 7th Street. East 2nd - east from Carroll. 4th Street - between Franklin & Main. 5th Street - between Si | 5909.5 | 7190.32 | 31748 | 5909.5 | Fully Completed |  | 2009-08-21
Schaller | The Council chose to purchase a John Deere riding mower with these funds. | Undecided | 3402.44 | 4139.88 | 3700 | 3402.44 | Fully Completed | IJOBS funds and funds from the water and sewer utility accounts. | 2010-06-30
| The Council chose to purchase a new SS Sander/Spreader for use on street sanding. | Within the City limits |  |  | 4950 | 4139.88 | Fully Completed | IJOBS funds | 2010-12-31
| The Council has not decided on a specific project for these funds yet. Hopefully they will make a decision when discussing the next budget. They may make a decision at the January meeting. | Undecided on specific project |  |  | 0 | 0 | Not Started | We hope to expend only funds from the IJOBS for whatever project the Council decides on. | 2010-04-28
Schleswig | Patching of asphalt streets. | Various streets throughout the City. | 3638.3 | 4426.86 | 3638.3 | 1908.06 | Fully Completed | IJobs Funds | 2010-05-20
| Street repairs to improve cross street water drainage at several intersections. | Glad & 3rd Street, Glad & 4th Street, Glad & 5th Street, Fir & 4th Street and Fir & 5th Street. |  |  | 27372 | 6157.1 | Fully Completed | I-Jobs, Street Funds | 2010-10-20
Scott County | HMA Surfacing in Scott County, Iowa. | On Slopertown Road from Y52 east to Hillandale | 109683.99 | 130903.69 | 351778.93 | 130903.69 | Fully Completed | Secondary Road Fund | 2010-10-08
| HMA Surfacing On 257th Ave | On 257th Ave and 200th St South of Territorial Road |  |  | 180000 | 109683.99 | Fully Completed | Scott County Secondary Road Fund | 2009-10-08
Scranton | ROAD/CONCRETE REPAIRS. SEVERAL LOCATIONS FROM WHERE STREETS WERE TORN UP FOR WATER MAIN REPAIRS AND FIRE HYDRANT REPLACEMENTS | UNDETERMINED. SEVERAL LOCATIONS. | 2638.09 | 3209.87 | 5847.96 | 5847.96 | Fully Completed | IJOBS and RUT funds | 2010-08-01
Searsboro | Most roads in town are gravel...with all the rain in the spring/late summer, roads have many ruts and no gravel.. Will regrade roads and haul in new gravel. | All over town | 676.99 | 823.73 | 1100 | 900 | Fully Completed | I-jobs | 2011-09-30
| Repair a major hole in the road and resurface the road | Railroad Street between 2nd and 3rd St |  |  | 600 | 570.88 | Fully Completed | Ijobs | 2009-10-15
Sergeant Bluff | Design work completed. No construction work done yet. | Residential subdivision | 14505.14 | 17744.63 | 147535.28 | 32249.77 | Fully Completed | IJOBS & possibly Road Use Tax | 2010-10-30
Seymour | Filling potholes with premix | Main Street, both East and West Winston Street Matkins Street East Lee Street North Park | 3537.84 | 4304.63 | 4000 | 5470.74 | 50% or More Complete | Road Use Tax | 2010-12-31
| Filling potholes with premix | Main Street, both East and West Winston Street Matkins Street East Lee Street North Park |  |  | 8500 | 5470.74 | 50% or More Complete | Road Use Tax | 2010-12-31
Shambaugh | Seal Coat and cover with rock to repair and service street | Will be on numerous streets in Town to repair the damaged areas. | 810.42 | 986.07 | 10000 | 1796.49 | Fully Completed | Road Use Tax Fund Property Tax Fund Local Option Tax Fund | 2010-10-01
Shannon City | Grading and graveling streets | Streets thoughout City | 206.82 | 251.66 | 2153.97 | 458.48 | Fully Completed | Road Use Tax | 2010-08-12
Sharpsburg | GRAVEL/COLD PATCH FOR ROADS | CITY STREETS | 274.9 | 334.49 | 0 | 0 | Not Started | I JOBS/ ROAD USE FUNDS | 2011-03-01
[5 empty] | 500 | 0 | Not Started | I JOBS/ ROAD USE FUNDS | 2011-03-01
| PATCH TO REPAIR NUMEROUS POT HOLES THROUGHOUT THE CITY | SHARPSBURG IA |  |  | 679 | 275 | Fully Completed | I JOBS/ROAD USE FUNDS | 2009-08-18
Sheffield | 4" asphalt mat(2411'),1 1/2" asphalt overlay(470'),2" asphalt patch(240') | North 5th street,Intersection of 2nd St and Gilman St,First street. | 4061.96 | 4942.35 | 49003.91 | 9004.3 | Fully Completed | I-JObs fund,local option mones,road use monies | 2010-08-31
| at this time the city of sheffield has not determined the project for the i-jobs funding monies | at this time the city of sheffield has not determined the location of the project for the i-jobs funding monies |  |  | 9004.31 | 0 | Fully Completed | i-jobs funding monies | 2009-09-23
Shelby | The money will be used for maintenance of city streets. Crack sealing. | City of Shelby | 3039.92 | 3698.79 | 5000 | 3039.92 | Fully Completed | Road Use Tax | 2010-05-26
Shelby County | Replace existing bridge on existing roadway | Section 32, Township 78, range 37 - 200th St. over Indian Creek | 101557.42 | 121251.14 | 222808.56 | 222808.56 | Fully Completed | I-JOBS Funding | 2011-05-15
Sheldahl | Pleace 2 new storm water drainage valves | 205 Jefferson 310 Willow | 995.95 | 1211.81 | 900 | 0 | Not Started | I-Jobs | 2010-02-19
Sheldon | Asphalt overlay in Sheldon, Iowa. | 7th Avenue from 7th Street to 9th Street. | 21462.89 | 26114.75 | 26114.75 | 26114.75 | Fully Completed | I-Jobs | 2010-10-14
| Asphalt resurfacing. Mill and remove flow lines. Place a 2" HMA lift. | 6th Avenue from 9th Street to 11th Street. |  |  | 102073.28 | 21462.89 | Fully Completed | RUT Improvement Fund | 2009-10-09
Shell Rock | Patching of asphalt streets | Jackson Street, Pearl Street, and Prospect Street | 5669.28 | 6898.03 | 13518.75 | 5669.28 | Fully Completed | I jobs funding and Road Use Tax Funds. | 2009-10-21
Shellsburg | Monies not spent. | Monies not spent | 4096.91 | 4984.87 | 0 | 0 | Not Started | IJOBS Dollars | 2010-03-09
| Seal Coat | City streets | 4096.91 | 4984.87 | 9081 | 9081 | Fully Completed | I-Jobs | 2011-07-05
Shenandoah | Description of Equipment: Used John Deere 772CH II All Wheel Drive Motor Grader, 2004 Model. Total Cost is $94,500. Current Balance of 42,286.70 will go to this purchase. | N/A | 24223.28 | 29473.42 | 42286.7 | 42286.7 | Fully Completed | Remaining IJOBS funds received for FY10- $12,813.28 and funds received for FY11 - $29,473.42 | 2011-06-27
| Intersection of S Center Street and Nishna Road.The South storm sewer inlet box was rebuilt. Finished patching with concrete and also did 30 L.F. of mono curb. This was completed on 8/20/10. $11,410.00 | Variety of other locations yet to be determined. |  |  | 24223.28 | 22820 | Fully Completed | IJOBS, Road USe | 2011-06-30
Shueyville | Project yet to be determined | City of Shueyville | 422.4 | 513.95 | 0 | 0 | Not Started | I-Jobs funds | 2010-12-31
| repair water street bridge | City of Shueyville |  |  | 62070 | 936.35 | Fully Completed | IJOBS and general account | 2010-12-20
| to be determined | CityofShueyville |  |  | 0 | 0 | Not Started | I-Jobs money | 2010-12-30
Sibley | Egret Drive Extension in the Industrial Park | City of Sibley Industrial Park | 12212.1 | 14858.94 | 167627.08 | 14858.94 | 50% or More Complete | I-Jobs funding, Industrial Site Fund Balance | 2010-10-08
| New Construction Conrete Road Extension | 4th Street NE past 15th Avenue NE |  |  | 23171.7 | 12212.1 | Fully Completed | Lot Sales | 2009-09-30
Sigourney | Curb Island at West Elm Street and North Stuart Street Intersection | West Elm Street and North Stuart Street Intersection | 9648.26 | 11739.41 | 7068.17 | 3683.13 | Fully Completed | I-Jobs and Sreet Improvement Funds | 2010-09-30
| Reconstructing Intersection of East Street and East Pleasant Valley Street | Intersection of East Street and East Pleasant Valley |  |  | 4511.57 | 4477 | Fully Completed | I-Jobs | 2010-09-30
| Reconstructing Intersection of South Street and Highway 149 (East Side) | Intersection South Street and Highway 149 |  |  | 4117.11 | 4082.54 | Fully Completed | I-Jobs | 2010-09-30
| Repair intake on East Washington Street | East Washington Street |  |  | 884.57 | 850 | Fully Completed | I-Jobs | 2010-09-30
| Repair two intakes on East Pleasant Valley Street | East Pleasant Valley Street |  |  | 5808.57 | 5774 | Fully Completed | I-Jobs | 2010-09-30
| Street Paving and Repair Storm Sewer Intake at Intersection of Elm Street and Stone Street | Intersection of Elm Street and Stone Street |  |  | 0 | 0 | Fully Completed | I-Jobs | 2010-09-30
Sioux Center | Street widening, curb and gutter | 7th St NW, Sioux Center Iowa | 27634.46 | 33623.93 | 690000 | 61258.39 | 50% or More Complete | part DOT grant, part assessments, part road use tax | 2010-12-31
Sioux City | Maintenance on the paved streets within the city limits of Sioux City, Iowa | Through-out Sioux City | 371311.53 | 451789.35 | 823100.88 | 823100.88 | Fully Completed | I-Jobs | 2009-09-22
Sioux County | Crack filling on B40 and B14 | Crackfilling on B40 from L-22 east 3 miles to L-26 and on B-14 from L-22 east 3 miles and west 3/4 miles to west edge of Matlock | 156742.25 | 192710.64 | 35235 | 70470 | Fully Completed | Secondary Road Fund | 2010-11-05
| Crackfilling on K-52 from 310th Street north to 270th Street (4.5 miles | Crackfilling on K-52 from 310th Street north to 270th Street (Lyon County Line) 4.5 miles |  |  | 8995 | 8995 | Fully Completed | Secondary Road Funds | 2011-09-14
| Cracksealing on B40 from L22 west to K64 (7 miles) Rout and Seal | On B40 from L22 west to K64 |  |  | 33005 | 33005 | Fully Completed | Secondary Road Funds | 2011-10-04
| Full Depth PCC Patching on 305th Street | 0n 305th Street Near Rock Valley, Iowa |  |  | 6654.55 | 13309.1 | Fully Completed | Secondary Road Fund | 2010-09-16
| Full Depth PCC Patching on K52 south of Hull, Iowa | K52 south of Hull, Iowa |  |  | 39628.3 | 39628.3 | Fully Completed | Secondary Road | 2011-07-29
| Full PCC Depth Patching on K 52 | On K52 from Ia Hwy 18 south to B-30 |  |  | 9301.9 | 18603.8 | Fully Completed | Secondary Road Fund | 2010-10-12
| HMA patching on B46 from Hwy 10 to K22 and spots on L14 and B14 | B46 (5 miles), K22 (4 spots), B14 (2 spots) |  |  | 26314.35 | 26314.34 | Fully Completed | Secondary Roads | 2011-08-25
| PCC Full Depth Patching on K52 and B58 | On K52 (Hickory Avenue) from Hwy 18 south 5.0 miles to 370th Street and on B58(470th Street)from Hwy 75 east 0.5 mile |  |  | 106397.51 | 106397.51 | Fully Completed |  | 2009-08-06
| Slurry leveling at various locations in Sioux County | Various locations |  |  | 38093.22 | 76186.44 | Fully Completed | Secondary Road Fund | 2010-10-01
| Stripping for gravel at Fairview (Van Woudenberg Pit) | Settlers Township, Sec 15, Sioux County, Iowa |  |  | 61029 | 50344.74 | Fully Completed | Secondary Road Funds | 2009-12-12
Sioux Rapids | 120.15 tons of hot asphalt patch furnished and installed on various streets in the city of Sioux Rapids | 1st St. from Maple to Walnut; Walnut St. from 1st to Hwy 71; 2nd St. from Blake to Main; 2nd St. from Thomas to Elm; 4th St. from Thomas to Hillside; 6th St. from Thomas to Evans | 3144.75 | 3826.34 | 15018.75 | 3144.75 | Fully Completed |  | 2009-07-13
| Hot asphalt patch will be furnished and installed on Blake Street in the city of Sioux Rapids. | Blake Street |  |  | 14780 | 3826.34 | Fully Completed | $3826.34 I-Jobs $10953.66 from other funding sources | 2010-10-15
Slater | Repair of deteriorating streets within the city. | To be determined | 5704.22 | 6940.55 | 12644.77 | 3050 | Less than 50% Complete | IJOBS funds and RUT | 2012-06-30
Sloan | 47 tons of street salt | Sloan, Iowa | 4507.47 | 5484.42 | 4507.47 | 4507.47 | Fully Completed | Road Use Tax Fund | 2009-12-16
| 84" Bucket Sweeper and Gutter Brush for Bobcat S650 | Sloan Iowa |  |  | 3893 | 3893 | Fully Completed | Road Use Tax Fund | 2010-11-15
| Repaint the parking stripes on the streets | Sloan Iowa |  |  | 762 | 762 | Fully Completed | Road Use Tax Fund | 2010-07-20
| Repairs to street sweeper | Sloan Iowa |  |  | 507 | 503.82 | Fully Completed | Road Use Tax Fund | 2010-12-20
| Sand to mix with salt for using on streets in winter | Sloan Iowa |  |  | 325.6 | 325.6 | Fully Completed | Road Use Tax Fund | 2010-11-15
Smithland | To be determined at a later date | To be determined | 806.08 | 980.79 | 0 | 0 | Not Started | Road Use Tax Fund | 2009-10-30
Soldier | Minor street improvements. | City of Soldier | 904.11 | 1100.07 | 2253.16 | 2004.18 | Fully Completed | I-JOBS funds | 2011-06-30
Somers | repair and replace street signs by the Traffic Sign Store.com | entire city | 476.68 | 580 | 2072 | 1056.68 | Fully Completed | Road Use Taxes and I-Jobs Funds | 2010-12-31
| road repair | somers | 476.68 | 580 | 0 | 0 | Not Started | rut funds | 2010-09-01
South English | purchase of mower for ditches, maintenance of snow plow and rock for roads. | South English, Iowa | 833.66 | 1014.35 | 2500 | 1014.35 | Fully Completed | I Jobs | 2011-06-26
| Snowplow purchase, to help with the purchase of the new snowplow | City of South English |  |  | 15000 | 833.66 | Fully Completed | I-Jobs | 2009-09-23
Spencer | Reconstruction of West 11th Street from Grand to 11th Av West | Spencer Iowa | 49429.29 | 60142.57 | 782639 | 109571 | Fully Completed | Special Assessments Street Improvement Reserve | 2010-09-01
Spirit Lake | Reconstruction of 11th St. from Fargo Ave. to East Lake Okoboji. | Spirit Lake, Iowa | 18667.56 | 22713.56 | 75302 | 18667 | Fully Completed | Other city funds | 2010-06-08
Springbrook | Patching of black top after watermain break | South Main Street | 171.77 | 209 | 1874 | 171.77 | Fully Completed |  | 2009-08-18
Springville | 6th Avenue base repair using 2" rock& double seal coat. Approximately 656'X27'. | city limits | 4765.16 | 5797.96 | 12233.96 | 10563.12 | Fully Completed | road use funds and I-Jobs funds | 2010-10-31
Stacyville | Industrial Park cement road | Industrial Drive and Enterprise Drive | 1605.54 | 1953.53 | 635748 | 1605.54 | Fully Completed | Bonds, RUT, RISE. IJOBS | 2009-10-29
| maintenance of roads in Stacyville | City wide |  |  | 5251.72 | 1953.53 | Fully Completed | I-Jobs and RUT | 2011-06-30
Stanhope | Asphalt Resurfacing, 2", 5", 7" | Patching: Park Street, Asphalt Resurfacing: Taylor Street from Parker to Bell, Hamilton Street from Parker to Bell, Bell Street from Hamilton to Taylor, Bell Street from Taylor to Railway | 2131.44 | 2593.41 | 51874 | 2131.44 | Fully Completed |  | 2009-07-29
| Repair of the City of Stanhope Maintenance Facility including replacement of exterior doors and repair/replacement of existing siding on facility. | 160 Parker Street, Stanhope, Iowa. |  |  | 2593 | 1300 | Less than 50% Complete | I-Jobs funds and internal City funds. | 2011-06-30
Stanton | Repaired intersection of Halland Ave and Thorn Street. | Halland Ave and Thorn Street | 3118.54 | 3794.45 | 29044 | 3794.45 | Fully Completed | Property Tax dollars allocataed to Roadway Maintenance & funds from water project located under the intersection | 2010-10-29
| Shape ditches and pull in slopes of road, then apply new rock. | 200 Block of Prospect Street |  |  | 3974.49 | 3118.54 | Fully Completed |  | 2009-07-15
Stanwood | Repair to 4 street approaches | Main Street in Stanwood | 2970.04 | 3613.76 | 5820 | 3606.83 | Fully Completed | I-Jobs and city funds | 2011-07-08
| replace culvert under street | near city park |  |  | 2875.26 | 5749.52 | Fully Completed | I-Jobs and RUT funds | 2010-09-20
State Center | Repair/replace curb sections | W Main Street | 5892.03 | 7169.07 | 1750 | 1750 | Fully Completed | I-Jobs | 2009-08-14
Steamboat Rock | 2" asphalt overlay South River Rd From D-35 to mailbox | South River Road | 914.97 | 1113.28 | 15052.8 | 2028.25 | Fully Completed | I-jobs | 2009-09-30
Storm Lake | HMA Resurfacing Project with Milling | South Lake Avenue from Intersection of Lakeshore Drive to Railroad | 44035.18 | 53579.34 | 405493 | 45000 | Fully Completed | Road Use Tax ISTEA Funding - Iowa DOT | 2011-07-15
| The money will be used for asphalt crushing. We save the asphalt from our street projects and then crush it. The crushings are used in the city's alleys. | Throughout the City of Storm Lake |  |  | 53489.13 | 52614.52 | Fully Completed | Road Use Tax funds | 2011-06-30
Story City | Crack sealing of streets in Story City | Story City | 14098.94 | 17154.74 | 36208 | 0 | Fully Completed | IJOBS and Road Use | 2009-10-29
| Purchase of bituminous material (MC-800) used in the maintenace of streets | City streets |  |  | 16222 | 16222 | Fully Completed | IJOBS | 2010-09-16
| Purchase of rock 130.07 ton for maintenance of streets | Story City |  |  | 932.74 | 932.74 | Fully Completed | IJOBS | 2011-03-02
| Reconstruct the intersection of Park and Linn | Park & Linn |  |  | 22275 | 14098 | Fully Completed | IJOBS and Road Use | 2009-10-29
Story County | Asphalt overlay on 2.25 miles of Hwy S27. | On Hwy S27 from north city limits of Maxwell north 2.25 miles. | 114759.79 | 142161.56 | 613674.66 | 142161.56 | Fully Completed | Local Secondary Roads funds plus I-Jobs | 2010-08-27
| HMA Overlay one mile on Dayton Ave. | North Dayton Ave. in Section 18, T84N, R23W |  |  | 216635.9 | 114759.79 | Fully Completed | Local funds and I-jobs funding. | 2009-10-16
Stratford | Project will be maintenance of North Street from Avon to Shakespeare in Stratford. | Stratford | 3258.31 | 3964.51 | 33532 | 0 | Not Started | I-Jobs for Roads $3964.51 and City of Stratford Road Use Tax funds | 2011-06-01
| Remove street patch due to water main work and replace with like material. First Quote high; Second quote approved at $3502.00. Project completed. | South intersection at Hwy 175 and Willow Street. |  |  | 3502 | 6516 | Fully Completed | I-Jobs Road Funding of $3258.31 and city road use funds of $243.69. | 2009-11-11
Strawberry Point | Repairing intakes in roadways | Various locations in the City | 6053.64 | 7365.7 | 2195.56 | 4391.12 | Fully Completed | I-Jobs City Funds | 2011-06-30
| Replace asphalt on roadway. | Prairie Avenu |  |  | 425 | 0 | Fully Completed | I-Jobs | 2011-11-02
| Replace sewer inlet and repair the road at the intersection of W. Spring and Westwood Dr. | W. Spring and Westwood Dr. |  |  | 33141 | 6053.64 | Fully Completed | I-Jobs for this portion of the job. | 2009-12-02
| The City of Strawberry Point will be replacing manholes that are in poor condition. | The exact location of the maholes to be replaced have not been determined as of this date. |  |  | 6500 | 0 | Not Started | We will be using RUT funds for this project instead of I-Jobs money. | 2010-05-31
Struble | Maintain and re-gravel streets and alleys | City of Struble | 254.38 | 309.51 | 2600 | 563.89 | 50% or More Complete | idot funds and Road Use Tax funds. | 2010-08-31
Stuart | Asphalt paving HMA/ HMA 50X30 | Division and Front Street | 7477.51 | 9098.18 | 40000 | 9098.18 | Fully Completed | I-JOBS | 2010-10-28
| seal coat project | N.Gaines street/ N. Main street/ N. Fremont/ NW 2ND STREET/ NE 3rd street/ NE 4th street |  |  | 40000 | 7477.51 | Fully Completed |  | 2009-08-12
Sully | Asphalt Patching of existing asphalt streets | Various streets throughout the city | 3948.4 | 4804.18 | 2632 | 2632 | Fully Completed | I-Jobs Funds | 2011-08-31
| Culvert Repair | 1103 8th Street |  |  | 1379 | 1379 | Fully Completed | I-Jobs funds | 2011-12-08
| Ditch cleaning and reshaping | Various city streets |  |  | 4350 | 3146.58 | Fully Completed | I-Jobs funds | 2012-09-21
| No project has been determined at this time | To be determined |  |  | 0 | 0 | Fully Completed | None | 2010-06-30
| Restripe street parking to include painting stall lines, hash areas, crosswalks, existing yellow curbs, (4) no parking stencils and handicap symbols. | Downtown area around the city square |  |  | 1595 | 1595 | Fully Completed | I-JOBS Fund | 2011-07-31
Sumner | Repairs to the South Walnut Street Bridge include Class A repairs and replace with HPC Concrete in accordance with the Bridge Inspection Report of 2008 | South Walnut St, Sumner Ia | 9198.38 | 11192.03 | 16332 | 9198.38 | Fully Completed | I-JOBS Road Funding | 2009-10-01
| Repairs to the street and shoulder of N Pleasant St included grinding of road, installing 3" asphalt and rocking of the shoulder. | North Pleasant Street 1,300 feet to the north city limit line. |  |  | 44825.01 | 11192.03 | Fully Completed | IJOBS - $11,192.03 RUT - $33,632.98 | 2010-11-15
Superior | Infrared heats on allegated areas of asphalt streets | Third St.-Fourth St.-Third Ave.-Ninth St. | 566.56 | 689.36 | 1650 | 1255.92 | Fully Completed | General Fund | 2010-09-14
Sutherland | Resurfaced street High Street in Sutherland, Iowa Furnishing and istallation of the asphalt strengtheningand leveling coarse and olil & chip single seal coat | High Street - Sutherland, Iowa | 3087.97 | 3757.25 | 17875.9 | 6845.22 | Fully Completed | I Jobs money and RUT money | 2010-08-26
Swaledale | 6" Asphalt patch repair of city streets | Inters. of Main St. & 5th St. N; Jefferson St. between Jonquil & 2nd Ave.; 2nd Ave. between north end of Douglas & Main St.; Main St. east of 3rd Ave. intersection; 5th Ave. from Main St. to Jefferson | 640.49 | 779.31 | 3994 | 1419.8 | Fully Completed | Road Use Tax | 2010-10-30
Swea City | Asphalt leveler & oil and chip single seal 20-25 city street blocks. | Various | 2804.07 | 3411.82 | 54692.9 | 2804.07 | Fully Completed | Local Option Sales Tax Road Use | 2010-06-25
Swisher | Crack Sealing | 2nd Street from Howard to Summit Jefferson Ave from 3rd to Division Rose Ave from 3rd to Division, Division from Swisher View Dr to City Limits South Side Division St from Swisher View Dr to East C | 3550.94 | 4320.57 | 8000 | 0 | Less than 50% Complete |  | 2009-10-06
Tabor | Repairing asphalt roads | Multiple spots in city limits | 4337.13 | 5277.16 | 4337.13 | 0 | Not Started |  | 2009-12-30
Tama | East 13th Street Overlay Street with asphalt install curb/gutter/storm sewer drains | East 13th Street | 11928.2 | 14513.51 | 413000 | 7487.71 | Fully Completed | I-Jobs Funds,Road Use Tax Funding and City Street Funds Total Project $413,000 Using Balance of I-Jobs $7,488 | 2011-10-15
| Remove manhole from Highway 63 and replace 3 sections of Highway 63 | Highway 63 intersection Siegel Street |  |  | 18000 | 17100 | Fully Completed | I-Jobs approximate cost $18,000 | 2011-08-15
| Repair right of way culvert under Highway 63. | Highway 63 (State Street) and 1st Street - Tama IA |  |  | 15000 | 1854 | Fully Completed | I Job Funds should pay for the project. | 2010-06-01
| S 1st Street and Highway 63 repair intersection that has sunk | corner of South 1st and Highway 63 |  |  | 2000 | 0 | Fully Completed | Est. $2,000 I-Jobs | 2011-08-01
Tama County | Winter operations, including labor & materials for snow & ice removal | County-wide | 125302.35 | 151223 | 415782 | 125302.35 | Fully Completed | General Operational (Local) Funds | 2010-03-31
| Winter operations, including labor & materials for snow & ice removal | Countywide |  |  | 250000 | 151223 | Fully Completed | I-Jobs and operational funds | 2012-03-31
Taylor County | Full Depth Patching on J35 & J20/Class A-Bridge Deck Repair on J20 & J35/Pressure grouting & mud-jacking on Denver Ave, Badger Ave, 210th St and P14. | J35 & J20,Denver Ave, Badger Ave, 210th St and P14 | 83710.94 | 103545.09 | 124872.67 | 0 | Fully Completed | county budget/I-Jobs | 2010-08-15
| PCC Full Depth Patching | J20 & J35 |  |  | 74685.82 | 74685.82 | Fully Completed |  | 2009-07-31
Templeton | Asphalt resurfacing approximately 340' long x 15' wide followed up with seal coating. | 3rd Avenue from 1st St. to 2nd St. | 1167.05 | 1420 | 4272.79 | 1420 | Fully Completed | $1,420.00 from I-Jobs money and balance of $2,852.79 from Road Use Tax Fund | 2010-08-05
| Remove seal coat and replace with hot mix asphalt 4" depth | S. 3rd Avenue between Railway Street and 2nd Street |  |  | 2000 | 1167.05 | Fully Completed | $1,167.05 I-Jobs money and $812.55 Road Use Tax Money | 2009-10-06
Terril | FUNDS AMOUNTING TO $ 1,459.45 WERE USED TO HELP PAY FOR LABOR TO PLOW STREETS AND MOVE SNOW TO VACANT LOTS DURING THE SEVERE WINTER WEATHER OF DECEMBER 2009 AND JANUARY 2010. | ALL PUBLIC STREETS AND ALLEYS IN TERRIL, IOWA | 1459.45 | 1775.77 | 1459.45 | 1459.45 | Fully Completed | I JOBS BALANCE OF $ 1,459.45 WAS USED | 2010-01-31
| Repair of blacktop street | 100 Block South State Street |  |  | 1775.77 | 0 | Fully Completed | IJOBS road Funding Balance of $ 1,775.77 was used. | 2010-11-05
| TO BE DETERMINED AT A LATER DATE | TO BE DETERMINED AT A LATER DATE |  |  | 0 | 0 | Not Started | TO BE DETERMINED AT A LATER DATE | 2010-01-15
Thompson | patch and repair streets | Adams Street - 2" patch Intersection of 2nd Ave & Madison St - 3" asphalt 3rd Ave from Adams to Jackson - seal coat 4th Ave between Jackson & Monroe - paver patch Helgren Street - seal coat West | 2603.15 | 3167.36 | 9182.95 | 2603.15 | Fully Completed |  | 2009-09-10
Thornburg | 8" digging tile filling, outlet, connection & intake | Broadway to Garfield | 366.89 | 446.41 | 2958.81 | 366.89 | Fully Completed | R41 Community Disaster Grant Program | 2010-01-12
| Repair or maintenance of various streets. | various streets in Thornburg |  |  | 0 | 0 | Not Started | Grant money and IJOBS money | 2011-09-15
Thornton | 4" asphalt patch resulting from a broken water main | E of 8th Street intersection on Larch Street | 1611.65 | 1960.96 | 1192 | 0 | Fully Completed | Funded by I-Jobs & State Road Use Tax | 2011-06-22
| Excavate 9" of dirt, install 6" of base rock with 2" asphalt overlay and a 3" asphalt mat | 2nd Street SE/Walnut Street to S. end |  |  | 3137 | 0 | Fully Completed | Funded by I-Jobs money | 2011-06-22
| No project for this quarter | Roads |  |  | 0 | 0 | Not Started | I-Jobs | 2010-09-30
| No project to report | Roads |  |  | 0 | 0 | Not Started | I-Jobs | 2010-06-30
| No Projects for the 1st quarter of 2010 | To be Determined |  |  | 0 | 0 | Not Started | Roads | 2010-03-31
| No projects for the 3rd quarter of 2009. | City of Thornton |  |  | 0 | 0 | Not Started | roads | 2009-09-30
| No Projects for the 4th quarter of 2009. | Thornton |  |  | 0 | 0 | Not Started | No funds expended | 2009-12-31
Tiffin | ANNUAL CITY STREET REPAIRS IN VARIOUS LOCATIONS IN CITY | VARIOUS CITY STREETS OF TIFFIN, IOWA | 4507.47 | 5484.42 | 49196.8 | 4507.47 | Fully Completed | I-JOBS, Road Use Tax, and General Funds | 2009-10-30
| VARIOUS LOCATIONS WITHIN CITY LIMITS REMOVE AND REPAIR STREET SECTIONS WITH ADJACENT CURB, GUTTER, AND SIDEWALK REPAIRS. | VARIOUS LOCATIONS WITHIN CITY LIMITS. |  |  | 47096.61 | 5484.42 | 50% or More Complete | i-JOBS FUNDS AND ROAD USE FUNDS | 2011-06-30
Tipton | New salt shed to mix sand and salt and prepare salt brine | Upper shop location at 204 East South Street | 13780.1 | 16766.79 | 30000 | 0 | Less than 50% Complete | I-JOBS funding and Road Use Tax | 2010-10-29
| Street repairs | Inland Road, Old Muscatine, Logan Ave |  |  | 14758 | 13780 | Fully Completed |  | 2009-09-07
Titonka | Fill hole with hot mix in Titonka, Iowa. | South end of Main Street, Dieckman St & 2nd Ave NE, intersection of Main Street & 3rd Ave, Main Street, Intersection of Wesley St & 3rd Ave | 2550.74 | 3103.58 | 3103.58 | 3103.58 | Fully Completed | I-Jobs monies | 2010-09-29
| Seal coat one block of street that has been cored out | 6th Street between Main Street & Dieckman Street |  |  | 2550.74 | 2550.74 | Fully Completed | Road Use Tax monies | 2010-07-30
Toledo | 3" HMA Paving Cemetery Road. 847.30 Sq ft used. Moblization. Mill and overlay Carleton Street from main Street to Broadway Street. Total cost of this was $15,756.00. This project is completed. | Toledo Cemetery on Elm Street and Carleton Street from Main Street to Broadway Street | 11089.6 | 13493.15 | 15756 | 13493.15 | Fully Completed | Stimulas Monies | 2010-10-28
| Repair frost boils on Ross Street and mill and overlay Carleton Street from Hwy 63 to West Street. Total cost of this was $11,544.00. Project finished. | Ross Street - Repair Frost Boils. Asphalt pave Carleton from Hwy 63 to West Mill and overlay. |  |  | 11544 | 11089.6 | Fully Completed | Federal IJOBS | 2010-06-14
Toronto | drop box | Mill/Washington Street corner | 432.48 | 526.21 | 2370 | 432.48 | Fully Completed |  | 2009-08-05
| Seal Coat | Toronto |  |  | 10222.35 | 432.48 | Fully Completed | RUTF & I Jobs | 2010-07-20
Traer | street resurfacing--to be determined | to be dertmined | 6962.12 | 8471.08 | 150000 | 15433.2 | Fully Completed | city reserves and bonding proceeds | 2010-09-30
Treynor | Repair street damage from storm water run off on Hillsdale Drive. Place fill in voids under the paving where the storm water caused undermining. Approximately 970 square feet of street was torn out and replaced. | 208 Hillsdale Drive, Treynor | 4149.32 | 5048.64 | 7522 | 4149.32 | Fully Completed | IJOBS $4,149.32 Comm Disaster Grant $2,000 Road Use Fund $1,372.68 | 2009-09-05
| The storm sewer inlet box on both sides of Terrel Ave. had shifted and cracked, which damaged the box structure and street around the inlet boxes. The infiltration of stormwater/groundwater through the damaged inlet boxes posed additional threat to the st | Terrel Ave. Treynor,IA |  |  | 5500 | 5048.64 | Fully Completed | IJOBS $5,048.64 Road Use Fund $354.36 | 2010-10-14
Tripoli | Install curb and gutter, storm sewer, and asphalt road along 1st Avenue S W, 2nd Avenue S W, and 5th Street S W. | Tripoli | 5721.69 | 6961.81 | 448828 | 5721.69 | Fully Completed | Road Use Tax and General Fund | 2009-09-30
| Repair of curb and gutter, and a storm intake along South Main Street. | 200 South Main Street |  |  | 9400 | 6961.81 | Fully Completed | General fund money from the street department and IJOBS money | 2010-08-16
Truro | STREET GRADING + REPAIR, POTHOLE PATCHING | N MCKINLEY STREET, W GARFIELD STREET, E GARFIELD STREET, S WEST STREET, LAGOON ROAD, SOUTH ALLEY | 1278.96 | 1556.16 | 4500 | 2835.12 | Fully Completed | IJOBS + RUTF | 2010-09-30
Turin | A load of rock to repair city streets | City of Turin | 240.61 | 292.76 | 400 | 190.36 | Fully Completed | I-Jobs Funds | 2012-06-30
| A load of rock will be purchase to help maintain City Streets | Turin City Streets |  |  | 350 | 343 | Fully Completed | I-Job Funding | 2010-10-31
Udell | repairing roads and getting rock on them | Main Street | 230.87 | 280.9 | 1629.17 | 230.87 | Fully Completed | road use | 2009-10-14
| we want to get rock on the roads, its been awhile since we did the whole town | wall |  |  | 2397 | 280.9 | Fully Completed | road use and i-jobs | 2011-05-19
Underwood | crack sealing for many of the streets in town | Clark Street, North Street, Highway Avenue 2nd Street, | 3004.98 | 3656.28 | 12040 | 3004.98 | Fully Completed | Road Use Tax Revenues and I-JObs | 2009-09-16
Union | Asphalt resurfacing Summer 2010 | 305 Commercial St | 1551.16 | 1887.35 | 17549.11 | 3438.51 | Fully Completed | IJOBS money | 2010-08-30
Union County | Pavement Random Crack Repair | Routes H17, P27, P17, H24, P33 | 69980.78 | 84694.86 | 60000 | 54547.36 | Fully Completed | I-Jobs | 2009-08-31
| Pavement Repair - random crack filling | Rte. H17 from Rte. P53 east 3.5 miles |  |  | 23639.35 | 23639.35 | Fully Completed | I-Jobs | 2010-08-20
| Pavement Repair - random crack filling | Rte. P53 from the Jct. of Rte. H17 to IA34 |  |  | 41875 | 36305.51 | Fully Completed | I-JOBS | 2010-08-20
| Pavement Repair - random crack sealing | Rte. P33 from Adair Co. line to Jct. Rte. H17 Rte. P27 from Ringgold Co. line to the north 5.5 miles |  |  | 24750 | 24750 | Fully Completed | I-Jobs | 2010-08-20
University Heights | Asphalt street repairs, sidewalk panel replacement, gutter grinding | Olive Court, George Street/Koser Avenue intersection | 4310.92 | 5245.27 | 21472.55 | 9556.19 | Fully Completed | IJOBS, Road Use funds | 2011-11-18
| The project has yet to be determined by the city | To be determined |  |  | 0 | 0 | Not Started | To be determined | 2010-06-30
University Park | Engineering report for street maintenance. | All streets in University Park. | 2341.09 | 2848.5 | 3228 | 2341.09 | Fully Completed | Ijobs and RUT | 2010-06-22
Urbana | Resealcoat 3000 linear feet of street surface that was being returned to gravel due to inability to pay for project | 30th Avenue between US150 south to the Urbana corporate limits. | 4450.69 | 5415.33 | 13524.54 | 4450.69 | Fully Completed |  | 2009-08-31
Urbandale | PCC Patching of existing roadways with full depth concrete | Prairie Avenue 70th to 66th Street Airline Avenue 72nd to 65th Street Horton Avenue 72nd to 70th Street Madison Avenue 72nd to 67th Street 71st Street - Prairie to Douglas 69th Street Aurora to D | 156818.01 | 190806.64 | 476493.37 | 347624.65 | Fully Completed | IJOBS & GOB | 2010-10-28
Ute | Mil out and relay 3" of class A 1/2" asphalt and replace and adjust 2 manholes | Day Avenue from Fourth Street to Sixth street | 1650.99 | 2008.83 | 33900 | 1650.99 | Fully Completed |  | 2009-07-29
| Mill and replace with asphalt, and spot patch | Riddle Ave between Main & Second St, and Monona Ave between Fourth & Main St. |  |  | 43351 | 2008.83 | Fully Completed | Property Tax dollars, Road Use Fund, IJobs Funding | 2010-09-02
Vail | REDO THE APPROACHS ON BRIDGE ON 5TH AVE | 5TH AVE. VAIL, IOWA | 1496.69 | 1825.41 | 2000 | 1496.69 | Fully Completed | IJOBS AND CITY GENERAL FUND | 2009-09-24
Valeria | trimed trees on the streets | center street, johnson street, and main street | 234.69 | 285.56 | 1300 | 520.25 | Fully Completed | street fund | 2011-09-15
Van Buren County | CLEAN AND SHAPE DITCHES ALONG ROBIN AVENUE | ROBIN AVENUE FROM HWY 2 NORTH 2 MILES | 79866.17 | 97468.51 | 21551.48 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND | 2010-09-13
| CLEAN AND SHAPE DITCHES AND REPLACE 3 CULVERTS | BENTONSPORT |  |  | 9860.84 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND | 2010-07-09
| CLEAN AND SHAPE DRAINAGE DITCHES | IOWA OAK GROVE SOUTH OF 265TH STREET |  |  | 9178.4 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND | 2010-11-08
| Crossroad Culvert Replacement | On 105th St. between Gray Ave. and Heather Ave |  |  | 10809 | 10809 | Fully Completed | Local Seconary Road Fund | 2009-07-26
| Culvert Replacement and Ditch Cleaning | On Iowa Oak Grove Ave. In Section 5, 68-10, Des Moines Twp. |  |  | 4086 | 3798 | Fully Completed | Local Secondary Road Fund | 2009-09-22
| Culvert Replacement Replace Black Box with 36" Pipe culvert | On Quail Ave. 1/4 mile North of 170th St. |  |  | 22416 | 22416 | Fully Completed | Local Secondary Road Fund | 2009-08-25
| Erosion Repair on Chequest Creek Below new bridge | On Jersey Ave @ Chequest Creek Bridge |  |  | 19159 | 19159 | Fully Completed | Local Secondary Road Fund | 2009-07-30
| Install Culvert Liner under HMA Pavement | At the Intersection of Routes J-40 and V-56 |  |  | 3016 | 3016 | Fully Completed | Local Secondary Road Fund | 2009-09-22
| REPLACE 50' x 60" STEEL PIPE CULVERT | ON 155TH STREET WEST OF TEAL AVENUE 1/4 MILE |  |  | 8127.84 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND | 2010-07-30
| REPLACE BRIDGE WITH TANK CAR | DAVIS-VAN BUREN COUNTY LINE 1/4 MILE NORTH OF 245TH STREET |  |  | 15560.48 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND | 2010-12-03
| Replace I-Beam bridge with Railroad Tank Car Culvert | On Nova Ave 1/8 mile South of 280th St. |  |  | 20668 | 20668 | Fully Completed | Local Secondary Road Fund | 2009-08-16
| REPLACE WOODEN BLACK BOX WITH 72' X 60" CMP AND CLEAN AND SHAPE DITCHES | ON 115TH STREET, 1/4 MILE EAST OF BIRMINGHAM CITY LIMITS |  |  | 16338.26 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND | 2010-08-11
| WELLS BRIDGE REPALCEMENT WITH BOX CULVERT FHWA NUMBER 329120 | 200TH ROAD WEST OF V64 |  |  | 160220 | 0 | Fully Completed | LOCAL SECONDARY ROAD FUND (LOCAL MATCH) | 2010-11-01
Van Horne | 2009 Sealcoat project | Van Horne | 3127.27 | 3805.08 | 17093 | 3127.27 | Fully Completed |  | 2009-08-07
Van Meter | Project not yet determined | Van Meter, Iowa | 3782.43 | 4602.23 | 0 | 0 | Not Started | I-Jobs | 2011-03-31
| Project not yet determined | Van Meter, Iowa |  |  | 0 | 0 | Not Started | I-Jobs | 2011-12-31
| roadway maintenance - added limestone on Richland Circle; and used contractor, The Pavement doctor, to repair asphalt | Richland Circle and multiple street patching |  |  | 2000 | 1981 | Fully Completed | I-Jobs | 2009-09-14
Varina | Ice and snow removal from storm | City streets | 325.27 | 395.77 | 242.24 | 242.24 | Fully Completed | Road Use I-Jobs funds | 2010-01-21
| Repair Streets after tornado | Various streets in city | 325.27 | 395.77 | 19650 | 478.8 | Fully Completed | Road Use funds, Disaster Grants, I-Jobs | 2011-09-06
Ventura | Main Street & West Lake Street Reconstruction Project | Ventura, Iowa, Main Street and West Lake Street | 2926.36 | 3560.62 | 3500000 | 3560.62 | Fully Completed | STP Funding, Enhancement Funding, General Obligation Bond, Special Assessments, IJOBS | 2012-12-31
| Street sweeper purchased 8/25/2009 Used 1998 Elgin Pelican (came from the City of Mason City via Trans Iowa) Check #19472 $37,500 paid on 9/14/2009 | Item was purchased from Trans Iowa, 4607 SE Rio Court, Ankeny, IA 50012 |  |  | 37500 | 2926.36 | Fully Completed | IJOBS and reserves from Road Use Fund | 2009-09-14
Villisca | Remove curb and widen U Avenue from High Street to 1st Street. | U Avenue from 1st St to High | 5870.19 | 7142.49 | 25000 | 13012.68 | Fully Completed | IJobs and Road Use Tax money | 2011-05-30
Vincent | Grading / Asphalt grindings for alleys | Alleys South of Brewster St. and east of North 1st. Street. Alley in Northwest corner of town by church between W. 2nd St. and W. 3rd St. | 547.13 | 665.71 | 5896 | 0 | Fully Completed | IJobs Road Use Tax fund | 2009-10-14
Vining | Fill holes and repair roadway all the way thru town. Fill potholes with new rock or use cold patch. Try to fix coldpatch areas that were fixed incorrectly by council members. | Second Street from Hwy E-44 to Fourth Avenue | 172.7 | 210.14 | 0 | 0 | Not Started | IJOBS money and if need be from savings | 2011-09-30
| Fill holes and repair roadway all the way thru town. Fill potholes with new rock or use cold patch. Try to fix coldpatch areas that were fixed incorrectly by council members. | Second Street from Hwy E-44 to Fourth Avenue |  |  | 1500 | 0 | Not Started | IJOBS money and if need be from savings | 2011-09-30
| Need rock delivered for repairing of potholes in roads from Hwy V-18 to 2nd Avenue and other potholes on streets | Hwy V-18 to 2nd Avenue and various other areas in town |  |  | 350 | 0 | Not Started | $210 from IJOBS should cover it for load of rock | 2011-11-07
| Repair 2nd Street from Main Street to 2nd Avenue to help with drainage issues | Vining, Iowa |  |  | 1666.53 | 0 | Fully Completed | we will use from savings if not enough in regular budget to accomplish | 2010-10-01
| Want to use cold patch to fill in potholes. | From Highway V-18 East down First Street all the way to County Road E-44. And also from Main Street from Highway V-18 to corner of First Street. |  |  | 1200 | 382.84 | Fully Completed | Savings account | 2010-09-09
Vinton | Building a new extension of West 11th Street. | North of the intersection of West 13th Street and K Avenue. | 22284.02 | 27113.84 | 170000 | 49397.86 | Fully Completed | From I-Jobs Street Construction funds (FY2010 and FY2011): $49,437 and from city reserve funds: $120,563. | 2010-05-03
Volga City | The funds will be used to assist the City of Volga in maintenance of roadways or equipment used for roadway maintenance | City of Volga | 748.19 | 910.36 | 910.36 | 910.36 | Fully Completed | Local funds matched with the special Road Use/IJobs funds received | 2011-06-30
| The Project will consist of maintenance on streets or equipment purchase to assist in maintenance on streets | unknown |  |  | 936.23 | 748.19 | Fully Completed | local funding | 2010-06-01
Wadena | replace damaged snow sewer | Water Avenue and Iowa Street | 634.31 | 771.8 | 771.8 | 771.8 | Fully Completed | $771.80 from I-Jobs | 2010-09-30
| storm sewer maintenance | River Street |  |  | 634.31 | 634.31 | Fully Completed |  | 2009-09-24
Wahpeton | Heat Crack Repairs | Danny Ave. | 2001.59 | 2435.41 | 13042.8 | 2435.41 | Fully Completed | I-Jobs, Property Tax, Road Use Tax | 2011-08-05
| Replace Bridge Street Bridge | on Bridge Street over canal |  |  | 143840.3 | 2001.59 | Fully Completed | Road Use Tax Fund, General Fund | 2010-05-14
Walcott | Reconstruction of the pavement for Memorial Road between County Road Y-40 and Main Street. Includes removal of the existing seal coat pavement, concrete curbs, sidewalks and driveway approaches. | Memorial Road between County Road Y-40 (A.K.A. Blue Grass Rd) and Main Street | 6673.85 | 8120.34 | 1131087.5 | 14794.19 | Fully Completed | Road Use Tax, Local Option Sales Tax, IJobs, and General Fund | 2010-03-31
Walford | 2010 Seal Coat Street Repairs | Various Streets | 5346.07 | 6504.77 | 26475.56 | 6504.77 | Fully Completed | Road Use Taxes | 2010-08-30
| Drainage and Grading of Drainage lots | 4th street North |  |  | 68503 | 5346.07 | Fully Completed | Road Use Taxes | 2009-09-15
Walker | Purchase of salt/sand mixture for 09/10 season. | Streets of Walker | 3275.78 | 3985.77 | 3262.08 | 3275.78 | Fully Completed | I-Jobs monies then regular budget | 2009-12-16
| Purchase of salt/sand mixture for 09/10 season. Purchased 26.48 tons to date ($1,198.22). | Streets of Walker |  |  | 5000 | 3275.78 | Fully Completed | When funds are gone will use regular budget monies. | 2009-12-10
| Repair & Seal Coat frost eruptions on Bever St, Park St, Wallington St, Maple Ln, Prairie Dr, Elk Ct, Buffalo Ct, | Streets of Walker, IA |  |  | 27843.1 | 3985.77 | Fully Completed | RUT monies | 2010-08-26
Wall Lake | Blacktop Services laid one half inch of blacktop and seal coated it with granite chips | two blocks of main street and intersecting block of 2nd street | 3673.24 | 4469.37 | 43881 | 0 | Fully Completed | Road-Use Tax | 2011-09-08
| City of Wall Lake tore out and completely rebuilt two storm drains. | Both storm drains are located on West 1st Street |  |  | 3900 | 3673.24 | Fully Completed |  | 2009-07-30
| City painted lines on county road d-54 heading east out of town | City of Wall Lake |  |  | 804.07 | 804.07 | Fully Completed | I-jobs | 2011-04-15
Wallingford | Snow Removal from Side Streets | City Side Streets | 549.68 | 668.82 | 4000 | 549.68 | Fully Completed | Road Use Tax Fund | 2011-05-01
| Snow Removal on city streets | City side streets |  |  | 4000 | 668.82 | 50% or More Complete | I-JOBS Road Use Tax | 2011-05-02
Walnut | Repair and Maintenance of City Streets | City of Walnut | 3830.48 | 4660.69 | 3830.17 | 3830.17 | Fully Completed | I-Jobs | 2011-01-06
| Repair and Maintenance of City streets | City of Walnut |  |  | 4675 | 4661 | Fully Completed | I-Jobs | 2010-08-31
| Replacement of the Shoulder along Pearl Street | north side of Pearl Street |  |  | 9287.45 | 0 | Fully Completed |  | 2009-10-01
Wapello | 2011 SealCoat Project in Wapello | North Pine St, North Prairie St, Marshall St and washington | 9277 | 11287.69 | 22311 | 11287.69 | Fully Completed | Road Use Funds | 2011-09-09
| Asphalt two blocks of North 2nd Street | Downtown - North 2nd street |  |  | 29670 | 9277 | Fully Completed | Street Fund | 2009-08-07
Wapello County | Full depth concrete patching | Madison Avenue from 65th Street to Highway 63 | 88809.26 | 105785.03 | 77727.37 | 77727.37 | Fully Completed |  | 2009-09-15
| Full Depth HMA patching and 2" HMA Ashpalt Overlay | Maddison Ave from 65th Street to Hwy 63. 1/2 mile of 65th St from Milner Ave easterly. |  |  | 255000 | 105785.03 | Fully Completed | I-Jobs monies and local funds | 2010-08-30
| Purchase and delivery of 1,000 Ton of salt | West Point Iowa |  |  | 70827.4 | 11081.89 | Fully Completed |  | 2009-09-21
Warren County | Patching | S23 Hwy in Lacona | 123038.23 | 148223.44 | 40800 | 40800 | Fully Completed | IJOBS | 2012-05-11
| Pavment markings | Various in Warren County |  |  | 39734.15 | 39734.15 | Fully Completed | IJOBS | 2011-10-21
| PCC full depth patching, various areas in Warren County | Warren Co roads, G-24, G-16, G-36, S-31, G58, G-76, R-45 and Crestview Drive |  |  | 122843.73 | 122843.73 | Fully Completed | IJOBS | 2010-10-01
| Repair pavement in 2 intersections | Interseciton of Hwy R63 & Hwy G14 & Intersection of Coolidge and Hwy R57 |  |  | 72473.6 | 67883.79 | Fully Completed | IJOBS | 2012-04-24
Washington | Build new Waste Water Treatment Facility for City of Washington , IA - project cost bid $14,987,500. New construction to replace old outdated facaility. | 1065 West Buchanan St Washington, IA 52353 | 30779.2 | 37450.27 | 14987500 | 0 | Less than 50% Complete | SRF Loan - DNR Project #CS-192522-01. | 2013-04-30
| Replacement of South 9th Ave., mill and overlay of Polk St.. 5th St. & Iowa Ave. and intersection of 5th St. & Madison Ave. Mill & ovedlay of 5th St. from Madison Ave, to North 2nd Ave. | Washington, IA - South 9th Ave., 5th St. & Iowa Ave. |  |  | 1068236 | 68229.47 | Less than 50% Complete | Federal participation thru Iowa DOT | 2011-06-30
| To Be Determined at a Later Date | Washington, Iowa |  |  | 0 | 0 | Not Started | I-JOBS | 2011-12-31
Washington County | 2009 Caterpillar 140M Motorgrader | Washington County Maintenance Garage, 821 E 7th St, Washington, IA 52353 | 99933.71 | 122086.62 | 158715 | 99933.71 | Fully Completed | Secondary Road Fund | 2009-11-02
| 2010 Caterpillar 140M Motorgrader | Washington County Maintenance Garage, 821 E 7th St, Washington, IA 52353 |  |  | 153570 | 122086.62 | Fully Completed | Secondary Road Fund | 2010-08-04
Washta | seal coat and asphalt overlay | Washta | 857.84 | 1043.77 | 59185 | 1043.77 | Fully Completed | Road Use monies and I-Jobs money | 2010-09-17
| seal coat and patch work | washta |  |  | 19412.4 | 857.84 | Fully Completed |  | 2009-07-30
Waterloo | Purchase of salt for snow and ice control. | Citywide | 300266.47 | 365346.03 | 390000 | 243884.86 | Fully Completed | Road Use Tax Fund | 2010-03-26
| Salt Purchases for Waterloo, Iowa | Citywide |  |  | 439674.34 | 336709.64 | Fully Completed | Road use tax and I-Jobs funding | 2011-06-30
| The City recycles asphalt from streets undergoing reconstruction. The City hires a contractor to crush the asphalt into material usable for other purposes, such as surface material for unimproved streets. | Waterloo |  |  | 85018 | 85018 | Fully Completed | Road Use Tax Fund | 2010-07-31
Waterville | City of Waterville has not yet determined a project | To be determined | 432.05 | 525.69 | 0 | 0 | Not Started | IJOBS | 2009-09-23
| City of Waterville has not yet determined a project | To Be Determined |  |  | 0 | 0 | Not Started | IJOBS | 2009-12-27
| Re Rock and Grade East Railroad Lane in Waterville | East Railroad lane, Waterville IA |  |  | 548.37 | 432.05 | Fully Completed | IJOBS and RUT Money | 2010-05-20
| replace culvert and cement on road | 82 Main Street |  |  | 2617 | 525.69 | Fully Completed | IJOBS and RUT money | 2011-08-18
| to be determined | to be determined |  |  | 0 | 0 | Not Started | to be determined | 2010-03-28
Waukee | Boone Drive Curb & Gutter Project | Boone Drive at Olson Drive | 35518.16 | 43216.34 | 65000 | 43216.34 | 50% or More Complete | IJOBS Road allocation and RUT | 2011-04-30
| Warrior Lane Asphalt Overlay Project | Warrior Lane from University Ave to Ashworth Dr |  |  | 274500 | 35518.16 | Fully Completed | Capital Projects Cash IJOBS August 09 funds | 2009-12-01
Waukon | Airport driveway repairs & repairs to north entrance of Fairground | Airport and Fairgrounds | 18042.98 | 21953.6 | 21953.6 | 21953.6 | Fully Completed | I-Jobs Fund | 2011-06-09
| Place 2.5" overlay on a secton of roadway in the City Park,paved with 2.5" of compacted hot mix asphalt and place 3" of compacted hot mix asphalt on three small parking areas. | Waukon City Park |  |  | 23450 | 18042.98 | Fully Completed | Street Improvements Fund | 2009-11-16
Waverly | Bituminous Seal Coat Program involves the seal coating of approximately 110 city blocks. | Various areas with the city limits | 39169.56 | 47659.14 | 125000 | 39169.56 | Fully Completed |  | 2009-08-01
| Bituminous seal coat program involves the seal coating of approximately 90 city blocks. | Various areas within the city limits. |  |  | 47659 | 0 | Fully Completed | Local Option Sales Tax and I-Jobs | 2010-08-16
Wayland | repair intersection resurface with cement 150' | hwy 78 & jefferson St | 4127.48 | 5022.07 | 20000 | 9149.55 | Fully Completed | Road Use Tax | 2010-05-28
Wayne County | Brush Cutting in Wayne County | Intersection of Summit and 50th St. | 75238.94 | 92621.09 | 4541.42 | 4541.42 | Fully Completed | IJOBS | 2009-09-11
| Purchase 4529 tons of aggregate for repair and maintenance of gravel roads | various sites in Wayne County |  |  | 53443.38 | 53443.38 | Fully Completed | IJOBS | 2011-03-02
| Purchase of Aggregate for roads from stock pile | Plano, Iowa |  |  | 13997.63 | 13997.63 | Fully Completed |  | 2009-08-10
| Purchased a Caterpillar 140M Motorgrader | Alttona, IA 50009-7200 |  |  | 177418 | 92621.09 | Fully Completed | I-Jobs | 2011-05-16
| Repair Tractor | Corydon, Iowa |  |  | 7349.89 | 7349.89 | Fully Completed |  | 2009-09-15
| Used 2007 Volvo Tractor Truck | Des Moines, Iowa |  |  | 49350 | 49350 | Fully Completed |  | 2009-08-27
Webb | Snow Removal for Winter 2010-2011 | Msin St | 494.89 | 602.15 | 400 | 272.04 | Fully Completed | Road Use Tax Fund | 2011-02-28
| Snow Removal for Winter 2010-2011 | Main Street |  |  | 825 | 825 | Fully Completed | Road Use Tax Fund | 2011-01-31
Webster | Covering street with a new layer of gravel | Market ST. From Lafayette ST. to the end of Market ST. | 392.8 | 477.93 | 201.73 | 201.73 | Fully Completed | IJOBS | 2009-09-30
| Repair areas of broken pavement | Junction of Lafayette ST and Highway 22 |  |  | 220 | 191.07 | Fully Completed | Road Use Fund | 2009-12-01
| Replace broken paving with new concrete | Junction of South St and East ST Fixmer St |  |  | 13139 | 477.93 | Fully Completed | IJobs Roas Use Tax Monies | 2010-10-18
Webster City | 2010 STREET RECONSTRUCTION PROJECT. | PATCHES ON GRAND ST & BICENTENNIAL ST. RECONSTRUCTION OF LEWIS DRIVE & DES MOINES ST INTERSECTION IN WEBSTER CITY, IOWA | 35710.34 | 43450.18 | 312827.14 | 79160.52 | Fully Completed | Capital Improvement Funds (local option sales tax money) and IJOBS Road Funding money. | 2010-09-04
Webster County | Purchase roadstone to be used in the maintenence of secondary roads. | Countywide | 142993.57 | 175531.85 | 189100 | 175531.85 | Fully Completed | Local | 2010-09-07
| Purchase roadstone to be used in the maintenence of secondary roads. | Countywide- Webster County |  |  | 225900 | 142993.57 | Fully Completed | Local | 2010-06-30
Weldon | resurface with rock and chip | 2nd Street East | 564.56 | 686.92 | 1500 | 1251.48 | Fully Completed | IJOBS | 2010-06-30
Wellman | repair and replace curbing and storm sewer repairs | Circle Drive | 6084.21 | 7402.9 | 2133.5 | 4267 | Fully Completed | I jobs | 2010-11-04
| resurfacing streets, chip & seal | various sections of streets |  |  | 27367 | 5323.53 | Fully Completed | ROAD USE TAX FUNDS AND IJOB FUNDS | 2011-10-05
| street improvement, paving and/or curb and gutter | Wellman |  |  | 6200 | 6084.21 | Fully Completed | I Job funds | 2010-06-15
Wellsburg | Repair storm sewer intakes | Washington St. from 1st St. to 4th St. | 3127.27 | 3805.08 | 29700 | 3127.27 | Fully Completed |  | 2009-09-24
Welton | Purchase of rock for shoulder of Old Hwy 61/Main Street | Old Hwy 61/Main Street | 694.47 | 844.98 | 1577.53 | 694.47 | Fully Completed |  | 2009-08-18
| Repair/replacement of culvert and ditch cleaning on Kershaw Street | Kershaw Street |  |  | 1899 | 844.98 | Fully Completed | I-Jobs funds and Road Use Funds | 2010-07-07
Wesley | Not started Zero dollars have been spent | In Wesley | 1841.3 | 2240.38 | 0 | 0 | Not Started |  | 2009-09-23
West Bend | Asphalt Milling, Asphalt Level & Single Seal | 5th Street SE, Between 1st Street SE & Broadway Avenue and 5th Street SW, Between Broadway Avenue & 1st Avenue SW | 3642.66 | 4432.17 | 14064.9 | 3642.66 | Fully Completed |  | 2009-08-03
| Asphalt Milling, Asphalt Level & Single Seal | 2nd Street NE, Between 1st Avenue NE & 2nd Avenue NE |  |  | 5787 | 4432.17 | Fully Completed | General Fund | 2010-07-09
West Branch | Cleaned intake boxes storm sewer and jetted line. | Main Street from Post Office to creek, south side of road going west to east. | 9556.53 | 11627.81 | 5000 | 4581.25 | Fully Completed | I-jobs road funding | 2010-09-17
| Concrete street patching and repair | Various locations within the City |  |  | 19000 | 9556 | Fully Completed | IJOBS funding and Road Use Tax funds | 2010-06-30
| Install manhole to change direction and allow for clean out, re-route storm sewer. Trucking and roadstone. | West side of Main Street bridge |  |  | 3505.04 | 3505.04 | Fully Completed | I-Jobs road funding | 2010-09-15
| Premix concrete | Used on various City streets. |  |  | 497.25 | 497.25 | Fully Completed | I-Jobs road funding. | 2011-06-20
| Purchase of grate, curb box and frame for street storm sewer. | Corner of Poplar St. and Main Street |  |  | 507.68 | 507.68 | Fully Completed | I-jobs road funding | 2010-10-27
| Repair and Maintenance on College St., widening of the street and installing storm sewers,catch basins and sealcoat work. | College St. West Branch, IA 52358 |  |  | 15000 | 2537 | Fully Completed | I-Jobs funding and Road Use tax funds | 2011-10-31
West Burlington | 2 LED stop signs for Division and Gear intersections 2 LED stop signs for Longmeadow and Ramsey interesections | Division and Gear intersections Longmeadow and Ramsey intersections | 13806.31 | 16798.68 | 8096.38 | 8096.38 | Fully Completed | I Job Funds | 2009-10-30
| Seal Coat Streets various streets through out the City of West Burlington. | Throughout City |  |  | 49445.84 | 22508.61 | Fully Completed | Road Use Funds and I-Job Funds | 2011-09-30
West Des Moines | 2009 HMA Resurfacing Program | Ashworth Road - Valley West Drive to 50th St | 226260.11 | 275299.58 | 616059.58 | 226260.11 | Fully Completed | GO Bonds | 2009-11-20
| 2010 HMA Resurfacing Project | Ashworth Road - 1st Street to 11th Street |  |  | 503522.49 | 275299.58 | Fully Completed | GO Bonds | 2010-11-30
West Liberty | Asphalt Resurfacing _________________________ | 300 block of east eighth Street - 50 foot section | 14553.19 | 17707.43 | 6825 | 0 | Fully Completed | Road Use Tax | 2009-11-13
| Remove & Replace brick street intersection with pcc slab base and brick surface, R&R curb & gutter, R&R walk adding ADA domes, connect house drain to storm sewer | Intersection of Fourth and Clark Streets |  |  | 18000 | 17707.43 | Fully Completed | General Fund - Local Streets | 2011-06-30
| Street Tree Trimming _________________ | Highway 6/East Third Street - 300 to 700 blocks |  |  | 10700 | 0 | Fully Completed | Road Use Tax | 2009-11-15
West Point | Purchase of road oil for sealcoating of City of West Point streets. | West Point, Iowa | 4280.35 | 5208.07 | 9488.42 | 9488.42 | Fully Completed | IJOBS | 2010-09-30
| Purchase road oil for sealcoating of city streets | City wide |  |  | 6000 | 0 | 50% or More Complete | I-Jobs | 2011-09-15
West Union | City will be using I-JOBS funds to apply to the purchase of a new street sweeper | West Union, Iowa | 11133.28 | 13546.29 | 150000 | 0 | Fully Completed |  | 2011-06-30
Westphalia | Truck updates | 207 Flusche Street, Westphalia, Iowa | 589.97 | 717.84 | 1380 | 1307.81 | Fully Completed | City and County Road funding | 2010-10-10
Westside | Reconstruction of street including storm sewer, curb & gutter | First Street | 1027.97 | 1250.77 | 9073 | 1027.97 | Fully Completed |  | 2009-08-25
Westwood | Contract - Westwood 01 In Progress - to be completed in April 2012, Bid = $36,800.00 Road repairs, patching and filling | Westwood Drive, Sycamore Dr, Hickory lane, Bittersweet Dr. | 554.7 | 674.92 | 36800 | 0 | Not Started | RIIF, Roud Use Funds, General Funds | 2012-05-31
| road repairs, patched sections of road with new asphalt | 4006 Sycamore Dr to 4013 Sycamore Dr |  |  | 7500 | 554.7 | Fully Completed |  | 2009-09-16
| Road repairs, patching and crack fill and seal coating | Westwood Dr, Bittersweet Circle, Hickory Lane,Oak Lane, and Sycamore Dr. |  |  | 12000 | 0 | Not Started | Road use tax and general funds (property taxes) | 2010-09-30
| road repairs, patching and fill crackss & seal coat | Sycamore Dr., Oak Lane and or low half of Westwood Dr. |  |  | 12000 | 0 | Not Started | Road Use Tax and General Funds ( property tax ) | 2011-10-31
What Cheer | New gravel on some of the towns gravel roads. | East and West Section Streets East and West Briney Streets East Mill Street Ohio Street | 2961.3 | 3603.13 | 3924.24 | 2961.3 | Fully Completed |  | 2009-09-01
Whiting | Repair potholes and worn down gravel roads in city | Whittier, West, Willard, Walnut & Maple St | 3498.53 | 4256.8 | 4261 | 3498.53 | Fully Completed | Road use tax | 2009-07-20
| Repairing pot holes and rough roads due to weather | gravel roads in Whiting |  |  | 14514.5 | 4256.8 | Fully Completed | road use | 2010-04-13
Whittemore | Needed repairs to streets throughout the community | various locations | 2314.88 | 2816.61 | 3500 | 2314.88 | Fully Completed | Road Use Tax | 2009-12-10
| TO BE DETERMINED AT A LATER DATE | TO BE DETERMINE |  |  | 0 | 0 | Not Started | Road Use Tax | 2009-09-30
Whitten | Asphalt Hardin and Center Streets | south Hardin St in Whitten and west Center St in Whitten | 434.89 | 529.16 | 20916.4 | 529.16 | Fully Completed | Road Use Tax and Local Option Sales Tax | 2010-08-16
| repairing and replacing parts on the snow plow truck | Conrad |  |  | 1778.15 | 434.89 | Fully Completed | Road Use Tax Fund | 2009-11-04
| to be determined just setting up this report | to be determined |  |  | 0 | 0 | Not Started | Road Use Tax Fund | 2009-10-15
Williams | Crack Sealing on City street as needed | Fourth Street | 1865.01 | 2269.23 | 15000 | 4134.23 | Fully Completed | Road Use Tax Fund | 2009-10-31
Williamsburg | Core out spots on road, repair, and overlay. | North Street Sunset Avenue | 11452.12 | 13934.24 | 5000 | 9684 | Fully Completed | $4,842.00 | 2010-09-24
| Removal of miscellaneous trees, cleaning of inlet and outlet of Industrial Park Drive Souble Box Culvert | Industrial Park Drive Project cost $3,850.00 |  |  | 3850 | 7700 | Fully Completed | $3,850.00 | 2010-06-18
| Removal of rotten trees and stumps at 201 E State St | 201 E State Street Cost of project $1,400.00 |  |  | 1400 | 2800 | Fully Completed | $1,400.00 | 2009-07-27
| Removed hard maple at State and Longs Streets-including stump. Removed large hard maple from Henry Street-including stump. | State and Long Streets Henry Street |  |  | 1700 | 3400 | Fully Completed | $1,700.00 | 2010-08-02
| Removed large cracked and rotten Maple, ground out stump, chipped, cleaned, and hauled away. | 500 Chatham Street |  |  | 700 | 1400 | Fully Completed | $700.00 | 2010-02-12
| Street Sweeper purchase | City of Williamsburg |  |  | 189855 | 12894.36 | Fully Completed | 12,894.36 I-Jobs | 2011-06-30
Williamson | Rebuild ditches and new culverts | South Elden from E. Vine to E. South | 612.92 | 745.76 | 4760 | 612.92 | Fully Completed | Disaster Grant Fund; General Funds | 2009-09-04
Wilton | storm sewer repair West View | West View Park/Parkview Street | 12356.23 | 15034.31 | 19000 | 5905.26 | Fully Completed | Road Use/IJOBS | 2009-12-04
| W Division Street storm sewer | 300 block of W Division |  |  | 6500 | 6450.97 | Fully Completed | Road Use/IJOBS | 2009-09-18
Windsor Heights | 2010 John Deere 326D Skid Loader | Des Moines |  | 25992.52 | 34591.52 | 25992.52 | Fully Completed | Road Use Tax | 2010-09-30
| We have a section of concrete on University Avenue in Windsor Heights that is in real bad shape and in need of replacement. We will use the funds to get new concrete for this section and for traffic control as the project goes on. | University Avenue around the 70th Street intersection in Windsor Heights. | 21362.44 | 25992.52 | 18991 | 18991 | Fully Completed | No supplemental funds were used | 2009-11-02
| Windsor Heights Public Works Department fixed and repaired pot holes throughout Windsor Heights using cold mix. | Windsor Heights |  |  | 2897.6 | 2371.44 | Fully Completed | Windsor Heights General Fund and I-Jobs road funds | 2010-03-12
Winfield | no plans has been decided yet. | unknown | 4939.87 | 6010.54 | 0 | 0 | Not Started |  | 2010-07-30
| project not started yet | unknown |  |  | 0 | 0 | Not Started | no plans yet | 2010-06-30
Winnebago County | Replace existing structure with a 14' x 12' x 72' Concrete Box Culvert | On County Route R26/50th Avenue. From 460th Street north .25 miles to existing structure. | 69102.85 | 82950.17 | 0 | 0 | Not Started | IJOBS/Local Funds | 2009-10-21
Winneshiek County | Asphalt patching work on Co. Rd. W14, Co. Rd. W20 and Co. Rd. A34 west of Decorah, IA | Co. Rd. W14 between Ridgeway and Spillville, Co. Rd. A34 between Decorah and the Howard County line and Co. Rd. A34 and Co. Rd. W20 northwest of Decorah. | 132592.95 | 160556.54 | 150000 | 132592.95 | Fully Completed | I-JOBS, Local Effort and RUTF | 2009-08-04
| Crack seal work on Co. Rd. B32, Co. Rd. W40, Co. Rd. W42, Co. Rd. W14, Co. Rd. A46 and transverse leveling on Co. Rd. W4B | County Wide |  |  | 300000 | 160556.54 | Fully Completed | IJOBS and RUTF funds | 2010-07-13
Winterset | 2009 10th Street Storm Sewer Improvement Project. | 10th Street, starting at storm sewer intake near the intersection with Green Street. | 20825.21 | 25338.85 | 42850 | 20825.21 | Fully Completed | 20,825.21 IJOBS 22,024.79 General Obligation bond | 2009-12-01
Winthrop | Concrete Street Patching | Hamilton Street | 3371.87 | 4102.68 | 0 | 0 | Fully Completed | I-Jobs Funds | 2010-09-20
| Patching of alley behind First Street. Double Seal Coat First Street. | First Street. |  |  | 12914.35 | 6632.85 | Fully Completed | 50% I Jobs and 50% County Funds | 2010-09-20
Woden | Reclaim and recondition the street that had been turned over to the school district for safety reasons. School now closed and a new business is starting in the building. Road will need to be openned and useable. Will grade the street and gravel. Prepa | 300 block of Fox Avenue within the city limits of Woden. | 825.49 | 1004.41 | 2000 | 1829.9 | Fully Completed | I-Jobs Funding and Road Use Tax money | 2010-05-14
Woodbine | 1994 International dump truck | None | 6831.09 | 8311.65 | 13000 | 6831.09 | Fully Completed | $6,831.09 - IJobs, $6,168.91 - General Fund | 2009-10-01
| Cleaned side road ditch, installed drain tile | Rawlins Avenue between 1st Street and Perry Trail |  |  | 5064.92 | 5064.92 | Fully Completed | $5,064.92 I-Jobs | 2010-09-07
| Supplier of 6.09T cold patch the City crew put out in various locations around town | Various location throughout the City of Woodbine |  |  | 718.62 | 624.07 | Fully Completed | I-Jobs -$624.07 General Fund - $94.55 | 2010-07-30
| Tore out broken aprons, and Re-concreted two alley aprons | 5th Street between Park and Normal Streets |  |  | 1187.5 | 1187.5 | Fully Completed | $1,187.50 I-Jobs | 2010-08-13
| Tore out cracked curb and re-concreted curb and pavement by the curb | On Lincoln Way between 4tha nd 5th Streets |  |  | 1435.16 | 1435.16 | Fully Completed | $1,435.16I-Jobs | 2010-09-10
Woodburn | Money was put towards Asphalt Project | City of Woodburn | 967.69 | 1177.43 | 85138.2 | 1177.43 | Fully Completed | I-JOBS/RUT/GENERAL | 2010-11-12
| Money was used for snow removal of the city streets. | City of Woodburn |  |  | 3800 | 967.69 | Fully Completed | I-JOBS | 2010-06-30
Woodbury County | Asphalt patching on County Highway L-21 and Lakeport Road | County Highway L21 in Grant Twp. from W1/4 Corner Sec. 15-87-44 to N1/4 corner sec. 1-87-44. County Highway K-29, Lakeport Road. | 163617.76 | 195335.36 | 135962.78 | 135962.78 | Fully Completed | Entire project funded with I Jobs money. | 2009-11-15
| HMA resurfacing of 230th Street and a portion of Story Avenue. | 230th Street and Story Avenue on the north and east sides of section 9-87-42 |  |  | 265346.49 | 222990.34 | Fully Completed | I Jobs funding plus local secondary road funds | 2010-11-15
Woodward | Crack Seal N 3rd Street on the North West side of Town. | N 3rd Street Woodward IA | 5241.24 | 6377.23 | 5300 | 5241 | Fully Completed | I Job Money and General Fund | 2010-06-30
| Repair approaches with cement. | E 2nd Street |  |  | 3242 | 3242 | Fully Completed | I Jobs & General Fund | 2010-12-01
Worth County | Deicing salt for Secondary Roads | Worth County storage shed, Kensett, IA | 70734.43 | 87391.24 | 110289.86 | 87391.24 | Fully Completed | Secondary Road Funds | 2011-01-31
| Granular Surfacing of Secondary Roads | Various locations in Worth County |  |  | 285740 | 70734.43 | Fully Completed | Local Funding | 2009-09-01
Worthington | Double seal coating all the alleys. | Various around town. | 1131.83 | 1377.14 | 19000 | 1131.83 | Fully Completed | Streets portion of local option sales tax. | 2009-09-18
| Mill out old asphalt and repave. | 1st Avenue East from Hwy 136 to 2nd Street NE |  |  | 26599.75 | 1377.14 | Fully Completed | I-JOBS and local option sales tax. | 2010-09-24
Wright County | Purchased a stockpile of road rock from local vendor to supply county secondary road surfacing. | Wright County granular roads | 94583.69 | 116405.64 | 222250 | 111902.13 | Fully Completed | Federal IJobs | 2012-01-09
| Slurry Leveling on transverse thermal cracks and road width | C32 |  |  | 61409 | 61409 | Fully Completed | Federal IJobs | 2009-11-15
| Slurry Leveling on transverse thermal cracks. | R45 and C25 |  |  | 37678.2 | 37678.2 | Fully Completed | Federal IJobs | 2009-08-17
Wyoming | seal coat | Jones Street from Hwy 136 to South Oak St. | 2734.18 | 3326.79 | 22328.6 | 2734.18 | Fully Completed |  | 2009-09-11
| Seal coat South Oak St. from West to Jones. Base repair and rock. | Wyoming IA |  |  | 0 | 0 | Not Started | Road Use tax and I-jobs funding | 2011-06-13
Yale | Blacktop of streets within city limits | various streets in Yale | 1078.54 | 1312.3 | 22000 | 1078.54 | Fully Completed | Road Use Tax Fund and Special Revenue Income | 2009-09-30
| repair, maintain, and refurbish various streets throughout town | several blocks |  |  | 20650 | 1312.3 | Fully Completed | road use tax fund, ijobs, special revenue | 2010-09-08
Yetter | Removing Snow from streets | Streets of City of Yetter | 109.44 | 133.16 | 109.44 | 109.44 | Fully Completed | I Jobs Road Funding | 2009-12-17
| Snow Removal in Yetter, Iowa | Various Location in Yetter |  |  | 225 | 133.16 | Fully Completed | I-JOBS and RUT | 2010-11-13
Zwingle | Repair storm water inlet under Washington Mill Road. Install large rip-rap to stabilize bank and inlet tube. | 60 Washington Mills Road, highway storm water inlet | 332.41 | 404.45 | 860 | 332.41 | Fully Completed | RIIF, ARRA, Road Use Tax funds | 2009-09-23

## RRLGP
FY 2014 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
HFCA (HF Chlor Alkali) Rail Road Project | Construction of three miles of new (private) track for new Cargill Plant | 150000000 | 324000 | Company match | 0 | 324000 | Agreement under review | 2017-01-01
Iowa Corn Processors (ICP) Rail Expansion | Construction of two spur tracks on ICP property to add capacity | 14832000 | 419000 | Company Match | 0 | 419000 | Agreement under review | 2017-01-01
Carter Lake Metals Processing Building (Owen Industries) | Construction of new rail spur to accommodate new production building | 30000000 | 108000 | Company Match | 0 | 108000 | Project in process | 2015-07-01
Heartland Co-op Greenfield Rail Loading Elevator | Build a 125-car load out facility | 24000000 | 1450000 | Company Match | 0 | 1450000 | Agreement under review | 2017-01-01
CRANDIC - Millrace & Price Creek Bridges | Replacement of two bridges | 2840000 | 725000 | Company Match | 0 | 725000 | Agreement under review | 2017-01-01
City of Knoxville - Red Rock Industrial Park | Planning Study | 118000 | 94400 | Local match | 0 | 94400 | Project in process | 2015-06-01
|  | 221790000 | 3120400 |  | 0 | 3120400
FY 2013 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
CRANDIC Iowa River Crossing North Bridge | Consruct replacement rail bridge | 2840400 | 1500000 | Company match | 0 | 1500000 | Completed - drawing money now | 2013-12-31
Iowa Falls UP/CN Connector | Upgrade rail infrastructure in industrial area | 5711369 | 900000 | Local match | 0 | 900000 | Agreement under review | 2014-12-31
Rail One | Industrial Rail Spur Construction | 4397880 | 1116000 | Company match | 1116000 | 0 | Project in process: needs certificate of completion | 2014-12-31
BJRY Rail/Truck/Barge Planning Study | Planning Study | 50000 | 40000 | Local match | 0 | 40000 | Agreement in process | 2014-09-30
Central Iowa Transloading Facility Feasibility Study | Planning Study | 125000 | 100000 | Local match | 0 | 100000 | Project in process | 2014-09-30
Iowa Falls/Hardin County Rail Port Planning Study | Planning Study | 125000 | 100000 | Local match | 80099 | 19901 | Project in process | 2014-09-30
Mills/Pottawattamie County Rail Port Study | Planning Study | 98000 | 78400 | Local match | 42641 | 35759 | Project in process | 2014-09-30
North Central Ag Park Planning Study | Planning Study | 100000 | 80000 | Local match | 0 | 80000 | Agreement under review | 2014-09-30
Sioux City Rail Study Phase II | Planning Study | 350000 | 100000 | Local match | 0 | 100000 | Project in process | 2014-09-30
|  | 13797649 | 4014400 |  | 1238740 | 2775660
FY 2012 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway Spur rehabilitation | Industrial Rail Spur Construction | 197435 | 157948 | Company match | 0 | 157948 | Project in progress | 2014-12-31
Butler Cross Dock | Industrial Rail Spur Construction | 1758922 | 705621 | Local match | 0 | 705621 | Agreement under review | 2014-12-31
Cherokee Industrial Spur | Industrial Rail Spur Construction | 771818 | 617454 | Local match | 617454 | 0 | Complete | 2012-04-17
CRANDIC Iowa River Crossing Improvement | Consruct replacement rail bridge | 3200000 | 1613596 | Company match | 0 | 1613596 | Completed - drawing money now | 2013-12-31
Global Foods | Rail Spur upgrade | 358525 | 72000 | Local match | 0 | 72000 | Agreement under review | 2013-12-31
Iowa River Railroad | Rail line acquisition & preservation | 2500000 | 1000000 | Company match | 0 | 0 | Project withdrawn by applicant | Not applicable
North Central Iowa Rail Corridor, LLC | Rail line acquisition & preservation | 1900000 | 400000 | Local match | 400000 | 0 | Complete | 2012-04-26
Valley Distribution Corporation | Industrial Rail Spur Construction | $ 297, 525 | 218652 | Company match | 218652 | 0 | Complete | 2012-04-18
Waverly GMT Rail Spur | Industrial Rail Spur Construction | 538100 | 389676 | Company match | 369276 | 20400 | Project in progress | 2014-12-31
|  | 10686700 | 5174947 |  | 1605382 | 2569565
Note 1: CRANDIC was awarded $2,000,000 from RRLG, however $386,404 of the award is from federal Rail Assistance Program (RAP) funds.
FY 2011 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Adams County Rail | Industrial Rail Spur Extension | 1758922 | 879461 | Local match | 0 | 0 | Project withdrawn | Not applicable
Eastern Iowa Industrial Center | Construct Transloading Facility | 8474244 | 2000000 | Federal, state and local match | 0 | 2000000 | Agreement under reivew | 2014-12-31
Lomont Molding Inc | Rail Spur upgrade | 138560 | 110848 | Company match | 0 | 0 | Project withdrawn | Not applicable
Nypro Kannaak | Rail Spur upgrade | 255951 | 174022 | Company match | 174022 | 0 | Completed | Construction complete 11/14/2012
|  | 10627677 | 3164331 |  | 174022 | 2000000
FY 2010 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Upgrade rail infrastructure in industrial park | 88000 | 55400 | Railroad match | 55400 | 0 | Completed | 2011-01-10
Cedar Rapids and Iowa City Railroad (CRANDIC) | Rebuild rail bridge | 886500 | 700000 | Railroad match | 700000 | 0 | Completed | 2011-04-14
Schau Recycling | Install industrial rail spur | 450000 | 225000 | Company match | 145187 | 0 | Completed | 2013-02-28
Shine Brothers Corp. | Upgrade rail infrastructure in industrial area | 467589 | 311071 | Company match | 311071 | 0 | Completed | 2011-10-15
City of Waterloo | Install industrial rail spur | 252005 | 126000 | City match | 118691 | 7309 | Completed | 2013-12-31
Webster County Board of Supervisors | Install industrial rail spur in industrial park | 10900000 | 900000 | County match and company investment | 0 | 0 | Project withdrawn | Not applicable
Union Pacific Railroad and Iowa Northern Railway | Rebuild rail bridge in Waterloo* | 5437200 | 1000000 | Railroad match and FRA grant award | 1000000 | 0 | Completed | 2009-12-31
| TOTAL | 18481294 | 3317471 |  | 2330349 | 7309
FY 2009 Railroad Revolving Loan and Grant Program (Flood Recovery)
Railroad | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Repair rail infrastructure damaged by flooding | 89333 | 71000 | Railroad match | 61164 | 0 | Completed | 2009-01-01
Cedar Rapids and Iowa City Railroad (CRANDIC) | Repair rail infrastructure damaged by flooding | 400000 | 320000 | Railroad match | 320000 | 0 | Completed | 2008-11-01
Keokuk Junction Railway Company | Repair rail infrastructure damaged by flooding | 693120 | 554000 | Railroad match | 405346 | 0 | Completed | 2009-03-01
Iowa, Chicago & Eastern Railroad Corp. | Repair rail infrastructure damaged by flooding | 1771463 | 1417000 | Railroad match | 1406627 | 0 | Completed | 2009-10-01
Iowa Interstate Railroad | Repair rail infrastructure damaged by flooding | 964707 | 772000 | Railroad match | 650000 | 0 | Completed | 2009-03-01
Iowa Northern Railway Co. | Repair rail infrastructure damaged by flooding | 851704 | 681000 | Railroad match | 616420 | 0 | Completed | 2008-11-01
Iowa River Railroad | Repair rail infrastructure damaged by flooding | 230000 | 184000 | Railroad match | 184000 | 0 | Completed | 2009-12-31
| TOTAL | 5000327 | 3999000 |  | 3643557 | 0
FY 2008 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2008 Funds used | FY 2008 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Cedar Rapids Terminal (Iowa Northern Railroad) Construct rail spur and intermodal loading facility in Palo | 884000 | 242000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Big River Resources Ethanol Plant industrial rail spur | 8500000 | 75000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Lincolnway Railport Industrial Park | 1072933 | 840000 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
| Norfolk Iron and Metal Company industrial rail spur | 1398000 | 810000 | State grant; Private investment | 810000 | 0 | Completed | 2009-09-30
| Oregon Trail Energy Rail spur | 7146000 | 75000 | State grant; Private investment | 0 | 0 | Project was withdrawn. Funding has been reprogrammed to FY2012 | Not applicable
| Prairie Creek Ethanol rail spur | 6055075 | 75000 | State Grant; Private investment | 0 | 0 | Project withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
| Raccoon Valley BioDiesel Rail spur | 2250000 | 50000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Trinity Towers | 414489 | 165795 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Unity Ethanol Cedar River | 9500000 | 270000 | State loan; Private investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
| Unity Ethanol Ottumwa | 9500000 | 270000 | State grant and loan; Private Investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
|  | 46720497 | 2872795 |  | 810000 | 0
FY 2007 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2007 Funds used | FY 2007 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Alternative Energy Resources Ethanol Plant industrial rail spur | 24240300 | 239000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Lincolnway Railport Industrial Park | 11852896 | 489000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Seimens Wind Power industrial rail spur | 457513 | 326000 | State grant; Private investment | 326000 | 0 | Complete | 2010-05-26
| Southern Bio Energy industrial rail spur | 1300000 | 250000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
|  | 37850709 | 1304000 |  | 326000 | 0
FY 2006 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2006 Funds used | FY 2006 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Absolute Energy industrial rail spur | 3712220 | 500000 | State grant and loan; Private investment; local investment | 500000 | 0 | Complete | 2008-02-05
| Cascade Lumber Company industrial rail spur | 694000 | 534000 | State grant and loan; Private investment; local investment | 534000 | 0 | Complete | 2007-09-19
| Eastern Iowa Industrial Center rail development for industrial park expansion | 4660791 | 760791 | State grant; Private investment; FHWA grant | 729711 | 31079 | Project in progress | 2014-12-31
| Green Plains Renewable Energy | 5700000 | 280000 | State grant and loan; Private investment; local investment | 126000 | 0 | Complete: loan portion of award declined | 2013-02-28
| Midwest I,LLC industrial rail spur | 2800000 | 280000 | State grant and loan; Private investment; local investment | 280000 | 0 | Complete | 2008-09-30
| Iowa Renewable Energy LLC industrial rail spur | 1258532 | 300000 | State grant and loan; Private investment; local investment | 300000 | 0 | Complete | 2007-11-01
| Lincolnway Railport Industrial park rail development | 2154086 | 319209 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed for flood recovery activities. | Not applicable
| Marco Group International industrial rail spur switching improvements | 30000 | 22500 | State grant; Private investment | 0 | 0 | Project withdrawn | Not applicable
| Metzler Automotive | 406711 | 60000 | State grant | 42691 | 0 | Complete | 2007-11-01
|  | 21416340 | 3056500 |  | 2512402 | 31079

## Rail Port FY 2011
FY 2011 Rail Port Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Wind Energy Supply Chain Industrial Park (Iowa City) | Construct rail siding | 2112400 | 1056200 | Local match | 1056200 | 0 | Project Construction Complete: certificate of completion pending | 2014-06-30
Southbridge Rail Yard (Sioux City) | Construct lead track and drop/pull yard | 6741980 | 3000000 | Local match | 0 | 3000000 | Project in progress | 2015-06-30
Manly Terminal Wind Rail Port (Worth County) | Construct rail spur and loop track | 8237468 | 3000000 | Local and private match | 2581808 | 418192 | Project in progress | 2014-12-31
Lincoln Way Rail Port (Clinton) | Construct lead track | 2032300 | 443800 | Local match | 0 | 443800 | Project in progress | 2015-06-30
|  | 19124148 | 7500000 |  | 3638008 | 3861992
updated 1-7-13

## Passenger Rail
2009 RIIF Appropriation for Dubuque Passenger Rail Depot/Platform
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Feasibility study and preliminary engineering of a depot and platform to accommodate the future AMTRAK service from Dubuque to Chicago | 2000000 | 300000 | Federal Transit Administration/Local | 300000 | 0 | Completed | 2012-02-29
TOTAL | 2000000 | 300000 |  | 300000 | 0
2010 Passenger Rail Service Revolving Fund (RIIF)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Support in Development of Intercity Passenger Rail efforts | 500000 | 500000 | None | 500000 | 0 | Completed | 2011-04-11
Funding reserved to match FY 2009 Recovery Act award to Iowa DOT for Chicago to Omaha Planning Study | 2000000 | 1000000 | Federal Railroad Administration FY 2009 HSIPR award | 1000000 | 0 | Completed | 2013-12-31
Funding reserved to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 108600000 | 1500000 | Federal Railroad Administration FY 2010 HSIPR award | 1352089 | 147911 | In Progress | 2016-07-01
TOTAL | 111100000 | 3000000 |  | 2852089 | 147911
2011 Passenger Rail Service Revolving Fund (funding from Underground Storage Tank Fund)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Funding reserved to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 108600000 | 2000000 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 2000000 | In Progress | 2016-07-01
TOTAL | 108600000 | 2000000 |  | 0 | 2000000

## PTIG
FY 2014 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
15510 | Region 5 | Construct new vehicle and administration facility | 433900 | 347120 | local funds |  | 347120 | Awarded 8-2013 | Est. 8/14/2015
15511 | Region 9 | Purchase and install new generator | 70000 | 56000 |  |  | 56000 | Awarded 8-2013 | Est. 8/14/2015
15512 | Region 13 | Construct wash bay addition | 202800 | 162240 |  |  | 162240 | Awarded 8-2013 | Est. 8/14/2015
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY13) | 688192.2775 | 475846 | federal transit funds local funds |  | 475846 | Awarded 8-2013 | Est. 8/14/2015
15513 | Des Moines | Rehabilitate maintenance lane | 45000 | 36000 | Local funds |  | 36000 | Awarded 8-2013 | Est. 8/14/2015
15514 | Sioux City | Replace bus wash system | 300000 | 240000 |  |  | 240000 | Awarded 8-2013 | Est. 8/14/2015
15514 | Sioux City | Rehabilitate roof | 185000 | 136000 |  |  | 136000 | Awarded 8-2013 | Est. 8/14/2015
15514 | Sioux City | Replace transit operations heating, ventilating, and air conditioning system | 50000 | 40000 | federal transit funds local funds |  | 40000 | Awarded 8-2013 | Est. 8/14/2015
|  | Funds available fore reprogramming |  | 6794 |  |  | 6794
|  | GRAND TOTAL |  | 1500000 |  |  | 1500000
FY 2013 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
14370 | Cedar Rapids | Administration facility/garage | 5294251 | 600000 | federal transit funds local funds | 600000 | 0 | Awarded 7-2012 | 2013-10-24 | 2013-10-24
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY10) | 384736.25 | 307789 | Local Funds | 0 | 307789 | Awarded 7-2012 | Est. 8/13/2014
14372 | Des Moines | Storage barn portals restoration | 467000 | 352000 | federal transit funds local funds | 0 | 352000 | Awarded 7-2012 | Est. 8/13/2014
14373 | Des Moines | Fuel delivery system | 192500 | 145000 | federal transit funds local funds | 0 | 145000 | Awarded 7-2012 | Est. 8/13/2014
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY14) | 137698.9088 | 95211 | federal transit funds local funds | 0 | 95211 | Awarded 8-2013 | Est. 8/14/2015
|  | GRAND TOTAL |  | 1500000 |  | 600000 | 900000
FY 2012 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
13415 | Ames | Facility renovation | 792000 | 600000 | Local Funds | 600000 | 0 | Awarded 7-2011 | 2013-11-27 | 2013-11-27
13416 | Cedar Rapids | New facility to replace transit garage and admin. facility | 3900000 | 600000 | local & FEMA | 600000 | 0 | Awarded 7-2011 | 2013-05-08 | 2013-05-08
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY11) | 63035 | 36600 | Local Funds | 0 | 36600 | Awarded 7-2011 | Est. 8/30/2014
13418 | Dubuque | Sprinkler replacement | 16000 | 12800 | Local Funds | 0 | 12800 | Awarded 7-2011 | Est. 12/31/2014
13418 | Dubuque | Roof replacement | 308000 | 245000 | Local Funds | 0 | 245000 | Awarded 7-2011 | Est. 6/30/2014
13419 | Muscatine | Passenger shelter | 7000 | 5600 | Local Funds | 5600 | 0 | Awarded 7-2011 | 2012-03-16 | 2012-03-16
|  | GRAND TOTAL |  | 1500000 |  | 1205600 | 294400
FY 2011 - I-Jobs Bonding (Revenue Bonds Capitals II)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12319 | Ames Transit Agency (CyRide) | Construct additional bus storage/maintenance areas | 4897614 | 800000 | Federal Transit Funds and Local | 800000 | 0 | Project complete | 2013-11-27 | 2013-11-27
12320 | Des Moines Area Regional Transit | Replace roof over maintenance area | 500000 | 381827 | Transit Agency Funds | 381827 | 0 | Project complete | 2011-07-05 | 2011-07-18
12733 | Dubuque | Transfer facility | 379211 | 298357 | Transit Agency Funds | 278214 | 20143 | Awarded 1-2011 | Est. 2/28/2014
12738 | Des Moines | Wash rack rehabilitation | 30000 | 24000 | Transit Agency Funds | 24000 | 0 | Awarded 1-2011 | 2012-06-07 | 2012-06-07
12321 | Southwest Iowa Transit Agency-SWITA (Region 13) | Construct a vehicle storage facility | 565732 | 452585 | Transit Agency Funds | 452585 | 0 | Awarded 10/2010 | 2012-06-30 | 2011-04-04
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY12) | 22716.25 | 18173 | Local Funds | 0 | 18173 | Awarded 7-2011 | Est. 8/30/2014
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY13 and FY14) | 36240.1325 | 25058 | federal transit funds local funds | 0 | 25058 | Awarded 8-2013 | Est. 8/14/2015
|  | GRAND TOTAL |  | 2000000 |  | 1936626 | 63374
FY 2010 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12738 | Des Moines | Locker/washroom renovations | 65000 | 48000 | Transit Agency Funds | 48000 | 0 | Awarded 1-2011 | 2012-06-07 | 2012-06-07
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY09) | 617904 | 436904 | Transit Agency Funds | 436904 | 0 | Awarded 12/2010 | 2013-02-14 | 2013-02-14
11761 | Des Moines Area Regional Transit | Restoration of masonry structures and upgrade of energy management system at DART facility | 100000 | 79920 | Transit Agency Funds | 79920 | 0 | Project completed | 2010-11-01 | 2010-11-16
11767 | Ottumwa Transit Authority | Expand maintenance shop serving OTA and 10-15 regional transit fleets to accommodate more vehicles and provide sufficient headroom to allow use of vehicle hoists | 235000 | 188000 | Transit Agency Funds | 188000 | 0 | Project complete | 2011-01-18 | 2011-01-18
11762 | Region 2 Transit - Mason City | Expand/renovate facility shared with Mason City Transit to accommodate dispatch function now required to support direct operation of transit services in Cerro Gordo County by regional system | 176000 | 140800 | Transit Agency Funds | 140800 | 0 | Project complete | 2010-12-31 | 2011-01-24
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilton Co. (partial see also funding in FY09) | 7347 | 5877 | Transit Agency Funds | 5877 | 0 | Awarded 12/09 | Est. 12/31/2011 | 2012-07-31
11765 | River Bend Transit (Region 9) - Davenport | Expand bus wash portion of River Bend facility to accommodate larger vehicles now being operated | 130000 | 67019 | Transit Agency Funds | 67019 | 0 | Awarded 12/09 | 2011-11-20 | 2011-11-26
11766 | Southeast Iowa Bus (region 16) - Burlington | Participate in transit share of purchase and remodeling of existing building to house planning commission functions including transit administration and operations | 296250 | 125179 | Transit Agency Funds | 125179 | 0 | Awarded 12/09 | Est. 12/31/2011 | 2011-06-21
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY13) | 139776.25 | 111821 | Local Funds | 0 | 111821 | Awarded 7-2012 | Est. 8/13/2014
12738 | Des Moines | Storm water rack and sanitation sewer (see FY11 and supplemental funding from FY09) | 12144 | 5534 | Transit Agency Funds | 5534 | 0 | Awarded 1-2011 | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY11, FY12) | 46326.25 | 37061 | Local Funds | 0 | 37061 | Awarded 7-2011 | Est. 8/30/2014
15513 | Des Moines | Renovate operations office (partial-- see funding from FY11, FY13 and FY14) | 5618.6812 | 3885 | federal transit funds local funds | 0 | 3885 | Awarded 8-2013 | Est. 8/14/2015
|  | GRAND TOTAL |  | 1250000 |  | 1097233 | 152767
FY 2009 - RC3 511 - Health Restricted Capital Bond Fund (Revenue Bonds Capitals)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
10482 | CyRide (Ames) | Reconstruction of the steam cleaning area (Moved to ARRA) | $640,000 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10481 | City of Davenport | Relocate transit offices (Cancelled 8-9-10) | 654000 | 0 | Transit Agency Funds | 0 | 0 | Project Cancelled | Est. 6/30/2010
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY10) |  | 385677 | FEMA Funds, Transit Agency Funds | 385677 | 0 | Awarded 12/10 | 2013-02-14 | 2013-02-14
10484 | River Bend Transit (Region 9) - Davenport | Vehicle storage and wash bays (Moved to ARRA) | $491,300 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10483 | Western Iowa Transit System (Region 12) - Carroll | Construct a vehicle storage addition (partial - see also supplimental funding from FY07) | 85446.25 | 68357 | Federal Transit Funds, Transit Agency Funds | 68357 | 0 | Project complete | 2009-08-31 | 2009-07-23
10968 | City of Coralville | Relocate transit office/maintenance facility out of floodway | 3643332 | 880000 | FEMA Funds, Transit Agency Funds | 880000 | 0 | Awarded 12/10 |  | 2013-01-02
11350 | CyRide (Ames) | Rehabitate west wall exterior insulation finish system (EIFS) of Cy-Ride maintenance facility | 200000 | 62577 | Transit Agency Funds | 62577 | 0 | Contract awarded 7/09 | 2011-05-25 | 2011-01-05
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilaton Co. (partial see also funding in FY10) | 699736.25 | 559789 | Transit Agency Funds | 559789 | 0 | Awarded 12/09 | Est. 12/31/2011 | 2012-07-31
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY10, FY13) | 10817.5 | 8654 | Local Funds | 0 | 8654 | Awarded 7-2012 | Est. 8/13/2014
12738 | Des Moines | Storm water rack and sanitation sewer (see FY10 and FY11) | 177300 | 137523 | Transit Agency Funds | 137523 | 0 | Awarded 1/2011 | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY10, FY11, FY12) | 121778.75 | 97423 | Local Funds | 47292 | 50131 | Awarded 7-2011 | Est. 8/30/2014
|  | GRAND TOTAL |  | 2200000 |  | 2141215 | 58785
FY 2008 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09522 | University of Iowa (Cambus) | Construct new vehicle storage building for CAMBUS (partial - see also supplimental funding from FY07) | 1166319 | 702268 | Federal Transit Funds, Transit Agency Funds | 702268 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines (DART) | Construct addition to vehicle storage building (partial - see also supplimental funding from FY07) | 1044250 | 820000 | Federal Transit Funds, Transit Agency Funds | 820000 | 0 | Project complete | 2010-11-03 | 2010-11-03
09524 | Region Six Planning Commission (Region 6) - Marshalltown | Transit portion of Joint Facility | 385043 | 100876 | Federal Transit Funds, Transit Agency Funds | 100876 | 0 | Project complete | 2009-05-31 | 2008-12-18
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Construct new regional transit office, storage and maintenance facility in Dubuque (partial - see also supplimental funding from FY07) | 721070 | 576856 | Transit Agency Funds | 576856 | 0 | Project complete | 2008-06-30 | 2008-07-31
|  | GRAND TOTAL |  | 2200000 |  | 2200000 | 0
FY 2007 - RC2 942 - Health Restricted Capitals Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09410 | Ames Transit Agency (CyRide) | Expand operations/administration area of CyRide maintenance facility-Ride Facility | 1100000 | 880000 | Transit Agency funds | 880000 | 0 | Project complete | 2008-05-31 | 2008-06-19
09409 | City of Cedar Rapids | Construct transit portion of new downtown Intermodal facility | 2589453 | 0 | Federal Transit Funds, Transit Agency funds | 0 | 0 | Project dropped after city reorganization | NA | NA
09402 | City of Davenport (CitiBus) | Construct new transit hubs adjacent to regional shopping center and on campus of local university | 138134 | 110507 | Transit Agency funds | 110507 | 0 | Project complete | 2009-02-18 | 2009-02-18
09408 | Des Moines Area Regional Transit (DART) | Renovate maintenance area of DART facility | 66677 | 53341 | Transit Agency funds | 53341 | 0 | Project complete | 2010-02-17 | 2010-02-17
09404 | City of Sioux City | Construct new parts storage building at transit maintenance facility | 50000 | 40000 | Transit Agency funds | 40000 | 0 | Project complete | 2008-09-16 | 2008-09-16
09407 | North Iowa Area Regional Transit (Region 2) - Mason City | Construct a variety of projects to finish out recently constructed transit maintenance facility shared with City of Mason City | 40267.5 | 32214 | Transit Agency funds | 32214 | 0 | Project complete | 2008-03-31 | 2008-05-14
09406 | RIDES/Regional Transit Authority (Region 3) - Spencer | Construct new satellite facility in Sheldon for transit vehicle storage and maintenance | 500000 | 163085 | Federal Transit Funds, Transit Agency funds | 163085 | 0 | Project complete | 2010-12-31 | 2009-11-25
09405 | Western Iowa Transit System (Region 12) - Carroll | Expand transit maintenance and storage facility in Carroll | 587500 | 220000 | Federal Transit Funds, Transit Agency funds | 220000 | 0 | Project complete | 2008-09-30 | 2008-09-17
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Partial funding for FY08 project to construct new regional transit office, storage and maintenance facility in Dubuque | 418122.5 | 303144 | Transit Agency Funds | 303144 | 0 | Project complete | 2008-06-30 | 2008-07-31
09522 | University of Iowa (Cambus) - Iowa City | Construct new vehicle storage building for CAMBUS (partial - see also funding from FY08) | 222165 | 177732 | Federal Transit Funds, Transit Agency Funds | 177732 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines Area Regional Transit (DART) | Construct addition to vehicle storage building (partial - see also funding from FY08) | 75000 | 60000 | Transit Agency Funds | 60000 | 0 | Project complete | 2010-11-03 | 2010-11-03
10483 | Western Iowa Transit System (Region 12) - Carroll | Partial funding for FY09 project to construct a vehicle storage addition in Carroll | 82053.75 | 65643 | Federal Transit Funds, Transit Agency funds | 65643 | 0 | Project complete | 2009-07-23 | 2009-07-23
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also funding from FY09 and FY10) | 71773.75 | 57419 | Transit Agency Funds | 57419 | 0 | Project complete | 2013-02-14 | 2013-02-14
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY09, FY10, FY11, FY12) | 46143.75 | 36915 | Local Funds | 36915 | 0 | Project complete | 2013-05-13 | 2013-05-13
|  | GRAND TOTAL |  | 2200000 |  | 2200000 | 0