## GAVI
FY 2018 RIIF/Aviation Trust Fund - General Aviation Vertical Infrastructure Program*
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Grinnell Regional Airport | 75x75 Hangar Construction | 550000 | 150000 | Airport funds | 0 | 150000 | In Progress | 2018-08-31
Muscatine Municipal Airport | T-Hangar Building Construction | 343000 | 150000 | Airport funds | 0 | 150000 | In Progress | 2018-12-31
Red Oak Municipal Airport | Rehab Hangar - New Bifold Doors | 63000 | 47250 | Airport funds | 0 | 47250 | In Progress | 2018-09-01
Sioux County Regional Airport | 10 Unit T - Hangar | 526680 | 150000 | Airport funds | 113203 | 36797 | In Progress | 2018-07-31
Waverly Municipal Airport | Bulk Hangar Insulation Renovation | 51000 | 22950 | Airport funds | 0 | 22950 | In Progress | 2018-05-01
| Total | 1533680 | 520200 |  | 113203 | 406997
* State share includes $20,200 of Aviation Trust Fund revenue not subject to Infrastructure Annual Status Report requirement but is included for information.
FY 2017 Aviation Trust Fund* - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Cherokee County Regional Airport | Eight Unit T-Hangar | 320292 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-08-28
Clinton Municipal Airport | Airport Fuel System | 391140 | 141140 | Airport funds | 141140 | 0 | Complete | 2017-12-20
Davenport Municipal Airport | Rehabilitate Hangar 8990 | 65000 | 32500 | Airport funds | 31750 | 0 | Complete | 2017-08-22
Denison Municipal Airport | Hangar Upgrades | 10000 | 7000 | Airport funds | 6243 | 0 | Complete | 2016-12-31
George L Scott Municipal Airport | Replace T-Hangar Roof | 27500 | 16500 | Airport funds | 10866 | 0 | Complete | 2017-06-15
Iowa City Municipal Airport | North T-Hangar Restroom | 80125 | 56088 | Airport funds | 12972 | 43116 | In Progress | 2018-08-01
Northeast Iowa Regional Airport | Hangar Development | 300000 | 150000 | Airport funds | 141376 | 8624 | In Progress | 2018-03-01
Sioux County Regional Airport | Terminal Building | 1120000 | 150000 | Airport funds | 130061 | 19939 | In Progress | 2018-09-30
Spencer Municipal Airport | Hangar Rehabilitation - Replace Roof, Sill, Repaint | 68000 | 47600 | Airport funds | 0 | 47600 | Final Close Out | 2018-02-01
| Total | 2382057 | 750828 |  | 624408 | 119279
* Not subject to Infrastructure Annual Status Report requirement due to appropriation funding source. However, the status is included for information.
FY 2016 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ames Municipal Airport | Site improvements for future terminal building | 2410000 | 150000 | Airport funds |  | 150000 | Final Close Out | 2018-01-31
Council Bluffs Municipal Airport | T-hangar Improvements | 216451 | 75000 | Airport funds | 46637 | 28363 | Final Close Out | 2018-06-30
Cresco Municipal Airport | Rehabilitate hangar and construct pilot lounge | 18728 | 15919 | Airport funds | 15919 | 0 | Complete | 2016-06-08
Lamoni Municipal Airport | Construct hangar | 322000 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-08-22
Marshalltown Municipal Airport | Pave hangar floor | 94500 | 80325 | Airport funds | 64936 | 0 | Complete | 2017-02-13
Perry Municipal Airport | Repair hangar roof | 20000 | 14000 | Airport funds | 13826 | 0 | Complete | 2016-12-15
Sibley Municipal Airport | Rehabilitate terminal building | 26836 | 16101 | Airport funds | 16101 | 0 | Complete | 2016-06-08
Sioux County Regional Airport | Construct maintenance and electrical vault buildings | 182200 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-04-30
Spencer Municipal Airport | Rehabilate hangar floor | 76650 | 45990 | Airport funds | 45990 | 0 | Complete | 2017-07-30
Washington Municipal Airport | Construct hangar | 630540 | 150000 | Airport funds |  | 150000 | In Progress | 2018-06-30
| Total | 3997905 | 847335 |  | 503409 | 328363
FY 2015 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Atlantic Municipal Airport | Construct 60' x 80' hangar | 717200 | 150000 | Airport funds | 150000 | 0 | Completed | 2015-12-01
Boone Municipal Airport | Construct 2-unit, 45' x 80' hangar | 201600 | 150000 | Airport funds | 150000 | 0 | Completed | 2017-08-25
Decorah Municipal Airport | Construct 3-stall rectangular hangar | 235000 | 117500 | Airport funds | 117500 | 0 | Completed | 2016-08-09
Fairfield Municipal Airport | Construct new public terminal building | 215657 | 150000 | Airport funds | 135000 | 0 | Completed | 2017-06-14
Grinnell Regional Airport | Terminal building and maintenance hangar renovation | 60000 | 30000 | Airport funds | 12250 | 0 | Completed | 2014-11-14
Osceola Municipal Airport | Construct 33' x 42' rectangular hangar | 107140 | 74998 | Airport funds | 74998 | 0 | Completed | 2017-11-29
Rock Rapids Municipal Airport | Rehabilitate hangar roof | 27135 | 21708 | Airport funds | 21628 | 0 | Completed | 2015-06-15
Sibley Municipal Airport | Renovate terminal building roof and addition of insulation in hangar | 24000 | 14400 | Airport funds | 14400 | 0 | Completed | 2016-01-20
Washington Municipal Airport | Rehabilitate hangar | 76500 | 57375 | Airport funds | 57375 | 0 | Completed | 2016-05-16
| Total | 1664232 | 765981 |  | 733151 | 0
FY 2014 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ankeny Regional | Construct 6-unit tee hangar | 326250 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-06-11
Davenport Municipal | Rehabilitate hangar 8970 | 56660 | 48161 | City funds | 48161 | 0 | Completed | 2014-09-22
Emmetsburg Municipal | Construct 80x100 hangar | 529170 | 100000 | Local funding uncertain | 100000 | 0 | Completed | 2016-06-09
Marshalltown Municipal | Renovate hangar | 88200 | 74970 | City funds | 72566 | 0 | Completed | 2017-08-11
Northeast Iowa Regional | Construct 70x120 hangar | 300000 | 150000 | Utility company loan | 150000 | 0 | Completed | 2014-09-23
Ottumwa Regional | Renovate hangar | 74470 | 59470 | Local airport funds | 57555 | 0 | Completed | 2015-06-30
Perry Municipal | Construct 45x100 hangar | 422375 | 150000 | City bonding | 128239 | 0 | Completed | 2015-06-01
Red Oak Municipal | Renovate hangar door | 20700 | 16560 | City funds | 16560 | 0 | Completed | 2013-12-18
Webster City Municipal | Renovate maintenance hangar | 40500 | 20250 | Airport funds | 20250 | 0 | Completed | 2014-06-01
| Total | 1817825 | 769411 |  | 743331 | 0
FY 2013 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Boone Municipal Airport | Construct hangar | 187500 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-12-08
Clinton Municipal Airport | Construct transient hangar | 600000 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-06-27
Iowa City Municipal Airport | Rehabilitate terminal and building roofs | 102000 | 75000 | Airport funds | 75000 | 0 | Completed | 2014-10-27
Iowa Falls Municipal Airport | Expand four unit t-hangar and apron | 326760 | 150000 | Airport funds | 149183 | 0 | Completed | 2014-09-18
Red Oak Municipal Airport | Construct hangar | 210000 | 150000 | Airport funds | 150000 | 0 | Completed | 2013-10-11
Vinton Veterans Airpark | Construct hangar | 271000 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-02-21
| Total | 1697260 | 825000 |  | 824183 | 0

## CSVI
FY 2018 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Terminal Improvements | 97000 | 58024 | Airport funds | 0 | 58024 | Not Started | 2019-06-30
Cedar Rapids- Eastern Iowa | Terminal Modernization PH 3 | 650000 | 191592 | Airport funds | 0 | 191592 | Design Phase | 2018-12-31
Des Moines | General Aviation Improvements | 3376278 | 348769 | Airport funds | 69023 | 279746 | In Progress | 2018-04-06
Dubuque | Guidance Signage, Relocate Airfield Infrastructure, Terminal Fuel Facility | 560125 | 63793 | Airport funds | 0 | 63793 | In Progress | 2018-05-01
Fort Dodge | Hangar Construction and Rehabilitation, Flight Service Station Reconfiguration | 222000 | 57281 | Airport funds | 0 | 57281 | In progress | 2018-06-30
Mason City | Construct T-Hangar | 770500 | 57581 | Airport funds | 0 | 57581 | Not Started | 2018-03-31
Sioux City | Rehabilitate Terminal and Hangar | 110000 | 61397 | Airport funds | 0 | 61397 | In progress | 2018-10-31
Waterloo | Hangar Improvements | 80220 | 61563 | Airport funds | 0 | 61563 | In Progress | 2018-07-01
| Total | 5866123 | 900000 |  | 69023 | 830977
FY 2017 RIIF/Aviation Trust Fund* - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Hangar Construction and Improve Terminal Area Infrastructure | 101000 | 95966.7333 | Airport funds | 0 | 95966.7333 | In Progress | 2018-12-31
Cedar Rapids- Eastern Iowa | Rehabilitate Terminal Building | 16330000 | 325245.8293 | Airport funds | 0 | 325245.8293 | Design Phase | 2018-12-31
Des Moines | General Aviation Improvements | 3619000 | 579266.8881 | Airport funds | 579267 | 0 | Completed | 2017-12-19
Dubuque | Guidance Signage, Relocate Airfield Infrastructure, Terminal Fuel Facility | 560125 | 105671.6423 | Airport funds | 0 | 105671.6423 | In Progress | 2018-05-01
Fort Dodge | Construct Hangar, Hangar roofing and Flight Service Station redesign | 222000 | 93901.3818 | Airport funds | 0 | 93901.3818 | In progress | 2018-06-30
Mason City | Replace Terminal Chiller Phase Two | 192500 | 94005.0898 | Airport funds | 94005 | 0 | Completed | 2017-10-30
Sioux City | Rehabilitate and Build Hangars | 104244 | 104243.6947 | Airport funds | 81500 | 22744 | In progress | 2018-07-31
Waterloo | GA Terminal Building Rehabilitation and Hangar 5 Rehabilitation | 104800 | 101698.7408 | Airport funds | 96431 | 5268 | Final Closeout | 2018-03-01
| Total | 21233669 | 1500000 |  | 851203 | 648797.5867
* $60,000 of the FY 2017 appropriation is from the Aviation Trust Fund and not subject to Infrastructure Annual Status Report requirement. However, the status of the entire appropriation is included for information.
FY 2016 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace Hangars | 288000 | 96034.2405 | Airport funds | 34339 | 61695 | In progress | 2018-06-30
Cedar Rapids- Eastern Iowa | Rehabilitate Terminal Building | 8018250 | 319397.9844 | Airport funds | 0 | 319397.9844 | In progress | 2018-12-31
Des Moines | General Aviation Improvements | 3619000 | 585229.5187 | Airport funds | 585230 | 0 | Completed | 2017-12-19
Dubuque | Guidance Signage, Relocate Airfield Infrastructure, Terminal Fuel Facility | 560125 | 105683.7904 | Airport funds | 0 | 105683.7904 | In Progress | 2018-05-01
Fort Dodge | Construct Hangar and Flight Service Station redesign | 100000 | 94844.5512 | Airport funds | 0 | 94845 | In progress | 2018-06-30
Mason City | Replace Overhead Garage Doors and Perform Terminal Systems Study | 46000 | 94881.917 | Airport funds | 94882 | 0 | Completed | 2017-06-19
Sioux City | Rehabilitate and Build Hangars | 120000 | 102731.8436 | Airport funds | 102732 | 0 | Completed | 2016-11-16
Waterloo | Hangar rehabilitation and baggage area renovation | 119720 | 101196.1542 | Airport funds | 73366 | 27830 | In Progress | 2018-07-01
| Total | 12871095 | 1500000 |  | 890549 | 609451.7748
FY 2015 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace three hangars | 240000 | 96692 | Airport funds | 96692 | 0 | Completed | 2017-07-27
Cedar Rapids- Eastern Iowa | Renovate terminal building lobby | 10387000 | 317297 | Airport funds | 317297 | 0 | Completed | 2015-10-16
Des Moines | Customs & Border Protection relocation | 1533500 | 583354 | Airport funds | 583354 | 0 | Completed | 2015-07-27
Dubuque | Construct new terminal building and Guidance Signage | 1277920 | 105886 | Airport funds | 30883 | 75003 | Final Close Out | 2018-05-01
Fort Dodge | Construct new hangar | 130000 | 95854 | Airport funds | 4875 | 90979 | In progress | 2018-06-30
Mason City | Upgrade terminal electrical service and replace overhead door in west maintenance facility | 121000 | 96001 | Airport funds | 96001 | 0 | Completed | 2017-06-19
Sioux City | Rehabilitate and build hangars | 103884 | 103884 | Airport funds | 103884 | 0 | Completed | 2016-10-17
Waterloo | Upgrade emergency generator, replace door at bag make-up, and terminal electrical improvements | 107375 | 101032 | Airport funds | 101032 | 0 | Completed | 2016-12-23
| Total | 13900679 | 1500000 |  | 1334018 | 165982
FY 2014 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Construct hangar | 480000 | 96594 | Airport funds | 96594 | 0 | Completed | 2017-05-31
Cedar Rapids- Eastern Iowa | Replace roofs on four buildings | 330000 | 311190 | Airport funds | 311190 | 0 | Completed | 2014-09-16
Des Moines | Relocate US Customs building | 4500000 | 579215 | Airport funds | 579214 | 0 | Completed | 2015-04-06
Dubuque | Construct terminal building | 1277920 | 108456 | Airport funds | 108456 | 0 | Completed | 2017-02-01
Fort Dodge | Re-design flight service station, replace overhead doors in ARFF/Maintenance building, demolish two hangars | 150000 | 98159 | Airport funds | 98159 | 0 | Completed | 2017-07-13
Mason City | Rehabilitate terminal: replace terminal cooling system, install security cameras, improve entrance soffit and ceiling | 99144 | 98450 | Airport funds | 98450 | 0 | Completed | 2017-05-18
Sioux City | Rehabilitate and construct new hangars | 120000 | 105151 | Airport funds | 105151 | 0 | Completed | 2017-02-13
Waterloo | Rehabilitate hangars | 106000 | 102785 | Airport funds | 102785 | 0 | Completed | 2016-11-22
| Total | 7063064 | 1500000 |  | 1499999 | 0
FY 2013 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace hangar | 450000 | 94903 | Airport funds | 94903 | 0 | Completed | 2014-10-27
Cedar Rapids- Eastern Iowa | Renovate terminal building lobby | 3430000 | 325782 | Airport funds | 325782 | 0 | Completed | 2014-09-16
Des Moines | Construct parking garage bridge | 5200000 | 568101 | Airport funds | 568101 | 0 | Completed | 2012-11-15
Dubuque | Construct terminal building | 1351480 | 107598 | Airport funds | 107598 | 0 | Completed | 2017-02-01
Fort Dodge | Renovate terminal operation area and former flight service station building | 100000 | 97119 | Airport funds | 97119 | 0 | Completed | 2015-06-30
Mason City | Construct office addition | 722170 | 99415 | Airport funds | 99415 | 0 | Completed | 2012-07-20
Sioux City | Rehabilitate hangars | 200000 | 103848 | Airport funds | 103848 | 0 | Completed | 2016-03-04
Waterloo | Rehabilitate hangars and snow removal equipment building | 103560 | 103234 | Airport funds | 103234 | 0 | Completed | 2017-04-20
| Total | 11557210 | 1500000 |  | 1500000 | 0
FY 2012 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Construct hangars | 898500 | 94579 | Airport funds | 94579 | 0 | Completed | 2014-06-19
Cedar Rapids- Eastern Iowa | Renovate terminal - relocate baggage screening area | 3904000 | 328020 | Airport funds | 328020 | 0 | Completed | 2013-01-07
Des Moines | Construct parking garage bridge | 800000 | 562349 | Airport funds | 562349 | 0 | Completed | 2012-09-24
Dubuque | Construct terminal building | 8752175 | 110137 | Airport funds | 110137 | 0 | Completed | 2013-08-08
Fort Dodge | Renovate terminal to prevent drainage issues; design renovation to flight service station; hangar A and B demolition | 225000 | 97119 | Airport funds | 97119 | 0 | Completed | 2015-06-26
Mason City | Construct office addition | 500000 | 99205 | Airport funds | 99205 | 0 | Completed | 2012-12-03
Sioux City | Rehabilitate hangars | 200000 | 107536 | Airport funds | 107536 | 0 | Completed | 2013-08-20
Waterloo | Rehabilitate hangars | 104929 | 103021 | Airport funds | 103021 | 0 | Completed | 2016-11-22
| Total | 15384604 | 1501966 |  | 1501966 | 0

## SRT
State Recreational Trails
Fund | Fiscal Year | Description of Project | Progress of Work | Total Estimated Project Cost | Revenue Sources | Funds Obligatedb |  | Funds Expended | Date of Completion / Estimated Completion
Recreational Trails - RIIF - 0017 | 2018 | Heritage Trail Bridge 27 Replacement (Dubuque County Conservation Board) | Agreement signed 12/27/2017 - work not started | 162482 | State Recreational Trail (SRT) Fund and County Conservation Board funds | 113185 |  | 0 | 2019-06-30
Recreational Trails - RIIF - 0017 | 2018 | Louisa County Fairground Trailhead and Connection to the Hoover Nature Trail (Louisa County Conservation Board and Louisa County Trails Council) | Agreement not signed - work not started | 456000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, CFLC, CJUW Endowment, Riverboat Foundation, County Conservation Board funds, Trails Council and private donations | 250000 |  | 0 | 2019-06-30
Recreational Trails - RIIF - 0017 | 2018 | Pottawattamie County Trail - Railroad Highway Trail Phase II (Pottawattamie County Conservation Board and Pottawattamie County Trail Association) | Agreement not signed - work not started | 1700000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and Iowa West Foundation | 400082 |  | 0 | 2019-06-30
Recreational Trails - RIIF - 0017 | 2018 | Raccoon River Valley Trail to High Trestle Trail Phase I Construction (Dallas County Conservation Board) | Agreement not signed - work not started | 556000 | State Recreational Trail (SRT) Fund, private donations and Wellmark Foundation | 366000 |  | 0 | 2019-06-30
Recreational Trails - RIIF - 0017 | 2018 | Wapsipinicon Trail - Phase I (Jones County and Anamosa) | Agreement signed 12/27/2017 - work not started | 765490 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, DNR REAP award, Iowa Parks Foundation/GWMRR, Wellmark Foundation, Anamosa and Jones County Community Foundations, Ignite Young Professionals and private donations | 139000 |  | 0 | 2019-06-30
Recreational Trails - RIIF - 0017 | 2017 | East Blue Creek Bridge Replacement along Cedar Valley Nature Trail (Linn and Black Hawk County Conservation Boards) | Agreement signed 3/2/2017 - development in process | 600000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and County Conservation Board CIP funds | 250000 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2017 | Extension of Felderman Trail (Bellevue and Iowa Department of Natural Resources) | Agreement signed 1/18/2017 - development in process | 753000 | State Recreational Trail (SRT) Fund, DNR REAP award, Northeast State Parks Region and Iowa Parks Foundation funds, private donation and Wellmark Foundation | 300000 |  | 285000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2017 | Interstate 29 Riverfront Trail Connection (Sioux City) | Agreement signed 3/13/17 - work not started | 3225917 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Missouri River Historical Development funds and city funds | 650000 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2017 | Iowa River Trail-Marshalltown to South Side of Iowa River (Marshalltown) | Agreement signed 9/18/2017- development in process | 1158614 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, DNR REAP award and fundraising | 650000 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2017 | Rolling Prairie Trail-Allison to Bristow (Butler County Conservation Board) | Agreement signed 5/18/17 - work not started | 1288380 | State Recreational Trail (SRT) Fund, County Board of Supervisors and County Conservation Board funds, Cities of Allison, Bristow, Dumont, Clarksville and Shell Rock funds, private donations and anticipated Guernsey's Foundation funds | 664678 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Cedar Valley Trail "Paving the Way for the American Discovery Trail" (Linn County & Black Hawk County Conservation Boards) | Agreement signed 2/12/2016 - development in process | 1209000 | State Recreational Trail (SRT) Fund, County Conservation Board CIP funds, Linn County Trails Association funds and anticipated city of Center Point funds | 600000 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Flint River Trail: Phase I South (Burlington) | Agreement signed 3/14/2016 - development in process | 850000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Two DNR REAP grants, city sales tax and local fundraising | 398500 |  | 376067 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Hoover Trail -- "The Missing Link" (Johnson County Conservation Board) | Agreement signed 12/21/2015 - development in process | 4321590 | State Recreational Trail (SRT) Fund, County Conservation Board funds, other grants and donations | 679699 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Hospital Connector Trail Bridge (Manning) h | Agreement signed 12/21/2015 - project completed | 296400 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and Great Places funding | 222300 | h | 197851 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Mitchellville to Prairie City Rails-to-Trails Corridor Development (Jasper County Conservation Board) | Agreement signed 11/24/2015 - development in process | 1200100 | State Recreational Trail (SRT) Fund and Federal Recreational Trails Fund | 749501 |  | 632661.72 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Turkey River Recreational Corridor - Elgin to Gilbertson Park and the Turkey River (Fayette County Conservation Board) | Agreement signed 12/21/2015 - development in process | 1136000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and private contributions | 750000 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Ankeny Connector - High Trestle Trail (Polk County Conservation Board) | Agreement signed 12/15/2014 - project completed | 2109860 | State Recreational Trail (SRT) Fund, city funds, County Conservation Board funds, and Iowa Natural Heritage Foundation funds | 782500 |  | 782500 | 2015-02-26
Recreational Trails - RIIF - 0017 | 2015 | Cedar Valley Nature Trail Bridge E4 Replacement (Black Hawk County Conservation Board) | Agreement signed 11/25/2014 - project completed | 214542 | State Recreational Trail (SRT) Fund and County Conservation Board funds | 160906 |  | 160906 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2015 | Coon Rapids Connector Trail Underpass (City of Coon Rapids) | Agreement signed 2/10/2015 - project completed | 299250 | State Recreational Trail (SRT) Fund and city funds | 224437 |  | 224437 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Great River Road Bike Lane (Louisa County Secondary Roads) | Agreement signed 6/19/2014 - project completed | 1690000 | State Recreational Trail (SRT) Fund and Scenic Byways grant | 340000 |  | 257045.57 | 2016-12-15
Recreational Trails - RIIF - 0017 | 2015 | Hoover Trail - "The Missing Link" (Johnson County Conservation Board) | Agreement signed 12/14/2014 - development in process | 605333 | State Recreational Trail (SRT) Fund and County Conservation Board funds | 454000 |  | 407355 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Iowa DNR AmeriCorps Trail Crew (Iowa Department of Natural Resources) | Agreement signed 12/17/2014 - project completed | 395000 | State Recreational Trail (SRT) Fund, DNR REAP grant and Lake Restoration Fund | 296250 |  | 296250 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2015 | Iowa River Trail Phase 1 Development (City of Marshalltown and Hardin County) | Agreement signed 3/2/2015 - project completed | 1335000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and DNR REAP grant | 775000 |  | 775000 | 2016-01-07
Recreational Trails - RIIF - 0017 | 2015 | Jurgensen Bridge Refurbishment (Winterset and Winterset Municipal Utility)f | Agreement signed 9/21/2015 - development in process | 1066590 | State Recreational Trail (SRT) Fund, FEMA funds and city funds | 500000 | f | 340113.83 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Lake Path Trail/JewEllsworth Trail Segment (Hamilton County Conservation Board) | Agreement signed 1/6/2015 - development in process | 862853 | State Recreational Trail (SRT) Fund, Regional Transportation Enhancement funds, cash from local entities and private donations | 647140 |  | 586181.78 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Mississippi River Trail - Pikes Peak Road to Guttenberg (Clayton County) | Agreement signed 8/31/2015 -development in process | 1369575 | State Recreational Trail (SRT) Fund and local option sales tax | 579074 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Pottawattamie County Trail-Phase I (Pottawattamie County Conservation Board and Pottawattamie County Trail Board) | Agreement signed 12/15/2014 -development in process | 933333 | State Recreational Trail (SRT) Fund, Federal Recreational Trails Fund, County Conservation Board funds and Iowa West Foundation funds | 700000 |  | 53379 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Red Cedar Trail and Connector (Linn County Conservation Board and Linn Area Mountain Bike Association) | Agreement signed 1/27/2015 - project completed | 75000 | State Recreational Trail (SRT) Fund, Specialized Dealer Grant, Marion Hotel/Motel and other local grants, LAMBA and other donors | 55000 |  | 55000 | 2017-06-27
Recreational Trails - RIIF - 0017 | 2015 | SW 5th (Jackson) Street Bridge Rehabilitation (City of Des Moines)f | Agreement signed 9/29/2015 - project completed | 3740000 | State Recreational Trail (SRT) Fund, City CIP funds, TIGER funds and private fundraising | 500000 | f | 500000 | 2017-01-11
| 2014 | [5 empty] | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2014 | Ankeny Connector - High Trestle Trail (Polk County Conservation Board and Ankeny) | Agreement signed 10/25/2013 - project completed | 3065000 | State Recreational Trail (SRT) Fund, city funds and county funds | 782500 |  | 782500 | 2014-05-01
Recreational Trails - RIIF - 0017 | 2014 | Bellevue Rivervue Trail-Phase II (City of Bellevue and Jackson County Conservation Board) | Agreement signed 1/30/2014 - project completed | 722275 | State Recreational Trail (SRT) Fund, city funds, DNR REAP grant, Regional Transportation Alternative funds and private donations | 260774 |  | 260774 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2014 | Bridging the Gap: Phase I Dry Run Trail-Connecting Decorah's Trout Run Trail to the Prairie Farmer Recreational Trail (Winneshiek County Conservation Board and City of Decorah) | Agreement signed 1/09/2014 - development in process | 1604512 | State Recreational Trail (SRT) Fund, Statewide Transportation Enhancement grant, DNR REAP grant and local public/private funds | 380265 |  | 50262.06 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2014 | Farragut to Shenandoah Trail Connection (City of Farragut) | Agreement signed 10/31/2013 - development in process | 650000 | State Recreational Trail (SRT) Fund and land value | 487500 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2014 | Iowa River Scenic Trail (Hardin County Board of Supervisors and City of Marshalltown) | Agreement signed 11/12/2013 - project completed | 1375694 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and land value | 775000 |  | 775000 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2014 | Multiuse Mississippi River Trail, Riverdale Section, Phase 2 (City of Riverdale) | Agreement signed 6/3/2014 - project completed | 1017000 | State Recreational Trail (SRT) Fund, city funds, County Regional Authority grant and National Scenic Byways grant | 318644 |  | 318644 | 2017-05-23
Recreational Trails - RIIF - 0017 | 2014 | Pioneer Beach Road Trail (City of Orleans and Dickinson County Trails Board) | Agreement signed 12/23/2013 - project completed | 521479 | State Recreational Trail (SRT) Fund, city funds and County Trails Board funds | 371479 |  | 371479 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2014 | Raccoon River Valley Trail to High Trestle Trail Connector (Dallas County Conservation Board) | Agreement signed 7/30/2013 - development in process | 290000 | State Recreational Trail (SRT) Fund, other grants, donations and foundations | 92897 |  | 29526.27 | 2018-06-30
| 2014 | [5 empty] | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2013 | Brushy Creek All-Weather Multi-Use Lake Trail Bridge (Iowa DNR) | Agreement signed 12/05/2012 - project completed | 125800 | State Recreational Trail (SRT) Fund and DNR REAP grant | 78000 |  | 78000 | 2015-08-17
Recreational Trails - RIIF - 0017 | 2013 | City of Clinton Mississippi River Trail Final Connection (City of Clinton) | Agreement signed 11/28/2012 - project completed | 535544 | State Recreational Trail (SRT) Fund and city G.O. Bonds | 400000 |  | 400000 | 2015-05-06
Recreational Trails - RIIF - 0017 | 2013 | Fayette-Volga River Multi-Use Trail (Upper Iowa University and Fayette County) | Agreement signed 11/13/2012 - project completed | 1190931 | State Recreational Trail (SRT) Fund, Upper Iowa University, city funds, County Community Foundation, Black Hills Energy, private donors, additional fundraising and DNR REAP grant | 700000 |  | 700000 | 2017-08-31
Recreational Trails - RIIF - 0017 | 2013 | Iowa River Trail – Phase 8 of 8 (City of Iowa City) | Agreement signed 11/25/2014 - project completed | 2100000 | State Recreational Trail (SRT) Fund, city G.O. Bonds, Regional STP Funds, Earmark funds and Regional Transportation Enhancement funds | 441000 |  | 441000 | 2017-01-27
Recreational Trails - RIIF - 0017 | 2013 | Mines of Spain Trail and Trailhead (City of Dubuque and Iowa DNR) | Agreement signed 11/28/2012 - project completed | 227333 | State Recreational Trail (SRT) Fund, city funds and fundraising/naming opportunities | 170500 |  | 170500 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2013 | Musser Park to Wiggens Road Trail (City of Muscatine) | Agreement signed 3/24/2014 - development in process | 984400 | State Recreational Trail (SRT) Fund, Federal Earmark funds and local contribution | 381100 |  | 362045 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2013 | Shaulis Road Trail Extension – Phase I (City of Waterloo) | Agreement signed 7/11/2013 - development in process | 1007592 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and city funds | 755694 |  | 495189.92 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2013 | South Troy Park Trail (City of Robins) | Agreement signed 12/12/2012 - project completed | 354000 | State Recreational Trail (SRT) Fund and city funds | 204000 |  | 204000 | 2017-04-17
|  |  |  | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2012 | Bee Branch Creek Trail-MRT Route (City of Dubuque) | Agreement signed 9/16/2014 - development in process | 506100 | State Recreational Trail (SRT) Fund, National Scenic Byway funds and city funds | 100000 |  | 95000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2012 | Bluff Creek OHV Park Development Plan (Iowa DNR) | Agreement signed 12/20/2011 - development in process | 80000 | State Recreational Trail (SRT) Fund and ATV registration funds | 60000 |  | 10198.59 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2012 | Buffalo to Wild Cat Den Road MRT (City of Buffalo) | Agreement signed 5/05/2012 - development in process | 562500 | State Recreational Trail (SRT) Fund, SAFETEA-LU earmark funds, and city funds | 108500 |  | 58850.42 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2012 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board)e | Agreement signed 12/20/2011 - project completed with other funding | 3612516 | State Recreational Trail (SRT) Fund and CDBG Jumpstart Infrastructure funds | 396516 | e | Rescinded | N/A
Recreational Trails - RIIF - 0017 | 2012 | Central IA Trail Loop-Chichaqua Valley Trail to Gay Lea Wilson Trail (Polk County Conservation Board) | Agreement signed 12/15/2011 - project completed | 10891016 | State Recreational Trail (SRT) Fund, Polk County Conservation and Partners funds | 753750 |  | 753750 | 2015-11-03
Recreational Trails - RIIF - 0017 | 2012 | Dickinson County Spine Trail-Henderson Woods to US71 in Arnolds Park (Arnolds Park and Dickinson County Trails Board) | Agreement signed 12/22/2011 - project completed | 165500 | State Recreational Trail (SRT) Fund, city funds and County Trails Board funds | 115850 |  | 115850 | 2013-10-08
Recreational Trails - RIIF - 0017 | 2012 | Gray's Lake Neighborhood Connecting Trail & SW 14th Quiet Street (City of Des Moines)g | Agreement signed 5/15/2012 - project completed | 586570 | State Recreational Trail (SRT) Fund, city CIP, Gray's Lake Neighborhood Association and land donations | 439920 | g | 439920 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2012 | Gypsum City OHV Park (WCIC and Iowa DNR) | Agreement signed 2/6/2012 - project completed | 626349 | State Recreational Trail (SRT) Fund, Federal Recreational Trails Fund, Webster County Conservation and ATV Registration funds | 211500 |  | 211500 | 2016-06-29
Recreational Trails - RIIF - 0017 | 2012 | Iowa DNR Trails Program (Iowa DNR) | Agreement signed 12/20/2011 - project completed | 350000 | State Recreational Trail (SRT) Fund, DNR REAP grant and Lake Restoration Fund | 262500 |  | 262500 | 2014-12-15
Recreational Trails - RIIF - 0017 | 2012 | NW Beaver Drive Trail (City of Johnston) | Agreement signed 1/10/2012 - project completed | 2400000 | State Recreational Trail (SRT) Fund, city G.O. bond and city park and trail improvement fund | 181464 |  | 181464 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2012 | Turkey River Recreational Corridor Trail-Elkader to Motor Mill (Clayton County Conservation Board) | Agreement signed 1/18/2012 - development in process | 880576 | State Recreational Trail (SRT) Fund, statewide Transportation Enhancement grant and local contributions | 250000 |  | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2012 | Water Trails Planning, Design and Construction Activities (Iowa DNR) | Agreement signed 2/23/2012 - project completed | 160000 | State Recreational Trail (SRT) Fund, marine fuel tax, U.S. Coast Guard, boat registration fees and RIIF | 120000 |  | 120000 | 2015-03-04
|  |  |  | #REF! |  | 3000000
Recreational Trails - RIIF - 0017 | 2010 | Allamakee County Mississippi River Bike Trail (Allamakee County and Allamakee County Economic Development)h | Agreement signed 1/5/2010- project completed | 7245382 | State Recreational Trail (SRT) Fund, Private and Local, Federal Earmark and Other State and Federal Grants | 750000 | h | 609630.41 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2010 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board) | Agreement signed 11/20/2009 - project completed | 2658938 | State Recreational Trail (SRT) Fund, CDBG - Jumpstart Infrastructure and FEMA-PA Funds | 250000 |  | 250000 | 2012-09-30
Recreational Trails - RIIF - 0017 | 2010 | Des Moines River Regional Trail Phase 1 (City of Des Moines)c | Agreement signed 1/29/2010 - project completed | 1937997.68 | State Recreational Trail (SRT) Fund, DNR REAP grant, Iowa Clean Air Attainment Program funds and City of Des Moines Capital Funds | 73474 | c | 73474 | 2015-01-12
Recreational Trails - RIIF - 0017 | 2010 | Iowa Department of Natural Resources (DNR) Trail Crew (Iowa DNR) | Agreement signed 11/20/2009 - project completed | 350000 | State Recreational Trail (SRT) Fund, DNR REAP grant and Lake Restoration Fund | 262500 |  | 262500 | 2012-12-03
Recreational Trails - RIIF - 0017 | 2010 | Iowa River Corridor Trail Connection - Sand Lake (City of Iowa City)c,h | Agreement signed 1/29/2010 - project completed | 375000 | State Recreational Trail (SRT) fund and Capital Improvement Funds | 281000 | c,h | 180059.72 | 2012-08-06
Recreational Trails - RIIF - 0017 | 2010 | Lewis and Clark Historic Riverfront Trail (City of Sioux City and Iowa DOT)c | Agreement signed 2/1/2010 - project completed | 1600000 | State Recreational Trail (SRT) Fund and City Funds | 128000 | c | 128000 | 2013-08-07
Recreational Trails - RIIF - 0017 | 2010 | Pinicon Ridge Trail (Linn County Conservation Board)a | Agreement signed 7/20/2009 - project completed | 666667 | State Recreational Trail (SRT) Fund and Local Contributions | 500000 | a | 500000 | 2012-08-27
Recreational Trails - RIIF - 0017 | 2010 | Principal Riverwalk Recreational Trail (city of Des Moines)a | Agreement signed 12/2/2009 - project completed | 1000000 | State Recreational Trail (SRT) fund and Local Contributions | 750000 | a | 750000 | 2013-04-15
Recreational Trails - RIIF - 0017 | 2010 | Raccoon River Valley Trail Addition--Forest Park to Minburn Trail (Dallas County Conservation Board)c | Agreement signed 11/6/2009 - project completed | 6655696 | State Recreational Trail (SRT) Fund, Community Attraction and Tourism Program, State Enhancement Project, Central Iowa Regional Transportation Planning Alliance, Dallas County, City of Perry, City of Waukee, Guthrie County Cash and Stimulus, City of Dallas Center, City of Jamaica, City of Redfield, City of Linden, Raccoon Valley Bank, Bock Family Foundation, Dallas County Conservation Foundation, Raccoon River Valley Trail Association, Celebrations Committee Dallas Center, Committee for Super Cooper, Dallas Center Beta Sigma Phi, Rotary Club of Dallas Center, Community of Herndon, Waukee YMCA, City of Dawson, Casey's Stores, Alliant Energy, Bikes Belong, Letter campaign, Prairie Meadows Community Betterment, Prairie Woodland Conservation Foundation and Bock Family Foundation October 08 | 484995 | c | 460745.25 | 2012-08-23
Recreational Trails - RIIF - 0017 | 2010 | Railbanking Purchase of IANW Railroad (Dickinson County Trails Board and Osceola County Conservation Board) | Agreement signed 1/4/2010 - project completed | 1203795 | State Recreational Trail (SRT) Fund, IANWRR Donated Land and Transportation Enhancement grant | 525000 |  | 525000 | 2010-07-19
Recreational Trails - RIIF - 0017 | 2010 | Summerset Trail Flood Repairs (Warren County Conservation Board)d | Agreement signed 1/5/2010 - project completed | 143028 | State Recreational Trail (SRT) Fund and County Budget | 107271 | d | 107271 | 2012-05-29
Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Box Culverts and Bridge Project (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 11/25/2009 - project completed | 782722 | State Recreational Trail (SRT) Fund, County Foundation, Winneshiek County and Winneshiek County Bridge grant | 300000 |  | 300000 | 2012-03-05
Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Decorah Fish Hatchery's Interpretive Restroom Facility (Northeast Iowa Resources Conservation and Development, Inc. and Iowa DNR's Fisheries) | Agreement signed 12/6/2009 - project completed | 105000 | State Recreational Trail (SRT) Fund and Friends of the Decorah Hatchery funds | 75000 |  | 75000 | 2012-07-02
|  |  |  | 24724225.68 |  | 4487240
Recreational Trails - RIIF - 0017 | 2009 | American Gothic Regional Trail Project (Area 15 Regional Planning Commission)a | Agreement signed 12/3/2008 - development in process | 133333 | State Recreational Trail (SRT) Fund, RPA, county, city, and private funds | 100000 | a | 95363 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2009 | Crawford County Trail (Crawford County)a | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund and county funds | 30000 | a | 30000 | 2010-09-20
Recreational Trails - RIIF - 0017 | 2009 | Garlock Slough Recreational Trail (City of West Okoboji and Dickinson County Tails Board)e | Agreement signed 11/3/2008 - project completed | 653550 | State Recreational Trail (SRT) Fund, Dickinson County Conservation, MPO, and City of West Okoboji funds | 490162 | e | 408425.41 | 2012-10-09
Recreational Trails - RIIF - 0017 | 2009 | Linn Creek Trail Connection with Iowa Highway 330 Trail (Marshall County) | Agreement signed 7/20/2009 - project completed | 1476000 | State Recreational Trail (SRT) Fund and county funds | 800000 |  | 800000 | 2012-09-05
Recreational Trails - RIIF - 0017 | 2009 | Maquoketa River Water Trail (Jones County)a | Agreement signed 7/8/2008 - project completed | 133334 | State Recreational Trail (SRT) Fund and county funds | 100000 | a | 100000 | 2011-08-08
Recreational Trails - RIIF - 0017 | 2009 | Mississippi River Trail - Liberty Avenue Connection (Clinton) | Agreement signed 12/3/2008 - project completed | 469000 | State Recreational Trail (SRT) Fund and City of Clinton funds | 351750 |  | 351750 | 2010-04-26
Recreational Trails - RIIF - 0017 | 2009 | Principal Riverwalk (Des Moines)a | Agreement signed 11/4/2008 - project completed | 1000000 | State Recreational Trail (SRT) Fund and City of Des Moines funds | 750000 | a | 750000 | 2013-04-15
Recreational Trails - RIIF - 0017 | 2009 | Riverview Recreation Area Expansion (Trailblazers Off Road Club)e | Agreement signed 6/8/2009 - funding rescinded | 71000 | State Recreational Trail (SRT) Fund | 40000 | e | Rescinded | N/A
Recreational Trails - RIIF - 0017 | 2009 | Stone State Park Trail (Woodbury County/DNR)a | Agreement signed 10/8/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund and county funds | 100000 | a | 0 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2009 | Summerset Trail (Cities of Indianola, Carlisle and Des Moines)a | Agreement signed 3/9/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund, SAFETEA-LU earmark funds and city funds | 100000 | a | 95000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2009 | Trout Run Trail - Bridging the Past and the Present (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 3/16/2009 - project completed | 443750 | State Recreational Trail (SRT) Fund, Winneshiek County Conservation and City of Decorah funds | 138088 |  | 138088 | 2010-10-18
|  |  |  | 4686633 |  | 3000000
Recreational Trails - RIIF - 0017 | 2008 | Ankeny to Woodward Trail Corridor (Boone County Conservation Board) | Agreement signed 3/25/2008 - project completed | 3415960 | State Recreational Trail (SRT) Fund, Land Value and Regional Transportation Enhancement funds | 565960 |  | 565960 | 2012-07-31
Recreational Trails - RIIF - 0017 | 2008 | Crawford County Trails (Crawford County)a | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund, county, city, and private funds | 30000 | a | 30000 | 2010-09-20
Recreational Trails - RIIF - 0017 | 2008 | Fairfield Loop Trail (Fairfield)a | Agreement signed 3/10/2009 - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | a | 200000 | 2012-05-29
Recreational Trails - RIIF - 0017 | 2008 | Heart of Iowa Nature Trail Phases VII & VIII (Story County Conservation Board) | Agreement signed 12/14/2007 - project completed | 1937254 | State Recreational Trail (SRT) Fund and county funds | 100000 |  | 100000 | 2013-12-30
Recreational Trails - RIIF - 0017 | 2008 | Jewell to Ellsworth Trail (Hamilton County Conservation Board)a | Agreement signed 9/5/2007 - development in process | 246667 | State Recreational Trail (SRT) Fund and county funds | 185000 | a | 182908 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2008 | Lewis & Clark Trail Planning Study (Iowa DOT) | Agreement IDOT - project completed | 66667 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2011-07-11
Recreational Trails - RIIF - 0017 | 2008 | Maquoketa River Water Trail (Jones County Conservation Board) | Agreement signed 12/13/2007 - project completed | 549605 | State Recreational Trail (SRT) Fund and county funds | 69300 |  | 69300 | 2011-08-08
Recreational Trails - RIIF - 0017 | 2008 | Mississippi River Trail Upper Scott County (Le Claire)c | Project was rescinded. Funding to be reprogrammed for flood damage projects. | 1227779 | State Recreational Trail (SRT) Fund and county funds | 799740 | c | Rescinded | N/A
|  |  |  | 7750599 |  | 2000000 |  | 0
Recreational Trails - RC2 - 0942 | 2007 | 4-Mile Creek Greenway Trail (Polk County Conservation Board/City of Ankeny Parks and Recreation Department) | Agreement signed 3/06/2007 - project completed | 1334331 | State Recreational Trail (SRT) Fund, Polk County Conservation, MPO, and City of Ankeny funds | 690000 |  | 690000 | 2012-05-30
Recreational Trails - RC2 - 0942 | 2007 | 18th Street to Riverview Trail Development (Waterloo) | Agreement signed 3/29/2007 - project completed | 336250 | State Recreational Trail (SRT) Fund and City of Waterloo | 252187 |  | 252187 | 2011-04-04
Recreational Trails - RC2 - 0942 | 2007 | Alice's Road Greenbelt Trail Improvements (Clive) | Agreement signed 2/07/2007 - project completed | 536540 | State Recreational Trail (SRT) Fund and City of Clive funds | 402405 |  | 402405 | 2014-09-18
Recreational Trails - RC2 - 0942 | 2007 | Cemar Trail - Phase 2 (Cedar Rapids) | Agreement signed 1/12/2010 - development in process | 200000 | State Recreational Trail (SRT) Fund, federal earmark funds, Transportation Alternative funds, and Cedar Rapids CIP funds | 150000 |  | 118764.12 | 2018-06-30
Recreational Trails - RC2 - 0942 | 2007 | Coon Rapids Town Loop Trail (Coon Rapids) | Agreement signed 4/16/2007 - project completed | 142500 | State Recreational Trail (SRT) Fund and City of Coon Rapids/Whiterock Conservancy funds | 106875 |  | 106875 | 2010-03-15
Recreational Trails - RC2 - 0942 | 2007 | Des Moines County Recreational Trail - Phase 1 Burlington to Starr's Cave (Des Moines County)h | Agreement signed 2/19/2007 - project completed | 480000 | State Recreational Trail (SRT) Fund, Federal Recreational Trails Fund, Regional Transportation Alternative funds and county funds | 360000 | h | 357491.87 | 2017-02-07
Recreational Trails - RC2 - 0942 | 2007 | Lakeview OHV Park Upgrades (Dirt Surfers Inc.)g | Agreement signed 6/27/2007 - project completed | 52420 | State Recreational Trail (SRT) Fund | 39315 | g | 39315 | 2016-06-30
Recreational Trails - RC2 - 0942 | 2007 | Trail Projects in Wapello County (Wapello County)a | Agreement signed 4/16/2007 - $30,000 was awarded to city of Eldon - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | a | 196072.35 | 2010-03-22
|  |  |  | 4674520 |  | 1124651
Recreational Trails - RIIF - 0017 | 2006 | Phase I of the Gypsum City OHV Park (Webster County) | Agreement signed 8/21/2006 - project completed | 1660250 | State Recreational Trail (SRT) Fund and All-Terrain Vehicle Registration funds | 250000 |  | 250000 | 2010-07-06
Recreational Trails - RIIF - 0017 | 2006 | Trail construction connecting the Little Sioux County Park to the city of Correctionville (Woodbury County Conservation Board) | Agreement signed 7/10/2006 - project completed | 1027760 | State Recreational Trail (SRT) Fund, Federal Transportation Enhancement funds, DNR REAP grant, county, city, and private funds | 150000 |  | 150000 | 2007-10-01
Recreational Trails - RIIF - 0017 | 2006 | Phase 4 of the Clear Creek Trail from Mormon Handcart Park to the Clear Creek bridge on U.S. Highway 6 (Coralville) | Agreement signed 8/9/2006 - Final Voucher dated 6/11/08; Remaining funds to be used on next phase of project-project completed | 437216 | State Recreational Trail (SRT) Fund and city hotel/motel tax | 327912 |  | 327912 | 2008-05-01
Recreational Trails - RIIF - 0017 | 2006 | Construction of trail connecting existing trails in Johnston to the Neal Smith Trail in Des Moines (Polk County Conservation Board) | Agreement signed 7/31/2006 - project completed | 1406960 | State Recreational Trail (SRT) Fund, county funds, Federal Transportation Enhancement funds and MPO Transportation Enhancement funds | 346739 |  | 346739 | 2010-06-21
Recreational Trails - RIIF - 0017 | 2006 | Development of a trail to fill a gap in the trail network around Clear Lake and extending to Mason City (Cerro Gordo County) | Agreement signed 7/10/2006 - project completed | 71167 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2008-05-09
|  |  |  | 4603353 |  | 1074651
NOTE: To avoid loss of funding, it is the Iowa Department of Transportation's policy to expend the oldest funding first when reimbursing any project costs. Thus, the FY 2006 $1,000,000 appropriation was spent, even though some of the FY 2006 projects listed don't show all their funding was utilized by the expiration date.
a. Direct Appropriation From Iowa Legislature
b. Funds obligated per Department of Transportation Commission Order.
c. FY 2006 and FY 2008 Funding Rescinded by Local Sponsors - Funding Reallocated to SRT Projects in FY 2010
d. The initial $87,500 is from I-Jobs and the remaining $19,771 from rescinded funds from FY 2008.
e. Funding for 2 Projects Rescinded by Local Sponsors and a $32,543 project underrun - Funding Reallocated to SRT Projects in FY 2014
f. Identifies 2 Projects funded through $1 million existing historic trail bridges allocation that was part of the FY 2015 appropriation.
g. Identifies 2 Project Underruns - Funding Balance Reallocated to SRT Projects in FY 2017
h. Identifies 4 Project Underruns - Funding Balance Reallocated to SRT Projects in FY 2018
The FY 2006 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,000,000 as result of awarding additional funding from previous project underruns.
The FY 2007 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is over $2,000,000 as result of awarding additional funding from previous project underruns.
The FY 2008 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is $2,000,000.
The FY 2009 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2010 SRT appropriation was for $3,500,000. The total amount of SRT funding for projects listed in this report is over $3,500,000 as a result of awarding additional funding from previous project underruns.
There was no SRT appropriation for FY 2011.
The FY 2012 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2013 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2014 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2015 SRT appropriation was for $6,000,000 with $1,000,000 for existing historic trail bridges. The total amount of SRT funding for projects listed in this report is over $5,500,000 as a result of awarding additional funding from a previous project underrun.
The FY 2016 SRT appropriation was for $3,400,000. The total amount of SRT funding for projects listed in this report is $3,400,000.
The FY 2017 SRT appropriation was for $2,500,000. The total amount of SRT funding for projects listed in this report is over $2,500,000 as a result of awarding additional funding from previous project underruns.
The FY 2018 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,200,000 as a result of awarding additional funding from previous project underruns.

## RRLGP
FY 2018 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
City of Davenport | Construction of approximately 9,800 lineal feet of track with 7 turnouts in order to meet the supply and demand needs of Sterilite | 5169660 | 1008000 | Company Match | $0 | 1008000 | Project in Process | Fall 2020
Progressive Rail | The rehabilitation of the rail line between Emery and Clear Lake, Iowa on the Iowa Traction Railway. The project consists of replacement of 3.6 mi of rail and will open up Clear Lake, Iowa for purpose of rail served industrail development on the community's east side in close proximity of I-35.. | 1384000 | 655000 | Company Match | $0 | 655000 | Project in Process | Fall 2020
Pattison Sand Company | Phase II of the project includes the required earthwork, the addition of 3,300 track feet and a rail scale resulting in 78 additional rail car spots. | 5334455.18 | 952482 | Company Match | $0 | 952482 | Project in Process | Fall 2020
FY 2017 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Elite Octane | Improvement to an exisiting spur to serve a grain elevator. | 10282248 | 926000 | Company Match | 0 | 926000 | Project in Process | January 2020
Barilla America | Expansion of rail yard to receive 110 hopper cars with one switch. Includes addition of 8700 feet of new track, ties, plates, 6 turnouts and repositioning of all 6 switches at the east end of the rail yard. | 3268280 | 156000 | Company Match | 0 | 156000 | Granted an Extention | January 2020
Pattison Sand Company | The required earthwork, installation of #111 mainline switch, two #9 yard switches, and approx. 6,625 feet of rail branching into the start of the main unit train storage tracks. | 5427934 | 1100000 | Company Match | 1100000 | 0 | Complete - Certificate of completion pending | To be closed Spring 2018
Hydrite Chemical | Adding additional track on the south side of the production facility to heat an unload railcars of sulfur. | 1100000 | 24000 | Company Match | 0 | 24000 | Project in Process | January 2020
Progressive Rail | Installation of 600 ties per mile for the southernmost 12 miles of the APNC line between Albia, Iowa and Centervill, Iowa. | 951866 | 696436 | Company Match | 0 | 696436 | Project in Process | January 2020
BJRY Le Mars | Includes 500 feet of rail, ties, ballast and other materials located at the south end of the spur track serving the industrial park in Le Mars, Iowa. | 196171 | 156936 | Company Match | 0 | 156936 | Project in Process | January 2020
Des Moines Cold Storage | Project will repair an exisiting spur track and add additional track length to extend it to the cold storage facility in Des Moines. | 602312 | 385000 | Company Match | 321611.17 | 63389 | Project in Process | January 2020
Oelwein Track Rehab | Project is a wood crosstie replacement project from Dewar, Iowa at Mile Post 322 to East of Fairbank, Iowa at Mile Post 346. | 987551 | 493775 | Company Match | 0 | 493775 | Project in Process | January 2020
Eastern Iowa Logistics Park/CRANDIC | RRLG fund will go toward the site grading and track construction to support the proposed transload facility in SW Cedar Rapids. | 2500000 | 500000 | Company Match | 0 | 500000 | In Agreement Phase - project also has federal funding | January 2020
KJRY Yard Enhancements III | Project will replace 400 ties, 27 sticks of rail and install two new switches in the KJRY middle yard area. OTM and ballast are included in the project as well. | 250196 | 200157 | Company Match | 0 | 200157 | Project in Process | January 2020
Council Bluffs Transload Study | Study will address the market potential of an expanded transload area in Council Bluffs, Iowa. | 70400 | 56320 | Company Match | 0 | 56320 | Project in Process | January 2019
|  | 25636958 | 4694624 |  | 1421611.17 | 3273013
FY 2016 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
ADM "S" Curve | Current rail spur into the Clinton facility has an "s" curve. Project proposes to straighten the curveto allow greater rail capacity and better safety. | 450000 | 165600 | Company Match | 0 | 0 | Project withdrawn by appliant | Not Applicable
A to Z Drying Rail Enhancement | A to Z Drying is replacing and changing the location of an exisiting spur due to expansion of neighboring company. | 419375 | 200000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Boone Scenic Valley Industrial Park Line Phase I | Construction of a 1700 ft passing track. Includes grading ballast, and installation of rail ties. Will also be replacing ties and adding ballast where needed to maintain 286K service. Company also constructing 1425 feet of track extending to their facility in nearby industrial park. | 706050 | 556050 | In Kind Match | 556050 | 0 | Completed | 4/13/216
Iowa Traction Transload Project | IATR improving their current site by constructing 950 ft siding to support currently transload operation. Project also includes installing a 90lb switch to accommodate 286K | 119306 | 95445 | Company Match | 0 | 95445 | Project in process | January 2019
KJRY Yard Enhancements II | Project involves replacing four switches and improving tracks, ties and ballast in the yard | 350356 | 280285 | Company Match | 0 | 280285 | Project in Process | January 2019
|  | 2045087 | 1297380 |  | 556050 | 375730
FY 2015 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
West Charles Street Viaduct | Reconstruction, removal and replacement of the east side of the West Charles Street Viaduct | 654315 | 523452 | Local Match | 523452 | 0 | Complete - Certificate of completion pending | Spring 2018
Five Star Coop | Expansion of current rail siding from 3 car capacity to 35 car capacity | 9614000 | 500000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Des Moines Transload Facility | Development of a transload facility to improve the overall freight capacity in Des Moines Metro area | 10000000 | 1700000 | Company Match | 0 | 1700000 | Project in process - extensive project, extension was granted | January 2021
Crossroads of Global Innovation | Phase two allows for connection to the CN mailline in the ICGI certrified site | 2100000 | 1600000 | Local Match | 0 | 1600000 | Project in process - extensive project, extension was granted | Spring 2018
KJRY Railnetwork Improvements | Upgrade a mainline yard switch along with heavily traveled mainline yard tracks | 286000 | 228800 | Local Match | 228800 | 0 | Complete - Certificate of completion pending | Spring 2018
Sioux Center Rail Port Study | A planning study to determine the potential for a rail port adjacent to a BNSF line that runs north/south through the City limits | 130000 | 100000 | Local Match | 95796.41 | 0 | Completed - unspent funds put back in pot | 2016-04-07
|  | 22784315 | 4652252 |  | 848048.41 | 3300000
FY 2014 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
HFCA (HF Chlor Alkali) Rail Road Project | Construction of three miles of new (private) track for new Cargill Plant | 150000000 | 324000 | Company match | 324000 | 0 | Completed | 2015-04-15
Iowa Corn Processors (ICP) Rail Expansion | Construction of two spur tracks on ICP property to add capacity | 14832000 | 419000 | Company Match | 419000 | 0 | Completed | 2014-06-11
Carter Lake Metals Processing Building (Owen Industries) | Construction of new rail spur to accommodate new production building | 30000000 | 108000 | Company Match | 0 | 0 | Withdrawn - funds returned 2017 | Not Applicable
Heartland Co-op Greenfield Rail Loading Elevator | Build a 125-car load out facility | 24000000 | 1450000 | Company Match | 1450000 | 0 | Completed | 2015-11-17
CRANDIC - Millrace & Price Creek Bridges | Replacement of two bridges | 2840000 | 725000 | Company Match | 725000 | 0 | Completed | 2015-05-19
City of Knoxville - Red Rock Industrial Park | Planning Study | 118000 | 94400 | Local match | 92568 | 0 | Completed - remianing funds put back in | 2016-01-01
|  | 221790000 | 3120400 |  | 3010568 | 0
FY 2013 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
CRANDIC Iowa River Crossing North Bridge | Consruct replacement rail bridge | 2840400 | 1500000 | Company match | 1500000 | 0 | Completed | 2014-04-15
Iowa Falls UP/CN Connector | Upgrade rail infrastructure in industrial area | 5711369 | 900000 | Local match | 0 | 900000 | Project in process | Spring 2018
Rail One | Industrial Rail Spur Construction | 4397880 | 1116000 | Company match | 1116000 | 0 | Completed | 2016-01-30
BJRY Rail/Truck/Barge Planning Study | Planning Study | 50000 | 40000 | Local match | 17542.78 | 22457.22 | Complete - Certificate of completion pending (remaing funds to go back in pot) | Spring 2018
Central Iowa Transloading Facility Feasibility Study | Planning Study | 125000 | 100000 | Local match | 98824.2 | 0 | Completed - remaining funds put back in | 2014-10-02
Iowa Falls/Hardin County Rail Port Planning Study | Planning Study | 125000 | 100000 | Local match | 100000 | 0 | Study Completed | 2014-10-01
Mills/Pottawattamie County Rail Port Study | Planning Study | 98000 | 78400 | Local match | 78400 | 0 | Study Completed | 2014-10-07
North Central Ag Park Planning Study | Planning Study | 100000 | 80000 | Local match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Sioux City Rail Study Phase II | Planning Study | 350000 | 100000 | Local match | 0 | 100000 | Project in process | Extension granted - Spring 2018
|  | 13797649 | 4014400 |  | 2910766.98 | 1022457.22
FY 2012 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway Spur rehabilitation | Industrial Rail Spur Construction | 197435 | 157948 | Company match | 87025.34 | 0 | Complete - remaining funds put back in pot | 2016-03-23
Butler Cross Dock | Industrial Rail Spur Construction | 1758922 | 705621 | Local match | 477295 | 0 | Complete - remaining returned | Close out Spring 2017
Cherokee Industrial Spur | Industrial Rail Spur Construction | 771818 | 617454 | Local match | 617454 | 0 | Completed | 2012-04-17
CRANDIC Iowa River Crossing Improvement | Consruct replacement rail bridge | 3200000 | 1613596 | Company match | 0 | 0 | Completed | 2014-04-15
Global Foods | Rail Spur upgrade | 358525 | 72000 | Local match | 0 | 0 | Project withdrawn by applicant | Not applicable
Iowa River Railroad | Rail line acquisition & preservation | 2500000 | 1000000 | Company match | 0 | 0 | Project withdrawn by applicant | Not applicable
North Central Iowa Rail Corridor, LLC | Rail line acquisition & preservation | 1900000 | 400000 | Local match | 400000 | 0 | Completed | 2012-04-26
Valley Distribution Corporation | Industrial Rail Spur Construction | $ 297, 525 | 218652 | Company match | 218652 | 0 | Completed | 2012-04-18
Waverly GMT Rail Spur | Industrial Rail Spur Construction | 538100 | 204000 | Company match | 204000 | 0 | Completed | 2014-11-10
|  | 11224800 | 4989271 |  | 2004426.34 | 0
Note 1: CRANDIC was awarded $2,000,000 from RRLG, however $386,404 of the award is from federal Rail Assistance Program (RAP) funds.
FY 2011 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Adams County Rail | Industrial Rail Spur Extension | 1758922 | 879461 | Local match | 0 | 0 | Project withdrawn | Not applicable
Eastern Iowa Industrial Center | Construct Transloading Facility | 8474244 | 2000000 | Federal, state and local match | 2000000 | 0 | Completed | 2016-04-26
Lomont Molding Inc | Rail Spur upgrade | 138560 | 110848 | Company match | 0 | 0 | Project withdrawn | Not applicable
Nypro Kannaak | Rail Spur upgrade | 255951 | 174022 | Company match | 174022 | 0 | Completed | 2012-11-14
|  | 10627677 | 3164331 |  | 2174022 | 0
FY 2010 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Upgrade rail infrastructure in industrial park | 88000 | 55400 | Railroad match | 55400 | 0 | Completed | 2011-01-10
Cedar Rapids and Iowa City Railroad (CRANDIC) | Rebuild rail bridge | 886500 | 700000 | Railroad match | 700000 | 0 | Completed | 2011-04-14
Schau Recycling | Install industrial rail spur | 450000 | 225000 | Company match | 145187 | 0 | Completed | 2013-02-28
Shine Brothers Corp. | Upgrade rail infrastructure in industrial area | 467589 | 311071 | Company match | 311071 | 0 | Completed | 2011-10-15
City of Waterloo | Install industrial rail spur | 252005 | 126000 | City match | 118691 | 0 | Completed | 2013-12-31
Webster County Board of Supervisors | Install industrial rail spur in industrial park | 10900000 | 900000 | County match and company investment | 0 |  | Project withdrawn | Not applicable
Union Pacific Railroad and Iowa Northern Railway | Rebuild rail bridge in Waterloo* | 5437200 | 1000000 | Railroad match and FRA grant award | 1000000 | 0 | Completed | 2009-12-31
| TOTAL | 18481294 | 3317471 |  | 2330349 | 0
FY 2009 Railroad Revolving Loan and Grant Program (Flood Recovery)
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Repair rail infrastructure damaged by flooding | 89333 | 71000 | Railroad match | 61164 | 0 | Completed | 2009-01-01
Cedar Rapids and Iowa City Railroad (CRANDIC) | Repair rail infrastructure damaged by flooding | 400000 | 320000 | Railroad match | 320000 | 0 | Completed | 2008-11-01
Keokuk Junction Railway Company | Repair rail infrastructure damaged by flooding | 693120 | 554000 | Railroad match | 405346 | 0 | Completed | 2009-03-01
Iowa, Chicago & Eastern Railroad Corp. | Repair rail infrastructure damaged by flooding | 1771463 | 1417000 | Railroad match | 1406627 | 0 | Completed | 2009-10-01
Iowa Interstate Railroad | Repair rail infrastructure damaged by flooding | 964707 | 772000 | Railroad match | 650000 | 0 | Completed | 2009-03-01
Iowa Northern Railway Co. | Repair rail infrastructure damaged by flooding | 851704 | 681000 | Railroad match | 616420 | 0 | Completed | 2008-11-01
Iowa River Railroad | Repair rail infrastructure damaged by flooding | 230000 | 184000 | Railroad match | 184000 | 0 | Completed | 2009-12-31
| TOTAL | 5000327 | 3999000 |  | 3643557 | 0
FY 2008 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2008 Funds used | FY 2008 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Cedar Rapids Terminal (Iowa Northern Railroad) Construct rail spur and intermodal loading facility in Palo | 884000 | 242000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Big River Resources Ethanol Plant industrial rail spur | 8500000 | 75000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Lincolnway Railport Industrial Park | 1072933 | 840000 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
| Norfolk Iron and Metal Company industrial rail spur | 1398000 | 810000 | State grant; Private investment | 810000 | 0 | Completed | 2009-09-30
| Oregon Trail Energy Rail spur | 7146000 | 75000 | State grant; Private investment | 0 | 0 | Project was withdrawn. Funding has been reprogrammed to FY2012 | Not applicable
| Prairie Creek Ethanol rail spur | 6055075 | 75000 | State Grant; Private investment | 0 | 0 | Project withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
| Raccoon Valley BioDiesel Rail spur | 2250000 | 50000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Trinity Towers | 414489 | 165795 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Unity Ethanol Cedar River | 9500000 | 270000 | State loan; Private investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
| Unity Ethanol Ottumwa | 9500000 | 270000 | State grant and loan; Private Investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
|  | 46720497 | 2872795 |  | 810000 | 0
FY 2007 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2007 Funds used | FY 2007 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Alternative Energy Resources Ethanol Plant industrial rail spur | 24240300 | 239000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Lincolnway Railport Industrial Park | 11852896 | 489000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Seimens Wind Power industrial rail spur | 457513 | 326000 | State grant; Private investment | 326000 | 0 | Complete | 2010-05-26
| Southern Bio Energy industrial rail spur | 1300000 | 250000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
|  | 37850709 | 1304000 |  | 326000 | 0
FY 2006 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2006 Funds used | FY 2006 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Absolute Energy industrial rail spur | 3712220 | 500000 | State grant and loan; Private investment; local investment | 500000 | 0 | Complete | 2008-02-05
| Cascade Lumber Company industrial rail spur | 694000 | 534000 | State grant and loan; Private investment; local investment | 534000 | 0 | Complete | 2007-09-19
| Eastern Iowa Industrial Center rail development for industrial park expansion | 4660791 | 760791 | State grant; Private investment; FHWA grant | 729711 | 31079 | Complete | 2015-06-30
| Green Plains Renewable Energy | 5700000 | 280000 | State grant and loan; Private investment; local investment | 126000 | 0 | Complete: loan portion of award declined | 2013-02-28
| Midwest I,LLC industrial rail spur | 2800000 | 280000 | State grant and loan; Private investment; local investment | 280000 | 0 | Complete | 2008-09-30
| Iowa Renewable Energy LLC industrial rail spur | 1258532 | 300000 | State grant and loan; Private investment; local investment | 300000 | 0 | Complete | 2007-11-01
| Lincolnway Railport Industrial park rail development | 2154086 | 319209 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed for flood recovery activities. | Not applicable
| Marco Group International industrial rail spur switching improvements | 30000 | 22500 | State grant; Private investment | 0 | 0 | Project withdrawn | Not applicable
| Metzler Automotive | 406711 | 60000 | State grant | 42691 | 0 | Complete | 2007-11-01
|  | 21416340 | 3056500 |  | 2512402 | 31079

## Passenger Rail
2010 Passenger Rail Service Revolving Fund (RIIF)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Support in Development of Intercity Passenger Rail efforts | 500000 | 499935 | None | 499935 | 0 | Completed | 2011-04-11
Funding reserved to match FY 2009 Recovery Act award to Iowa DOT for Chicago to Omaha Planning Study | 2000000 | 1016039.5 | Federal Railroad Administration FY 2009 HSIPR award | 1016039.5 | 0 | Completed | 2014-01-09
Funding reserved for PE/NEPA activities to match a federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 6213000 | 1242600 | Federal Railroad Administration FY 2010 HSIPR award | 609755.56 | 632844.44 | In Progress | 2018-12-31
Funding reserved for the Iowa City-Cedar Rapids Passenger Rail Conceptual Feasibility Study - Phase 1 (Task A) | 40000 | 14233.1 | CRANDIC and MPOJC | 14233.1 | 0 | Completed | 2015-11-01
Funding reserved for the Iowa City-North Liberty Passenger Rail Conceptual Feasibility Study - Phase 1 (Task B) | 49999 | 15918.75 | CRANDIC and MPOJC | 15918.75 | 0 | Completed | 2016-10-29
Funding reserved for Final Design & Construction to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 125000000 | 211273.65 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 211273.65 | Not Started | TBD
TOTAL | 133802999 | 3000000 |  | 2155881.91 | 844118.09
2011 Passenger Rail Service Revolving Fund (funding from Underground Storage Tank Fund)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Funding reserved for Final Design & Construction to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 125000000 | 2000000 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 2000000 | Not Started | TBD
TOTAL | 125000000 | 2000000 |  | 0 | 2000000

## PTIG
FY 2018 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
(#19448) | Ames | Three in-ground hoists (partial funding---also see FY16, FY17) | 408750 | 327000 | Local funds | 0 | 327000 | Awarded 8-1-2017 | Est. 7/10/19
(#19449) | Cambus | Maintenance facility rehab | 1289000 | 600000 | Local funds | 0 | 600000 | Awarded 8-1-2017 | Est. 7/10/19
(#19450) | Region 5 | Humboldt land/construction of transit storage | 806400 | 539895 | Local funds | 0 | 539895 | Awarded 8-1-2017 | Est. 7/10/19
|  | Funds available for reprogramming |  | 33105
|  | GRAND TOTAL |  | 1500000 |  |  | 1466895
FY 2017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
(#18417) | Ames | Reconstruct roof | 400000 | 320000 | Local funds | 240206 | 79794 | Awarded 8-2016 | Est. 7/11/2018
(#18418) | Dubuque - The Jule | Bus storage facility | 6340247 | 569823 | Federal transit funds Local funds | 569823 | 0 | Project Complete | 2017-11-13 | 2017-11-13
(#18419) | Region 10 | Monticello bus faclity construction | 281887 | 225509 | Local funds | 25487 | 200022 | Awarded 8-2016 | Est. 7/11/2018
(#18420) | Region 12 | Replace overhead doors | 20000 | 16000 | Local funds | 13232 | 2768 | Awarded 8-2016 | Est. 7/11/2018
(#18421) | Region 15 | Purchase of transit facility | 600000 | 323764 | Federal transit funds Amoco Loan | 323764 | 0 | Project Complete | 2016-09-26 | 2016-09-26
(#19448) | Ames | Three in-ground hoists (partial funding---also see FY16, FY18) | 56130 | 44904 | Local funds | 0 | 44904 | Awarded 8-1-2017 | Est. 7/10/19
|  | GRAND TOTAL |  | 1500000 |  |  | 327488
FY 2016 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
(#17521) | Burlington | Building improvements | 645846 | 480000 | Local funds | 480000 | 0 | Project complete | 2016-12-13 | 2016-12-13
(#17522) | Des Moines | Rehabilitate facility | 1050000 | 369007 | Federal transit funds Local funds | 369007 | 0 | Project Complete | 2017-01-09 | 2017-01-09
(#17523) | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial funding---also see FY11, FY12, FY14 ) | 17741 | 14193 | Local funds | 0 | 14193 | Awarded 8-2015 | Est. 3/30/2018
(#17519) | Region 2 | Construction of indoor parking facility | 763390 | 600000 | Local funds | 600000 | 0 | Project Complete | 2017-07-12 | 2017-07-12
(#17520) | Region 8 | Roof mounted solar array (partial funding--also see FY15) | 46000 | 3695 | Local funds | 3695 | 0 | Project Complete | 2017-12-18 | 2017-12-18
(#19448) | Ames | Three in-ground hoists (partial funding---also see FY17, FY18) | 41381.25 | 33105 | Local funds | 0 | 33105 | Awarded 8-1-2017 | Est. 7/10/19
|  | GRAND TOTAL |  | 1500000 |  |  | 14193
FY 2015 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
(#16399) | Burlington | Bus depot improvements | 55000 | 44000 | Local | 44000 | 0 | Project complete | 2015-04-22 | 2015-04-22
(#16400) | Des Moines | DART Way front office remodel | 965000 | 600000 | federal transit funds local funds | 600000 | 0 | Project complete | 2015-12-16 | 2015-12-16
(#16401) | Dubuque | Bus storage facility | 5184568 | 600000 | federal transit funds local funds | 600000 | 0 | Project Complete | 2017-07-10 | 2017-07-10
(#16402) | Sioux City | Maintenance, repairs, and improvements for MLK Center | 280000 | 208800 | federal transit funds local funds | 208800 | 0 | Project complete | 2016-01-12 | 2016-01-12
(#17520) | Region 8 | Roof mounted solar array (partial funding---also see FY16) | 59000 | 47200 | Local funds | 47200 | 0 | Project Complete | 2017-12-18 | 2017-12-18
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2014 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
15510 | Region 5 | Construct new vehicle and administration facility | 433900 | 347120 | Local funds | 347120 | 0 | Project complete | 2015-03-16 | 2015-03-16
15511 | Region 9 | Purchase and install new generator | 70000 | 32880 | Local funds | 32880 | 0 | Project Complete | 2016-08-18 | 2016-08-18
15512 | Region 13 | Construct wash bay addition | 202800 | 162240 | Local funds | 162240 | 0 | Project complete | 2014-07-27 | 2014-07-27
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY13) | 688192.2775 | 475846 | federal transit funds local funds | 475846 | 0 | Project complete | 2015-11-12 | 2015-11-13
15513 | Des Moines | Rehabilitate maintenance lane | 45000 | 36000 | Local funds | 36000 | 0 | Project complete | 2016-01-12 | 2016-01-12
15514 | Sioux City | Replace bus wash system | 300000 | 199338 | Local funds | 199338 | 0 | Project complete | 2015-12-31 | 2015-12-31
15514 | Sioux City | Rehabilitate roof | 185000 | 123546 | Local funds | 123546 | 0 | Project complete | 2015-12-31 | 2015-12-31
15514 | Sioux City | Replace transit operations heating, ventilating, and air conditioning system | 50000 | 40000 | federal transit funds local funds | 40000 | 0 | Project complete | 2014-05-08 | 2014-05-08
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY11, FY12 and FY16) | 8493 | 6794 | Local funds |  | 6794 | Awarded 8-2015 | Est. 3/30/2018
18421 | Region 15 | Purchase of transit facility (partial funding--also see FY17) |  | 76236 |  | 76236 | 0 | Project complete | 2016-09-26 | 2016-09-26
|  | GRAND TOTAL |  | 1500000 |  |  | 6794
FY 2013 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
14370 | Cedar Rapids | Administration facility/garage | 5294251 | 600000 | federal transit funds local funds | 600000 | 0 | Project complete | 2013-10-24 | 2013-10-24
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY10) | 384736.25 | 307789 | Local Funds | 307789 | 0 | Project complete | 2014-08-13 | 2014-08-13
14372 | Des Moines | Storage barn portals restoration | 467000 | 352000 | federal transit funds local funds | 352000 | 0 | Project complete | 2014-11-03 | 2014-11-03
14373 | Des Moines | Fuel delivery system | 192500 | 145000 | federal transit funds local funds | 145000 | 0 | Project complete | 2014-10-13 | 2014-10-13
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY14) | 137698.9088 | 95211 |  | 95211 | 0 | Project complete | 2015-11-12 | 2015-11-13
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2012 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
13415 | Ames | Facility renovation | 792000 | 600000 | Local Funds | 600000 | 0 | Project complete | 2013-11-27 | 2013-11-27
13416 | Cedar Rapids | New facility to replace transit garage and admin. facility | 3900000 | 600000 | local & FEMA | 600000 | 0 | Project complete | 2013-05-08 | 2013-05-08
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY11) | 63035 | 35452 | Local Funds | 35452 | 0 | Project complete | 2014-10-31 | 2014-10-31
13418 | Dubuque | Sprinkler replacement | 64677 | 51742 | Local Funds | 51742 | 0 | Project complete | 2015-04-03 | 2015-04-03
13418 | Dubuque | Roof replacement | 171920 | 137536 | Local Funds | 137536 | 0 | Project complete | 2015-04-03 | 2015-04-03
13419 | Muscatine | Passenger shelter | 7000 | 5600 | Local Funds | 5600 | 0 | Project complete | 2012-03-16 | 2012-03-16
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY11, FY14 and FY16) | 87087 | 69670 | Local funds | 4946 | 64724 | Awarded 8-2015 | Est. 3/30/2018
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2011 - I-Jobs Bonding (Revenue Bonds Capitals II)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12319 | Ames Transit Agency (CyRide) | Construct additional bus storage/maintenance areas | 4897614 | 800000 | Federal Transit Funds and Local | 800000 | 0 | Project complete | 2013-11-27 | 2013-11-27
12320 | Des Moines Area Regional Transit | Replace roof over maintenance area | 500000 | 381827 | Transit Agency Funds | 381827 | 0 | Project complete | 2011-07-05 | 2011-07-18
12733 | Dubuque | Transfer facility | 379211 | 278214 | Transit Agency Funds | 278214 | 0 | Project complete | 2014-01-14 | 2014-01-14
12738 | Des Moines | Wash rack rehabilitation | 30000 | 24000 | Transit Agency Funds | 24000 | 0 | Project complete | 2012-06-07 | 2012-06-07
12321 | Southwest Iowa Transit Agency-SWITA (Region 13) | Construct a vehicle storage facility | 565732 | 452585 | Transit Agency Funds | 452585 | 0 | Project complete | 2012-06-30 | 2011-04-04
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY12) | 22716.25 | 18173 | Local Funds | 18173 | 0 | Project complete | 2014-10-31 | 2014-10-31
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY13 and FY14) | 36240.1325 | 25058 |  | 25058 | 0 | Project complete | 2015-11-12 | 2015-11-13
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY12, FY14 and FY16) | 25179 | 20143 | Local funds | 20143 | 0 | Awarded 8-2015 | Est. 3/30/2018
|  | GRAND TOTAL |  | 2000000 |  |  | 0
FY 2010 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12738 | Des Moines | Locker/washroom renovations | 65000 | 48000 | Transit Agency Funds | 48000 | 0 | Project complete | 2012-06-07 | 2012-06-07
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY09) | 617904 | 436904 | Transit Agency Funds | 436904 | 0 | Project complete | 2013-02-14 | 2013-02-14
11761 | Des Moines Area Regional Transit | Restoration of masonry structures and upgrade of energy management system at DART facility | 100000 | 79920 | Transit Agency Funds | 79920 | 0 | Project complete | 2010-11-01 | 2010-11-16
11767 | Ottumwa Transit Authority | Expand maintenance shop serving OTA and 10-15 regional transit fleets to accommodate more vehicles and provide sufficient headroom to allow use of vehicle hoists | 235000 | 188000 | Transit Agency Funds | 188000 | 0 | Project complete | 2011-01-18 | 2011-01-18
11762 | Region 2 Transit - Mason City | Expand/renovate facility shared with Mason City Transit to accommodate dispatch function now required to support direct operation of transit services in Cerro Gordo County by regional system | 176000 | 140800 | Transit Agency Funds | 140800 | 0 | Project complete | 2010-12-31 | 2011-01-24
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilton Co. (partial see also funding in FY09) | 7347 | 5877 | Transit Agency Funds | 5877 | 0 | Project complete | 2012-07-31 | 2012-07-31
11765 | River Bend Transit (Region 9) - Davenport | Expand bus wash portion of River Bend facility to accommodate larger vehicles now being operated | 130000 | 67019 | Transit Agency Funds | 67019 | 0 | Project complete | 2011-11-20 | 2011-11-26
11766 | Southeast Iowa Bus (region 16) - Burlington | Participate in transit share of purchase and remodeling of existing building to house planning commission functions including transit administration and operations | 296250 | 125179 | Transit Agency Funds | 125179 | 0 | Project complete | 2011-06-21 | 2011-06-21
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY13) | 139776.25 | 111821 | Local Funds | 111821 | 0 | Project complete | 2014-08-13 | 2014-08-13
12738 | Des Moines | Storm water rack and sanitation sewer (see FY11 and supplemental funding from FY09) | 12144 | 5534 | Transit Agency Funds | 5534 | 0 | Project complete | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY11, FY12) | 46326.25 | 37061 | Local Funds | 37061 | 0 | Project complete | 2014-10-31 | 2014-10-31
15513 | Des Moines | Renovate operations office (partial-- see funding from FY11, FY13 and FY14) | 5618.6812 | 3885 |  | 3885 | 0 | Project complete | 2015-11-12 | 2015-11-13
|  | GRAND TOTAL |  | 1250000 |  |  | 0
FY 2009 - RC3 511 - Health Restricted Capital Bond Fund (Revenue Bonds Capitals)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
10482 | CyRide (Ames) | Reconstruction of the steam cleaning area (Moved to ARRA) | $640,000 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10481 | City of Davenport | Relocate transit offices (Cancelled 8-9-10) | 654000 | 0 | Transit Agency Funds | 0 | 0 | Project Cancelled | Est. 6/30/2010
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY10) |  | 385677 | FEMA Funds, Transit Agency Funds | 385677 | 0 | Project Complete | 2013-02-14 | 2013-02-14
10484 | River Bend Transit (Region 9) - Davenport | Vehicle storage and wash bays (Moved to ARRA) | $491,300 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10483 | Western Iowa Transit System (Region 12) - Carroll | Construct a vehicle storage addition (partial - see also supplimental funding from FY07) | 85446.25 | 68357 | Federal Transit Funds, Transit Agency Funds | 68357 | 0 | Project complete | 2009-08-31 | 2009-07-23
10968 | City of Coralville | Relocate transit office/maintenance facility out of floodway | 3643332 | 880000 | FEMA Funds, Transit Agency Funds | 880000 | 0 | Project Complete |  | 2013-01-02
11350 | CyRide (Ames) | Rehabitate west wall exterior insulation finish system (EIFS) of Cy-Ride maintenance facility | 200000 | 62577 | Transit Agency Funds | 62577 | 0 | Project Complete | 2011-05-25 | 2011-01-05
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilaton Co. (partial see also funding in FY10) | 699736.25 | 559789 | Transit Agency Funds | 559789 | 0 | Project Complete | 2012-07-31 | 2012-07-31
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY10, FY13) | 10817.5 | 8654 | Local Funds | 8654 | 0 | Project complete | 2014-08-13 | 2014-08-13
12738 | Des Moines | Storm water rack and sanitation sewer (see FY10 and FY11) | 177300 | 137523 | Transit Agency Funds | 137523 | 0 | Project Complete | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY10, FY11, FY12) | 121778.75 | 97423 | Local Funds | 97423 | 0 | Project complete | 2014-10-31 | 2014-10-31
|  | GRAND TOTAL |  | 2200000 |  |  | 0
FY 2008 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09522 | University of Iowa (Cambus) | Construct new vehicle storage building for CAMBUS (partial - see also supplimental funding from FY07) | 1166319 | 702268 | Federal Transit Funds, Transit Agency Funds | 702268 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines (DART) | Construct addition to vehicle storage building (partial - see also supplimental funding from FY07) | 1044250 | 820000 | Federal Transit Funds, Transit Agency Funds | 820000 | 0 | Project complete | 2010-11-03 | 2010-11-03
09524 | Region Six Planning Commission (Region 6) - Marshalltown | Transit portion of Joint Facility | 385043 | 100876 | Federal Transit Funds, Transit Agency Funds | 100876 | 0 | Project complete | 2009-05-31 | 2008-12-18
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Construct new regional transit office, storage and maintenance facility in Dubuque (partial - see also supplimental funding from FY07) | 721070 | 576856 | Transit Agency Funds | 576856 | 0 | Project complete | 2008-06-30 | 2008-07-31
|  | GRAND TOTAL |  | 2200000 |  |  | 0
FY 2007 - RC2 942 - Health Restricted Capitals Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09410 | Ames Transit Agency (CyRide) | Expand operations/administration area of CyRide maintenance facility-Ride Facility | 1100000 | 880000 | Transit Agency funds | 880000 | 0 | Project complete | 2008-05-31 | 2008-06-19
09409 | City of Cedar Rapids | Construct transit portion of new downtown Intermodal facility | 2589453 | 0 | Federal Transit Funds, Transit Agency funds | 0 | 0 | Project dropped after city reorganization | NA | NA
09402 | City of Davenport (CitiBus) | Construct new transit hubs adjacent to regional shopping center and on campus of local university | 138134 | 110507 | Transit Agency funds | 110507 | 0 | Project complete | 2009-02-18 | 2009-02-18
09408 | Des Moines Area Regional Transit (DART) | Renovate maintenance area of DART facility | 66677 | 53341 | Transit Agency funds | 53341 | 0 | Project complete | 2010-02-17 | 2010-02-17
09404 | City of Sioux City | Construct new parts storage building at transit maintenance facility | 50000 | 40000 | Transit Agency funds | 40000 | 0 | Project complete | 2008-09-16 | 2008-09-16
09407 | North Iowa Area Regional Transit (Region 2) - Mason City | Construct a variety of projects to finish out recently constructed transit maintenance facility shared with City of Mason City | 40267.5 | 32214 | Transit Agency funds | 32214 | 0 | Project complete | 2008-03-31 | 2008-05-14
09406 | RIDES/Regional Transit Authority (Region 3) - Spencer | Construct new satellite facility in Sheldon for transit vehicle storage and maintenance | 500000 | 163085 | Federal Transit Funds, Transit Agency funds | 163085 | 0 | Project complete | 2010-12-31 | 2009-11-25
09405 | Western Iowa Transit System (Region 12) - Carroll | Expand transit maintenance and storage facility in Carroll | 587500 | 220000 | Federal Transit Funds, Transit Agency funds | 220000 | 0 | Project complete | 2008-09-30 | 2008-09-17
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Partial funding for FY08 project to construct new regional transit office, storage and maintenance facility in Dubuque | 418122.5 | 303144 | Transit Agency Funds | 303144 | 0 | Project complete | 2008-06-30 | 2008-07-31
09522 | University of Iowa (Cambus) - Iowa City | Construct new vehicle storage building for CAMBUS (partial - see also funding from FY08) | 222165 | 177732 | Federal Transit Funds, Transit Agency Funds | 177732 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines Area Regional Transit (DART) | Construct addition to vehicle storage building (partial - see also funding from FY08) | 75000 | 60000 | Transit Agency Funds | 60000 | 0 | Project complete | 2010-11-03 | 2010-11-03
10483 | Western Iowa Transit System (Region 12) - Carroll | Partial funding for FY09 project to construct a vehicle storage addition in Carroll | 82053.75 | 65643 | Federal Transit Funds, Transit Agency funds | 65643 | 0 | Project complete | 2009-07-23 | 2009-07-23
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also funding from FY09 and FY10) | 71773.75 | 57419 | Transit Agency Funds | 57419 | 0 | Project complete | 2013-02-14 | 2013-02-14
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY09, FY10, FY11, FY12) | 46143.75 | 36915 | Local Funds | 36915 | 0 | Project complete | 2013-05-13 | 2013-05-13
|  | GRAND TOTAL |  | 2200000 |  |  | 0
19150000
| FY2018 | 1500000
20650000