## GAVI
FY 2016 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ames Municipal Airport | Site improvements for future terminal building | 2410000 | 150000 | Airport funds |  | 150000 | Under Construction | 2016-07-31
Council Bluffs Municipal Airport | T-hangar Improvements | 216451 | 75000 | Airport funds |  | 75000 | Under Construction | 2016-12-31
Cresco Municipal Airport | Rehabilitate hangar and construct pilot lounge | 18728 | 15919 | Airport funds |  | 15919 | Under Construction | 2016-06-30
Lamoni Municipal Airport | Construct hangar | 322000 | 150000 | Airport funds | 57450 | 92550 | Under Construction | 2016-12-31
Marshalltown Municipal Airport | Pave hangar floor | 94500 | 80325 | Airport funds |  | 80325 | Project on Hold
Perry Municipal Airport | Repair hangar roof | 20000 | 14000 | Airport funds |  | 14000 | Under Contract | 2016-07-21
Sibley Municipal Airport | Rehabilitate terminal building | 26836 | 16101 | Airport funds |  | 16101 | Under Contract | 2016-04-30
Sioux County Regional Airport | Construct maintenance and electrical vault buildings | 182200 | 150000 | Airport funds |  | 150000 | In Design | 2016-12-31
Spencer Municipal Airport | Rehabilate hangar floor | 76650 | 45990 | Airport funds |  | 45990 | In Design | 2016-09-30
Washington Municipal Airport | Construct hangar | 630540 | 150000 | Airport funds |  | 150000 | Preliminary Design | 2016-12-31
| Total | 3997905 | 847335 |  | 57450 | 789885
FY 2015 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Atlantic Municipal Airport | Construct 60' x 80' hangar | 717200 | 150000 | Airport funds | 150000 | 0 | Completed | 2015-12-01
Boone Municipal Airport | Construct 2-unit, 45' x 80' hangar | 201600 | 150000 | Airport funds |  | 150000 | Under Construction | 2016-06-01
Decorah Municipal Airport | Construct 3-stall rectangular hangar | 235000 | 117500 | Airport funds | 10770 | 106730 | Under Construction | 2016-07-31
Fairfield Municipal Airport | Construct new public terminal building | 215657 | 150000 | Airport funds |  | 150000 | Under Construction | 2016-04-15
Grinnell Regional Airport | Terminal building and maintenance hangar renovation | 60000 | 30000 | Airport funds | 12250 | 0 | Completed | 2014-11-14
Osceola Municipal Airport | Construct 33' x 42' rectangular hangar | 107140 | 74998 | Airport funds | 13355 | 61643 | Under Construction | 2016-05-27
Rock Rapids Municipal Airport | Rehabilitate hangar roof | 27135 | 21708 | Airport funds | 21628 | 0 | Completed | 2015-06-15
Sibley Municipal Airport | Renovate terminal building roof and addition of insulation in hangar | 24000 | 14400 | Airport funds | 2895 | 11505 | Under Construction | 2016-04-30
Washington Municipal Airport | Rehabilitate hangar | 76500 | 57375 | Airport funds |  | 57375 | Final punch list items. | 2016-03-31
| Total | 1664232 | 765981 |  | 210898 | 537253
FY 2014 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ankeny Regional | Construct 6-unit tee hangar | 326250 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-06-11
Davenport Municipal | Rehabilitate hangar 8970 | 56660 | 48161 | City funds | 48161 | 0 | Completed | 2014-09-22
Emmetsburg Municipal | Construct 80x100 hangar | 529170 | 100000 | Local funding uncertain | 35522 | 64478 | Under Construction | 2016-01-31
Marshalltown Municipal | Renovate hangar | 88200 | 74970 | City funds | 29273 | 45697 | Final punch list items. | 4/31/2016
Northeast Iowa Regional | Construct 70x120 hangar | 300000 | 150000 | Utility company loan | 150000 | 0 | Completed | 2014-09-23
Ottumwa Regional | Renovate hangar | 74470 | 59470 | Local airport funds | 57555 | 0 | Completed | 2015-06-30
Perry Municipal | Construct 45x100 hangar | 422375 | 150000 | City bonding | 128239 | 0 | Completed | 2015-06-01
Red Oak Municipal | Renovate hangar door | 20700 | 16560 | City funds | 16560 | 0 | Completed | 2013-12-18
Webster City Municipal | Renovate maintenance hangar | 40500 | 20250 | Airport funds | 20250 | 0 | Completed | 2014-06-01
| Total | 1817825 | 769411 |  | 635560 | 110175
FY 2013 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Boone Municipal Airport | Construct hangar | 187500 | 150000 | Airport funds | 122457 | 27543 | Final punch list items. | 2016-03-31
Clinton Municipal Airport | Construct transient hangar | 600000 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-06-27
Iowa City Municipal Airport | Rehabilitate terminal and building roofs | 102000 | 75000 | Airport funds | 75000 | 0 | Completed | 2014-10-27
Iowa Falls Municipal Airport | Expand four unit t-hangar and apron | 326760 | 150000 | Airport funds | 149183 | 0 | Completed | 2014-09-18
Red Oak Municipal Airport | Construct hangar | 210000 | 150000 | Airport funds | 150000 | 0 | Completed | 2013-10-11
Vinton Veterans Airpark | Construct hangar | 271000 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-02-21
| Total | 1697260 | 825000 |  | 796640 | 27543
FY 2012 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Atlantic | Rehabilitate hangar | 35000 | 7649 | City funds, other infrastructure funds | 7649 | 0 | Completed | 2012-01-17
Clinton Municipal Airport | Design airport terminal and transient hangar | 63600 | 54060 | Airport funds | 54060 | 0 | Completed | 2013-06-03
Fairfield Municipal Airport | Design terminal building | 75000 | 63750 | Airport funds | 61963 | 0 | Completed | 2014-05-06
Iowa City Municipal Airport | Rehabilitate terminal building | 118000 | 100300 | Airport funds | 100300 | 0 | Completed | 2012-08-29
Maquoketa Airport | Replace B-Cap roof | 42962 | 25266 | Airport funds | 25266 | 0 | Completed | 2013-01-28
Monticello Municipal Airport | Rehabilitate FBO city owned building | 103124 | 65999 | Airport funds | 65999 | 0 | Completed | 2011-12-15
Osceola Municipal Airport | Improve terminal / office building | 64630 | 43962 | Airport funds | 43962 | 0 | Completed | 2012-06-05
Ottumwa Regional Airport | Construct 6 unit t-hangar | 169000 | 135200 | Airport funds | 135200 | 0 | Completed | 2012-10-25
Shenandoah Airport | Construct 4 unit t-hangar | 200000 | 150000 | Airport funds | 150000 | 0 | Completed | 2013-06-18
Iowa City Municipal Airport | Rehabilitate terminal and building D roofs (FY 2013 project) | 118000 | 75000 | Airport funds | 75000 | 0 | Completed | 2012-12-12
Ottumwa Regional Airport | Rehabilitate terminal roof (FY 2013 project) | 65000 | 30297 | Airport funds, other infrastructure funds from other years | 30297 | 0 | Completed | 2013-10-11
| Total | 871316 | 751483 |  | 749696 | 0

## CSVI
FY 2016 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace Hangars | 288000 | 96034.2405 | Airport funds | 0 | 96034.2405 | Design Phase | 2016-11-30
Cedar Rapids- Eastern Iowa | Rehabilitate Terminal Building | 8018250 | 319397.9844 | Airport funds | 0 | 319397.9844 | In progress | 2017-12-31
Des Moines | General Aviation Improvements | 3619000 | 585229.5187 | Airport funds | 0 | 585229.5187 | In progress | 2018-12-31
Dubuque | Storage Hangar Design | 2500000 | 105683.7904 | Airport funds | 0 | 105683.7904 | In progress | 2016-12-31
Fort Dodge | Construct Hangar and Flight Service Station redesign | 100000 | 94844.5512 | Airport funds | 0 | 94844.5512 | In progress | 2016-06-30
Mason City | Replace Overhead Garage Doors and Perform Terminal Systems Study | 46000 | 94881.917 | Airport funds | 0 | 94881.917 | In progress | 2016-06-30
Sioux City | Rehabilitate and Build Hangars | 120000 | 102731.8436 | Airport funds | 0 | 102731.8436 | In progress | 2016-10-31
Waterloo | Hangar rehabilitation and baggage area renovation | 119720 | 101196.1542 | Airport funds | 0 | 101196.1542 | In progress | 2017-06-30
| Total | 14810970 | 1500000 |  | 0 | 1500000
FY 2015 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace three hangars | 240000 | 96692 | Airport funds |  | 96692 | Design Phase | 2016-11-30
Cedar Rapids- Eastern Iowa | Renovate terminal building lobby | 10387000 | 317297 | Airport funds | 317297 | 0 | Completed | 2015-10-16
Des Moines | Customs & Border Protection relocation | 1533500 | 583354 | Airport funds | 583354 | 0 | Completed | 2015-07-27
Dubuque | Construct new terminal building | 1277920 | 105886 | Airport funds |  | 105886 | In progress | 2016-12-31
Fort Dodge | Construct new hangar | 130000 | 95854 | Airport funds |  | 95854 | In progress | 2016-06-30
Mason City | Upgrade terminal electrical service and replace overhead door in west maintenance facility | 121000 | 96001 | Airport funds | 33367 | 62634 | In progress | 2016-08-31
Sioux City | Rehabilitate and build hangars | 103884 | 103884 | Airport funds | 9379 | 94505 | In Progress | 2016-10-31
Waterloo | Upgrade emergency generator, replace door at bag make-up, and terminal electrical improvements | 107375 | 101032 | Airport funds | 16234 | 84798 | In progress | 2016-03-31
| Total | 13900679 | 1500000 |  | 959631 | 540369
FY 2014 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Construct hangar | 480000 | 96594 | Airport funds | 79402 | 17192 | Design Phase | 2016-11-30
Cedar Rapids- Eastern Iowa | Replace roofs on four buildings | 330000 | 311190 | Airport funds | 311190 | 0 | Completed | 2014-09-16
Des Moines | Relocate US Customs building | 4500000 | 579215 | Airport funds | 579214 | 0 | Completed | 2015-04-06
Dubuque | Construct terminal building | 1277920 | 108456 | Airport funds |  | 108456 | In progress | 2016-12-31
Fort Dodge | Re-design flight service station, replace overhead doors in ARFF/Maintenance building, demolish two hangars | 150000 | 98159 | Airport funds | 28853 | 69306 | In progress | 2016-09-15
Mason City | Rehabilitate terminal: replace terminal cooling system, install security cameras, improve entrance soffit and ceiling | 99144 | 98450 | Airport funds | 32560 | 65890 | In progress | 2017-06-30
Sioux City | Rehabilitate and construct new hangars | 120000 | 105151 | Airport funds | 58280 | 46871 | In progress | 2016-10-31
Waterloo | Rehabilitate hangars | 106000 | 102785 | Airport funds | 80621 | 22164 | In progress | 2016-12-31
| Total | 7063064 | 1500000 |  | 1170120 | 329879
FY 2013 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace hangar | 450000 | 94903 | Airport funds | 94903 | 0 | Completed | 2014-10-27
Cedar Rapids- Eastern Iowa | Renovate terminal building lobby | 3430000 | 325782 | Airport funds | 325782 | 0 | Completed | 2014-09-16
Des Moines | Construct parking garage bridge | 5200000 | 568101 | Airport funds | 568101 | 0 | Completed | 2012-11-15
Dubuque | Construct terminal building | 1351480 | 107598 | Airport funds | 31505 | 76093 | In progress | 2016-12-31
Fort Dodge | Renovate terminal operation area and former flight service station building | 100000 | 97119 | Airport funds | 97119 | 0 | Completed | 2015-06-30
Mason City | Construct office addition | 722170 | 99415 | Airport funds | 99415 | 0 | Completed | 2012-07-20
Sioux City | Rehabilitate hangars | 200000 | 103848 | Airport funds | 101869 | 1979 | In progress | 2016-03-31
Waterloo | Rehabilitate hangars and snow removal equipment building | 103560 | 103234 | Airport funds | 36671 | 66563 | In progress | 2016-12-31
| Total | 11557210 | 1500000 |  | 1355365 | 144635
FY 2012 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Construct hangars | 898500 | 94579 | Airport funds | 94579 | 0 | Completed | 2014-06-19
Cedar Rapids- Eastern Iowa | Renovate terminal - relocate baggage screening area | 3904000 | 328020 | Airport funds | 328020 | 0 | Completed | 2013-01-07
Des Moines | Construct parking garage bridge | 800000 | 562349 | Airport funds | 562349 | 0 | Completed | 2012-09-24
Dubuque | Construct terminal building | 8752175 | 110137 | Airport funds | 110137 | 0 | Completed | 2013-08-08
Fort Dodge | Renovate terminal to prevent drainage issues; design renovation to flight service station; hangar A and B demolition | 225000 | 95992 | Airport funds | 97119 | 0 | Completed | 2015-06-26
Mason City | Construct office addition | 500000 | 99205 | Airport funds | 99205 | 0 | Completed | 2012-12-03
Sioux City | Rehabilitate hangars | 200000 | 107536 | Airport funds | 107536 | 0 | Completed | 2013-08-20
Waterloo | Rehabilitate hangars | 104929 | 103021 | Airport funds | 16865 | 86156 | In progress | 2016-12-31
| Total | 15384604 | 1500839 |  | 1415810 | 86156

## SRT
State Recreational Trails
Fund | Fiscal Year | Description of Project | Progress of Work | Total Estimated Project Cost | Revenue Sources | Funds Obligated ** |  | Funds Expended | Date of Completion / Estimated Completion
Recreational Trails - RIIF - 0017 | 2016 | Cedar Valley Trail "Paving the Way for the American Discovery Trail" (Linn County & Black Hawk County Conservation Boards) | Agreement not signed - work not started | 1209000 | State Recreational Trail (SRT) Fund | 600000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Flint River Trail: Phase I South (Burlington) | Agreement not signed - work not started | 850000 | State Recreational Trail (SRT) Fund | 398500 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Hoover Trail -- "The Missing Link" (Johnson County Conservation Board) | Agreement not signed - work not started | 4321590 | State Recreational Trail (SRT) Fund | 679699 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Hospital Connector Trail Bridge (Manning) | Agreement signed 12/21/2015 - development in process | 296400 | State Recreational Trail (SRT) Fund | 222300 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Mitchellville to Prairie City Rails-to-Trails Corridor Development (Jasper County Conservation Board) | Agreement signed 11/24/2015 - development in process | 1200100 | State Recreational Trail (SRT) Fund | 749501 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Turkey River Recreational Corridor - Elgin to Gilbertson Park and the Turkey River (Fayette County Conservation Board) | Agreement not signed - work not started | 1136000 | State Recreational Trail (SRT) Fund and Regional TAP funds | 750000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Ankeny Connector - High Trestle Trail (Polk County Conservation Board) | Agreement signed 12/15/2014 - project completed | 2109860 | State Recreational Trail (SRT) Fund, city funds, county funds, and Iowa Natural Heritage Foundation funds | 782500 |  | 782500 | 2015-02-26
Recreational Trails - RIIF - 0017 | 2015 | Cedar Valley Nature Trail Bridge E4 Replacement (Black Hawk County Conservation Board) | Agreement signed 11/25/2014 - development in process | 214542 | State Recreational Trail (SRT) Fund and county funds | 160906 |  | 15088.04 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Coon Rapids Connector Trail Underpass (City of Coon Rapids) | Agreement signed 2/10/2015 - development in process | 299250 | State Recreational Trail (SRT) Fund and city funds | 224437 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Great River Road Bike Lane (Louisa County Secondary Roads) | Agreement signed 6/19/2014 - development in process | 1690000 | State Recreational Trail (SRT) Fund and Scenic Byways grant | 340000 |  | 151890.7 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Hoover Trail - "The Missing Link" (Johnson County Conservation Board) | Agreement signed 12/14/2014 - development in process | 605333 | State Recreational Trail (SRT) Fund and county funds | 454000 |  | 256912.22 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Iowa DNR AmeriCorps Trail Crew (Iowa Department of Natural Resources) | Agreement signed 12/17/2014 - development in process | 395000 | State Recreational Trail (SRT) Fund, REAP and Lake Restoration Fund | 296250 |  | 91731.74 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Iowa River Trail Phase 1 Development (City of Marshalltown and Hardin County) | Agreement signed 3/2/2015 - development in process | 1335000 | State Recreational Trail (SRT) Fund, Region 6 TAP funds and REAP | 775000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Jurgensen Bridge Refurbishment (Winterset and Winterset Municipal Utility) | Agreement signed 9/21/2015 - development in process | 1066590 | State Recreational Trail (SRT) Fund, FEMA funds, and city funds | 500000 | ****** | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Lake Path Trail/JewEllsworth Trail Segment (Hamilton County Conservation Board) | Agreement signed 1/6/2015 - development in process | 862853 | State Recreational Trail (SRT) Fund, Regional TE, cash from local entities and private donations | 647140 |  | 20627.65 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Mississippi River Trail - Pikes Peak Road to Guttenberg (Clayton County) | Agreement signed 8/31/2015 -development in process | 1369575 | State Recreational Trail (SRT) Fund and local option sales tax | 579074 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Pottawattamie County Trail-Phase I (Pottawattamie County Conservation Board and Pottawattamie County Trail Board) | Agreement signed 12/15/2014 -development in process | 933333 | State Recreational Trail (SRT) Fund, Federal Recreational Trails funding, county funds and Iowa West Foundation funds | 700000 |  | 5350.69 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Red Cedar Trail and Connector (Linn County Conservation Board and Linn Area Mountain Bike Association) | Agreement signed 1/27/2015 - development in process | 75000 | State Recreational Trail (SRT) Fund, Specialized Dealer Grant, Marion Hotel/Motel and other local grants, LAMBA and other donors | 55000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | SW 5th (Jackson) Street Bridge Rehabilitation (City of Des Moines) | Agreement signed 9/29/2015 - development in process | 3740000 | State Recreational Trail (SRT) Fund, City CIP funds, TIGER funds and private fundraising | 500000 | ****** | 0 | 2017-06-30
| 2014 | [5 empty] | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2014 | Ankeny Connector - High Trestle Trail (Polk County Conservation Board and Ankeny) | Agreement signed 10/25/2013 - project completed | 3065000 | State Recreational Trail (SRT) Fund, city funds and county funds | 782500 |  | 782500 | 2014-05-01
Recreational Trails - RIIF - 0017 | 2014 | Bellevue Rivervue Trail-Phase II (City of Bellevue and Jackson County Conservation Board) | Agreement signed 1/30/2014 - development in process | 722275 | State Recreational Trail (SRT) Fund, city funds, REAP, Regional Transportation Alternative funds and private donations | 260774 |  | 247735.3 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2014 | Bridging the Gap: Phase I Dry Run Trail-Connecting Decorah's Trout Run Trail to the Prairie Farmer Recreational Trail (Winneshiek County Conservation Board and City of Decorah) | Agreement signed 1/09/2014 - development in process | 1604512 | State Recreational Trail (SRT) Fund, Statewide Transportation Enhancement grant, REAP and local public/private funds | 380265 |  | 38559.82 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2014 | Farragut to Shenandoah Trail Connection (City of Farragut) | Agreement signed 10/31/2013 - work not started | 650000 | State Recreational Trail (SRT) Fund and land value | 487500 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2014 | Iowa River Scenic Trail (Hardin County Board of Supervisors and City of Marshalltown) | Agreement signed 11/12/2013 - development in process | 1375694 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and land value | 775000 |  | 755832.36 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2014 | Multiuse Mississippi River Trail, Riverdale Section, Phase 2 (City of Riverdale) | Agreement signed 6/3/2014 - development in process | 1017000 | State Recreational Trail (SRT) Fund, city funds, County Regional Authority Grant and National Scenic Byways Grant | 318644 |  | 302711.8 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2014 | Pioneer Beach Road Trail (City of Orleans and Dickinson County Trails Board) | Agreement signed 12/23/2013 - development in process | 521479 | State Recreational Trail (SRT) Fund, city funds and County Trails Board funds | 371479 |  | 329145.53 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2014 | Raccoon River Valley Trail to High Trestle Trail Connector (Dallas County Conservation Board) | Agreement signed 7/30/2013 - development in process | 290000 | State Recreational Trail (SRT) Fund, other grants, donations and foundations | 92897 |  | 7427.07 | 2017-06-30
| 2014 | [5 empty] | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2013 | Brushy Creek All-Weather Multi-Use Lake Trail Bridge (Iowa DNR) | Agreement signed 12/05/2012 - project completed | 125800 | State Recreational Trail (SRT) Fund and DNR REAP Grant Award | 78000 |  | 78000 | 2015-08-17
Recreational Trails - RIIF - 0017 | 2013 | City of Clinton Mississippi River Trail Final Connection (City of Clinton) | Agreement signed 11/28/2012 - project completed | 535544 | State Recreational Trail (SRT) Fund and city G.O. Bonds | 400000 |  | 400000 | 2015-05-06
Recreational Trails - RIIF - 0017 | 2013 | Fayette-Volga River Multi-Use Trail (Upper Iowa University and Fayette County) | Agreement signed 11/13/2012 - development in process | 1190931 | State Recreational Trail (SRT) Fund, Upper Iowa University, city funds, County Community Foundation, Black Hills Energy, private donors, additional fundraising and DNR REAP Grant Award | 700000 |  | 687574 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2013 | Iowa River Trail – Phase 8 of 8 (City of Iowa City) | Agreement signed 11/25/2014 - development in process | 2100000 | State Recreational Trail (SRT) Fund, city G.O. Bonds, Regional STP Funds, Earmark funds and Regional TE Funds | 441000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2013 | Mines of Spain Trail and Trailhead (City of Dubuque and Iowa DNR) | Agreement signed 11/28/2012 - development in process | 227333 | State Recreational Trail (SRT) Fund, city funds and fundraising/naming opportunities | 170500 |  | 161975 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2013 | Musser Park to Wiggens Road Trail (City of Muscatine) | Agreement signed 3/24/2014 - development in process | 984400 | State Recreational Trail (SRT) Fund, Federal Earmark funds and local contribution | 300000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2013 | Shaulis Road Trail Extension – Phase I (City of Waterloo) | Agreement signed 7/11/2013 - development in process | 1007592 | State Recreational Trail (SRT) Fund, Regional TAP funds, and city funds | 755694 |  | 86160.84 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2013 | South Troy Park Trail (City of Robins) | Agreement signed 12/12/2012 - development in process | 354000 | State Recreational Trail (SRT) Fund and city funds | 204000 |  | 0 | 2017-06-30
|  |  |  | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2012 | Bee Branch Creek Trail-MRT Route (City of Dubuque) | Agreement signed 9/16/2014 - development in process | 506100 | State Recreational Trail (SRT) Fund, National Scenic Byway funds, and city funds | 100000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0018 | 2012 | Bluff Creek OHV Park Development Plan (Iowa DNR) | Agreement signed 12/20/2011 - development in process | 80000 | State Recreational Trail (SRT) Fund and ATV registration funds | 60000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0018 | 2012 | Buffalo to Wild Cat Den Road MRT (City of Buffalo) | Agreement signed 5/05/2012 - development in process | 562500 | State Recreational Trail (SRT) Fund, SAFETEA-LU earmark funds, and city funds | 108500 |  | 16921.02 | 2017-06-30
Recreational Trails - RIIF - 0019 | 2012 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board)***** | Agreement signed 12/20/2011 - project completed with other funding | 3612516 | State Recreational Trail (SRT) Fund and CDBG Jumpstart Infrastructure | 396516 | ***** | Rescinded | N/A
Recreational Trails - RIIF - 0020 | 2012 | Central IA Trail Loop-Chichaqua Valley Trail to Gay Lea Wilson Trail (Polk County Conservation Board) | Agreement signed 12/15/2011 - project completed | 10891016 | State Recreational Trail (SRT) Fund, Polk County Conservation and Partners | 753750 |  | 753750 | 2015-11-03
Recreational Trails - RIIF - 0021 | 2012 | Dickinson County Spine Trail-Henderson Woods to US71 in Arnolds Park (Arnolds Park and Dickinson County Trails Board) | Agreement signed 12/22/2011 - project completed | 165500 | State Recreational Trail (SRT) Fund, city funds and County Trails Board | 115850 |  | 115850 | 2013-10-08
Recreational Trails - RIIF - 0022 | 2012 | Gray's Lake Neighborhood Connecting Trail & SW 14th Quiet Street (City of Des Moines) | Agreement signed 5/15/2012 - development in process | 586570 | State Recreational Trail (SRT) Fund, city CIP, Gray's Lake Neighborhood Association and land donations | 439920 |  | 368689.37 | 2017-06-30
Recreational Trails - RIIF - 0023 | 2012 | Gypsum City OHV Park (WCIC and Iowa DNR) | Agreement signed 2/6/2012 - project completed | 626349 | State Recreational Trail (SRT) Fund, Federal Recreational Trails, Webster County Conservation and ATV registration funds | 211500 |  | 199354.37 | 2015-06-16
Recreational Trails - RIIF - 0024 | 2012 | Iowa DNR Trails Program (Iowa DNR) | Agreement signed 12/20/2011 - project completed | 350000 | State Recreational Trail (SRT) Fund, REAP and Lake Restoration Fund | 262500 |  | 262500 | 2014-12-15
Recreational Trails - RIIF - 0025 | 2012 | NW Beaver Drive Trail (City of Johnston) | Agreement signed 1/10/2012 - development in process | 2400000 | State Recreational Trail (SRT) Fund, city G.O. bond and city park and trail improvement fund | 181464 |  | 121501.77 | 2017-06-30
Recreational Trails - RIIF - 0026 | 2012 | Turkey River Recreational Corridor Trail-Elkader to Motor Mill (Clayton County Conservation Board) | Agreement signed 1/18/2012 - development in process | 880576 | State Recreational Trail (SRT) Fund, statewide TE grant and local contributions | 250000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0027 | 2012 | Water Trails Planning, Design and Construction Activities (Iowa DNR) | Agreement signed 2/23/2012 - project completed | 160000 | State Recreational Trail (SRT) Fund, marine fuel tax, U.S. Coast Guard, boat registration fees and RIIF | 120000 |  | 120000 | 2015-03-04
|  |  |  | #REF! |  | 3000000
Recreational Trails - RIIF - 0017 | 2010 | Allamakee County Mississippi River Bike Trail (Allamakee County and Allamakee County Economic Development) | Agreement signed 1/5/2010 - development in process | 7245382 | State Recreational Trail (SRT) Fund, Private and Local, Federal Earmark and Other State and Federal Grants | 750000 |  | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2010 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board) | Agreement signed 11/20/2009 - project completed | 2658938 | State Recreational Trail (SRT) Fund, CDBG - Jumpstart Infrastructure and FEMA-PA | 250000 |  | 250000 | 2012-09-30
Recreational Trails - RIIF - 0017 | 2010 | Des Moines River Regional Trail Phase 1 (City of Des Moines) *** | Agreement signed 1/29/2010 - project completed | 1937997.68 | State Recreational Trail (SRT) Fund, DNR REAP Grant Award, ICAAP funds, and City of Des Moines Capital Funds | 73474 | *** | 73474 | 2015-01-12
Recreational Trails - RIIF - 0017 | 2010 | Iowa Department of Natural Resources (DNR) Trail Crew (Iowa DNR) | Agreement signed 11/20/2009 - project completed | 350000 | State Recreational Trail (SRT) Fund, REAP and Lake Restoration Fund | 262500 |  | 262500 | 2012-12-03
Recreational Trails - RIIF - 0017 | 2010 | Iowa River Corridor Trail Connection - Sand Lake (City of Iowa City) *** | Agreement signed 1/29/2010 - project completed | 375000 | State Recreational Trail (SRT) fund and Capital Improvement Funds | 281000 | *** | 180059.72 | 2012-08-06
Recreational Trails - RIIF - 0017 | 2010 | Lewis and Clark Historic Riverfront Trail (City of Sioux City and Iowa DOT) *** | Agreement signed 2/1/2010 - project completed | 1600000 | State Recreational Trail (SRT) Fund and City Funds | 128000 | *** | 128000 | 2013-08-07
Recreational Trails - RIIF - 0017 | 2010 | Pinicon Ridge Trail (Linn County Conservation Board) * | Agreement signed 7/20/2009 - project completed | 666667 | State Recreational Trail (SRT) Fund and Local Contributions | 500000 | * | 500000 | 2012-08-27
Recreational Trails - RIIF - 0017 | 2010 | Principal Riverwalk Recreational Trail (city of Des Moines) * | Agreement signed 12/2/2009 - project completed | 1000000 | State Recreational Trail (SRT) fund and Local Contributions | 750000 | * | 750000 | 2013-04-15
Recreational Trails - RIIF - 0017 | 2010 | Raccoon River Valley Trail Addition--Forest Park to Minburn Trail (Dallas County Conservation Board) *** | Agreement signed 11/6/2009 - project completed | 6655696 | State Recreational Trail (SRT) Fund, Community Attraction and Tourism Program, State Enhancement Project, Central Iowa Regional Transportation Planning Alliance, Dallas County, City of Perry, City of Waukee, Guthrie County Cash and Stimulus, City of Dallas Center, City of Jamaica, City of Redfield, City of Linden, Raccoon Valley Bank, Bock Family Foundation, Dallas County Conservation Foundation, Raccoon River Valley Trail Association, Celebrations Committee Dallas Center, Committee for Super Cooper, Dallas Center Beta Sigma Phi, Rotary Club of Dallas Center, Community of Herndon, Waukee YMCA, City of Dawson, Casey's Stores, Alliant Energy, Bikes Belong, Letter campaign, Prairie Meadows Community Betterment, Prairie Woodland Conservation Foundation and Bock Family Foundation October 08 | 484995 | *** | 460745.25 | 2012-08-23
Recreational Trails - RIIF - 0017 | 2010 | Railbanking Purchase of IANW Railroad (Dickinson County Trails Board and Osceola County Conservation Board) | Agreement signed 1/4/2010 - project completed | 1203795 | State Recreational Trail (SRT) Fund, IANWRR Donated Land and Transportation Enhancement Grant | 525000 |  | 525000 | 2010-07-19
Recreational Trails - RIIF - 0017 | 2010 | Summerset Trail Flood Repairs (Warren County Conservation Board)**** | Agreement signed 1/5/2010 - project completed | 143028 | State Recreational Trail (SRT) Fund and County Budget | 107271 | **** | 107271 | 2012-05-29
Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Box Culverts and Bridge Project (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 11/25/2009 - project completed | 782722 | State Recreational Trail (SRT) Fund, County Foundation, Winneshiek County and Winneshiek County Bridge Grant | 300000 |  | 300000 | 2012-03-05
Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Decorah Fish Hatchery's Interpretive Restroom Facility (Northeast Iowa Resources Conservation and Development, Inc. and Iowa DNR's Fisheries) | Agreement signed 12/6/2009 - project completed | 105000 | State Recreational Trail (SRT) Fund and Friends of the Decorah Hatchery | 75000 |  | 75000 | 2012-07-02
|  |  |  | 24724225.68 |  | 4487240
Recreational Trails - RIIF - 0017 | 2009 | American Gothic Regional Trail Project (Area 15 Regional Planning Commission)* | Agreement signed 12/3/2008 - development in process | 133333 | State Recreational Trail (SRT) Fund, RPA, county, city, and private funds | 100000 | * | 95363 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2009 | Crawford County Trail (Crawford County)* | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund and county funds | 30000 | * | 30000 | 2010-09-20
Recreational Trails - RIIF - 0017 | 2009 | Garlock Slough Recreational Trail (City of West Okoboji and Dickinson County Tails Board)***** | Agreement signed 11/3/2008 - project completed | 653550 | State Recreational Trail (SRT) Fund, Dickinson County Conservation, MPO, and City of West Okoboji | 490162 | ***** | 408425.41 | 2012-10-09
Recreational Trails - RIIF - 0017 | 2009 | Linn Creek Trail Connection with Iowa Highway 330 Trail (Marshall County) | Agreement signed 7/20/2009 - project completed | 1476000 | State Recreational Trail (SRT) Fund and county funds | 800000 |  | 800000 | 2012-09-05
Recreational Trails - RIIF - 0017 | 2009 | Maquoketa River Water Trail (Jones County)* | Agreement signed 7/8/2008 - project completed | 133334 | State Recreational Trail (SRT) Fund and county funds | 100000 | * | 100000 | 2011-08-08
Recreational Trails - RIIF - 0017 | 2009 | Mississippi River Trail - Liberty Avenue Connection (Clinton) | Agreement signed 12/3/2008 - project completed | 469000 | State Recreational Trail (SRT) Fund and City of Clinton | 351750 |  | 351750 | 2010-04-26
Recreational Trails - RIIF - 0017 | 2009 | Principal Riverwalk (Des Moines)* | Agreement signed 11/4/2008 - project completed | 1000000 | State Recreational Trail (SRT) Fund and City of Des Moines | 750000 | * | 750000 | 2013-04-15
Recreational Trails - RIIF - 0017 | 2009 | Riverview Recreation Area Expansion (Trailblazers Off Road Club)***** | Agreement signed 6/8/2009 - funding rescinded | 71000 | State Recreational Trail (SRT) Fund | 40000 | ***** | Rescinded | N/A
Recreational Trails - RIIF - 0017 | 2009 | Stone State Park Trail (Woodbury County/DNR)* | Agreement signed 10/8/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund and county funds | 100000 | * | 0 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2009 | Summerset Trail (Cities of Indianola, Carlisle and Des Moines)* | Agreement signed 3/9/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund, SAFETEA-LU earmark funds, and city funds | 100000 | * | 95000 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2009 | Trout Run Trail - Bridging the Past and the Present (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 3/16/2009 - project completed | 443750 | State Recreational Trail (SRT) Fund, Winneshiek County Conservation, and City of Decorah | 138088 |  | 138088 | 2010-10-18
|  |  |  | 4686633 |  | 3000000
Recreational Trails - RIIF - 0017 | 2008 | Ankeny to Woodward Trail Corridor (Boone County Conservation Board) | Agreement signed 3/25/2008 - project completed | 3415960 | State Recreational Trail (SRT) Fund, Land Value and Regional Enhancement | 565960 |  | 565960 | 2012-07-31
Recreational Trails - RIIF - 0017 | 2008 | Crawford County Trails (Crawford County)* | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund, county, city, and private funds | 30000 | * | 30000 | 2010-09-20
Recreational Trails - RIIF - 0017 | 2008 | Fairfield Loop Trail (Fairfield)* | Agreement signed 3/10/2009 - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | * | 200000 | 2012-05-29
Recreational Trails - RIIF - 0017 | 2008 | Heart of Iowa Nature Trail Phases VII & VIII (Story County Conservation Board) | Agreement signed 12/14/2007 - project completed | 1937254 | State Recreational Trail (SRT) Fund and county funds | 100000 |  | 100000 | 2013-12-30
Recreational Trails - RIIF - 0017 | 2008 | Jewell to Ellsworth Trail (Hamilton County Conservation Board)* | Agreement signed 9/5/2007 - development in process | 246667 | State Recreational Trail (SRT) Fund and county funds | 185000 | * | 143164.66 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2008 | Lewis & Clark Trail Planning Study (Iowa DOT) | Agreement IDOT - project completed | 66667 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2011-07-11
Recreational Trails - RIIF - 0017 | 2008 | Maquoketa River Water Trail (Jones County Conservation Board) | Agreement signed 12/13/2007 - project completed | 549605 | State Recreational Trail (SRT) Fund and county funds | 69300 |  | 69300 | 2011-08-08
Recreational Trails - RIIF - 0017 | 2008 | Mississippi River Trail Upper Scott County (Le Claire) *** | Project was rescinded. Funding to be reprogrammed for flood damage projects. | 1227779 | State Recreational Trail (SRT) Fund and county funds | 799740 | *** | Rescinded | N/A
|  |  |  | 7750599 |  | 2000000 |  | 0
Recreational Trails - RC2 - 0942 | 2007 | 4-Mile Creek Greenway Trail (Polk County Conservation Board/City of Ankeny Parks and Recreation Department) | Agreement signed 3/06/2007 - project completed | 1334331 | State Recreational Trail (SRT) Fund, Polk County Conservation, MPO, and City of Ankeny | 690000 |  | 690000 | 2012-05-30
Recreational Trails - RC2 - 0942 | 2007 | 18th Street to Riverview Trail Development (Waterloo) | Agreement signed 3/29/2007 - project completed | 336250 | State Recreational Trail (SRT) Fund and City of Waterloo | 252187 |  | 252187 | 2011-04-04
Recreational Trails - RC2 - 0942 | 2007 | Alice's Road Greenbelt Trail Improvements (Clive) | Agreement signed 2/07/2007 - project completed | 536540 | State Recreational Trail (SRT) Fund and City of Clive | 402405 |  | 402405 | 2014-09-18
Recreational Trails - RC2 - 0942 | 2007 | Cemar Trail - Phase 2 (Cedar Rapids) | Agreement signed 1/12/2010 - development in process | 200000 | State Recreational Trail (SRT) Fund, federal earmark funds, federal Transportation Alternatives funds, and Cedar Rapids CIP Funds | 150000 |  | 0 | 2016-06-30
Recreational Trails - RC2 - 0942 | 2007 | Coon Rapids Town Loop Trail (Coon Rapids) | Agreement signed 4/16/2007 - project completed | 142500 | State Recreational Trail (SRT) Fund and City of Coon Rapids/Whiterock Conservancy | 106875 |  | 106875 | 2010-03-15
Recreational Trails - RC2 - 0942 | 2007 | Des Moines County Recreational Trail - Phase 1 Burlington to Starr's Cave (Des Moines County) | Agreement signed 2/19/2007 - development in process | 480000 | State Recreational Trail (SRT) Fund, Federal Recreational Trails, Regional TAP funds, and county funds | 360000 |  | 223215.97 | 2017-06-30
Recreational Trails - RC2 - 0942 | 2007 | Lakeview OHV Park Upgrades (Dirt Surfers Inc.) | Agreement signed 6/27/2007 - development in process | 52420 | State Recreational Trail (SRT) Fund | 39315 |  | 34193 | 2017-06-30
Recreational Trails - RC2 - 0942 | 2007 | Trail Projects in Wapello County (Wapello County) * | Agreement signed 4/16/2007 - $30,000 was awarded to city of Eldon - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | * | 196072.35 | 2010-03-22
|  |  |  | 4674520 |  | 1124651
Recreational Trails - RIIF - 0017 | 2006 | Phase I of the Gypsum City OHV Park (Webster County) | Agreement signed 8/21/2006 - project completed | 1660250 | State Recreational Trail (SRT) Fund and All-Terrain Vehicle Registration Funds | 250000 |  | 250000 | 2010-07-06
Recreational Trails - RIIF - 0017 | 2006 | Trail construction connecting the Little Sioux County Park to the city of Correctionville (Woodbury County Conservation Board) | Agreement signed 7/10/2006 - project completed | 1027760 | State Recreational Trail (SRT) Fund, Federal Transportation Enhancement Funds, REAP grant, county, city, and private funds | 150000 |  | 150000 | 2007-10-01
Recreational Trails - RIIF - 0017 | 2006 | Phase 4 of the Clear Creek Trail from Mormon Handcart Park to the Clear Creek bridge on U.S. Highway 6 (Coralville) | Agreement signed 8/9/2006 - Final Voucher entered 6/11/08; Remaining funds to be used on next phase of project-project completed | 437216 | State Recreational Trail (SRT) Fund and city hotel/motel tax | 327912 |  | 327912 | 2008-05-01
Recreational Trails - RIIF - 0017 | 2006 | Construction of trail connecting existing trails in Johnston to the Neal Smith Trail in Des Moines (Polk County Conservation Board) | Agreement signed 7/31/2006 - project completed | 1406960 | State Recreational Trail (SRT) Fund, county funds, Federal Transportation Enhancement Funds and MPO Transportation Enhancement Funds | 346739 |  | 346739 | 2010-06-21
Recreational Trails - RIIF - 0017 | 2006 | Development of a trail to fill a gap in the trail network around Clear Lake and extending to Mason City (Cerro Gordo County) | Agreement signed 7/10/2006 - project completed | 71167 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2008-05-09
|  |  |  | 4603353 |  | 1074651
NOTE: To avoid loss of funding, it is the Iowa Department of Transportation's policy to expend the oldest funding first when reimbursing any project costs. Thus, the FY 2006 $1,000,000 appropriation was spent, even though some of the FY 2006 projects listed don't show all their funding was utilized by the expiration date.
* Direct Appropriation From Iowa Legislature
** Funds obligated per Department of Transportation Commission Order.
*** FY 2006 and FY 2008 Funding Rescinded by Local Sponsors - Funding Reallocated to SRT Projects in FY 2010
**** The initial $87,500 is from I-Jobs and the remaining $19,771 from rescinded funds from FY 2008.
*****Funding for 2 Projects Rescinded by Local Sponsors and a $32,543 project underrun - Funding Reallocated to SRT Projects in FY 2014
******Identifies 2 Projects funded through $1 million existing historic trail bridges allocation that was part of the FY 2015 appropriation.
The FY 2006 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,000,000 as result of awarding additional funding from previous project underruns.
The FY 2007 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is over $2,000,000 as result of awarding additional funding from previous project underruns.
The FY 2008 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is $2,000,000.
The FY 2009 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2010 SRT appropriation was for $3,500,000. The total amount of SRT funding for projects listed in this report is over $3,500,000 as a result of awarding additional funding from previous project underruns.
There was no SRT appropriation for FY 2011.
The FY 2012 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2013 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2014 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2015 SRT appropriation was for $6,000,000 with $1,000,000 for existing historic trail bridges. The total amount of SRT funding for projects listed in this report is over $5,500,000 as a result of awarding additional funding from a previous project underrun.
The FY 2016 SRT appropriation was for $3,400,000. The total amount of SRT funding for projects listed in this report is $3,400,000.

## RRLGP
FY 2016 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
ADM "S" Curve | Current rail spur into the Clinton facility has an "s" curve. Project proposes to straighten the curveto allow greater rail capacity and better safety. | 450000 | 165600 | Company Match | 0 | 165600 | In Agreement Phase | 2019-01-01
A to Z Drying Rail Enhancement | A to Z Drying is replacing and changing the location of an exisiting spur due to expansion of neighboring company. | 419375 | 200000 | Company Match | 0 | 200000 | In Agreement Phase | 2019-01-01
Boone Scenic Valley Industrial Park Line Phase I | Construction of a 1700 ft passing track. Includes grading ballast, and installation of rail ties. Will also be replacing ties and adding ballast where needed to maintain 286K service. Company also constructing 1425 feet of track extending to their facility in nearby industrial park. | 706050 | 556050 | In Kind Match | 0 | 556050 | In Agreement Phase | 2019-01-01
Iowa Traction Transload Project | IATR improving their current site by constructing 950 ft siding to support currently transload operation. Project also includes installing a 90lb switch to accommodate 286K | 119306 | 95445 | Company Match | 0 | 95445 | In Agreement Phase | 2019-01-01
KJRY Yard Enhancements II | Project involves replacing four switches and improving tracks, ties and ballast in the yard | 350356 | 280285 | Company Match | 0 | 280285 | In Agreement Phase | 2019-01-01
|  | 2045087 | 1297380 |  | 0 | 1297380
FY 2015 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
West Charles Street Viaduct | Reconstruction, removal and replacement of the east side of the West Charles Street Viaduct | 654315 | 523452 | Local Match | 0 | 523452 | Project in process | 2018-01-01
Five Star Coop | Expansion of current rail siding from 3 car capacity to 35 car capacity | 9614000 | 500000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Des Moines Transload Facility | Development of a transload facility to improve the overall freight capacity in Des Moines Metro area | 10000000 | 1700000 | Company Match | 0 | 1700000 | In Agreement Phase | 2018-01-01
Crossroads of Global Innovation | Phase two allows for connection to the CN mailline in the ICGI certrified site | 2100000 | 1600000 | Local Match | 0 | 1600000 | Project in process | 2018-01-01
KJRY Railnetwork Improvements | Upgrade a mainline yard switch along with heavily traveled mainline yard tracks | 286000 | 228800 | Local Match | 0 | 228800 | Project in process | 2018-01-01
Sioux Center Rail Port Study | A planning study to determine the potential for a rail port adjacent to a BNSF line that runs north/south through the City limits | 130000 | 100000 | Local Match | 0 | 100000 | Project in process | 2016-07-01
|  | 22784315 | 4652252 |  | 0 | 4152252
FY 2014 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
HFCA (HF Chlor Alkali) Rail Road Project | Construction of three miles of new (private) track for new Cargill Plant | 150000000 | 324000 | Company match | 324000 | 0 | Project complete | 2015-04-15
Iowa Corn Processors (ICP) Rail Expansion | Construction of two spur tracks on ICP property to add capacity | 14832000 | 419000 | Company Match | 419000 | 0 | Project Complete | 2014-06-11
Carter Lake Metals Processing Building (Owen Industries) | Construction of new rail spur to accommodate new production building | 30000000 | 108000 | Company Match | 0 | 108000 | Project in process | 2017-07-01
Heartland Co-op Greenfield Rail Loading Elevator | Build a 125-car load out facility | 24000000 | 1450000 | Company Match | 1450000 | 0 | Project complete | 2015-11-17
CRANDIC - Millrace & Price Creek Bridges | Replacement of two bridges | 2840000 | 725000 | Company Match | 725000 | 0 | Project Complete | 2015-05-19
City of Knoxville - Red Rock Industrial Park | Planning Study | 118000 | 94400 | Local match | 91160 | 3240 | Complete - drawing last of funds - Certificate of completion pending | 2016-01-01
|  | 221790000 | 3120400 |  | 3009160 | 111240
FY 2013 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
CRANDIC Iowa River Crossing North Bridge | Consruct replacement rail bridge | 2840400 | 1500000 | Company match | 1500000 | 0 | Complete | 2014-04-15
Iowa Falls UP/CN Connector | Upgrade rail infrastructure in industrial area | 5711369 | 900000 | Local match | 0 | 900000 | Project in process | 2017-05-30
Rail One | Industrial Rail Spur Construction | 4397880 | 1116000 | Company match | 1116000 | 0 | Complete - Certificate of Completion Peding | 2016-01-30
BJRY Rail/Truck/Barge Planning Study | Planning Study | 50000 | 40000 | Local match | 0 | 40000 | Project in process | 2016-05-01
Central Iowa Transloading Facility Feasibility Study | Planning Study | 125000 | 100000 | Local match | 46067 | 1700 | Complete | 2014-10-02
Iowa Falls/Hardin County Rail Port Planning Study | Planning Study | 125000 | 100000 | Local match | 100000 | 0 | Study Complete | 2014-10-01
Mills/Pottawattamie County Rail Port Study | Planning Study | 98000 | 78400 | Local match | 78400 | 0 | Study Complete | 2014-10-07
North Central Ag Park Planning Study | Planning Study | 100000 | 80000 | Local match | 0 | 0 | Project withdrawn by applicants | Not Applicable
Sioux City Rail Study Phase II | Planning Study | 350000 | 100000 | Local match | 0 | 100000 | Project in process - granted 18 mo extension | 2016-10-01
|  | 13797649 | 4014400 |  | 2840467 | 1041700
FY 2012 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway Spur rehabilitation | Industrial Rail Spur Construction | 197435 | 157948 | Company match | 87025.34 | 70923 | Project complete pending certificate of completion - still drawing funds | 2016-03-01
Butler Cross Dock | Industrial Rail Spur Construction | 1758922 | 705621 | Local match | 477295 | 228326 | In progress | 2016-03-01
Cherokee Industrial Spur | Industrial Rail Spur Construction | 771818 | 617454 | Local match | 617454 | 0 | Complete | 2012-04-17
CRANDIC Iowa River Crossing Improvement | Consruct replacement rail bridge | 3200000 | 1613596 | Company match | 0 | 0 | Complete | 2014-04-15
Global Foods | Rail Spur upgrade | 358525 | 72000 | Local match | 0 | 0 | Project withdrawn by applicant | Not applicable
Iowa River Railroad | Rail line acquisition & preservation | 2500000 | 1000000 | Company match | 0 | 0 | Project withdrawn by applicant | Not applicable
North Central Iowa Rail Corridor, LLC | Rail line acquisition & preservation | 1900000 | 400000 | Local match | 400000 | 0 | Complete | 2012-04-26
Valley Distribution Corporation | Industrial Rail Spur Construction | $ 297, 525 | 218652 | Company match | 218652 | 0 | Complete | 2012-04-18
Waverly GMT Rail Spur | Industrial Rail Spur Construction | 538100 | 204000 | Company match | 204000 | 0 | Complete | 2014-11-10
|  | 11224800 | 4989271 |  | 2004426.34 | 299249
Note 1: CRANDIC was awarded $2,000,000 from RRLG, however $386,404 of the award is from federal Rail Assistance Program (RAP) funds.
FY 2011 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Adams County Rail | Industrial Rail Spur Extension | 1758922 | 879461 | Local match | 0 | 0 | Project withdrawn | Not applicable
Eastern Iowa Industrial Center | Construct Transloading Facility | 8474244 | 2000000 | Federal, state and local match | 2000000 | 0 | Complete - pending certificate of completion | 2016-01-30
Lomont Molding Inc | Rail Spur upgrade | 138560 | 110848 | Company match | 0 | 0 | Project withdrawn | Not applicable
Nypro Kannaak | Rail Spur upgrade | 255951 | 174022 | Company match | 174022 | 0 | Completed | Construction complete 11/14/2012
|  | 10627677 | 3164331 |  | 2174022 | 0
FY 2010 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Upgrade rail infrastructure in industrial park | 88000 | 55400 | Railroad match | 55400 | 0 | Completed | 2011-01-10
Cedar Rapids and Iowa City Railroad (CRANDIC) | Rebuild rail bridge | 886500 | 700000 | Railroad match | 700000 | 0 | Completed | 2011-04-14
Schau Recycling | Install industrial rail spur | 450000 | 225000 | Company match | 145187 | 0 | Completed | 2013-02-28
Shine Brothers Corp. | Upgrade rail infrastructure in industrial area | 467589 | 311071 | Company match | 311071 | 0 | Completed | 2011-10-15
City of Waterloo | Install industrial rail spur | 252005 | 126000 | City match | 118691 | 0 | Completed | 2013-12-31
Webster County Board of Supervisors | Install industrial rail spur in industrial park | 10900000 | 900000 | County match and company investment | 0 |  | Project withdrawn | Not applicable
Union Pacific Railroad and Iowa Northern Railway | Rebuild rail bridge in Waterloo* | 5437200 | 1000000 | Railroad match and FRA grant award | 1000000 | 0 | Completed | 2009-12-31
| TOTAL | 18481294 | 3317471 |  | 2330349 | 0
FY 2009 Railroad Revolving Loan and Grant Program (Flood Recovery)
Railroad | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Repair rail infrastructure damaged by flooding | 89333 | 71000 | Railroad match | 61164 | 0 | Completed | 2009-01-01
Cedar Rapids and Iowa City Railroad (CRANDIC) | Repair rail infrastructure damaged by flooding | 400000 | 320000 | Railroad match | 320000 | 0 | Completed | 2008-11-01
Keokuk Junction Railway Company | Repair rail infrastructure damaged by flooding | 693120 | 554000 | Railroad match | 405346 | 0 | Completed | 2009-03-01
Iowa, Chicago & Eastern Railroad Corp. | Repair rail infrastructure damaged by flooding | 1771463 | 1417000 | Railroad match | 1406627 | 0 | Completed | 2009-10-01
Iowa Interstate Railroad | Repair rail infrastructure damaged by flooding | 964707 | 772000 | Railroad match | 650000 | 0 | Completed | 2009-03-01
Iowa Northern Railway Co. | Repair rail infrastructure damaged by flooding | 851704 | 681000 | Railroad match | 616420 | 0 | Completed | 2008-11-01
Iowa River Railroad | Repair rail infrastructure damaged by flooding | 230000 | 184000 | Railroad match | 184000 | 0 | Completed | 2009-12-31
| TOTAL | 5000327 | 3999000 |  | 3643557 | 0
FY 2008 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2008 Funds used | FY 2008 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Cedar Rapids Terminal (Iowa Northern Railroad) Construct rail spur and intermodal loading facility in Palo | 884000 | 242000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Big River Resources Ethanol Plant industrial rail spur | 8500000 | 75000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Lincolnway Railport Industrial Park | 1072933 | 840000 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
| Norfolk Iron and Metal Company industrial rail spur | 1398000 | 810000 | State grant; Private investment | 810000 | 0 | Completed | 2009-09-30
| Oregon Trail Energy Rail spur | 7146000 | 75000 | State grant; Private investment | 0 | 0 | Project was withdrawn. Funding has been reprogrammed to FY2012 | Not applicable
| Prairie Creek Ethanol rail spur | 6055075 | 75000 | State Grant; Private investment | 0 | 0 | Project withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
| Raccoon Valley BioDiesel Rail spur | 2250000 | 50000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Trinity Towers | 414489 | 165795 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
| Unity Ethanol Cedar River | 9500000 | 270000 | State loan; Private investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
| Unity Ethanol Ottumwa | 9500000 | 270000 | State grant and loan; Private Investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
|  | 46720497 | 2872795 |  | 810000 | 0
FY 2007 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2007 Funds used | FY 2007 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Alternative Energy Resources Ethanol Plant industrial rail spur | 24240300 | 239000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Lincolnway Railport Industrial Park | 11852896 | 489000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| Seimens Wind Power industrial rail spur | 457513 | 326000 | State grant; Private investment | 326000 | 0 | Complete | 2010-05-26
| Southern Bio Energy industrial rail spur | 1300000 | 250000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
|  | 37850709 | 1304000 |  | 326000 | 0
FY 2006 Railroad Revolving Loan and Grant Program
| Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2006 Funds used | FY 2006 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
| Absolute Energy industrial rail spur | 3712220 | 500000 | State grant and loan; Private investment; local investment | 500000 | 0 | Complete | 2008-02-05
| Cascade Lumber Company industrial rail spur | 694000 | 534000 | State grant and loan; Private investment; local investment | 534000 | 0 | Complete | 2007-09-19
| Eastern Iowa Industrial Center rail development for industrial park expansion | 4660791 | 760791 | State grant; Private investment; FHWA grant | 729711 | 31079 | Project in progress | 2015-06-30
| Green Plains Renewable Energy | 5700000 | 280000 | State grant and loan; Private investment; local investment | 126000 | 0 | Complete: loan portion of award declined | 2013-02-28
| Midwest I,LLC industrial rail spur | 2800000 | 280000 | State grant and loan; Private investment; local investment | 280000 | 0 | Complete | 2008-09-30
| Iowa Renewable Energy LLC industrial rail spur | 1258532 | 300000 | State grant and loan; Private investment; local investment | 300000 | 0 | Complete | 2007-11-01
| Lincolnway Railport Industrial park rail development | 2154086 | 319209 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed for flood recovery activities. | Not applicable
| Marco Group International industrial rail spur switching improvements | 30000 | 22500 | State grant; Private investment | 0 | 0 | Project withdrawn | Not applicable
| Metzler Automotive | 406711 | 60000 | State grant | 42691 | 0 | Complete | 2007-11-01
|  | 21416340 | 3056500 |  | 2512402 | 31079

## Rail Port FY 2011
FY 2011 Rail Port Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Wind Energy Supply Chain Industrial Park (Iowa City) | Construct rail siding | 2112400 | 1056200 | Local match | 1056200 | 0 | Complete | 2014-04-15
Southbridge Rail Yard (Sioux City) | Construct lead track and drop/pull yard | 6741980 | 3000000 | Local match | 3000000 | 0 | Complete pending certificate of completion | 2016-02-01
Manly Terminal Wind Rail Port (Worth County) | Construct rail spur and loop track | 8237468 | 3000000 | Local and private match | 3000000 | 0 | Complete | 2015-09-10
Lincoln Way Rail Port (Clinton) | Construct lead track | 2032300 | 443800 | Local match | 329518.24 | 114282 | Drawing remaining funds | 2016-01-30
|  | 19124148 | 7500000 |  | 7385718.24 | 114282

## Passenger Rail
2010 Passenger Rail Service Revolving Fund (RIIF)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Support in Development of Intercity Passenger Rail efforts | 500000 | 499935 | None | 499935 | 0 | Completed | 2011-04-11
Funding reserved to match FY 2009 Recovery Act award to Iowa DOT for Chicago to Omaha Planning Study | 2000000 | 1016039.5 | Federal Railroad Administration FY 2009 HSIPR award | 1016039.5 | 0 | Completed | 2014-01-09
Funding reserved for PE/NEPA activities to match a federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 6213000 | 1242600 | Federal Railroad Administration FY 2010 HSIPR award | 532186.11 | 710413.89 | In Progress | 2017-07-01
Funding reserved for the Iowa City-Cedar Rapids Passenger Rail Conceptual Feasibility Study - Phase 1 | 40000 | 15000 | CRANDIC and MPOJC | 14233.1 | 0 | Completed | 2015-11-01
Funding reserved for Final Design & Construction to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 125000000 | 226425.5 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 227192.4 | Not Started | TBD
TOTAL | 133753000 | 3000000 |  | 2062393.71 | 937606.29
2011 Passenger Rail Service Revolving Fund (funding from Underground Storage Tank Fund)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Funding reserved for Final Design & Construction to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 125000000 | 2000000 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 2000000 | Not Started | TBD
TOTAL | 125000000 | 2000000 |  | 0 | 2000000

## PTIG
FY 2016 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
(#17521) | Burlington | Building improvements | 645846 | 480000 | Local funds |  | 480000 | Awarded 8-2015 | Est. 8/10/2017
(#17522) | Des Moines | Rehabilitate facility | 1050000 | 369007 | Federal transit funds Local funds |  | 369007 | Awarded 8-2015 | Est. 8/10/2017
(#17523) | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial funding---also see FY11, FY12, FY14 ) | 17741 | 14193 | Local funds | 0 | 14193 | Awarded 8-2015 | Est. 8/10/2017
(#17519) | Region 2 | Construction of indoor parking facility | 763390 | 600000 | Local funds |  | 600000 | Awarded 8-2015 | Est. 8/10/2017
(#17520) | Region 8 | Roof mounted solar array (partial funding--also see FY15) | 46000 | 36800 | Local funds | 2140 | 34660 | Awarded 8-2015 | Est. 8/10/2017
|  | GRAND TOTAL |  | 1500000 |  |  | 1497860
FY 2015 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
(#16399) | Burlington | Bus depot improvements | 55000 | 44000 | Local | 44000 | 0 | Project complete | 2015-04-22 | 2015-04-22
(#16400) | Des Moines | DART Way front office remodel | 965000 | 600000 | federal transit funds local funds | 600000 | 0 | Project complete | 2015-12-16 | 2015-12-16
(#16401) | Dubuque | Bus storage facility | 5184568 | 600000 | federal transit funds local funds |  | 600000 | Awarded 8-2014 | Est. 7/7/2016
(#16402) | Sioux City | Maintenance, repairs, and improvements for MLK Center | 280000 | 208800 | federal transit funds local funds | 140000 | 68800 | Awarded 8-2014 | Est. 7/7/2016
(#17520) | Region 8 | Roof mounted solar array (partial funding---also see FY16) | 59000 | 47200 | Local funds | 47200 | 0 | Awarded 8-2015 | Est. 8/10/2017
|  | GRAND TOTAL |  | 1500000 |  |  | 668800
FY 2014 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
15510 | Region 5 | Construct new vehicle and administration facility | 433900 | 347120 | Local funds | 347120 | 0 | Project complete | 2015-03-16 | 2015-03-16
15511 | Region 9 | Purchase and install new generator | 70000 | 56000 | Local funds |  | 56000 | Awarded 8-2013 | Est. 3/30/2016
15512 | Region 13 | Construct wash bay addition | 202800 | 162240 | Local funds | 162240 | 0 | Project complete | 2014-07-27 | 2014-07-27
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY13) | 688192.2775 | 475846 | federal transit funds local funds | 475846 | 0 | Project complete | 2015-11-12 | 2015-11-13
15513 | Des Moines | Rehabilitate maintenance lane | 45000 | 36000 | Local funds | 30416 | 5584 | Awarded 8-2013 | Est. 3/30/2016
15514 | Sioux City | Replace bus wash system | 300000 | 240000 | Local funds | 199338 | 40662 | Awarded 8-2013 | 2015-12-31 | 2015-12-31
15514 | Sioux City | Rehabilitate roof | 185000 | 136000 | Local funds | 123546 | 12454 | Awarded 8-2013 | 2015-12-31 | 2015-12-31
15514 | Sioux City | Replace transit operations heating, ventilating, and air conditioning system | 50000 | 40000 | federal transit funds local funds | 40000 | 0 | Awarded 8-2013 | 2014-05-08 | 2014-05-08
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY11, FY12 and FY16) | 8493 | 6794 | Local funds |  | 6794 | Awarded 8-2015 | Est. 8/10/2017
|  | GRAND TOTAL |  | 1500000 |  |  | 121494
FY 2013 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
14370 | Cedar Rapids | Administration facility/garage | 5294251 | 600000 | federal transit funds local funds | 600000 | 0 | Project complete | 2013-10-24 | 2013-10-24
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY10) | 384736.25 | 307789 | Local Funds | 307789 | 0 | Project complete | 2014-08-13 | 2014-08-13
14372 | Des Moines | Storage barn portals restoration | 467000 | 352000 | federal transit funds local funds | 352000 | 0 | Project complete | 2014-11-03 | 2014-11-03
14373 | Des Moines | Fuel delivery system | 192500 | 145000 | federal transit funds local funds | 145000 | 0 | Project complete | 2014-10-13 | 2014-10-13
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY14) | 137698.9088 | 95211 |  | 95211 | 0 | Project complete | 2015-11-12 | 2015-11-13
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2012 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
13415 | Ames | Facility renovation | 792000 | 600000 | Local Funds | 600000 | 0 | Project complete | 2013-11-27 | 2013-11-27
13416 | Cedar Rapids | New facility to replace transit garage and admin. facility | 3900000 | 600000 | local & FEMA | 600000 | 0 | Project complete | 2013-05-08 | 2013-05-08
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY11) | 63035 | 35452 | Local Funds | 35452 | 0 | Project complete | 2014-10-31 | 2014-10-31
13418 | Dubuque | Sprinkler replacement | 64677 | 51742 | Local Funds | 51742 | 0 | Project complete | 2015-04-03 | 2015-04-03
13418 | Dubuque | Roof replacement | 171920 | 137536 | Local Funds | 137536 | 0 | Project complete | 2015-04-03 | 2015-04-03
13419 | Muscatine | Passenger shelter | 7000 | 5600 | Local Funds | 5600 | 0 | Project complete | 2012-03-16 | 2012-03-16
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY11, FY14 and FY16) | 87087 | 69670 | Local funds | 21990 | 47680 | Awarded 8-2015 | Est. 8/10/2017
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2011 - I-Jobs Bonding (Revenue Bonds Capitals II)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12319 | Ames Transit Agency (CyRide) | Construct additional bus storage/maintenance areas | 4897614 | 800000 | Federal Transit Funds and Local | 800000 | 0 | Project complete | 2013-11-27 | 2013-11-27
12320 | Des Moines Area Regional Transit | Replace roof over maintenance area | 500000 | 381827 | Transit Agency Funds | 381827 | 0 | Project complete | 2011-07-05 | 2011-07-18
12733 | Dubuque | Transfer facility | 379211 | 278214 | Transit Agency Funds | 278214 | 0 | Project complete | 2014-01-14 | 2014-01-14
12738 | Des Moines | Wash rack rehabilitation | 30000 | 24000 | Transit Agency Funds | 24000 | 0 | Project complete | 2012-06-07 | 2012-06-07
12321 | Southwest Iowa Transit Agency-SWITA (Region 13) | Construct a vehicle storage facility | 565732 | 452585 | Transit Agency Funds | 452585 | 0 | Project complete | 2012-06-30 | 2011-04-04
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY12) | 22716.25 | 18173 | Local Funds | 18173 | 0 | Project complete | 2014-10-31 | 2014-10-31
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY13 and FY14) | 36240.1325 | 25058 |  | 25058 | 0 | Project complete | 2015-11-12 | 2015-11-13
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY12, FY14 and FY16) | 25179 | 20143 | Local funds | 20143 | 0 | Awarded 8-2015 | Est. 8/10/2017
|  | GRAND TOTAL |  | 2000000 |  |  | 0
FY 2010 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12738 | Des Moines | Locker/washroom renovations | 65000 | 48000 | Transit Agency Funds | 48000 | 0 | Project complete | 2012-06-07 | 2012-06-07
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY09) | 617904 | 436904 | Transit Agency Funds | 436904 | 0 | Project complete | 2013-02-14 | 2013-02-14
11761 | Des Moines Area Regional Transit | Restoration of masonry structures and upgrade of energy management system at DART facility | 100000 | 79920 | Transit Agency Funds | 79920 | 0 | Project complete | 2010-11-01 | 2010-11-16
11767 | Ottumwa Transit Authority | Expand maintenance shop serving OTA and 10-15 regional transit fleets to accommodate more vehicles and provide sufficient headroom to allow use of vehicle hoists | 235000 | 188000 | Transit Agency Funds | 188000 | 0 | Project complete | 2011-01-18 | 2011-01-18
11762 | Region 2 Transit - Mason City | Expand/renovate facility shared with Mason City Transit to accommodate dispatch function now required to support direct operation of transit services in Cerro Gordo County by regional system | 176000 | 140800 | Transit Agency Funds | 140800 | 0 | Project complete | 2010-12-31 | 2011-01-24
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilton Co. (partial see also funding in FY09) | 7347 | 5877 | Transit Agency Funds | 5877 | 0 | Project complete | 2012-07-31 | 2012-07-31
11765 | River Bend Transit (Region 9) - Davenport | Expand bus wash portion of River Bend facility to accommodate larger vehicles now being operated | 130000 | 67019 | Transit Agency Funds | 67019 | 0 | Project complete | 2011-11-20 | 2011-11-26
11766 | Southeast Iowa Bus (region 16) - Burlington | Participate in transit share of purchase and remodeling of existing building to house planning commission functions including transit administration and operations | 296250 | 125179 | Transit Agency Funds | 125179 | 0 | Project complete | 2011-06-21 | 2011-06-21
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY13) | 139776.25 | 111821 | Local Funds | 111821 | 0 | Project complete | 2014-08-13 | 2014-08-13
12738 | Des Moines | Storm water rack and sanitation sewer (see FY11 and supplemental funding from FY09) | 12144 | 5534 | Transit Agency Funds | 5534 | 0 | Project complete | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY11, FY12) | 46326.25 | 37061 | Local Funds | 37061 | 0 | Project complete | 2014-10-31 | 2014-10-31
15513 | Des Moines | Renovate operations office (partial-- see funding from FY11, FY13 and FY14) | 5618.6812 | 3885 |  | 3885 | 0 | Project complete | 2015-11-12 | 2015-11-13
|  | GRAND TOTAL |  | 1250000 |  |  | 0
FY 2009 - RC3 511 - Health Restricted Capital Bond Fund (Revenue Bonds Capitals)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
10482 | CyRide (Ames) | Reconstruction of the steam cleaning area (Moved to ARRA) | $640,000 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10481 | City of Davenport | Relocate transit offices (Cancelled 8-9-10) | 654000 | 0 | Transit Agency Funds | 0 | 0 | Project Cancelled | Est. 6/30/2010
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY10) |  | 385677 | FEMA Funds, Transit Agency Funds | 385677 | 0 | Awarded 12/10 | 2013-02-14 | 2013-02-14
10484 | River Bend Transit (Region 9) - Davenport | Vehicle storage and wash bays (Moved to ARRA) | $491,300 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10483 | Western Iowa Transit System (Region 12) - Carroll | Construct a vehicle storage addition (partial - see also supplimental funding from FY07) | 85446.25 | 68357 | Federal Transit Funds, Transit Agency Funds | 68357 | 0 | Project complete | 2009-08-31 | 2009-07-23
10968 | City of Coralville | Relocate transit office/maintenance facility out of floodway | 3643332 | 880000 | FEMA Funds, Transit Agency Funds | 880000 | 0 | Awarded 12/10 |  | 2013-01-02
11350 | CyRide (Ames) | Rehabitate west wall exterior insulation finish system (EIFS) of Cy-Ride maintenance facility | 200000 | 62577 | Transit Agency Funds | 62577 | 0 | Contract awarded 7/09 | 2011-05-25 | 2011-01-05
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilaton Co. (partial see also funding in FY10) | 699736.25 | 559789 | Transit Agency Funds | 559789 | 0 | Awarded 12/09 | 2012-07-31 | 2012-07-31
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY10, FY13) | 10817.5 | 8654 | Local Funds | 8654 | 0 | Project complete | 2014-08-13 | 2014-08-13
12738 | Des Moines | Storm water rack and sanitation sewer (see FY10 and FY11) | 177300 | 137523 | Transit Agency Funds | 137523 | 0 | Awarded 1/2011 | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY10, FY11, FY12) | 121778.75 | 97423 | Local Funds | 97423 | 0 | Project complete | 2014-10-31 | 2014-10-31
|  | GRAND TOTAL |  | 2200000 |  |  | 0
FY 2008 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09522 | University of Iowa (Cambus) | Construct new vehicle storage building for CAMBUS (partial - see also supplimental funding from FY07) | 1166319 | 702268 | Federal Transit Funds, Transit Agency Funds | 702268 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines (DART) | Construct addition to vehicle storage building (partial - see also supplimental funding from FY07) | 1044250 | 820000 | Federal Transit Funds, Transit Agency Funds | 820000 | 0 | Project complete | 2010-11-03 | 2010-11-03
09524 | Region Six Planning Commission (Region 6) - Marshalltown | Transit portion of Joint Facility | 385043 | 100876 | Federal Transit Funds, Transit Agency Funds | 100876 | 0 | Project complete | 2009-05-31 | 2008-12-18
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Construct new regional transit office, storage and maintenance facility in Dubuque (partial - see also supplimental funding from FY07) | 721070 | 576856 | Transit Agency Funds | 576856 | 0 | Project complete | 2008-06-30 | 2008-07-31
|  | GRAND TOTAL |  | 2200000 |  |  | 0
FY 2007 - RC2 942 - Health Restricted Capitals Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09410 | Ames Transit Agency (CyRide) | Expand operations/administration area of CyRide maintenance facility-Ride Facility | 1100000 | 880000 | Transit Agency funds | 880000 | 0 | Project complete | 2008-05-31 | 2008-06-19
09409 | City of Cedar Rapids | Construct transit portion of new downtown Intermodal facility | 2589453 | 0 | Federal Transit Funds, Transit Agency funds | 0 | 0 | Project dropped after city reorganization | NA | NA
09402 | City of Davenport (CitiBus) | Construct new transit hubs adjacent to regional shopping center and on campus of local university | 138134 | 110507 | Transit Agency funds | 110507 | 0 | Project complete | 2009-02-18 | 2009-02-18
09408 | Des Moines Area Regional Transit (DART) | Renovate maintenance area of DART facility | 66677 | 53341 | Transit Agency funds | 53341 | 0 | Project complete | 2010-02-17 | 2010-02-17
09404 | City of Sioux City | Construct new parts storage building at transit maintenance facility | 50000 | 40000 | Transit Agency funds | 40000 | 0 | Project complete | 2008-09-16 | 2008-09-16
09407 | North Iowa Area Regional Transit (Region 2) - Mason City | Construct a variety of projects to finish out recently constructed transit maintenance facility shared with City of Mason City | 40267.5 | 32214 | Transit Agency funds | 32214 | 0 | Project complete | 2008-03-31 | 2008-05-14
09406 | RIDES/Regional Transit Authority (Region 3) - Spencer | Construct new satellite facility in Sheldon for transit vehicle storage and maintenance | 500000 | 163085 | Federal Transit Funds, Transit Agency funds | 163085 | 0 | Project complete | 2010-12-31 | 2009-11-25
09405 | Western Iowa Transit System (Region 12) - Carroll | Expand transit maintenance and storage facility in Carroll | 587500 | 220000 | Federal Transit Funds, Transit Agency funds | 220000 | 0 | Project complete | 2008-09-30 | 2008-09-17
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Partial funding for FY08 project to construct new regional transit office, storage and maintenance facility in Dubuque | 418122.5 | 303144 | Transit Agency Funds | 303144 | 0 | Project complete | 2008-06-30 | 2008-07-31
09522 | University of Iowa (Cambus) - Iowa City | Construct new vehicle storage building for CAMBUS (partial - see also funding from FY08) | 222165 | 177732 | Federal Transit Funds, Transit Agency Funds | 177732 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines Area Regional Transit (DART) | Construct addition to vehicle storage building (partial - see also funding from FY08) | 75000 | 60000 | Transit Agency Funds | 60000 | 0 | Project complete | 2010-11-03 | 2010-11-03
10483 | Western Iowa Transit System (Region 12) - Carroll | Partial funding for FY09 project to construct a vehicle storage addition in Carroll | 82053.75 | 65643 | Federal Transit Funds, Transit Agency funds | 65643 | 0 | Project complete | 2009-07-23 | 2009-07-23
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also funding from FY09 and FY10) | 71773.75 | 57419 | Transit Agency Funds | 57419 | 0 | Project complete | 2013-02-14 | 2013-02-14
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY09, FY10, FY11, FY12) | 46143.75 | 36915 | Local Funds | 36915 | 0 | Project complete | 2013-05-13 | 2013-05-13
|  | GRAND TOTAL |  | 2200000 |  |  | 0