## GAVI
FY 2021 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Algona Municipal Airport | 2 Stall Hangar Extension | 384000 | 150000 | Airport funds | 0 | 150000 | In Design | 2022-06-01
Webster City Municipal Airport | Hangar Upgrade | 65921 | 32960 | Airport funds | 0 | 32960 | In Design | 2022-06-01
Spencer Municipal Airport | Terminal Building Rehabilitation Project | 140000 | 70000 | Airport funds | 0 | 70000 | In Design | 2022-05-01
Cherokee County Regional Airport | Replace Bi-Fold Hangar Door | 45000 | 22500 | Airport funds | 0 | 22500 | In Design | 2021-03-01
Webster City Municipal Airport | Hangar Demolition | 30000 | 15000 | Airport funds | 0 | 15000 | In Design | 2022-06-01
Ankeny Regional Airport | Terminal Hangar Bi-Fold Door Replacement | 120000 | 75000 | Airport funds | 0 | 75000 | In Progress | 2021-03-01
Harlan Municipal Airport | Install Bi-Fold Doors | 101140 | 75000 | Airport funds | 0 | 75000 | In Progress | 2022-06-01
Lamoni Municipal Airport | Fuel Pump and Dispenser Improvement | 16000 | 8000 | Airport funds | 0 | 8000 | In Progress | 2021-05-01
Rock Rapids Municipal Airport | Hangar Rehabilitation | 66000 | 49500 | Airport funds | 0 | 49500 | In Progress | 2021-09-01
Vinton Veterans Municipal Airport | Rehabilitate Hangar Doors | 85000 | 68000 | Airport funds | 0 | 68000 | In Design | 2021-12-01
Perry Municipal Airport | T-Hangar Drainage Improvement | 68400 | 58140 | Airport funds | 0 | 58140 | In Design | 2022-06-01
Sioux County Regional Airport | Snow Removal Equipment Building Addition | 195000 | 150000 | Airport funds | 0 | 150000 | In Design | 2022-01-01
| Total | 1316461 | 774100 |  | 0 | 774100
FY 2020 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Marshalltown Municipal Airport | Terminal Building Improvements | 1050000 | 150000 | Airport funds | 25093 | 124907 | In Progress | 2021-12-31
Algona Municipal Airport | 3 Stall Hangar Extension | 360000 | 150000 | Airport funds | 4270 | 145730 | In Progress | 2021-05-31
Atlantic Municipal Airport | Hangar Rehabilitation | 168750 | 75000 | Airport funds | 60437 | 14563 | Close Out | 2021-03-01
Knoxville Municipal Airport | Construct T-Hangar | 300000 | 150000 | Airport funds |  | 150000 | In Design | 2021-05-31
Forest City Municipal Airport | Hangar Building | 55000 | 30250 | Airport funds | 29750 | 500 | Close Out | 2021-05-31
Shenandoah Regional Airport | Construct 6 Unit T-Hangar | 250000 | 150000 | Airport funds |  | 150000 | In Progress | 2021-05-31
Iowa City Municipal Airport | Fuel Facility Expansion | 177900 | 150000 | Airport funds | 20412 | 129588 | In Progress | 2021-06-01
Perry Municipal Airport | New Fuel Facility | 149800 | 104860 | Airport funds |  | 104860 | In Progress | 2021-06-01
Harlan Municipal Airport | Install Hangar Doors | 101140 | 75000 | Airport funds | 22218 | 52782 | In Progress | 2021-05-31
Sibley Municipal Airport | Construct New Hangar | 233500 | 150000 | Airport funds | 12195 | 137805 | In Progress | 2021-06-15
| Total | 2846090 | 1185110 |  | 174375 | 1010735
FY 2019 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Algona Municipal Airport | 3 Stall Hangar Extension | 282000 | 149460 | Airport funds | 149460 | 0 | Complete | 2020-08-24
Boone Municipal Airport | Construct 8 Unit T-Hangar | 480250 | 150000 | Airport funds | 0 | 0 | Cancelled
Cherokee County Regional Airport | Paint and Repair Hangars | 75000 | 37500 | Airport funds | 37500 | 0 | Complete | 2020-01-14
Estherville Municipal Airport | Hangar Paint and Roof Repairs | 24800 | 14880 | Airport funds | 14880 | 0 | Complete | 2019-08-23
Perry Municipal Airport | Construct 100x100 Hangar | 656500 | 150000 | Airport funds | 150000 | 0 | Complete | 2020-12-01
Red Oak Municipal Airport | Rehabilitate Hangar Doors | 65000 | 48750 | Airport funds | 48750 | 0 | Complete | 2020-01-14
Sioux County Regional Airport | Construct 100x100 Hangar | 600000 | 150000 | Airport funds | 150000 | 0 | Complete | 2019-06-02
Spencer Municipal Airport | Rehabilitate Hanger Bi-fold Doors | 20500 | 16400 | Airport funds | 0 | 16400 | In Progress | 2021-03-01
Webster City Municipal Airport | Terminal Building and Hangar Repairs | 30000 | 15000 | Airport funds | 13867 | 0 | Complete | 2020-06-04
| Total | 2234050 | 731990 |  | 564457 | 16400
FY 2018 RIIF/Aviation Trust Fund - General Aviation Vertical Infrastructure Program*
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Grinnell Regional Airport | 75x75 Hangar Construction | 550000 | 150000 | Airport funds | 150000 | 0 | Complete | 2020-10-02
Muscatine Municipal Airport | T-Hangar Building Construction | 343000 | 150000 | Airport funds | 0 | 150000 | Final Closeout | 2021-02-01
Red Oak Municipal Airport | Rehab Hangar - New Bifold Doors | 63000 | 47250 | Airport funds | 47250 | 0 | Complete | 2018-08-15
Sioux County Regional Airport | 10 Unit T - Hangar | 526680 | 150000 | Airport funds | 138141 | 0 | Complete | 2019-01-08
Waverly Municipal Airport | Bulk Hangar Insulation Renovation | 51000 | 22950 | Airport funds | 22950 | 0 | Complete | 2018-07-31
| Total | 1533680 | 520200 |  | 358341 | 150000
* State share includes $20,200 of Aviation Trust Fund revenue not subject to Infrastructure Annual Status Report requirement but is included for information.
FY 2017 Aviation Trust Fund* - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Cherokee County Regional Airport | Eight Unit T-Hangar | 320292 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-08-28
Clinton Municipal Airport | Airport Fuel System | 391140 | 141140 | Airport funds | 141140 | 0 | Complete | 2017-12-20
Davenport Municipal Airport | Rehabilitate Hangar 8990 | 65000 | 32500 | Airport funds | 31750 | 0 | Complete | 2017-08-22
Denison Municipal Airport | Hangar Upgrades | 10000 | 7000 | Airport funds | 6243 | 0 | Complete | 2016-12-31
George L Scott Municipal Airport | Replace T-Hangar Roof | 27500 | 16500 | Airport funds | 10866 | 0 | Complete | 2017-06-15
Iowa City Municipal Airport | North T-Hangar Restroom | 80125 | 56088 | Airport funds | 56088 | 0 | Complete | 2019-01-09
Northeast Iowa Regional Airport | Hangar Development | 300000 | 150000 | Airport funds | 150000 | 0 | Complete | 2018-02-07
Sioux County Regional Airport | Terminal Building | 1120000 | 150000 | Airport funds | 150000 | 0 | Complete | 2019-01-09
Spencer Municipal Airport | Hangar Rehabilitation - Replace Roof, Sill, Repaint | 68000 | 47600 | Airport funds | 42833 | 0 | Complete | 2018-01-22
| Total | 2382057 | 750828 |  | 738920 | 0
* Not subject to Infrastructure Annual Status Report requirement due to appropriation funding source. However, the status is included for information.
FY 2016 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ames Municipal Airport | Site improvements for future terminal building | 2410000 | 150000 | Airport funds | 150000 | 0 | Complete | 2018-04-16
Council Bluffs Municipal Airport | T-hangar Improvements | 216451 | 75000 | Airport funds | 47060 | 0 | Complete | 2018-06-30
Cresco Municipal Airport | Rehabilitate hangar and construct pilot lounge | 18728 | 15919 | Airport funds | 15919 | 0 | Complete | 2016-06-08
Lamoni Municipal Airport | Construct hangar | 322000 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-08-22
Marshalltown Municipal Airport | Pave hangar floor | 94500 | 80325 | Airport funds | 64936 | 0 | Complete | 2017-02-13
Perry Municipal Airport | Repair hangar roof | 20000 | 14000 | Airport funds | 13826 | 0 | Complete | 2016-12-15
Sibley Municipal Airport | Rehabilitate terminal building | 26836 | 16101 | Airport funds | 16101 | 0 | Complete | 2016-06-08
Sioux County Regional Airport | Construct maintenance and electrical vault buildings | 182200 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-04-30
Spencer Municipal Airport | Rehabilate hangar floor | 76650 | 45990 | Airport funds | 45990 | 0 | Complete | 2017-07-30
Washington Municipal Airport | Construct hangar | 630540 | 150000 | Airport funds | 0 | 0 | Project withdrawn by applicant
| Total | 3997905 | 847335 |  | 653832 | 0
FY 2015 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Atlantic Municipal Airport | Construct 60' x 80' hangar | 717200 | 150000 | Airport funds | 150000 | 0 | Completed | 2015-12-01
Boone Municipal Airport | Construct 2-unit, 45' x 80' hangar | 201600 | 150000 | Airport funds | 150000 | 0 | Completed | 2017-08-25
Decorah Municipal Airport | Construct 3-stall rectangular hangar | 235000 | 117500 | Airport funds | 117500 | 0 | Completed | 2016-08-09
Fairfield Municipal Airport | Construct new public terminal building | 215657 | 150000 | Airport funds | 135000 | 0 | Completed | 2017-06-14
Grinnell Regional Airport | Terminal building and maintenance hangar renovation | 60000 | 30000 | Airport funds | 12250 | 0 | Completed | 2014-11-14
Osceola Municipal Airport | Construct 33' x 42' rectangular hangar | 107140 | 74998 | Airport funds | 74998 | 0 | Completed | 2017-11-29
Rock Rapids Municipal Airport | Rehabilitate hangar roof | 27135 | 21708 | Airport funds | 21628 | 0 | Completed | 2015-06-15
Sibley Municipal Airport | Renovate terminal building roof and addition of insulation in hangar | 24000 | 14400 | Airport funds | 14400 | 0 | Completed | 2016-01-20
Washington Municipal Airport | Rehabilitate hangar | 76500 | 57375 | Airport funds | 57375 | 0 | Completed | 2016-05-16
| Total | 1664232 | 765981 |  | 733151 | 0
FY 2014 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Ankeny Regional | Construct 6-unit tee hangar | 326250 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-06-11
Davenport Municipal | Rehabilitate hangar 8970 | 56660 | 48161 | City funds | 48161 | 0 | Completed | 2014-09-22
Emmetsburg Municipal | Construct 80x100 hangar | 529170 | 100000 | Local funding uncertain | 100000 | 0 | Completed | 2016-06-09
Marshalltown Municipal | Renovate hangar | 88200 | 74970 | City funds | 72566 | 0 | Completed | 2017-08-11
Northeast Iowa Regional | Construct 70x120 hangar | 300000 | 150000 | Utility company loan | 150000 | 0 | Completed | 2014-09-23
Ottumwa Regional | Renovate hangar | 74470 | 59470 | Local airport funds | 57555 | 0 | Completed | 2015-06-30
Perry Municipal | Construct 45x100 hangar | 422375 | 150000 | City bonding | 128239 | 0 | Completed | 2015-06-01
Red Oak Municipal | Renovate hangar door | 20700 | 16560 | City funds | 16560 | 0 | Completed | 2013-12-18
Webster City Municipal | Renovate maintenance hangar | 40500 | 20250 | Airport funds | 20250 | 0 | Completed | 2014-06-01
| Total | 1817825 | 769411 |  | 743331 | 0
FY 2013 RIIF - General Aviation Vertical Infrastructure Program
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Boone Municipal Airport | Construct hangar | 187500 | 150000 | Airport funds | 150000 | 0 | Complete | 2017-12-08
Clinton Municipal Airport | Construct transient hangar | 600000 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-06-27
Iowa City Municipal Airport | Rehabilitate terminal and building roofs | 102000 | 75000 | Airport funds | 75000 | 0 | Completed | 2014-10-27
Iowa Falls Municipal Airport | Expand four unit t-hangar and apron | 326760 | 150000 | Airport funds | 149183 | 0 | Completed | 2014-09-18
Red Oak Municipal Airport | Construct hangar | 210000 | 150000 | Airport funds | 150000 | 0 | Completed | 2013-10-11
Vinton Veterans Airpark | Construct hangar | 271000 | 150000 | Airport funds | 150000 | 0 | Completed | 2014-02-21
| Total | 1697260 | 825000 |  | 824183 | 0

## CSVI
FY 2021 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Des Moines International Airport | Parking Garage Addition | 21440934 | 376123 | Airport funds | 0 | 376123 | In Design | 2023-01-01
Dubuque Regional Airport | Equipment Wash Facility | 500000 | 69958 | Airport funds | 0 | 69958 | In Design | 2022-12-01
Fort Dodge Regional Airport | Terminal Exterior Renovation, Renovate SRE Building, Hangar Insulation, Hangar A Construction | 120000 | 64106 | Airport funds | 0 | 64106 | In Design | 2022-12-01
Mason City Municipal Airport | Replace Entrance Road Lighting | 135000 | 64090 | Airport funds | 0 | 64090 | In Design | 2021-09-01
Sioux Gateway Airport | Terminal and Hangar Improvements | 135097 | 71104 | Airport funds | 0 | 71104 | In Design | 2022-06-01
Southeast Iowa Regional Airport | Terminal Upgrades | 121857 | 64135 | Airport funds | 0 | 64135 | In Design | 2022-02-01
The Eastern Iowa Airport | Cargo Logistics Facility | 14602007 | 223394 | Airport funds | 0 | 223394 | In Design | 2021-08-01
Waterloo Regional Airport | Hangar Rehabilitation | 127460 | 67090 | Airport funds | 0 | 67090 | In Design | 2022-06-01
| Total | 37182355 | 1000000 |  | 0 | 1000000
FY 2020 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington-Southeast Iowa Regional Airport Authority | Terminal Upgrades | 121752 | 121752.4231 | Airport funds | 65929 | 55823.4231 | In Progress | 2021-10-01
Cedar Rapids Airport Commission | Air Cargo Facility | 15866250 | 408751.8009 | Airport funds | 0 | 408751.8009 | In Progress | 2021-08-01
Des Moines Airport Authority | South Quadrant FBO Site Development | 11312438 | 727692.3662 | Airport funds | 727692 | 0 | Complete | 2020-08-18
Dubuque Regional Airport Commission | Equipment Wash Facility | 500000 | 134372.3151 | Airport funds | 0 | 134372.3151 | In Design | 2021-12-01
Fort Dodge Airport Commission | Renovate Hangars and AFSS Building, Construct Hangar A and IT Room | 125000 | 121512.8948 | Airport funds | 16960 | 104552.8948 | In Progress | 2021-06-01
Mason City Airport Commission | Boiler Replacement and roadway lighting | 231000 | 121652.9743 | Airport funds | 12925 | 108727.9743 | In Progress | 2021-02-01
Sioux City | Terminal and Hangar Repair | 155000 | 134923.0579 | Airport funds | 0 | 134923.0579 | In Progress | 2021-12-01
Waterloo | Hangar and Terminal Improvements | 132950 | 129342.1677 | Airport funds | 21373 | 107969.1677 | In Progress | 2021-08-01
| Total | 28444390 | 1900000 |  | 844879 | 1055120.6338
FY 2019 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Terminal Improvements | 96002 | 96002.3005 | Airport funds | 96002 | 0 | Complete | 2020-02-25
Cedar Rapids- Eastern Iowa | Signage Improvements | 322000 | 304613.4252 | Airport funds | 304613 | 0 | Complete | 2020-05-01
Des Moines | South Quadrant Site Imp. Phase 1 | 995000 | 593615.5299 | Airport funds | 593616 | 0 | Complete | 2019-10-09
Dubuque | Relocate Airfield Infrastructure and GA Terminal Renovations | 105815 | 105814.5472 | Airport funds | 0 | 105814.5472 | In Progress | 2021-12-01
Fort Dodge | Renovate Maintance Facility, Hangars and AFSS Building | 96061 | 96061.1031 | Airport funds | 13168 | 82893 | In Progress | 2021-06-01
Mason City | Boiler Replacement | 170000 | 96208.2687 | Airport funds | 93304 | 0 | Complete | 2019-12-01
Sioux City | Hangar Repair | 105330 | 105330.3381 | Airport funds | 0 | 105330.3381 | In Progress | 2021-12-01
Waterloo | Hangar and Terminal Improvements | 102354 | 102354.4874 | Airport funds | 5861 | 96493 | In Progress | 2021-08-01
| Total | 1992562 | 1500000 |  | 1106564 | 390530.8854
FY 2018 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Terminal Improvements | 97000 | 58024 | Airport funds | 58024 | 0 | Complete | 2020-02-04
Cedar Rapids- Eastern Iowa | Terminal Modernization PH 3 | 650000 | 191592 | Airport funds | 191592 | 0 | Complete | 2020-04-14
Des Moines | General Aviation Improvements | 3376278 | 348769 | Airport funds | 348769 | 0 | Complete | 2018-04-06
Dubuque | Guidance Signage, Relocate Airfield Infrastructure, Terminal Fuel Facility | 560125 | 63793 | Airport funds | 63793 | 0 | Complete | 2020-12-01
Fort Dodge | Hangar Construction and Rehabilitation, Flight Service Station Reconfiguration | 222000 | 57281 | Airport funds | 55754 | 0 | Complete | 2020-03-02
Mason City | Construct T-Hangar | 770500 | 57581 | Airport funds | 57581 | 0 | Complete | 2019-06-19
Sioux City | Rehabilitate Terminal and Hangar | 110000 | 61397 | Airport funds | 61397 | 0 | Complete | 2020-01-03
Waterloo | Hangar Improvements | 80220 | 61563 | Airport funds | 61563 | 0 | Complete | 2018-04-18
| Total | 5866123 | 900000 |  | 898473 | 0
FY 2017 RIIF/Aviation Trust Fund* - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Hangar Construction and Improve Terminal Area Infrastructure | 101000 | 95966.7333 | Airport funds | 95967 | 0 | Completed | 2020-01-02
Cedar Rapids- Eastern Iowa | Rehabilitate Terminal Building | 16330000 | 325245.8293 | Airport funds | 325246 | 0 | Completed | 2020-03-19
Des Moines | General Aviation Improvements | 3619000 | 579266.8881 | Airport funds | 579267 | 0 | Completed | 2017-12-19
Dubuque | Guidance Signage, Relocate Airfield Infrastructure, Terminal Fuel Facility | 560125 | 105671.6423 | Airport funds | 105672 | 0 | Completed | 2019-01-09
Fort Dodge | Construct Hangar, Hangar roofing and Flight Service Station redesign | 222000 | 93901.3818 | Airport funds | 93901 | 0 | Completed | 2018-07-16
Mason City | Replace Terminal Chiller Phase Two | 192500 | 94005.0898 | Airport funds | 94005 | 0 | Completed | 2017-10-30
Sioux City | Rehabilitate and Build Hangars | 104244 | 104243.6947 | Airport funds | 104244 | 0 | Completed | 2019-07-24
Waterloo | GA Terminal Building Rehabilitation and Hangar 5 Rehabilitation | 104800 | 101698.7408 | Airport funds | 101699 | 0 | Completed | 2018-01-16
| Total | 21233669 | 1500000 |  | 1500001 | 0
* $60,000 of the FY 2017 appropriation is from the Aviation Trust Fund and not subject to Infrastructure Annual Status Report requirement. However, the status of the entire appropriation is included for information.
FY 2016 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace Hangars | 288000 | 96034.2405 | Airport funds | 96034 | 0 | Completed | 2019-06-02
Cedar Rapids- Eastern Iowa | Rehabilitate Terminal Building | 8018250 | 319397.9844 | Airport funds | 319398 | 0 | Completed | 2018-12-31
Des Moines | General Aviation Improvements | 3619000 | 585229.5187 | Airport funds | 585230 | 0 | Completed | 2017-12-19
Dubuque | Guidance Signage, Relocate Airfield Infrastructure, Terminal Fuel Facility | 560125 | 105683.7904 | Airport funds | 105684 | 0 | Completed | 2019-01-09
Fort Dodge | Construct Hangar and Flight Service Station redesign | 100000 | 94844.5512 | Airport funds | 94845 | 0 | Completed | 2018-07-16
Mason City | Replace Overhead Garage Doors and Perform Terminal Systems Study | 46000 | 94881.917 | Airport funds | 94882 | 0 | Completed | 2017-06-19
Sioux City | Rehabilitate and Build Hangars | 120000 | 102731.8436 | Airport funds | 102732 | 0 | Completed | 2016-11-16
Waterloo | Hangar rehabilitation and baggage area renovation | 119720 | 101196.1542 | Airport funds | 101196 | 0 | Completed | 2018-07-30
| Total | 12871095 | 1500000 |  | 1500001 | 0
FY 2015 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace three hangars | 240000 | 96692 | Airport funds | 96692 | 0 | Completed | 2017-07-27
Cedar Rapids- Eastern Iowa | Renovate terminal building lobby | 10387000 | 317297 | Airport funds | 317297 | 0 | Completed | 2015-10-16
Des Moines | Customs & Border Protection relocation | 1533500 | 583354 | Airport funds | 583354 | 0 | Completed | 2015-07-27
Dubuque | Construct new terminal building and Guidance Signage | 1277920 | 105886 | Airport funds | 105866 | 0 | Completed | 2019-01-09
Fort Dodge | Construct new hangar | 130000 | 95854 | Airport funds | 95854 | 0 | Completed | 2018-07-16
Mason City | Upgrade terminal electrical service and replace overhead door in west maintenance facility | 121000 | 96001 | Airport funds | 96001 | 0 | Completed | 2017-06-19
Sioux City | Rehabilitate and build hangars | 103884 | 103884 | Airport funds | 103884 | 0 | Completed | 2016-10-17
Waterloo | Upgrade emergency generator, replace door at bag make-up, and terminal electrical improvements | 107375 | 101032 | Airport funds | 101032 | 0 | Completed | 2016-12-23
| Total | 13900679 | 1500000 |  | 1499980 | 0
FY 2014 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Construct hangar | 480000 | 96594 | Airport funds | 96594 | 0 | Completed | 2017-05-31
Cedar Rapids- Eastern Iowa | Replace roofs on four buildings | 330000 | 311190 | Airport funds | 311190 | 0 | Completed | 2014-09-16
Des Moines | Relocate US Customs building | 4500000 | 579215 | Airport funds | 579214 | 0 | Completed | 2015-04-06
Dubuque | Construct terminal building | 1277920 | 108456 | Airport funds | 108456 | 0 | Completed | 2017-02-01
Fort Dodge | Re-design flight service station, replace overhead doors in ARFF/Maintenance building, demolish two hangars | 150000 | 98159 | Airport funds | 98159 | 0 | Completed | 2017-07-13
Mason City | Rehabilitate terminal: replace terminal cooling system, install security cameras, improve entrance soffit and ceiling | 99144 | 98450 | Airport funds | 98450 | 0 | Completed | 2017-05-18
Sioux City | Rehabilitate and construct new hangars | 120000 | 105151 | Airport funds | 105151 | 0 | Completed | 2017-02-13
Waterloo | Rehabilitate hangars | 106000 | 102785 | Airport funds | 102785 | 0 | Completed | 2016-11-22
| Total | 7063064 | 1500000 |  | 1499999 | 0
FY 2013 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Replace hangar | 450000 | 94903 | Airport funds | 94903 | 0 | Completed | 2014-10-27
Cedar Rapids- Eastern Iowa | Renovate terminal building lobby | 3430000 | 325782 | Airport funds | 325782 | 0 | Completed | 2014-09-16
Des Moines | Construct parking garage bridge | 5200000 | 568101 | Airport funds | 568101 | 0 | Completed | 2012-11-15
Dubuque | Construct terminal building | 1351480 | 107598 | Airport funds | 107598 | 0 | Completed | 2017-02-01
Fort Dodge | Renovate terminal operation area and former flight service station building | 100000 | 97119 | Airport funds | 97119 | 0 | Completed | 2015-06-30
Mason City | Construct office addition | 722170 | 99415 | Airport funds | 99415 | 0 | Completed | 2012-07-20
Sioux City | Rehabilitate hangars | 200000 | 103848 | Airport funds | 103848 | 0 | Completed | 2016-03-04
Waterloo | Rehabilitate hangars and snow removal equipment building | 103560 | 103234 | Airport funds | 103234 | 0 | Completed | 2017-04-20
| Total | 11557210 | 1500000 |  | 1500000 | 0
FY 2012 RIIF - Commercial Service Vertical Infrastructure (CSVI) Projects
Airport | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Expected to be Completed
Burlington- Southeast Iowa | Construct hangars | 898500 | 94579 | Airport funds | 94579 | 0 | Completed | 2014-06-19
Cedar Rapids- Eastern Iowa | Renovate terminal - relocate baggage screening area | 3904000 | 328020 | Airport funds | 328020 | 0 | Completed | 2013-01-07
Des Moines | Construct parking garage bridge | 800000 | 562349 | Airport funds | 562349 | 0 | Completed | 2012-09-24
Dubuque | Construct terminal building | 8752175 | 110137 | Airport funds | 110137 | 0 | Completed | 2013-08-08
Fort Dodge | Renovate terminal to prevent drainage issues; design renovation to flight service station; hangar A and B demolition | 225000 | 97119 | Airport funds | 97119 | 0 | Completed | 2015-06-26
Mason City | Construct office addition | 500000 | 99205 | Airport funds | 99205 | 0 | Completed | 2012-12-03
Sioux City | Rehabilitate hangars | 200000 | 107536 | Airport funds | 107536 | 0 | Completed | 2013-08-20
Waterloo | Rehabilitate hangars | 104929 | 103021 | Airport funds | 103021 | 0 | Completed | 2016-11-22
| Total | 15384604 | 1501966 |  | 1501966 | 0

## SRT
State Recreational Trails
Fund | Fiscal Year | Description of Project | Progress of Work | Total Estimated Project Cost | Revenue Sources | Funds Obligatedb |  | Funds Expended | Date of Completion / Estimated Completion
Recreational Trails - RIIF - 0017 | 2021 | Flint River Trail - Bluff Road Connector (Burlington) | Agreement not signed - work not started | 515000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Wellmark Foundation, local matching funds | 165000 |  | 0 | 2022-06-30
Recreational Trails - RIIF - 0017 | 2021 | High Trestle Trail Extension to Oralabor Road (Ankeny) | Agreement signed 9/01/2020 - development in process | 2231700 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, local matching funds | 295060 |  | 0 | 2022-06-30
Recreational Trails - RIIF - 0017 | 2021 | Little River Scenic Pathway - Phase I (Decatur County Conservation Board) | Agreement signed 11/20/2020 - development in process | 631800 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Wellmark MATCH grant, South Central Iowa Community Foundation | 161800 |  | 0 | 2022-06-30
Recreational Trails - RIIF - 0017 | 2021 | Raccoon River Valley Trail to High Trestle Trail Connector Phase IV Construction (Dallas County Conservation Board) | Agreement signed 11/03/2020 - development in process | 669300 | State Recreational Trail (SRT) Fund, Federal Recreational Trail (FRT) funds, local matching funds | 201618 |  | 0 | 2022-06-30
Recreational Trails - RIIF - 0017 | 2021 | Tatonka Ska Trace Trail Phase III(c) (Dickinson County) | Agreement signed 12/15/2020 - development in process | 867022 | State Recreational Trail (SRT) Fund, Imagine Iowa Great Lakes, Dallas County Trails Board devleopment funds, land donation | 176522 |  | 0 | 2022-06-30
Recreational Trails - RIIF - 0017 | 2020 | Raccoon River Valley Trail to High Trestle Trail Connector Phase II Construction (Dallas County Conservation Board) | Agreement signed 8/13/2020-development in process | 569000 | State Recreational Trail (SRT) Fund and local funds | 392610 |  | 0 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2020 | Iowa River Trail from Steamboat Rock to Edgington Avenue Paving (Hardin County) | Agreement signed 12/15/2020-development in process | 1115136 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Federal Recreational Trail (FRT) funds, local funds, Hardin County Commission | 375000 |  | 0 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2020 | Heart of Iowa Nature Trail Paving from 560th Avenue to South Skunk River Bridge (Story County Conservation) | Agreement signed 2/17/2020 - development in process | 1077000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, local matching funds | 530000 |  | 0 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2020 | Tatonka Ska Trace Rail Trail Phase III(a) (Dickinson County) | Agreement signed 2/3/2020 - development in process | 612356 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, in-kind easement value and Dickinson County Trails Board development funds | 202390 |  | 0 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2019 | Cedar Valley Nature Trail Wolf Creek Bridge Replacement (Black Hawk County Conservation Board) | Agreement signed 2/17/2019 - development in process | 850000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and local fundraising | 360000 |  | 173063 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2019 | Connecting Fort Madison! Phase 3-Community Hospital Connector (Fort Madison) | Agreement signed 4/01/2019 - development in process | 531840 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and Wellmark Foundation Large Match Grant | 91100 |  | 13002.19 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2019 | Davis County Regional Trail Construction-Phase 3 (Davis County and Davis County Trails Council) | Agreement signed 11/28/2018 - project completed | 461000 | State Recreational Trail (SRT) Fund, Wellmark Foundation, DNR REAP City Park and Open Spaces and Davis County Trails Council | 230000 |  | 230000 | 2020-12-01
Recreational Trails - RIIF - 0017 | 2019 | Heart of Iowa Nature Trail-Slater to Huxley Hard Surfacing and Trail Improvements (Story County Conservation Board) | Agreement signed 10/30/2019 - development in process | 939000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and Story County Conservation | 300000 |  | 195000 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2019 | Lake Belva Deer Area Trail-Phase 3 (Keokuk County and Keokuk County Highway Department) | Agreement signed 12/20/2018 - development in process | 1188000 | State Recreational Trail (SRT) Fund and Regional Transportation Alternative funds | 328000 |  | 112447 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2018 | Heritage Trail Bridge 27 Replacement (Dubuque County Conservation Board) | Agreement signed 12/27/2017 - project completed | 162482 | State Recreational Trail (SRT) Fund and County Conservation Board funds | 113185 |  | 113185 | 2019-04-11
Recreational Trails - RIIF - 0017 | 2018 | Louisa County Fairground Trailhead and Connection to the Hoover Nature Trail (Louisa County Conservation Board and Louisa County Trails Council) | Agreement signed 2/1/2018 - development in process | 456000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, CFLC, CJUW Endowment, Riverboat Foundation, County Conservation Board funds, Trails Council and private donations | 250000 |  | 52107 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2018 | Pottawattamie County Trail - Railroad Highway Trail Phase II (Pottawattamie County Conservation Board and Pottawattamie County Trail Association) | Agreement signed 3/19/2018- development in process | 1700000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and Iowa West Foundation | 612410 |  | 0 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2018 | Raccoon River Valley Trail to High Trestle Trail Phase I Construction (Dallas County Conservation Board) | Agreement signed 1/16/2018 - project completed | 556000 | State Recreational Trail (SRT) Fund, private donations and Wellmark Foundation | 366000 |  | 366000 | 2020-05-07
Recreational Trails - RIIF - 0017 | 2018 | Wapsipinicon Trail - Phase I (Jones County and Anamosa) | Agreement signed 12/27/2017 - development in process | 765490 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, DNR REAP award, Iowa Parks Foundation/GWMRR, Wellmark Foundation, Anamosa and Jones County Community Foundations, Ignite Young Professionals and private donations | 139000 |  | 139000 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2017 | East Blue Creek Bridge Replacement along Cedar Valley Nature Trail (Linn and Black Hawk County Conservation Boards) | Agreement signed 3/2/2017 - development in process | 600000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and County Conservation Board CIP funds | 250000 |  | 243750 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2017 | Extension of Felderman Trail (Bellevue and Iowa Department of Natural Resources) | Agreement signed 1/18/2017 - project completed | 753000 | State Recreational Trail (SRT) Fund, DNR REAP award, Northeast State Parks Region and Iowa Parks Foundation funds, private donation and Wellmark Foundation | 300000 |  | 300000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2017 | Interstate 29 Riverfront Trail Connection (Sioux City) | Agreement signed 3/13/17 - development in process | 3225917 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Missouri River Historical Development funds and city funds | 650000 |  | 74036 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2017 | Iowa River Trail-Marshalltown to South Side of Iowa River (Marshalltown) | Agreement signed 9/18/2017- development in process | 1158614 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, DNR REAP award and fundraising | 650000 |  | 558554 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2017 | Rolling Prairie Trail-Allison to Bristow (Butler County Conservation Board) | Agreement signed 5/18/17 - project completed | 1288380 | State Recreational Trail (SRT) Fund, County Board of Supervisors and County Conservation Board funds, Cities of Allison, Bristow, Dumont, Clarksville and Shell Rock funds, private donations and anticipated Guernsey's Foundation funds | 664678 |  | 664678 | 2020-10-27
Recreational Trails - RIIF - 0017 | 2016 | Cedar Valley Trail "Paving the Way for the American Discovery Trail" (Linn County & Black Hawk County Conservation Boards) | Agreement signed 2/12/2016 - project completed | 1209000 | State Recreational Trail (SRT) Fund, County Conservation Board CIP funds, Linn County Trails Association funds and anticipated city of Center Point funds | 600000 |  | 600000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Flint River Trail: Phase I South (Burlington) | Agreement signed 3/14/2016 - project completed | 850000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds, Two DNR REAP grants, city sales tax and local fundraising | 398500 |  | 398500 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2016 | Hoover Trail -- "The Missing Link" (Johnson County Conservation Board) | Agreement signed 12/21/2015 - project completed | 4321590 | State Recreational Trail (SRT) Fund, County Conservation Board funds, other grants and donations | 726344 | j | 772989 | 2020-08-04
Recreational Trails - RIIF - 0017 | 2016 | Hospital Connector Trail Bridge (Manning)h | Agreement signed 12/21/2015 - project completed | 296400 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and Great Places funding | 222300 | h | 197851 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2016 | Mitchellville to Prairie City Rails-to-Trails Corridor Development (Jasper County Conservation Board) | Agreement signed 11/24/2015 - development in process | 1200100 | State Recreational Trail (SRT) Fund and Federal Recreational Trails Fund | 749501 |  | 656740 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2016 | Turkey River Recreational Corridor - Elgin to Gilbertson Park and the Turkey River (Fayette County Conservation Board) | Agreement signed 12/21/2015 - project completed | 1136000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and private contributions | 750000 |  | 750000 | 2019-10-03
Recreational Trails - RIIF - 0017 | 2015 | Ankeny Connector - High Trestle Trail (Polk County Conservation Board) | Agreement signed 12/15/2014 - project completed | 2109860 | State Recreational Trail (SRT) Fund, city funds, County Conservation Board funds, and Iowa Natural Heritage Foundation funds | 782500 |  | 782500 | 2015-02-26
Recreational Trails - RIIF - 0017 | 2015 | Cedar Valley Nature Trail Bridge E4 Replacement (Black Hawk County Conservation Board) | Agreement signed 11/25/2014 - project completed | 214542 | State Recreational Trail (SRT) Fund and County Conservation Board funds | 160906 |  | 160906 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2015 | Coon Rapids Connector Trail Underpass (City of Coon Rapids) | Agreement signed 2/10/2015 - project completed | 299250 | State Recreational Trail (SRT) Fund and city funds | 224437 |  | 224437 | 2017-06-30
Recreational Trails - RIIF - 0017 | 2015 | Great River Road Bike Lane (Louisa County Secondary Roads)i | Agreement signed 6/19/2014 - project completed | 1690000 | State Recreational Trail (SRT) Fund and Scenic Byways grant | 340000 | i | 257045.57 | 2016-12-15
Recreational Trails - RIIF - 0017 | 2015 | Hoover Trail - "The Missing Link" (Johnson County Conservation Board) | Agreement signed 12/14/2014 - project completed | 605333 | State Recreational Trail (SRT) Fund and County Conservation Board funds | 454000 | j | 407355 | 2018-08-29
Recreational Trails - RIIF - 0017 | 2015 | Iowa DNR AmeriCorps Trail Crew (Iowa Department of Natural Resources) | Agreement signed 12/17/2014 - project completed | 395000 | State Recreational Trail (SRT) Fund, DNR REAP grant and Lake Restoration Fund | 296250 |  | 296250 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2015 | Iowa River Trail Phase 1 Development (City of Marshalltown and Hardin County) | Agreement signed 3/2/2015 - project completed | 1335000 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and DNR REAP grant | 775000 |  | 775000 | 2016-01-07
Recreational Trails - RIIF - 0017 | 2015 | Jurgensen Bridge Refurbishment (Winterset and Winterset Municipal Utility)f | Agreement signed 9/21/2015 - project completed | 1066590 | State Recreational Trail (SRT) Fund, FEMA funds and city funds | 500000 | f | 500000 | 2019-12-30
Recreational Trails - RIIF - 0017 | 2015 | Lake Path Trail/JewEllsworth Trail Segment (Hamilton County Conservation Board)i | Agreement signed 1/6/2015 - project completed | 862853 | State Recreational Trail (SRT) Fund, Regional Transportation Enhancement funds, cash from local entities and private donations | 647140 | i | 631947.12 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Mississippi River Trail - Pikes Peak Road to Guttenberg (Clayton County)i | Agreement signed 8/31/2015 -project completed | 1369575 | State Recreational Trail (SRT) Fund and local option sales tax | 579074 | i | 282679.69 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2015 | Pottawattamie County Trail-Phase I (Pottawattamie County Conservation Board and Pottawattamie County Trail Board) | Agreement signed 12/15/2014 -development in process | 933333 | State Recreational Trail (SRT) Fund, Federal Recreational Trails Fund, County Conservation Board funds and Iowa West Foundation funds | 700000 |  | 487671 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2015 | Red Cedar Trail and Connector (Linn County Conservation Board and Linn Area Mountain Bike Association) | Agreement signed 1/27/2015 - project completed | 75000 | State Recreational Trail (SRT) Fund, Specialized Dealer Grant, Marion Hotel/Motel and other local grants, LAMBA and other donors | 55000 |  | 55000 | 2017-06-27
Recreational Trails - RIIF - 0017 | 2015 | SW 5th (Jackson) Street Bridge Rehabilitation (City of Des Moines)f | Agreement signed 9/29/2015 - project completed | 3740000 | State Recreational Trail (SRT) Fund, City CIP funds, TIGER funds and private fundraising | 500000 | f | 500000 | 2017-01-11
| 2014 | [5 empty] | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2014 | Ankeny Connector - High Trestle Trail (Polk County Conservation Board and Ankeny) | Agreement signed 10/25/2013 - project completed | 3065000 | State Recreational Trail (SRT) Fund, city funds and county funds | 782500 |  | 782500 | 2014-05-01
Recreational Trails - RIIF - 0017 | 2014 | Bellevue Rivervue Trail-Phase II (City of Bellevue and Jackson County Conservation Board) | Agreement signed 1/30/2014 - project completed | 722275 | State Recreational Trail (SRT) Fund, city funds, DNR REAP grant, Regional Transportation Alternative funds and private donations | 260774 |  | 260774 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2014 | Bridging the Gap: Phase I Dry Run Trail-Connecting Decorah's Trout Run Trail to the Prairie Farmer Recreational Trail (Winneshiek County Conservation Board and City of Decorah) | Agreement signed 1/09/2014 - development in process | 1604512 | State Recreational Trail (SRT) Fund, Statewide Transportation Enhancement grant, DNR REAP grant and local public/private funds | 380265 |  | 71948 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2014 | Farragut to Shenandoah Trail Connection (City of Farragut) | Agreement signed 10/31/2013 - development in process | 650000 | State Recreational Trail (SRT) Fund and land value | 487500 |  | 318485 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2014 | Iowa River Scenic Trail (Hardin County Board of Supervisors and City of Marshalltown) | Agreement signed 11/12/2013 - project completed | 1375694 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and land value | 775000 |  | 775000 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2014 | Multiuse Mississippi River Trail, Riverdale Section, Phase 2 (City of Riverdale) | Agreement signed 6/3/2014 - project completed | 1017000 | State Recreational Trail (SRT) Fund, city funds, County Regional Authority grant and National Scenic Byways grant | 318644 |  | 318644 | 2017-05-23
Recreational Trails - RIIF - 0017 | 2014 | Pioneer Beach Road Trail (City of Orleans and Dickinson County Trails Board) | Agreement signed 12/23/2013 - project completed | 521479 | State Recreational Trail (SRT) Fund, city funds and County Trails Board funds | 371479 |  | 371479 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2014 | Raccoon River Valley Trail to High Trestle Trail Connector (Dallas County Conservation Board) | Agreement signed 7/30/2013 - project completed | 290000 | State Recreational Trail (SRT) Fund, other grants, donations and foundations | 92897 |  | 92879.59 | 2019-07-30
| 2014 | [5 empty] | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2013 | Brushy Creek All-Weather Multi-Use Lake Trail Bridge (Iowa DNR) | Agreement signed 12/05/2012 - project completed | 125800 | State Recreational Trail (SRT) Fund and DNR REAP grant | 78000 |  | 78000 | 2015-08-17
Recreational Trails - RIIF - 0017 | 2013 | City of Clinton Mississippi River Trail Final Connection (City of Clinton) | Agreement signed 11/28/2012 - project completed | 535544 | State Recreational Trail (SRT) Fund and city G.O. Bonds | 400000 |  | 400000 | 2015-05-06
Recreational Trails - RIIF - 0017 | 2013 | Fayette-Volga River Multi-Use Trail (Upper Iowa University and Fayette County) | Agreement signed 11/13/2012 - project completed | 1190931 | State Recreational Trail (SRT) Fund, Upper Iowa University, city funds, County Community Foundation, Black Hills Energy, private donors, additional fundraising and DNR REAP grant | 700000 |  | 700000 | 2017-08-31
Recreational Trails - RIIF - 0017 | 2013 | Iowa River Trail – Phase 8 of 8 (City of Iowa City) | Agreement signed 11/25/2014 - project completed | 2100000 | State Recreational Trail (SRT) Fund, city G.O. Bonds, Regional STP Funds, Earmark funds and Regional Transportation Enhancement funds | 441000 |  | 441000 | 2017-01-27
Recreational Trails - RIIF - 0017 | 2013 | Mines of Spain Trail and Trailhead (City of Dubuque and Iowa DNR) | Agreement signed 11/28/2012 - project completed | 227333 | State Recreational Trail (SRT) Fund, city funds and fundraising/naming opportunities | 170500 |  | 170500 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2013 | Musser Park to Wiggens Road Trail (City of Muscatine) | Agreement signed 3/24/2014 - project completed | 984400 | State Recreational Trail (SRT) Fund, Federal Earmark funds and local contribution | 381100 |  | 381100 | 2019-05-07
Recreational Trails - RIIF - 0017 | 2013 | Shaulis Road Trail Extension – Phase I (City of Waterloo) | Agreement signed 7/11/2013 - project completed | 1007592 | State Recreational Trail (SRT) Fund, Regional Transportation Alternative funds and city funds | 755694 |  | 659506.71 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2013 | South Troy Park Trail (City of Robins) | Agreement signed 12/12/2012 - project completed | 354000 | State Recreational Trail (SRT) Fund and city funds | 204000 |  | 204000 | 2017-04-17
|  |  |  | #REF! |  | #REF!
Recreational Trails - RIIF - 0017 | 2012 | Bee Branch Creek Trail-MRT Route (City of Dubuque) | Agreement signed 9/16/2014 - project completed | 506100 | State Recreational Trail (SRT) Fund, National Scenic Byway funds and city funds | 100000 |  | 100000 | 2019-12-17
Recreational Trails - RIIF - 0017 | 2012 | Bluff Creek OHV Park Development Plan (Iowa DNR)i | Agreement signed 12/20/2011 - project completed | 80000 | State Recreational Trail (SRT) Fund and ATV registration funds | 60000 | i | 25959.74 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2012 | Buffalo to Wild Cat Den Road MRT (City of Buffalo) | Agreement signed 5/05/2012 - project completed | 562500 | State Recreational Trail (SRT) Fund, SAFETEA-LU earmark funds, and city funds | 108500 |  | 108500 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2012 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board)e | Agreement signed 12/20/2011 - project completed with other funding | 3612516 | State Recreational Trail (SRT) Fund and CDBG Jumpstart Infrastructure funds | 396516 | e | Rescinded | N/A
Recreational Trails - RIIF - 0017 | 2012 | Central IA Trail Loop-Chichaqua Valley Trail to Gay Lea Wilson Trail (Polk County Conservation Board) | Agreement signed 12/15/2011 - project completed | 10891016 | State Recreational Trail (SRT) Fund, Polk County Conservation and Partners funds | 753750 |  | 753750 | 2015-11-03
Recreational Trails - RIIF - 0017 | 2012 | Dickinson County Spine Trail-Henderson Woods to US71 in Arnolds Park (Arnolds Park and Dickinson County Trails Board) | Agreement signed 12/22/2011 - project completed | 165500 | State Recreational Trail (SRT) Fund, city funds and County Trails Board funds | 115850 |  | 115850 | 2013-10-08
Recreational Trails - RIIF - 0017 | 2012 | Gray's Lake Neighborhood Connecting Trail & SW 14th Quiet Street (City of Des Moines)g | Agreement signed 5/15/2012 - project completed | 586570 | State Recreational Trail (SRT) Fund, city CIP, Gray's Lake Neighborhood Association and land donations | 439920 | g | 439920 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2012 | Gypsum City OHV Park (WCIC and Iowa DNR) | Agreement signed 2/6/2012 - project completed | 626349 | State Recreational Trail (SRT) Fund, Federal Recreational Trails Fund, Webster County Conservation and ATV Registration funds | 211500 |  | 211500 | 2016-06-29
Recreational Trails - RIIF - 0017 | 2012 | Iowa DNR Trails Program (Iowa DNR) | Agreement signed 12/20/2011 - project completed | 350000 | State Recreational Trail (SRT) Fund, DNR REAP grant and Lake Restoration Fund | 262500 |  | 262500 | 2014-12-15
Recreational Trails - RIIF - 0017 | 2012 | NW Beaver Drive Trail (City of Johnston) | Agreement signed 1/10/2012 - project completed | 2400000 | State Recreational Trail (SRT) Fund, city G.O. bond and city park and trail improvement fund | 181464 |  | 181464 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2012 | Turkey River Recreational Corridor Trail-Elkader to Motor Mill (Clayton County Conservation Board) | Agreement signed 1/18/2012 - development in process | 880576 | State Recreational Trail (SRT) Fund, statewide Transportation Enhancement grant and local contributions | 220000 |  | 125725 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2012 | Water Trails Planning, Design and Construction Activities (Iowa DNR) | Agreement signed 2/23/2012 - project completed | 160000 | State Recreational Trail (SRT) Fund, marine fuel tax, U.S. Coast Guard, boat registration fees and RIIF | 120000 |  | 120000 | 2015-03-04
|  |  |  | #REF! |  | 2970000
Recreational Trails - RIIF - 0017 | 2010 | Allamakee County Mississippi River Bike Trail (Allamakee County and Allamakee County Economic Development) h | Agreement signed 1/5/2010- project completed | 7245382 | State Recreational Trail (SRT) Fund, Private and Local, Federal Earmark and Other State and Federal Grants | 750000 | h | 750000 | 2016-06-30
Recreational Trails - RIIF - 0017 | 2010 | Cedar Valley Nature Trail Bridge at McFarlane Park (Black Hawk County Conservation Board) | Agreement signed 11/20/2009 - project completed | 2658938 | State Recreational Trail (SRT) Fund, CDBG - Jumpstart Infrastructure and FEMA-PA Funds | 250000 |  | 250000 | 2012-09-30
Recreational Trails - RIIF - 0017 | 2010 | Des Moines River Regional Trail Phase 1 (City of Des Moines)c | Agreement signed 1/29/2010 - project completed | 1937997.68 | State Recreational Trail (SRT) Fund, DNR REAP grant, Iowa Clean Air Attainment Program funds and City of Des Moines Capital Funds | 73474 | c | 73474 | 2015-01-12
Recreational Trails - RIIF - 0017 | 2010 | Iowa Department of Natural Resources (DNR) Trail Crew (Iowa DNR) | Agreement signed 11/20/2009 - project completed | 350000 | State Recreational Trail (SRT) Fund, DNR REAP grant and Lake Restoration Fund | 262500 |  | 262500 | 2012-12-03
Recreational Trails - RIIF - 0017 | 2010 | Iowa River Corridor Trail Connection - Sand Lake (City of Iowa City)c,h | Agreement signed 1/29/2010 - project completed | 375000 | State Recreational Trail (SRT) fund and Capital Improvement Funds | 281000 | c,h | 180059.72 | 2012-08-06
Recreational Trails - RIIF - 0017 | 2010 | Lewis and Clark Historic Riverfront Trail (City of Sioux City and Iowa DOT)c | Agreement signed 2/1/2010 - project completed | 1600000 | State Recreational Trail (SRT) Fund and City Funds | 128000 | c | 128000 | 2013-08-07
Recreational Trails - RIIF - 0017 | 2010 | Pinicon Ridge Trail (Linn County Conservation Board)a | Agreement signed 7/20/2009 - project completed | 666667 | State Recreational Trail (SRT) Fund and Local Contributions | 500000 | a | 500000 | 2012-08-27
Recreational Trails - RIIF - 0017 | 2010 | Principal Riverwalk Recreational Trail (city of Des Moines)a | Agreement signed 12/2/2009 - project completed | 1000000 | State Recreational Trail (SRT) fund and Local Contributions | 750000 | a | 750000 | 2013-04-15
Recreational Trails - RIIF - 0017 | 2010 | Raccoon River Valley Trail Addition--Forest Park to Minburn Trail (Dallas County Conservation Board)c | Agreement signed 11/6/2009 - project completed | 6655696 | State Recreational Trail (SRT) Fund, Community Attraction and Tourism Program, State Enhancement Project, Central Iowa Regional Transportation Planning Alliance, Dallas County, City of Perry, City of Waukee, Guthrie County Cash and Stimulus, City of Dallas Center, City of Jamaica, City of Redfield, City of Linden, Raccoon Valley Bank, Bock Family Foundation, Dallas County Conservation Foundation, Raccoon River Valley Trail Association, Celebrations Committee Dallas Center, Committee for Super Cooper, Dallas Center Beta Sigma Phi, Rotary Club of Dallas Center, Community of Herndon, Waukee YMCA, City of Dawson, Casey's Stores, Alliant Energy, Bikes Belong, Letter campaign, Prairie Meadows Community Betterment, Prairie Woodland Conservation Foundation and Bock Family Foundation October 08 | 484995 | c | 460745.25 | 2012-08-23
Recreational Trails - RIIF - 0017 | 2010 | Railbanking Purchase of IANW Railroad (Dickinson County Trails Board and Osceola County Conservation Board) | Agreement signed 1/4/2010 - project completed | 1203795 | State Recreational Trail (SRT) Fund, IANWRR Donated Land and Transportation Enhancement grant | 525000 |  | 525000 | 2010-07-19
Recreational Trails - RIIF - 0017 | 2010 | Summerset Trail Flood Repairs (Warren County Conservation Board)d | Agreement signed 1/5/2010 - project completed | 143028 | State Recreational Trail (SRT) Fund and County Budget | 107271 | d | 107271 | 2012-05-29
Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Box Culverts and Bridge Project (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 11/25/2009 - project completed | 782722 | State Recreational Trail (SRT) Fund, County Foundation, Winneshiek County and Winneshiek County Bridge grant | 300000 |  | 300000 | 2012-03-05
Recreational Trails - RIIF - 0017 | 2010 | Trout Run Trail - Decorah Fish Hatchery's Interpretive Restroom Facility (Northeast Iowa Resources Conservation and Development, Inc. and Iowa DNR's Fisheries) | Agreement signed 12/6/2009 - project completed | 105000 | State Recreational Trail (SRT) Fund and Friends of the Decorah Hatchery funds | 75000 |  | 75000 | 2012-07-02
|  |  |  | 24724225.68 |  | 4487240
Recreational Trails - RIIF - 0017 | 2009 | American Gothic Regional Trail Project (Area 15 Regional Planning Commission)a | Agreement signed 12/3/2008 - project completed | 133333 | State Recreational Trail (SRT) Fund, RPA, county, city, and private funds | 100000 | a | 100000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2009 | Crawford County Trail (Crawford County)a | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund and county funds | 30000 | a | 30000 | 2010-09-20
Recreational Trails - RIIF - 0017 | 2009 | Garlock Slough Recreational Trail (City of West Okoboji and Dickinson County Tails Board)e | Agreement signed 11/3/2008 - project completed | 653550 | State Recreational Trail (SRT) Fund, Dickinson County Conservation, MPO, and City of West Okoboji funds | 490162 | e | 408425.41 | 2012-10-09
Recreational Trails - RIIF - 0017 | 2009 | Linn Creek Trail Connection with Iowa Highway 330 Trail (Marshall County) | Agreement signed 7/20/2009 - project completed | 1476000 | State Recreational Trail (SRT) Fund and county funds | 800000 |  | 800000 | 2012-09-05
Recreational Trails - RIIF - 0017 | 2009 | Maquoketa River Water Trail (Jones County)a | Agreement signed 7/8/2008 - project completed | 133334 | State Recreational Trail (SRT) Fund and county funds | 100000 | a | 100000 | 2011-08-08
Recreational Trails - RIIF - 0017 | 2009 | Mississippi River Trail - Liberty Avenue Connection (Clinton) | Agreement signed 12/3/2008 - project completed | 469000 | State Recreational Trail (SRT) Fund and City of Clinton funds | 351750 |  | 351750 | 2010-04-26
Recreational Trails - RIIF - 0017 | 2009 | Principal Riverwalk (Des Moines)a | Agreement signed 11/4/2008 - project completed | 1000000 | State Recreational Trail (SRT) Fund and City of Des Moines funds | 750000 | a | 750000 | 2013-04-15
Recreational Trails - RIIF - 0017 | 2009 | Riverview Recreation Area Expansion (Trailblazers Off Road Club)e | Agreement signed 6/8/2009 - funding rescinded | 71000 | State Recreational Trail (SRT) Fund | 40000 | e | Rescinded | N/A
Recreational Trails - RIIF - 0017 | 2009 | Stone State Park Trail (Woodbury County/DNR)a | Agreement signed 10/8/2009 - development in process | 133333 | State Recreational Trail (SRT) Fund and county funds | 100000 | a | 0 | 2021-06-30
Recreational Trails - RIIF - 0017 | 2009 | Summerset Trail (Cities of Indianola, Carlisle and Des Moines)a | Agreement signed 3/9/2009 - project completed | 133333 | State Recreational Trail (SRT) Fund, SAFETEA-LU earmark funds and city funds | 100000 | a | 100000 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2009 | Trout Run Trail - Bridging the Past and the Present (City of Decorah and Winneshiek County Conservation Board) | Agreement signed 3/16/2009 - project completed | 443750 | State Recreational Trail (SRT) Fund, Winneshiek County Conservation and City of Decorah funds | 138088 |  | 138088 | 2010-10-18
|  |  |  | 4686633 |  | 3000000
Recreational Trails - RIIF - 0017 | 2008 | Ankeny to Woodward Trail Corridor (Boone County Conservation Board) | Agreement signed 3/25/2008 - project completed | 3415960 | State Recreational Trail (SRT) Fund, Land Value and Regional Transportation Enhancement funds | 565960 |  | 565960 | 2012-07-31
Recreational Trails - RIIF - 0017 | 2008 | Crawford County Trails (Crawford County)a | Agreement signed 11/5/2008 - project completed | 40000 | State Recreational Trail (SRT) Fund, county, city, and private funds | 30000 | a | 30000 | 2010-09-20
Recreational Trails - RIIF - 0017 | 2008 | Fairfield Loop Trail (Fairfield)a | Agreement signed 3/10/2009 - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | a | 200000 | 2012-05-29
Recreational Trails - RIIF - 0017 | 2008 | Heart of Iowa Nature Trail Phases VII & VIII (Story County Conservation Board) | Agreement signed 12/14/2007 - project completed | 1937254 | State Recreational Trail (SRT) Fund and county funds | 100000 |  | 100000 | 2013-12-30
Recreational Trails - RIIF - 0017 | 2008 | Jewell to Ellsworth Trail (Hamilton County Conservation Board)a | Agreement signed 9/5/2007 - project completed | 246667 | State Recreational Trail (SRT) Fund and county funds | 185000 | a | 182908 | 2018-06-30
Recreational Trails - RIIF - 0017 | 2008 | Lewis & Clark Trail Planning Study (Iowa DOT) | Agreement IDOT - project completed | 66667 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2011-07-11
Recreational Trails - RIIF - 0017 | 2008 | Maquoketa River Water Trail (Jones County Conservation Board) | Agreement signed 12/13/2007 - project completed | 549605 | State Recreational Trail (SRT) Fund and county funds | 69300 |  | 69300 | 2011-08-08
Recreational Trails - RIIF - 0017 | 2008 | Mississippi River Trail Upper Scott County (Le Claire)c | Project was rescinded. Funding to be reprogrammed for flood damage projects. | 1227779 | State Recreational Trail (SRT) Fund and county funds | 799740 | c | Rescinded | N/A
|  |  |  | 7750599 |  | 2000000 |  | 0
Recreational Trails - RC2 - 0942 | 2007 | 4-Mile Creek Greenway Trail (Polk County Conservation Board/City of Ankeny Parks and Recreation Department) | Agreement signed 3/06/2007 - project completed | 1334331 | State Recreational Trail (SRT) Fund, Polk County Conservation, MPO, and City of Ankeny funds | 690000 |  | 690000 | 2012-05-30
Recreational Trails - RC2 - 0942 | 2007 | 18th Street to Riverview Trail Development (Waterloo) | Agreement signed 3/29/2007 - project completed | 336250 | State Recreational Trail (SRT) Fund and City of Waterloo | 252187 |  | 252187 | 2011-04-04
Recreational Trails - RC2 - 0942 | 2007 | Alice's Road Greenbelt Trail Improvements (Clive) | Agreement signed 2/07/2007 - project completed | 536540 | State Recreational Trail (SRT) Fund and City of Clive funds | 402405 |  | 402405 | 2014-09-18
Recreational Trails - RC2 - 0942 | 2007 | Cemar Trail - Phase 2 (Cedar Rapids)i | Agreement signed 1/12/2010 - project completed | 200000 | State Recreational Trail (SRT) Fund, federal earmark funds, Transportation Alternative funds, and Cedar Rapids CIP funds | 150000 | i | 129112.3 | 2018-06-30
Recreational Trails - RC2 - 0942 | 2007 | Coon Rapids Town Loop Trail (Coon Rapids) | Agreement signed 4/16/2007 - project completed | 142500 | State Recreational Trail (SRT) Fund and City of Coon Rapids/Whiterock Conservancy funds | 106875 |  | 106875 | 2010-03-15
Recreational Trails - RC2 - 0942 | 2007 | Des Moines County Recreational Trail - Phase 1 Burlington to Starr's Cave (Des Moines County)h | Agreement signed 2/19/2007 - project completed | 480000 | State Recreational Trail (SRT) Fund, Federal Recreational Trails Fund, Regional Transportation Alternative funds and county funds | 360000 | h | 357491.87 | 2017-02-07
Recreational Trails - RC2 - 0942 | 2007 | Lakeview OHV Park Upgrades (Dirt Surfers Inc.)g | Agreement signed 6/27/2007 - project completed | 52420 | State Recreational Trail (SRT) Fund | 39315 | g | 39315 | 2016-06-30
Recreational Trails - RC2 - 0942 | 2007 | Trail Projects in Wapello County (Wapello County)a | Agreement signed 4/16/2007 - $30,000 was awarded to city of Eldon - project completed | 266667 | State Recreational Trail (SRT) Fund and county funds | 200000 | a | 196072.35 | 2010-03-22
|  |  |  | 4674520 |  | 1124651
Recreational Trails - RIIF - 0017 | 2006 | Phase I of the Gypsum City OHV Park (Webster County) | Agreement signed 8/21/2006 - project completed | 1660250 | State Recreational Trail (SRT) Fund and All-Terrain Vehicle Registration funds | 250000 |  | 250000 | 2010-07-06
Recreational Trails - RIIF - 0017 | 2006 | Trail construction connecting the Little Sioux County Park to the city of Correctionville (Woodbury County Conservation Board) | Agreement signed 7/10/2006 - project completed | 1027760 | State Recreational Trail (SRT) Fund, Federal Transportation Enhancement funds, DNR REAP grant, county, city, and private funds | 150000 |  | 150000 | 2007-10-01
Recreational Trails - RIIF - 0017 | 2006 | Phase 4 of the Clear Creek Trail from Mormon Handcart Park to the Clear Creek bridge on U.S. Highway 6 (Coralville) | Agreement signed 8/9/2006 - Final Voucher dated 6/11/08; Remaining funds to be used on next phase of project-project completed | 437216 | State Recreational Trail (SRT) Fund and city hotel/motel tax | 327912 |  | 327912 | 2008-05-01
Recreational Trails - RIIF - 0017 | 2006 | Construction of trail connecting existing trails in Johnston to the Neal Smith Trail in Des Moines (Polk County Conservation Board) | Agreement signed 7/31/2006 - project completed | 1406960 | State Recreational Trail (SRT) Fund, county funds, Federal Transportation Enhancement funds and MPO Transportation Enhancement funds | 346739 |  | 346739 | 2010-06-21
Recreational Trails - RIIF - 0017 | 2006 | Development of a trail to fill a gap in the trail network around Clear Lake and extending to Mason City (Cerro Gordo County) | Agreement signed 7/10/2006 - project completed | 71167 | State Recreational Trail (SRT) Fund and county funds | 50000 |  | 50000 | 2008-05-09
|  |  |  | 4603353 |  | 1074651
NOTE: To avoid loss of funding, it is the Iowa Department of Transportation's policy to expend the oldest funding first when reimbursing any project costs. Thus, the FY 2006 $1,000,000 appropriation was spent, even though some of the FY 2006 projects listed don't show all their funding was utilized by the expiration date.
a. Direct Appropriation from Iowa Legislature
b. Funds obligated per Department of Transportation Commission Order
c. FY 2006 and FY 2008 Funding Rescinded by Local Sponsors - Funding Reallocated to SRT Projects in FY 2010
d. The initial $87,500 is from I-Jobs and the remaining $19,771 from rescinded funds from FY 2008.
e. Funding for 2 Projects Rescinded by Local Sponsors and a $32,543 project underrun - Funding Reallocated to SRT Projects in FY 2014
f. Identifies 2 Projects funded through $1 million existing historic trail bridges allocation that was part of the FY 2015 appropriation
g. Identifies 2 Project Underruns - Funding Balance Reallocated to SRT Projects in FY 2017
h. Identifies 4 Project Underruns - Funding Balance Reallocated to SRT Projects in FY 2018 (includes underrun for 2010 Allamakee Co. project that was included in error)
i. Identifies 5 Project Underruns - Funding Balance Reallocated to SRT Projects in FY 2019 (total underun balance applied adjusted for amount included in FY 2018 in error)
j. Following 2015 project completion, remaining $46,645 funding balance added to 2016 Linn County Hoover Trail "The Missing Link" project with adjacent scope.
The FY 2006 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,000,000 as result of awarding additional funding from previous project underruns.
The FY 2007 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is over $2,000,000 as result of awarding additional funding from previous project underruns.
The FY 2008 SRT appropriation was for $2,000,000. The total amount of SRT funding for projects listed in this report is $2,000,000.
The FY 2009 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2010 SRT appropriation was for $3,500,000. The total amount of SRT funding for projects listed in this report is over $3,500,000 as a result of awarding additional funding from previous project underruns.
There was no SRT appropriation for FY 2011.
The FY 2012 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is $3,000,000.
The FY 2013 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2014 SRT appropriation was for $3,000,000. The total amount of SRT funding for projects listed in this report is over $3,000,000 as a result of awarding additional funding from previous project underruns.
The FY 2015 SRT appropriation was for $6,000,000 with $1,000,000 for existing historic trail bridges. The total amount of SRT funding for projects listed in this report is over $5,500,000 as a result of awarding additional funding from a previous project underrun.
The FY 2016 SRT appropriation was for $3,400,000. The total amount of SRT funding for projects listed in this report is $3,400,000.
The FY 2017 SRT appropriation was for $2,500,000. The total amount of SRT funding for projects listed in this report is over $2,500,000 as a result of awarding additional funding from previous project underruns.
The FY 2018 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,200,000 as a result of awarding additional funding from previous project underruns.
The FY 2019 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is over $1,300,000 as a result of awarding additional funding from previous project underruns.
The FY 2020 SRT appropriation was for $1,500,000. The total amount of SRT funding for projects listed in this report is $1,500,000.
The FY 2021 SRT appropriation was for $1,000,000. The total amount of SRT funding for projects listed in this report is $1,000,000.
Note on B2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: When I did this report in Jan 2020, there were a few projects that either had balances remaining that were allowed to go on another project or where balances were accepted from another project. I left these projects alone and did not make things complicated in order to get the report done quickly. For next year, review the database notes carefully. Most of these should be closed. Discuss with me before finalizing the report to determine if we need to add notes and what they say.

## RRLGP
FY 2021 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
CRANDIC - AW 2235 | The proposed project is for construction of industry lead tracks and industry tracks to support the competitive shipment of their product in the Cedar Rapids area. | 5400000 | 2700000 | Company Match | 0 | 2700000 | Agreement Phase | Spring 2023
BJRY Passing Track | The project will construct 1,300 feet of rail that will serve as a relocated passing track on the BJRY mainline. This project will increase efficiency and capacity of BJRY’s operations. | 285259 | 228207 | Company Match | 0 | 228207 | Project in Process | Spring 2023
IANR Bridge Replacement | IANR is the applicant. IANR recently entered into a long term operation and maintenance agreement with the Union Pacific Railroad (April 2019). IANR has assumed all maintenance of the line. One of the main areas of focus on the line is the Railroad bridge in Waterloo, Iowa. This bridge can no longer hold 286# railcars, and is in need of replacement. | 1300000 | 487500 | Company Match | 365849.5 | 12150.5 | Project in Process | Spring 2023
Merchants | The proposed study is to plan for future rail service on a site known as the Gerdau site as a railport in Dallas County, Iowa. This study will determine potential developmental and startup costs, spur expansion and addition options, site design and engineering as well as determine options for future direction of rail yard services and capabilities of expansion and property acquisition. Site currently has a rail spur that connects to the IAIS mainline. | 125000 | 100000 | Company Match | 0 | 100000 | Agreement Phase | Summer 2022
River Cities Business Park Rail Spur | This planning study will evaluate the need and ability to create a rail spur that will connect River City Management’s properties from Davenport to neighboring Eldridge, Iowa. At one point, CP served the site, however mainline connections were disconnected. River Cities is again interested in connecting these two properties via a rail spur and want to conduct a study to see if the two properties can accommodate additional rail spurs and again be served by CP. | 100000 | 80000 | Company Match | 0 | 80000 | Project in Process | Summer 2022
Western Iowa Energy | This project is adding track capacity and track infrastructure to Western Iowa Energy’s existing facility in Wall Lake, IA. The rail expansion involves a series of storage tracks at the end of the current spur. The existing spur is currently inadequate for outbound product. | 4677405 | 500000 | Company Match | 0 | 500000 | Agreement Phase | Spring 2023
[5 empty] | 365849.5 | 692150.5
FY 2020 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
TrinityRail | The proposed project will construct a loop track for railcar cleaning and maintenance in the Butler Logistics park. Iowa Northern will serve the site. Project will create 263 new jobs. | 60000000 | 2130973 | Company Match | 1051598.46 | 1079374.46 | Project in Process | Fall 2022
Ottumwa/BJRY Rail Port Relocation Study | The City of Ottumwa has proposed to do a study seeking to determine the feasibility and potential costs associated with relocating- and potentially expanding the transload facility to a different location outside of the riverfront redevelopment area. | 100000 | 80000 | City Match | 38413.5 | 41586.5 | Project in Process | Fall 2022
Sioux City 27 Flags Study | The purpose of this study is to plan for the future of rail service in the Southbridge Business Park, which includes land currently owned by the City. | 40000 | 32000 | City Match | 32000 | 0 | Pending Certificate of Completion | Fall 2022
Agri Trading | The project will build track for a new transload facility allowing additional rail to truck movement in and out of the area. UP will serve the site. Project will create 30 new jobs. | 2070284 | 1657027 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
|  | 62210284 | 3900000 |  | 1122011.96 | 1120960.96
FY 2019 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Heartland Goodwill | Goodwill of the Heartland has contract to package vegetable oil for the USDA international and domestic food aid program – rail best way to transport these goods and are building a rail spur to connect to IAIS. (IAIS) | 638070 | 510456 | Company Match | 0 | 510456 | Project in Process | Fall 2021
City of Cedar Rapids | Reconstruction of switches and track re-configuration along the Cedar River due to installation and impacts from the Cedar River flood control system being built to better protect Quaker Oats facility. | 2456000 | 1028000 | EDA/City Match | 0 | 1028000 | Project in Process | Fall 2021
Pattison Sand Company | Phase III, which is a continuation of phase II by adding an additional 1,800 feet of track to the previously installed 3,330 feet of track adding an additional 78 rail car spots and a rail scale. | 5868666.88 | 835732 | Company Match | 384677.8 | 451054 | Project in Process | Fall 2021
Farmers Feed and Grain Company | Rehabilitation of track and sidings at their grain elevator site. The track is old and in poor condition. Elevator owners want to re-connect it to CP mainline | 881000 | 660750 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Keokuk Junction Railway | Surfacing and tie replacement of a mainline switch along with surfacing and tie replacement of two heavily utilized yard tracks in Keokuk. | 189905.62 | 151925 | Company Match | 0 | 0 | Project withdrawn by appliant | Not Applicable
|  | 10033642.5 | 3186863 |  | 384677.8 | 1989510
FY 2018 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
City of Davenport | Construction of approximately 9,800 lineal feet of track with 7 turnouts in order to meet the supply and demand needs of Sterilite | 5169660 | 1008000 | Company Match | 1008000 | 0 | Project Complete | 2020-11-04
Progressive Rail | The rehabilitation of the rail line between Emery and Clear Lake, Iowa on the Iowa Traction Railway. The project consists of replacement of 3.6 mi of rail and will open up Clear Lake, Iowa for purpose of rail served industrail development on the community's east side in close proximity of I-35.. | 1384000 | 655000 | Company Match | $0 | 0 | Project withdrawn by applicant | Not applicable
Pattison Sand Company Phase II | Phase II of the project includes the required earthwork, the addition of 3,300 track feet and a rail scale resulting in 78 additional rail car spots. | 5334455.18 | 952482 | Company Match | 952482 | 0 | Project Complete | 2019-04-16
|  | 11888115.18 | 2615482 |  | 1960482 | 0
FY 2017 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Rail Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Elite Octane | Improvement to an exisiting spur to serve a grain elevator. | 10282248 | 926000 | Company Match | 926000 | 0 | Completed | 2018-03-09
Barilla America | Expansion of rail yard to receive 110 hopper cars with one switch. Includes addition of 8700 feet of new track, ties, plates, 6 turnouts and repositioning of all 6 switches at the east end of the rail yard. | 3268280 | 108000 | Company Match | 108000 | 0 | Complete | 11/20/2018
Pattison Sand Company | The required earthwork, installation of #111 mainline switch, two #9 yard switches, and approx. 6,625 feet of rail branching into the start of the main unit train storage tracks. | 5427934 | 1100000 | Company Match | 1100000 | 0 | Complete | 4/16/2019
Hydrite Chemical | Adding additional track on the south side of the production facility to heat an unload railcars of sulfur. | 1100000 | 24000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Progressive Rail | Installation of 600 ties per mile for the southernmost 12 miles of the APNC line between Albia, Iowa and Centervill, Iowa. | 951866 | 696436 | Company Match | 522570.46 | 173865.54 | Complete- remaining funds put back in pot. | January 2021
BJRY Le Mars | Includes 500 feet of rail, ties, ballast and other materials located at the south end of the spur track serving the industrial park in Le Mars, Iowa. | 196171 | 156936 | Company Match | 0 | 156936 | Project in Process - extension granted (spring 2020) | Summer 2021
Des Moines Cold Storage | Project will repair an exisiting spur track and add additional track length to extend it to the cold storage facility in Des Moines. | 602312 | 385000 | Company Match | 321611.17 | 0 | Project complete - remaining funds back in pot. | 8/13/2018
Oelwein Track Rehab | Project is a wood crosstie replacement project from Dewar, Iowa at Mile Post 322 to East of Fairbank, Iowa at Mile Post 346. | 987551 | 493775 | Company Match | 493775 | 0 | Project complete - Certificate of completion pending (Covid) | Winter 2021
Eastern Iowa Logistics Park/CRANDIC | RRLG fund will go toward the site grading and track construction to support the proposed transload facility in SW Cedar Rapids. | 2500000 | 500000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
KJRY Yard Enhancements III | Project will replace 400 ties, 27 sticks of rail and install two new switches in the KJRY middle yard area. OTM and ballast are included in the project as well. | 250196 | 200157 | Company Match | 174795.97 | 0 | Project complete - remaining funds back in pot, pending cert of completion (covid) | Winter 2021
Council Bluffs Transload Study | Study will address the market potential of an expanded transload area in Council Bluffs, Iowa. | 70400 | 56320 | Company Match | 56320 | 0 | Project complete | January 2019
|  | 25636958 | 4646624 |  | 3703072.6 | 330801.54
FY 2016 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
ADM "S" Curve | Current rail spur into the Clinton facility has an "s" curve. Project proposes to straighten the curveto allow greater rail capacity and better safety. | 450000 | 165600 | Company Match | 0 | 0 | Project withdrawn by appliant | Not Applicable
A to Z Drying Rail Enhancement | A to Z Drying is replacing and changing the location of an exisiting spur due to expansion of neighboring company. | 419375 | 200000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Boone Scenic Valley Industrial Park Line Phase I | Construction of a 1700 ft passing track. Includes grading ballast, and installation of rail ties. Will also be replacing ties and adding ballast where needed to maintain 286K service. Company also constructing 1425 feet of track extending to their facility in nearby industrial park. | 706050 | 556050 | In Kind Match | 556050 | 0 | Completed | 4/13/216
Iowa Traction Transload Project | IATR improving their current site by constructing 950 ft siding to support currently transload operation. Project also includes installing a 90lb switch to accommodate 286K | 119306 | 95445 | Company Match | 95445 | 0 | Project Complete | 11/27/18
KJRY Yard Enhancements II | Project involves replacing four switches and improving tracks, ties and ballast in the yard | 350356 | 280285 | Company Match | 228800 | 0 | Project Complete - Certificate of completion pending (covid) | Winter 2021
|  | 2045087 | 1297380 |  | 880295 | 0
FY 2015 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
West Charles Street Viaduct | Reconstruction, removal and replacement of the east side of the West Charles Street Viaduct | 654315 | 523452 | Local Match | 523452 | 0 | Complete | 2018-03-15
Five Star Coop | Expansion of current rail siding from 3 car capacity to 35 car capacity | 9614000 | 500000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Des Moines Transload Facility | Development of a transload facility to improve the overall freight capacity in Des Moines Metro area | 10000000 | 1700000 | Company Match | 826765 | 873234 | Project in process - extensive project, extension was granted, Federal Funding obtained | January 2021
Crossroads of Global Innovation | Phase two allows for connection to the CN mailline in the ICGI certrified site | 2100000 | 1600000 | Local Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
KJRY Railnetwork Improvements | Upgrade a mainline yard switch along with heavily traveled mainline yard tracks | 286000 | 228800 | Local Match | 228800 | 0 | Complete - Certificate of completion pending (covid) | Winter 2021
Sioux Center Rail Port Study | A planning study to determine the potential for a rail port adjacent to a BNSF line that runs north/south through the City limits | 130000 | 100000 | Local Match | 95796.41 | 0 | Completed | 2016-04-07
|  | 22784315 | 4652252 |  | 1674813.41 | 873234
FY 2014 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
HFCA (HF Chlor Alkali) Rail Road Project | Construction of three miles of new (private) track for new Cargill Plant | 150000000 | 324000 | Company match | 324000 | 0 | Completed | 2015-04-15
Iowa Corn Processors (ICP) Rail Expansion | Construction of two spur tracks on ICP property to add capacity | 14832000 | 419000 | Company Match | 419000 | 0 | Completed | 2014-06-11
Carter Lake Metals Processing Building (Owen Industries) | Construction of new rail spur to accommodate new production building | 30000000 | 108000 | Company Match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Heartland Co-op Greenfield Rail Loading Elevator | Build a 125-car load out facility | 24000000 | 1450000 | Company Match | 1450000 | 0 | Completed | 2015-11-17
CRANDIC - Millrace & Price Creek Bridges | Replacement of two bridges | 2840000 | 725000 | Company Match | 725000 | 0 | Completed | 2015-05-19
City of Knoxville - Red Rock Industrial Park | Planning Study | 118000 | 94400 | Local match | 92568 | 0 | Completed | 2016-01-01
|  | 221790000 | 3120400 |  | 3010568 | 0
FY 2013 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
CRANDIC Iowa River Crossing North Bridge | Consruct replacement rail bridge | 2840400 | 1500000 | Company match | 1500000 | 0 | Completed | 2014-04-15
Iowa Falls UP/CN Connector | Upgrade rail infrastructure in industrial area | 5711369 | 900000 | Local match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Rail One | Industrial Rail Spur Construction | 4397880 | 1116000 | Company match | 1116000 | 0 | Completed | 2016-01-30
BJRY Rail/Truck/Barge Planning Study | Planning Study | 50000 | 40000 | Local match | 17542.78 | 0 | Complete - (remaing funds back in pot) | 2018-04-06
Central Iowa Transloading Facility Feasibility Study | Planning Study | 125000 | 100000 | Local match | 98824.2 | 0 | Completed - remaining funds put back in | 2014-10-02
Iowa Falls/Hardin County Rail Port Planning Study | Planning Study | 125000 | 100000 | Local match | 100000 | 0 | Study Completed | 2014-10-01
Mills/Pottawattamie County Rail Port Study | Planning Study | 98000 | 78400 | Local match | 78400 | 0 | Study Completed | 2014-10-07
North Central Ag Park Planning Study | Planning Study | 100000 | 80000 | Local match | 0 | 0 | Project withdrawn by applicant | Not Applicable
Sioux City Rail Study Phase II | Planning Study | 350000 | 100000 | Local match | 99914.99 | 0 | Study Completed - remaining funds put back in pot | 2019-05-29
|  | 13797649 | 4014400 |  | 3010681.97 | 0
FY 2012 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway Spur rehabilitation | Industrial Rail Spur Construction | 197435 | 157948 | Company match | 87025.34 | 0 | Complete - remaining funds put back in pot | 2016-03-23
Butler Cross Dock | Industrial Rail Spur Construction | 1758922 | 705621 | Local match | 477295 | 0 | Complete - remaining returned | 2017-03-15
Cherokee Industrial Spur | Industrial Rail Spur Construction | 771818 | 617454 | Local match | 617454 | 0 | Completed | 2012-04-17
CRANDIC Iowa River Crossing Improvement | Consruct replacement rail bridge | 3200000 | 1613596 | Company match | 0 | 0 | Completed | 2014-04-15
Global Foods | Rail Spur upgrade | 358525 | 72000 | Local match | 0 | 0 | Project withdrawn by applicant | Not applicable
Iowa River Railroad | Rail line acquisition & preservation | 2500000 | 1000000 | Company match | 0 | 0 | Project withdrawn by applicant | Not applicable
North Central Iowa Rail Corridor, LLC | Rail line acquisition & preservation | 1900000 | 400000 | Local match | 400000 | 0 | Completed | 2012-04-26
Valley Distribution Corporation | Industrial Rail Spur Construction | $ 297, 525 | 218652 | Company match | 218652 | 0 | Completed | 2012-04-18
Waverly GMT Rail Spur | Industrial Rail Spur Construction | 538100 | 204000 | Company match | 204000 | 0 | Completed | 2014-11-10
|  | 11224800 | 4989271 |  | 2004426.34 | 0
Note 1: CRANDIC was awarded $2,000,000 from RRLG, however $386,404 of the award is from federal Rail Assistance Program (RAP) funds.
FY 2011 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Adams County Rail | Industrial Rail Spur Extension | 1758922 | 879461 | Local match | 0 | 0 | Project withdrawn | Not applicable
Eastern Iowa Industrial Center | Construct Transloading Facility | 8474244 | 2000000 | Federal, state and local match | 2000000 | 0 | Completed | 2016-04-26
Lomont Molding Inc | Rail Spur upgrade | 138560 | 110848 | Company match | 0 | 0 | Project withdrawn | Not applicable
Nypro Kannaak | Rail Spur upgrade | 255951 | 174022 | Company match | 174022 | 0 | Completed | 2012-11-14
|  | 10627677 | 3164331 |  | 2174022 | 0
FY 2010 Railroad Revolving Loan and Grant Program
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Upgrade rail infrastructure in industrial park | 88000 | 55400 | Railroad match | 55400 | 0 | Completed | 2011-01-10
Cedar Rapids and Iowa City Railroad (CRANDIC) | Rebuild rail bridge | 886500 | 700000 | Railroad match | 700000 | 0 | Completed | 2011-04-14
Schau Recycling | Install industrial rail spur | 450000 | 225000 | Company match | 145187 | 0 | Completed | 2013-02-28
Shine Brothers Corp. | Upgrade rail infrastructure in industrial area | 467589 | 311071 | Company match | 311071 | 0 | Completed | 2011-10-15
City of Waterloo | Install industrial rail spur | 252005 | 126000 | City match | 118691 | 0 | Completed | 2013-12-31
Webster County Board of Supervisors | Install industrial rail spur in industrial park | 10900000 | 900000 | County match and company investment | 0 |  | Project withdrawn | Not applicable
Union Pacific Railroad and Iowa Northern Railway | Rebuild rail bridge in Waterloo* | 5437200 | 1000000 | Railroad match and FRA grant award | 1000000 | 0 | Completed | 2009-12-31
| TOTAL | 18481294 | 3317471 |  | 2330349 | 0
FY 2009 Railroad Revolving Loan and Grant Program (Flood Recovery)
Project Sponsor | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated | Status of Project | Date Completed or Estimated Completion Date
Burlington Junction Railway | Repair rail infrastructure damaged by flooding | 89333 | 71000 | Railroad match | 61164 | 0 | Completed | 2009-01-01
Cedar Rapids and Iowa City Railroad (CRANDIC) | Repair rail infrastructure damaged by flooding | 400000 | 320000 | Railroad match | 320000 | 0 | Completed | 2008-11-01
Keokuk Junction Railway Company | Repair rail infrastructure damaged by flooding | 693120 | 554000 | Railroad match | 405346 | 0 | Completed | 2009-03-01
Iowa, Chicago & Eastern Railroad Corp. | Repair rail infrastructure damaged by flooding | 1771463 | 1417000 | Railroad match | 1406627 | 0 | Completed | 2009-10-01
Iowa Interstate Railroad | Repair rail infrastructure damaged by flooding | 964707 | 772000 | Railroad match | 650000 | 0 | Completed | 2009-03-01
Iowa Northern Railway Co. | Repair rail infrastructure damaged by flooding | 851704 | 681000 | Railroad match | 616420 | 0 | Completed | 2008-11-01
Iowa River Railroad | Repair rail infrastructure damaged by flooding | 230000 | 184000 | Railroad match | 184000 | 0 | Completed | 2009-12-31
| TOTAL | 5000327 | 3999000 |  | 3643557 | 0
FY 2008 Railroad Revolving Loan and Grant Program
Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2008 Funds used | FY 2008 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
Cedar Rapids Terminal (Iowa Northern Railroad) Construct rail spur and intermodal loading facility in Palo | 884000 | 242000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
Big River Resources Ethanol Plant industrial rail spur | 8500000 | 75000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
Lincolnway Railport Industrial Park | 1072933 | 840000 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
Norfolk Iron and Metal Company industrial rail spur | 1398000 | 810000 | State grant; Private investment | 810000 | 0 | Completed | 2009-09-30
Oregon Trail Energy Rail spur | 7146000 | 75000 | State grant; Private investment | 0 | 0 | Project was withdrawn. Funding has been reprogrammed to FY2012 | Not applicable
Prairie Creek Ethanol rail spur | 6055075 | 75000 | State Grant; Private investment | 0 | 0 | Project withdrawn by applicant. Funding has been reprogrammed to flood recovery assistance. | Not Applicable
Raccoon Valley BioDiesel Rail spur | 2250000 | 50000 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
Trinity Towers | 414489 | 165795 | State grant; Private investment | 0 | 0 | Project withdrawn | Not Applicable
Unity Ethanol Cedar River | 9500000 | 270000 | State loan; Private investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
Unity Ethanol Ottumwa | 9500000 | 270000 | State grant and loan; Private Investment | 0 | 0 | Project withdrawn. Funding has been reprogrammed to FY12. | Not Applicable
| 46720497 | 2872795 |  | 810000 | 0
FY 2007 Railroad Revolving Loan and Grant Program
Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2007 Funds used | FY 2007 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
Alternative Energy Resources Ethanol Plant industrial rail spur | 24240300 | 239000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
Lincolnway Railport Industrial Park | 11852896 | 489000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
Seimens Wind Power industrial rail spur | 457513 | 326000 | State grant; Private investment | 326000 | 0 | Complete | 2010-05-26
Southern Bio Energy industrial rail spur | 1300000 | 250000 | State grant and loan; Private investment; local investment | 0 | 0 | Project withdrawn | Not Applicable
| 37850709 | 1304000 |  | 326000 | 0
FY 2006 Railroad Revolving Loan and Grant Program
Description of Project | Total Estimated Project Cost | State Share | List of all revenue sources | FY 2006 Funds used | FY 2006 Remaining Funds Obligated | Status of project | Date Completed or Estimated Completion Date
Absolute Energy industrial rail spur | 3712220 | 500000 | State grant and loan; Private investment; local investment | 500000 | 0 | Complete | 2008-02-05
Cascade Lumber Company industrial rail spur | 694000 | 534000 | State grant and loan; Private investment; local investment | 534000 | 0 | Complete | 2007-09-19
Eastern Iowa Industrial Center rail development for industrial park expansion | 4660791 | 760791 | State grant; Private investment; FHWA grant | 729711 | 31079 | Complete | 2015-06-30
Green Plains Renewable Energy | 5700000 | 280000 | State grant and loan; Private investment; local investment | 126000 | 0 | Complete: loan portion of award declined | 2013-02-28
Midwest I,LLC industrial rail spur | 2800000 | 280000 | State grant and loan; Private investment; local investment | 280000 | 0 | Complete | 2008-09-30
Iowa Renewable Energy LLC industrial rail spur | 1258532 | 300000 | State grant and loan; Private investment; local investment | 300000 | 0 | Complete | 2007-11-01
Lincolnway Railport Industrial park rail development | 2154086 | 319209 | State grant and loan; Private investment; local investment | 0 | 0 | Project was withdrawn by applicant. Funding has been reprogrammed for flood recovery activities. | Not applicable
Marco Group International industrial rail spur switching improvements | 30000 | 22500 | State grant; Private investment | 0 | 0 | Project withdrawn | Not applicable
Metzler Automotive | 406711 | 60000 | State grant | 42691 | 0 | Complete | 2007-11-01
| 21416340 | 3056500 |  | 2512402 | 31079

## Passenger Rail
2010 Passenger Rail Service Revolving Fund (RIIF)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Support in Development of Intercity Passenger Rail efforts | 500000 | 499935 | None | 499935 | 0 | Completed | 2011-04-11
Funding reserved to match FY 2009 Recovery Act award to Iowa DOT for Chicago to Omaha Planning Study | 2000000 | 1016039.5 | Federal Railroad Administration FY 2009 HSIPR award | 1016039.5 | 0 | Completed | 2014-01-09
Funding reserved for PE/NEPA activities to match a federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 6213000 | 1242600 | Federal Railroad Administration FY 2010 HSIPR award | 815929.31 | 426670.69 | In Progress | 2021-06-30
Funding reserved for the Iowa City-Cedar Rapids Passenger Rail Conceptual Feasibility Study - Phase 1 (Task A) | 40000 | 14233.1 | CRANDIC and MPOJC | 14233.1 | 0 | Completed | 2015-11-01
Funding reserved for the Iowa City-North Liberty Passenger Rail Conceptual Feasibility Study - Phase 1 (Task B) | 49999 | 15918.75 | CRANDIC and MPOJC | 15918.75 | 0 | Completed | 2016-10-29
Funding reserved for the Iowa City-North Liberty Passenger Rail Conceptual Feasibility Study - Phase 1 (Task C) | 101399 | 33799 | CRANDIC and MPOJC | 33525.3 | 273.7 | Completed | 2020-07-31
Funding reserved for the Iowa City-North Liberty Passenger Rail Conceptual Feasibility Study - Phase 1 (Special Survey) | 100000 | 50000 | CRANDIC | 50000 | 0 | Completed | 2020-07-31
Funding reserved for Final Design & Construction to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 125000000 | 127474.65 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 127474.65 | Not Started | TBD
TOTAL | 134004398 | 3000000 |  | 2445580.96 | 554419.04
2011 Passenger Rail Service Revolving Fund (funding from Underground Storage Tank Fund)
Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Used | Remaining Obligated Funds | Status of Project | Date Completed or Estimated Completion Date
Funding reserved for the Ft. Madison Station Project | 2800000 | 400000 | Amtrak, TE Funds & City | 0 | 400000 | In Progress | 2021-09-30
Funding reserved for Final Design & Construction to match federal FY 2010 High Speed and Intercity Passenger Rail (HSIPR) award to Iowa DOT for Chicago to Iowa City. Award announced by FRA in October 2010 to Iowa. | 125000000 | 1600000 | Federal Railroad Administration FY 2010 HSIPR award | 0 | 1600000 | Not Started | TBD
TOTAL | 127800000 | 2000000 |  | 0 | 2000000

## PTIG
FY 2021 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
21513 | Ames | New HVAC system (Phase 2) | 468920 | 292093 | Local funds | 0 | 292093 | Awarded 7-1-2020 | Est. 8/15/21
22586 | Cedar Rapids | Remodel bus storage and administrative facility (partial funding--also see FY18) | 933144.0523 | 179395 | Local funds | 0 | 179395 | Awarded 7-1-2020 | Est. 1/31/22
22587 | Region 16 | West Burlington SEIBUS vehicle storage site (partial funding--also see FY20) | 35640 | 28512 | Local funds | 0 | 28512 | Awarded 7-1-2020 | Est. 12/01/21
|  | Funds avaiable to reprogram to other projects |  | 0
|  | GRAND TOTAL |  | 500000
FY 2020 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
21513 | Ames | New HVAC system | 651373 | 521098 | Local funds | 0 | 521098 | Awarded 7-1-2019 | Est. 7/8/21
21514 | Dubuque - The Jule | Phase II Transfer Center | 430929 | 0 | Local funds | 0 | 0 | Project canceled | 2020-06-18
21515 | Sioux City | Renovated Transit maintenance/storage facility | 169000 | 135200 | Local funds | 0 | 135200 | Awarded 7-1-2019 | Est. 7/8/21
21516 | Region 10 | New bus storage and adminstrative facility (Benton County) (partial funding---also see FY18, FY19) | 248443.75 | 198755 | Local funds | 42170 | 156585 | Awarded 7-1-2019 | Est. 7/8/21
21518 | Region 15 | New bus storage/vehicle wash facility | 522750 | 273459 | Local funds | 273459 | 0 | Project complete | 2020-04-16 | 2020-04-16
22587 | Region 16 | West Burlington SEIBUS vehicle storage site (partial funding--also see FY21) | 464360 | 371488 | Local funds |  | 371488 | Awarded 7-1-2020 | Est. 12/01/21
|  | Funds avaiable to reprogram to other projects |  | 0
|  | GRAND TOTAL |  | 1500000
FY 2019 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
20412 | Ames | Bus washer and HVAC system | 743284 | 517042 | Local funds | 517042 | 0 | Project complete | 2020-07-07 | 2020-07-07
20413 | Des Moines | Update electrical system | 1108500 | 0 | Federal transit funds Local funds | 0 | 0 | Project canceled | 2018-07-10 | 2018-07-10
20414 | Region 8 | Earlville new bus storage facility | 414000 | 329000 | Local funds | 329000 | 0 | Project complete | 2019-11-14 | 2019-11-14
20415 | Sioux City | Security cameras and vehicle fuel system | 243830 | 195064 | Local funds | 195064 | 0 | Project complete | 2020-10-30 | 2020-10-30
20416 | Region 15 | Ottumwa bus storage facility (partial funding --also see FY12, FY14, FY17, FY18) | 700000 | 366394 | Local funds | 366394 | 0 | Project complete | 2019-05-30 | 2019-05-30
21516 | Region 10 | New bus storage and adminstrative facility (Benton County) (partial funding---also see FY18, FY20) | 115625 | 92500 | Local funds | 92500 | 0 | Awarded 7-1-2019 | Est. 7/8/21
|  | Funds avaiable to reprogram to other projects |  | 0
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2018 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
20271 | Ames | Three in-ground hoists (partial funding---also see FY16, FY17) | 375318.75 | 300255 | Local funds | 300255 | 0 | Project Complete | 2019-05-28 | 2019-05-28
19449 | Cambus | Maintenance facility rehab | 1289000 | 318000 | Local funds | 318000 | 0 | Project Complete | 2020-01-08 | 2020-01-08
19450 | Region 5 | Humboldt land/construction of transit storage | 806400 | 539895 | Local funds | 539895 | 0 | Project Complete | 2018-12-19 | 2018-12-19
20416 | Region 15 | Ottumwa bus storage facility (partial funding --also see FY12, FY14, FY17, FY19) | 700000 | 33105 | Local funds | 33105 | 0 | Project Complete | 2019-05-30 | 2019-05-30
21516 | Region 10 | New bus storage and adminstrative facility (Benton County) (partial funding---also see FY2019, FY20) | 33431.25 | 26745 | Local funds | 26745 | 0 | Awarded 7-1-2019 | Est. 7/8/21
22586 | Cedar Rapids | Remodel bus storage and administrative facility (partial funding--also see FY21) | 1466855.9477 | 282000 | Local funds |  | 282000 | Awarded 7/1/2020 | Est 7/1/2022
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
18417 | Ames | Reconstruct roof | 400000 | 252486 | Local funds | 252486 | 0 | Project Complete | 2018-05-18 | 2018-05-18
18418 | Dubuque - The Jule | Bus storage facility | 6340247 | 569823 | Federal transit funds Local funds | 569823 | 0 | Project Complete | 2017-11-13 | 2017-11-13
18419 | Region 10 | Monticello bus faclity construction | 281887 | 225509 | Local funds | 225509 | 0 | Project Complete | 2018-06-07 | 2018-06-07
18420 | Region 12 | Replace overhead doors | 20000 | 13232 | Local funds | 13232 | 0 | Project Complete | 2018-05-17 | 2018-05-17
18421 | Region 15 | Purchase of transit facility | 600000 | 323764 | Federal transit funds Amoco Loan | 323764 | 0 | Project Complete | 2016-09-26 | 2016-09-26
20271 | Ames | Three in-ground hoists (partial funding---also see FY16, FY18) | 56130 | 44904 | Local funds | 44904 | 0 | Project Complete | 2019-05-28 | 2019-05-28
20416 | Region 15 | Ottumwa bus storage facility (partial funding --also see FY12, FY 14, FY18, FY19) | 700000 | 70282 | Local funds | 70282 | 0 | Project Complete | 2019-05-30 | 2019-05-30
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2016 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
17521 | Burlington | Building improvements | 645846 | 480000 | Local funds | 480000 | 0 | Project complete | 2016-12-13 | 2016-12-13
17522 | Des Moines | Rehabilitate facility | 1050000 | 369007 | Federal transit funds Local funds | 369007 | 0 | Project Complete | 2017-01-09 | 2017-01-09
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial funding---also see FY11, FY12, FY14 ) | 17741 | 14193 | Local funds | 14193 | 0 | Project complete | 2018-02-28 | 2018-02-28
17519 | Region 2 | Construction of indoor parking facility | 763390 | 600000 | Local funds | 600000 | 0 | Project Complete | 2017-07-12 | 2017-07-12
17520 | Region 8 | Roof mounted solar array (partial funding--also see FY15) | 46000 | 3695 | Local funds | 3695 | 0 | Project Complete | 2017-12-18 | 2017-12-18
20271 | Ames | Three in-ground hoists (partial funding---also see FY17, FY18) | 41381.25 | 33105 | Local funds | 33105 | 0 | Project Complete | 2019-05-28 | 2019-05-28
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2015 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
16399 | Burlington | Bus depot improvements | 55000 | 44000 | Local | 44000 | 0 | Project complete | 2015-04-22 | 2015-04-22
16400 | Des Moines | DART Way front office remodel | 965000 | 600000 | federal transit funds local funds | 600000 | 0 | Project complete | 2015-12-16 | 2015-12-16
16401 | Dubuque | Bus storage facility | 5184568 | 600000 | federal transit funds local funds | 600000 | 0 | Project Complete | 2017-07-10 | 2017-07-10
16402 | Sioux City | Maintenance, repairs, and improvements for MLK Center | 280000 | 208800 | federal transit funds local funds | 208800 | 0 | Project complete | 2016-01-12 | 2016-01-12
17520 | Region 8 | Roof mounted solar array (partial funding---also see FY16) | 59000 | 47200 | Local funds | 47200 | 0 | Project Complete | 2017-12-18 | 2017-12-18
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2014 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
15510 | Region 5 | Construct new vehicle and administration facility | 433900 | 347120 | Local funds | 347120 | 0 | Project complete | 2015-03-16 | 2015-03-16
15511 | Region 9 | Purchase and install new generator | 70000 | 32880 | Local funds | 32880 | 0 | Project complete | 2016-08-18 | 2016-08-18
15512 | Region 13 | Construct wash bay addition | 202800 | 162240 | Local funds | 162240 | 0 | Project complete | 2014-07-27 | 2014-07-27
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY13) | 688192.2775 | 475846 | federal transit funds local funds | 475846 | 0 | Project complete | 2015-11-12 | 2015-11-13
15513 | Des Moines | Rehabilitate maintenance lane | 45000 | 36000 | Local funds | 36000 | 0 | Project complete | 2016-01-12 | 2016-01-12
15514 | Sioux City | Replace bus wash system | 300000 | 199338 | Local funds | 199338 | 0 | Project complete | 2015-12-31 | 2015-12-31
15514 | Sioux City | Rehabilitate roof | 185000 | 123546 | Local funds | 123546 | 0 | Project complete | 2015-12-31 | 2015-12-31
15514 | Sioux City | Replace transit operations heating, ventilating, and air conditioning system | 50000 | 40000 | federal transit funds local funds | 40000 | 0 | Project complete | 2014-05-08 | 2014-05-08
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY11, FY12 and FY16) | 8493 | 2851 | Local funds | 2851 | 0 | Project complete | 2018-02-28 | 2018-02-28
18421 | Region 15 | Purchase of transit facility (partial funding--also see FY17) |  | 76236 | Local funds | 76236 | 0 | Project complete | 2016-09-26 | 2016-09-26
20416 | Region 15 | Ottumwa bus storage facility (partial funding --also see FY12, FY17, FY18, FY19) | 700000 | 3943 | Local funds | 3943 | 0 | Project complete | 2019-05-30 | 2019-05-30
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2013 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
14370 | Cedar Rapids | Administration facility/garage | 5294251 | 600000 | federal transit funds local funds | 600000 | 0 | Project complete | 2013-10-24 | 2013-10-24
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY10) | 384736.25 | 307789 | Local Funds | 307789 | 0 | Project complete | 2014-08-13 | 2014-08-13
14372 | Des Moines | Storage barn portals restoration | 467000 | 352000 | federal transit funds local funds | 352000 | 0 | Project complete | 2014-11-03 | 2014-11-03
14373 | Des Moines | Fuel delivery system | 192500 | 145000 | federal transit funds local funds | 145000 | 0 | Project complete | 2014-10-13 | 2014-10-13
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY11 and FY14) | 137698.9088 | 95211 | Local funds | 95211 | 0 | Project complete | 2015-11-12 | 2015-11-13
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2012 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
13415 | Ames | Facility renovation | 792000 | 600000 | Local Funds | 600000 | 0 | Project complete | 2013-11-27 | 2013-11-27
13416 | Cedar Rapids | New facility to replace transit garage and admin. facility | 3900000 | 600000 | local & FEMA | 600000 | 0 | Project complete | 2013-05-08 | 2013-05-08
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY11) | 63035 | 35452 | Local Funds | 35452 | 0 | Project complete | 2014-10-31 | 2014-10-31
13418 | Dubuque | Sprinkler replacement | 64677 | 51742 | Local Funds | 51742 | 0 | Project complete | 2015-04-03 | 2015-04-03
13418 | Dubuque | Roof replacement | 171920 | 137536 | Local Funds | 137536 | 0 | Project complete | 2015-04-03 | 2015-04-03
13419 | Muscatine | Passenger shelter | 7000 | 5600 | Local Funds | 5600 | 0 | Project complete | 2012-03-16 | 2012-03-16
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY11, FY14 and FY16) | 87087 | 18394 | Local Funds | 18394 | 0 | Project complete | 2018-02-28 | 2018-02-28
20416 | Region 15 | Ottumwa bus storage facility (partial funding --also see FY14, FY17, FY18, FY19) | 700000 | 51276 | Local Funds | 51276 | 0 | Project complete | 2019-05-30 | 2019-05-30
|  | GRAND TOTAL |  | 1500000 |  |  | 0
FY 2011 - I-Jobs Bonding (Revenue Bonds Capitals II)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12319 | Ames Transit Agency (CyRide) | Construct additional bus storage/maintenance areas | 4897614 | 800000 | Federal Transit Funds Local Funds | 800000 | 0 | Project complete | 2013-11-27 | 2013-11-27
12320 | Des Moines Area Regional Transit | Replace roof over maintenance area | 500000 | 381827 | Transit Agency Funds | 381827 | 0 | Project complete | 2011-07-05 | 2011-07-18
12733 | Dubuque | Transfer facility | 379211 | 278214 | Transit Agency Funds | 278214 | 0 | Project complete | 2014-01-14 | 2014-01-14
12738 | Des Moines | Wash rack rehabilitation | 30000 | 24000 | Transit Agency Funds | 24000 | 0 | Project complete | 2012-06-07 | 2012-06-07
12321 | Southwest Iowa Transit Agency-SWITA (Region 13) | Construct a vehicle storage facility | 565732 | 452585 | Transit Agency Funds | 452585 | 0 | Project complete | 2012-06-30 | 2011-04-04
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY10, FY12) | 22716.25 | 18173 | Local Funds | 18173 | 0 | Project complete | 2014-10-31 | 2014-10-31
15513 | Des Moines | Renovate operations office (partial-- see funding from FY10, FY13 and FY14) | 36240.1325 | 25058 | Local funds | 25058 | 0 | Project complete | 2015-11-12 | 2015-11-13
17523 | Sioux City | Maintenance, repairs, and replacement of bus shelters (partial-- see funding from FY12, FY14 and FY16) | 25179 | 20143 | Local funds | 20143 | 0 | Project complete | 2018-02-28 | 2018-02-28
|  | GRAND TOTAL |  | 2000000 |  |  | 0
FY 2010 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
12738 | Des Moines | Locker/washroom renovations | 65000 | 48000 | Transit Agency Funds | 48000 | 0 | Project complete | 2012-06-07 | 2012-06-07
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY09) | 617904 | 436904 | Transit Agency Funds | 436904 | 0 | Project complete | 2013-02-14 | 2013-02-14
11761 | Des Moines Area Regional Transit | Restoration of masonry structures and upgrade of energy management system at DART facility | 100000 | 79920 | Transit Agency Funds | 79920 | 0 | Project complete | 2010-11-01 | 2010-11-16
11767 | Ottumwa Transit Authority | Expand maintenance shop serving OTA and 10-15 regional transit fleets to accommodate more vehicles and provide sufficient headroom to allow use of vehicle hoists | 235000 | 188000 | Transit Agency Funds | 188000 | 0 | Project complete | 2011-01-18 | 2011-01-18
11762 | Region 2 Transit - Mason City | Expand/renovate facility shared with Mason City Transit to accommodate dispatch function now required to support direct operation of transit services in Cerro Gordo County by regional system | 176000 | 140800 | Transit Agency Funds | 140800 | 0 | Project complete | 2010-12-31 | 2011-01-24
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilton Co. (partial see also funding in FY09) | 7347 | 5877 | Transit Agency Funds | 5877 | 0 | Project complete | 2012-07-31 | 2012-07-31
11765 | River Bend Transit (Region 9) - Davenport | Expand bus wash portion of River Bend facility to accommodate larger vehicles now being operated | 130000 | 67019 | Transit Agency Funds | 67019 | 0 | Project complete | 2011-11-20 | 2011-11-26
11766 | Southeast Iowa Bus (region 16) - Burlington | Participate in transit share of purchase and remodeling of existing building to house planning commission functions including transit administration and operations | 296250 | 125179 | Transit Agency Funds | 125179 | 0 | Project complete | 2011-06-21 | 2011-06-21
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY09, FY13) | 139776.25 | 111821 | Local Funds | 111821 | 0 | Project complete | 2014-08-13 | 2014-08-13
12738 | Des Moines | Storm water rack and sanitation sewer (see FY11 and supplemental funding from FY09) | 12144 | 5534 | Transit Agency Funds | 5534 | 0 | Project complete | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY09, FY11, FY12) | 46326.25 | 37061 | Local Funds | 37061 | 0 | Project complete | 2014-10-31 | 2014-10-31
15513 | Des Moines | Renovate operations office (partial-- see funding from FY11, FY13 and FY14) | 5618.6812 | 3885 |  | 3885 | 0 | Project complete | 2015-11-12 | 2015-11-13
|  | GRAND TOTAL |  | 1250000 |  |  | 0
FY 2009 - RC3 511 - Health Restricted Capital Bond Fund (Revenue Bonds Capitals)
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
10482 | CyRide (Ames) | Reconstruction of the steam cleaning area (Moved to ARRA) | $640,000 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10481 | City of Davenport | Relocate transit offices (Cancelled 8-9-10) | 654000 | 0 | Transit Agency Funds | 0 | 0 | Project Cancelled | Est. 6/30/2010
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also supplemental funding from FY07 and FY10) |  | 385677 | FEMA Funds, Transit Agency Funds | 385677 | 0 | Project Complete | 2013-02-14 | 2013-02-14
10484 | River Bend Transit (Region 9) - Davenport | Vehicle storage and wash bays (Moved to ARRA) | $491,300 | 0 | Transit Agency Funds | 0 | 0 | Project switched to ARRA | NA
10483 | Western Iowa Transit System (Region 12) - Carroll | Construct a vehicle storage addition (partial - see also supplimental funding from FY07) | 85446.25 | 68357 | Federal Transit Funds, Transit Agency Funds | 68357 | 0 | Project complete | 2009-08-31 | 2009-07-23
10968 | City of Coralville | Relocate transit office/maintenance facility out of floodway | 3643332 | 880000 | FEMA Funds, Transit Agency Funds | 880000 | 0 | Project Complete |  | 2013-01-02
11350 | CyRide (Ames) | Rehabitate west wall exterior insulation finish system (EIFS) of Cy-Ride maintenance facility | 200000 | 62577 | Transit Agency Funds | 62577 | 0 | Project Complete | 2011-05-25 | 2011-01-05
11764 | MIDAS Regional Transit (Region 5) - Ft. Dodge | Construct satellite transit operations and vehicle storage/maintenance facility in Webster City to support MIDAS transit services in Hamilaton Co. (partial see also funding in FY10) | 699736.25 | 559789 | Transit Agency Funds | 559789 | 0 | Project Complete | 2012-07-31 | 2012-07-31
14371 | Davenport | Administrative/operations offices (partial--also see funding from FY10, FY13) | 10817.5 | 8654 | Local Funds | 8654 | 0 | Project complete | 2014-08-13 | 2014-08-13
12738 | Des Moines | Storm water rack and sanitation sewer (see FY10 and FY11) | 177300 | 137523 | Transit Agency Funds | 137523 | 0 | Project Complete | 2013-02-18 | 2013-06-19
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY07, FY10, FY11, FY12) | 121778.75 | 97423 | Local Funds | 97423 | 0 | Project complete | 2014-10-31 | 2014-10-31
|  | GRAND TOTAL |  | 2200000 |  |  | 0
FY 2008 - RIIF 017 - Rebuild Iowa Infrastructure Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09522 | University of Iowa (Cambus) | Construct new vehicle storage building for CAMBUS (partial - see also supplimental funding from FY07) | 1166319 | 702268 | Federal Transit Funds, Transit Agency Funds | 702268 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines (DART) | Construct addition to vehicle storage building (partial - see also supplimental funding from FY07) | 1044250 | 820000 | Federal Transit Funds, Transit Agency Funds | 820000 | 0 | Project complete | 2010-11-03 | 2010-11-03
09524 | Region Six Planning Commission (Region 6) - Marshalltown | Transit portion of Joint Facility | 385043 | 100876 | Federal Transit Funds, Transit Agency Funds | 100876 | 0 | Project complete | 2009-05-31 | 2008-12-18
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Construct new regional transit office, storage and maintenance facility in Dubuque (partial - see also supplimental funding from FY07) | 721070 | 576856 | Transit Agency Funds | 576856 | 0 | Project complete | 2008-06-30 | 2008-07-31
|  | GRAND TOTAL |  | 2200000 |  |  | 0
FY 2007 - RC2 942 - Health Restricted Capitals Fund
Contract Number | Transit System | Description of Project | Total Estimated Project Cost | State Share | Other Revenue Sources | State Funds Paid to Date | Remaining Balance | Status of Project | Date Completed or Estimated Completion Date | Final Payment
09410 | Ames Transit Agency (CyRide) | Expand operations/administration area of CyRide maintenance facility-Ride Facility | 1100000 | 880000 | Transit Agency funds | 880000 | 0 | Project complete | 2008-05-31 | 2008-06-19
09409 | City of Cedar Rapids | Construct transit portion of new downtown Intermodal facility | 2589453 | 0 | Federal Transit Funds, Transit Agency funds | 0 | 0 | Project dropped after city reorganization | NA | NA
09402 | City of Davenport (CitiBus) | Construct new transit hubs adjacent to regional shopping center and on campus of local university | 138134 | 110507 | Transit Agency funds | 110507 | 0 | Project complete | 2009-02-18 | 2009-02-18
09408 | Des Moines Area Regional Transit (DART) | Renovate maintenance area of DART facility | 66677 | 53341 | Transit Agency funds | 53341 | 0 | Project complete | 2010-02-17 | 2010-02-17
09404 | City of Sioux City | Construct new parts storage building at transit maintenance facility | 50000 | 40000 | Transit Agency funds | 40000 | 0 | Project complete | 2008-09-16 | 2008-09-16
09407 | North Iowa Area Regional Transit (Region 2) - Mason City | Construct a variety of projects to finish out recently constructed transit maintenance facility shared with City of Mason City | 40267.5 | 32214 | Transit Agency funds | 32214 | 0 | Project complete | 2008-03-31 | 2008-05-14
09406 | RIDES/Regional Transit Authority (Region 3) - Spencer | Construct new satellite facility in Sheldon for transit vehicle storage and maintenance | 500000 | 163085 | Federal Transit Funds, Transit Agency funds | 163085 | 0 | Project complete | 2010-12-31 | 2009-11-25
09405 | Western Iowa Transit System (Region 12) - Carroll | Expand transit maintenance and storage facility in Carroll | 587500 | 220000 | Federal Transit Funds, Transit Agency funds | 220000 | 0 | Project complete | 2008-09-30 | 2008-09-17
09525 | Delaware, Dubuque and Jackson County Regional Transit Authority (Region 8) - Dubuque | Partial funding for FY08 project to construct new regional transit office, storage and maintenance facility in Dubuque | 418122.5 | 303144 | Transit Agency Funds | 303144 | 0 | Project complete | 2008-06-30 | 2008-07-31
09522 | University of Iowa (Cambus) - Iowa City | Construct new vehicle storage building for CAMBUS (partial - see also funding from FY08) | 222165 | 177732 | Federal Transit Funds, Transit Agency Funds | 177732 | 0 | Project complete | 2010-10-31 | 2011-01-14
09523 | Des Moines Area Regional Transit (DART) | Construct addition to vehicle storage building (partial - see also funding from FY08) | 75000 | 60000 | Transit Agency Funds | 60000 | 0 | Project complete | 2010-11-03 | 2010-11-03
10483 | Western Iowa Transit System (Region 12) - Carroll | Partial funding for FY09 project to construct a vehicle storage addition in Carroll | 82053.75 | 65643 | Federal Transit Funds, Transit Agency funds | 65643 | 0 | Project complete | 2009-07-23 | 2009-07-23
11760 | City of Coralville | Construct bus wash bash and expanded parts storage, etc. for relocated transit maintenance facility (partial -- see also funding from FY09 and FY10) | 71773.75 | 57419 | Transit Agency Funds | 57419 | 0 | Project complete | 2013-02-14 | 2013-02-14
13417 | Des Moines | Storage barn (partial--also see supplemental funding from FY09, FY10, FY11, FY12) | 46143.75 | 36915 | Local Funds | 36915 | 0 | Project complete | 2013-05-13 | 2013-05-13
|  | GRAND TOTAL |  | 2200000 |  |  | 0